## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | include_onshore_construction | max_waveheight | max_windspeed | transit_speed | num_vessels | num_ahts_vessels
0.5 | Export Cable Installation Vessel | Mobilize | 72 | 450000 | ACTION | 0 | ExportCableInstallation
1 | Mooring System Installation Vessel | Mobilize | 168 | 700000 | ACTION | 0 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Load Cable | 6 | 75000 | ACTION | 6 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5 | 20833.3333 | ACTION | 15 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 45 | 187500 | ACTION | 60 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 5 | 20833.3333 | ACTION | 65 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 67 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 71 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 77 | 962500 | ACTION | 83 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Tow Plow | 0.4 | 5000 | ACTION | 83.4 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Pull Winch | 0.4 | 5000 | ACTION | 83.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Prepare Cable | 1 | 12500 | ACTION | 84.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 88.065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 90.3 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 93.13 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 95.13 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 99.13 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 120.13 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 137.195 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 142.26 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 144.26 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 148.26 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 165.325 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 170.39 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 172.39 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 176.39 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 193.455 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 198.52 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 200.52 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 204.52 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 19 | 79166.6667 | ACTION | 223.52 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 240.585 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 153 | 1912500 | ACTION | 243.3 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 245.65 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 247.65 | MooringSystemInstallation
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 248.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Lower Cable | 1 | 12500 | ACTION | 249.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 251.65 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 10 | 125000 | ACTION | 259.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Delay | 44 | 183333.3333 | ACTION | 295.65 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 312.715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 317.78 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 327.78 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 332.78 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 337.78 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 347.78 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 349.78 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 353.78 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 370.845 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 375.91 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 377.91 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 381.91 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 398.975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 404.04 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 406.04 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 410.04 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 156 | 1950000 | ACTION | 415.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 427.105 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 432.17 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 434.17 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 438.17 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 29 | 362500 | ACTION | 444.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 455.235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 460.3 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 462.3 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 466.3 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 483.365 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 488.43 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 490.43 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 494.43 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substation Assembly Line 1 | Substation Substructure Assembly | 0 | 0 | ACTION | 524.8526 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 36 | 150000 | ACTION | 530.43 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 547.495 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substation Assembly Line 1 | Attach Topside | 24 | 0 | ACTION | 548.8526 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay: Waiting on Substation Assembly | 24 | 100000 | ACTION | 548.8526 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 552.56 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 109 | 1362500 | ACTION | 553.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 562.56 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 9 | 112500 | ACTION | 562.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Tow Substation to Site | 16.6667 | 69444.4444 | ACTION | 565.5192 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 567.5192 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 567.56 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 572.56 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 573.5192 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 577.5192 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 582.56 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 17 | 70833.3333 | ACTION | 594.5192 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 12 | 50000 | ACTION | 594.56 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 596.56 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 600.56 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 16.065 | 66937.5 | ACTION | 610.5842 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 615.6492 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 617.625 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 7 | 29166.6667 | ACTION | 622.6492 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 622.69 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 624.69 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 628.69 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 76 | 316666.6667 | ACTION | 704.69 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 721.755 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 3 | 12500 | ACTION | 724.755 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 729.82 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 731.82 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 735.82 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 122 | 508333.3333 | ACTION | 744.6492 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 752.885 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 757.95 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 15 | 62500 | ACTION | 759.6492 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 759.95 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 763.95 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 771.6492 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 775.6492 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 781.015 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 56 | 233333.3333 | ACTION | 837.015 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 62 | 258333.3333 | ACTION | 837.6492 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 842.08 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 844.08 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 848.08 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 16.065 | 66937.5 | ACTION | 853.7142 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 858.7792 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 865.145 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 870.21 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 872.21 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 876.21 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 880.7792 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 324 | 4050000 | ACTION | 886.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 892.7792 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 893.275 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 896.7792 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 898.34 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 908.34 | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 16.065 | 66937.5 | ACTION | 912.8442 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 913.34 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 28 | 350000 | ACTION | 914.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 917.9092 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 918.34 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 7 | 29166.6667 | ACTION | 924.9092 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 928.34 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 930.34 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 934.34 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 37 | 154166.6667 | ACTION | 971.34 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 55 | 229166.6667 | ACTION | 979.9092 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 988.405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 993.47 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 15 | 62500 | ACTION | 994.9092 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 995.47 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 999.47 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1006.9092 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 99 | 1237500 | ACTION | 1013.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1016.535 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1016.9092 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 6 | 75000 | ACTION | 1019.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1021.6 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1023.6 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1027.6 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1044.665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1049.73 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1051.73 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1055.73 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 41 | 512500 | ACTION | 1060.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1072.795 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1077.86 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1079.86 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1083.86 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 29 | 362500 | ACTION | 1089.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1100.925 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1105.99 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1107.99 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1111.99 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1129.055 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1134.12 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1144.12 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1149.12 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1154.12 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1164.12 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 75 | 937500 | ACTION | 1164.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 1 | 12500 | ACTION | 1165.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1166.12 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1170.12 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1187.185 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 24 | 300000 | ACTION | 1189.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1192.25 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1194.25 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1198.25 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1215.315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1220.38 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1222.38 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1226.38 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 52 | 650000 | ACTION | 1241.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1243.445 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1248.51 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1250.51 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1254.51 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1271.575 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1276.64 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1278.64 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 1282.64 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1286.64 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 42 | 175000 | ACTION | 1328.64 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1345.705 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1350.77 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 109 | 1362500 | ACTION | 1350.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1352.77 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1356.77 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1373.835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1378.9 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1388.9 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 40 | 500000 | ACTION | 1390.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1393.9 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1398.9 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1408.9 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1410.9 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1414.9 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1431.965 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 1452.965 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1458.03 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1460.03 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1464.03 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 32 | 133333.3333 | ACTION | 1496.03 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1513.095 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1518.16 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1520.16 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1524.16 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1541.225 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1546.29 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1548.29 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1552.29 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 178 | 2225000 | ACTION | 1568.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1569.355 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1574.42 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1576.42 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1580.42 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 19 | 237500 | ACTION | 1587.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1597.485 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1602.55 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1604.55 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1608.55 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1625.615 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1630.68 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1640.68 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1645.68 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1650.68 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 67 | 837500 | ACTION | 1654.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1660.68 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1662.68 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1666.68 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1683.745 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1688.81 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1690.81 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1694.81 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1711.875 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1716.94 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1718.94 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1722.94 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 70 | 875000 | ACTION | 1724.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1740.005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1745.07 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1747.07 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1751.07 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1768.135 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 44 | 550000 | ACTION | 1768.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1773.2 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1775.2 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1779.2 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 12 | 150000 | ACTION | 1780.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1796.265 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1801.33 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1803.33 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1807.33 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 35 | 437500 | ACTION | 1815.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1824.395 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1829.46 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1839.46 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1844.46 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1849.46 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1859.46 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1861.46 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1865.46 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1882.525 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1887.59 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1889.59 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1893.59 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1910.655 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1915.72 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1917.72 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1921.72 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1938.785 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1943.85 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1945.85 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1949.85 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1966.915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1971.98 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1973.98 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1977.98 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 176 | 2200000 | ACTION | 1991.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1995.045 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 5 | 62500 | ACTION | 1996.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2000.11 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2002.11 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2006.11 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 24.9147 | 311433.2719 | ACTION | 2021.7147 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2023.175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Position Onsite | 2 | 25000 | ACTION | 2023.7147 | ExportCableInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2028.24 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 2029.2147 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2038.24 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2043.24 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2048.24 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2058.24 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2060.24 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2064.24 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2081.305 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 56 | 700000 | ACTION | 2085.2147 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2086.37 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2088.37 | MooringSystemInstallation
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 2090.7147 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2092.37 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Transit | 8.6957 | 108695.6522 | ACTION | 2099.4103 | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2109.435 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2114.5 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2116.5 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2120.5 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2137.565 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2142.63 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2144.63 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2148.63 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2165.695 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2170.76 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2172.76 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2176.76 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2193.825 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2198.89 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2200.89 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 25 | 104166.6667 | ACTION | 2225.89 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2229.89 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 29 | 120833.3333 | ACTION | 2258.89 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2275.955 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2281.02 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2291.02 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2296.02 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2301.02 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2311.02 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2313.02 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2317.02 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2334.085 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2339.15 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2341.15 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2345.15 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2362.215 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2367.28 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2369.28 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2373.28 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2390.345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2395.41 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2397.41 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2401.41 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2418.475 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2423.54 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2425.54 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2429.54 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2446.605 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2451.67 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2453.67 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2457.67 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2474.735 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2479.8 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2489.8 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2494.8 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2499.8 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2509.8 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2511.8 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2515.8 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2532.865 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2537.93 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2539.93 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2543.93 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2560.995 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2566.06 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2568.06 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2572.06 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2589.125 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2594.19 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2596.19 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2600.19 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2617.255 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2622.32 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2624.32 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2628.32 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2645.385 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2650.45 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2652.45 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2656.45 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2673.515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2678.58 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2688.58 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2693.58 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2698.58 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2708.58 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2710.58 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2714.58 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2731.645 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2736.71 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2738.71 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2742.71 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2759.775 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2764.84 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2766.84 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2770.84 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2787.905 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2792.97 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2794.97 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2798.97 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2816.035 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2821.1 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2823.1 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2827.1 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2844.165 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2849.23 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2851.23 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2855.23 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2872.295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2877.36 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2887.36 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2892.36 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2897.36 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2907.36 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2909.36 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2913.36 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2930.425 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2935.49 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2937.49 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2941.49 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2958.555 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2963.62 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2965.62 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2969.62 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2986.685 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2991.75 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2993.75 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2997.75 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3014.815 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3019.88 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3021.88 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3025.88 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3042.945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3048.01 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3050.01 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3054.01 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3071.075 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3076.14 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3086.14 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3091.14 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3096.14 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3106.14 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3108.14 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3112.14 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3129.205 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3134.27 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3136.27 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3140.27 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3157.335 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3162.4 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3164.4 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3168.4 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3185.465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3190.53 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3192.53 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3196.53 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3213.595 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3218.66 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3220.66 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3224.66 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3241.725 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3246.79 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3248.79 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3252.79 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3269.855 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3274.92 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3284.92 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3289.92 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3294.92 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3304.92 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3306.92 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3310.92 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3327.985 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3333.05 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3335.05 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3339.05 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3356.115 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3361.18 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3363.18 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3367.18 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3384.245 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3389.31 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3391.31 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3395.31 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3412.375 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3417.44 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3419.44 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3423.44 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 18 | 75000 | ACTION | 3441.44 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3458.505 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3463.57 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3465.57 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3469.57 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3486.635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3491.7 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3501.7 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3506.7 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3511.7 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3521.7 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3523.7 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3527.7 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3544.765 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3549.83 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3551.83 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3555.83 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3572.895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3577.96 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3579.96 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3583.96 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3601.025 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3606.09 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3608.09 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3612.09 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3629.155 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3634.22 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3636.22 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3640.22 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3657.285 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3662.35 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3664.35 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3668.35 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3685.415 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3690.48 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3700.48 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3705.48 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3710.48 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3720.48 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3722.48 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3726.48 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3743.545 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3748.61 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3750.61 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3754.61 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3771.675 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3776.74 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3778.74 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3782.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 3782.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 3782.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 3782.565 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3782.74 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3790.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 3790.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3799.805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3802.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3802.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3804.87 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3806.87 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3810.87 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 22 | 0 | ACTION | 3824.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 22 | 0 | ACTION | 3824.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3827.935 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3828.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3828.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3832.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3832.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3833 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3835 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3836.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3836.565 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3840.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3840.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 3852.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 3852.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 3854.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 2 | 0 | ACTION | 3854.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3856.065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3858.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3858.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3861.13 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3863.13 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3867.13 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3884.195 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3889.26 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3899.26 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 45 | 0 | ACTION | 3903.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 45 | 0 | ACTION | 3903.065 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3904.26 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3906.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3906.565 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3909.26 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 10 | 0 | ACTION | 3916.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 10 | 0 | ACTION | 3916.565 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 3919.26 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3920.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3920.065 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3921.26 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3925.26 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3942.325 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3944.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 3944.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3947.39 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3949.39 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3950.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 3950.565 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3953.39 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3970.455 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3975.52 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3977.52 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3981.52 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3998.585 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4003.65 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4005.65 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4009.65 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4016.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 4016.065 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 401.5 | 3178541.6667 | ACTION | 4016.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 401.5 | 3178541.6667 | ACTION | 4016.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4024.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 4024.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4026.715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4031.78 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4033.78 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4036.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4036.065 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4037.78 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 25 | 197916.6667 | ACTION | 4041.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 25 | 197916.6667 | ACTION | 4041.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 4041.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 5 | 0 | ACTION | 4041.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4045.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4045.065 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4047.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4047.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4049.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4049.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4053.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4053.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4054.845 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4057.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4057.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4059.91 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4061.91 | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 4065.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 4065.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4065.91 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 4067.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 4067.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4069.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4069.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4072.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4072.565 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4073.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4073.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4076.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4076.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4079.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4079.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4082.975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4088.04 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 4093.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 4093.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4098.04 | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 4099.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 4099.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4103.04 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4103.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 4103.565 | MooredSubInstallation
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 4106.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 4106.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4108.04 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4118.04 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4118.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 4118.565 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4120.04 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4124.04 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4141.105 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4146.17 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4148.17 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4152.17 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4169.235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4174.3 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4175.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 4175.565 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 561 | 4441250 | ACTION | 4175.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 69.1753 | 547637.987 | ACTION | 4175.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4176.3 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4180.3 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4181.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4181.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4183.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 4183.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4195.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4195.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4197.365 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4199.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4199.565 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 4199.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 4199.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 4201.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 4201.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4202.43 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4203.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4203.565 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4204.43 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4207.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4207.565 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4207.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4207.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4208.43 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4211.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4211.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4223.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4223.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4225.495 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4227.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4227.065 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 4227.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 4227.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4230.56 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4232.56 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 4233.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 6 | 0 | ACTION | 4233.065 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 4233.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 4233.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4236.56 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4236.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4236.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4240.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4240.065 | MooredSubInstallation
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 4240.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 4240.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4253.625 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4258.69 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4260.69 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4264.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 4264.065 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4264.69 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4281.755 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4286.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 4286.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4286.82 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4296.82 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4301.82 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4306.82 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4316.82 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4318.82 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4322.82 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4336.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 4336.065 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 229.6753 | 1818262.987 | ACTION | 4336.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 95.1753 | 753471.3203 | ACTION | 4336.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4339.885 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4342.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4342.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4344.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 4344.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4344.95 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4346.95 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4350.95 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4356.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4356.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4360.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4360.065 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 4360.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 4360.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 4362.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 4362.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4364.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4364.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4368.015 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4368.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4368.065 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4368.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4368.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4372.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4372.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4373.08 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 39583.3333 | ACTION | 4373.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 39583.3333 | ACTION | 4373.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4375.08 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4379.08 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4384.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4384.065 | MooredSubInstallation
| Towing Group 2 | Delay | 11 | 87083.3333 | ACTION | 4384.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 11 | 87083.3333 | ACTION | 4384.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4387.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4387.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4391.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4391.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4394.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4394.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4396.145 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 118750 | ACTION | 4399.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 118750 | ACTION | 4399.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4401.21 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4403.21 | MooringSystemInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 4405.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 4405.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4407.21 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 4412.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 4412.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4418.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 4418.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4424.275 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4429.34 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4431.34 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4435.34 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4452.405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4454.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 4454.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4457.47 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4459.47 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4463.47 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4480.535 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4485.6 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8 | 33333.3333 | ACTION | 4493.6 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 4501.6 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2 | 8333.3333 | ACTION | 4503.6 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 6 | 25000 | ACTION | 4509.6 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4514.6 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4519.6 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 102 | 0 | ACTION | 4520.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 102 | 0 | ACTION | 4520.565 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4529.6 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4531.6 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4535.6 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4552.665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4557.73 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4559.73 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4563.73 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4580.795 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4585.86 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4587.86 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4591.86 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4592.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 4592.565 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 351.6753 | 2784096.3203 | ACTION | 4592.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 180.1753 | 1426387.987 | ACTION | 4592.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4598.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4598.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4600.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 4600.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4608.925 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4612.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4612.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4613.99 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4615.99 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4616.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4616.565 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 4616.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 4616.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 4618.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 4618.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4619.99 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4620.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4620.565 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4622.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 4622.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4624.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4624.565 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4624.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4624.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4628.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4628.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4637.055 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4640.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4640.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4642.12 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4644.12 | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 4644.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 4644.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4648.12 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 4650.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 4650.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 4 | 31666.6667 | ACTION | 4654.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 4 | 31666.6667 | ACTION | 4654.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4665.185 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 12 | 95000 | ACTION | 4666.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 12 | 95000 | ACTION | 4666.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 3.1429 | 24880.9524 | ACTION | 4669.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 3.1429 | 24880.9524 | ACTION | 4669.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4670.25 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4672.25 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4676.25 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 48 | 0 | ACTION | 4688.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 48 | 0 | ACTION | 4688.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4692.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4692.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4693.315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4695.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4695.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4698.38 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4699.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4699.065 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4708.38 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4713.38 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4718.38 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4723.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 4723.065 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4728.38 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4730.38 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4734.38 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4751.445 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4756.51 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4758.51 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4762.51 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4779.575 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4784.64 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4786.64 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4790.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 4790.565 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4790.64 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4795.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 4795.065 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 382.6753 | 3029512.987 | ACTION | 4795.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 125.1753 | 990971.3203 | ACTION | 4795.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4801.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4801.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4803.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 4803.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4807.705 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4812.77 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4814.77 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4815.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4815.065 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4818.77 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4819.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4819.065 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 4819.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 4819.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 4821.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 4821.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4823.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4823.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4827.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4827.065 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4827.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4827.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4831.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4831.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4835.835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4840.9 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4842.9 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4843.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4843.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4846.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4846.565 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4846.9 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 4847.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 4847.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4850.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4850.065 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 4853.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 4853.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4853.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4853.565 | MooredSubInstallation
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 4860.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 4860.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4863.965 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4869.03 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4871.03 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4875.03 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4877.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 4877.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4892.095 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4897.16 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4907.16 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4912.16 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4917.16 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 4927.16 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4929.16 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4933.16 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4949.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 4949.565 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 279.6753 | 2214096.3203 | ACTION | 4949.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 89.1753 | 705971.3203 | ACTION | 4949.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4950.225 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4955.29 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4955.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4955.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4957.29 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4957.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 4957.565 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4958.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 4958.565 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4961.29 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4969.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4969.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4973.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4973.565 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 4973.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 4973.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 4975.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 4975.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4977.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4977.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4978.355 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4981.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4981.565 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4981.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4981.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4983.42 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4985.42 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4985.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4985.565 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4989.42 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4997.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4997.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5001.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5001.065 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5001.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5001.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5004.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5004.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5006.485 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 5007.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 5007.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5008.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5008.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5011.55 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5013.55 | MooringSystemInstallation
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 5014.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 5014.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5017.55 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5032.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 5032.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5034.615 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5039.68 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5041.68 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5045.68 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5062.745 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5067.81 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5069.81 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5073.81 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5090.875 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5095.94 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5104.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 5104.065 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 243.6753 | 1929096.3203 | ACTION | 5104.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 89.1753 | 705971.3203 | ACTION | 5104.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5105.94 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5110.94 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5112.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 5112.065 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5115.94 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5124.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5124.065 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5125.94 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5126.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 5126.565 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5127.94 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5131.94 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5149.005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5154.07 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5156.07 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5160.07 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5177.135 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5182.2 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5184.2 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5188.2 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 92 | 728333.3333 | ACTION | 5196.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 92 | 728333.3333 | ACTION | 5196.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 72 | 0 | ACTION | 5196.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 72 | 0 | ACTION | 5196.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5200.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5200.065 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5202.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5202.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5204.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5204.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5205.265 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5210.33 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5212.33 | MooringSystemInstallation
| Towing Group 1 | Delay | 12 | 95000 | ACTION | 5214.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 12 | 95000 | ACTION | 5214.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 10 | 0 | ACTION | 5214.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 10 | 0 | ACTION | 5214.065 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5216.33 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5218.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5218.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5222.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5222.065 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 5232.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 5232.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5233.395 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5234.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5234.065 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 5234.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 5234.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5238.46 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5240.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5240.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5240.46 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 5241.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 7 | 0 | ACTION | 5241.065 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5244.46 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5244.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5244.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5248.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5248.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5251.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5251.565 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 134583.3333 | ACTION | 5257.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 134583.3333 | ACTION | 5257.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 2 | 15833.3333 | ACTION | 5259.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 2 | 15833.3333 | ACTION | 5259.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5261.525 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 5262.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 5262.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5266.59 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 5268.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 5268.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5268.59 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5272.59 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 5275.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 5275.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5275.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 5275.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5289.655 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5294.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 5294.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5294.72 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5304.72 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5309.72 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5314.72 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5324.72 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5326.72 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5330.72 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5347.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 5347.565 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 332.6753 | 2633679.6537 | ACTION | 5347.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 72.1753 | 571387.987 | ACTION | 5347.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5347.785 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5352.85 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5353.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5353.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5354.85 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5355.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 5355.565 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5358.85 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5367.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5367.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5371.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5371.565 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 5371.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 5371.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 5373.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 5373.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5375.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5375.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5375.915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5379.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5379.565 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5379.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5379.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5380.98 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5382.98 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5383.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5383.565 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5386.98 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5395.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5395.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5399.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5399.065 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5399.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5399.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5402.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5402.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5404.045 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 5405.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 5405.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5406.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5406.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5409.11 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5411.11 | MooringSystemInstallation
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 5412.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 5412.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5415.11 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5430.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 5430.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5432.175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5437.24 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5439.24 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5443.24 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5460.305 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5462.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 5462.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5465.37 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5467.37 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5471.37 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5488.435 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5493.5 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5502.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 5502.065 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 226.6753 | 1794512.987 | ACTION | 5502.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 89.1753 | 705971.3203 | ACTION | 5502.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5503.5 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5508.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5508.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5508.5 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5510.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 5510.065 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5513.5 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5522.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5522.065 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5523.5 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5525.5 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5529.5 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 9 | 0 | ACTION | 5531.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 9 | 0 | ACTION | 5531.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5535.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5535.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5539.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5539.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5546.565 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5551.63 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5553.63 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5557.63 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5574.695 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5579.76 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5581.76 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5585.76 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5602.825 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5607.89 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5609.89 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5613.89 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 117 | 926250 | ACTION | 5625.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 117 | 926250 | ACTION | 5625.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 86 | 0 | ACTION | 5625.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 86 | 0 | ACTION | 5625.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5629.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5629.065 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5630.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 5630.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5630.955 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5633.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5633.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5636.02 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5638.02 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5642.02 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 5643.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 5643.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5645.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5645.065 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 5645.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 5645.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5648.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5648.565 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5651.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5651.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5652.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5652.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5655.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5655.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5659.085 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5664.15 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5666.15 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5670.15 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5671.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5671.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 5677.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 5677.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5679.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 5679.565 | MooredSubInstallation
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 5684.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 5684.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5687.215 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5692.28 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5702.28 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5707.28 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5712.28 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5722.28 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5724.28 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5728.28 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5745.345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5750.41 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5751.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 5751.565 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 338.6753 | 2681179.6537 | ACTION | 5751.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 67.1753 | 531804.6537 | ACTION | 5751.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5752.41 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5756.41 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5757.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5757.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5759.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 5759.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5771.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5771.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5773.475 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5775.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5775.565 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 5775.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 5775.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 5777.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 5777.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5778.54 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5779.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5779.565 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5780.54 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5783.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5783.565 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5783.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5783.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5784.54 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5787.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5787.565 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5798.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 5798.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5799.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5799.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5801.605 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5803.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5803.065 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5803.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5803.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5806.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5806.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5806.67 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5808.67 | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 5809.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 5809.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5810.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5810.065 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5812.67 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 5816.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 5816.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5829.735 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5834.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 5834.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5834.8 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5836.8 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5840.8 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5857.865 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5862.93 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5864.93 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5868.93 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5885.995 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5891.06 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5901.06 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5906.06 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5906.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 5906.065 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 221.6753 | 1754929.6537 | ACTION | 5906.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 89.1753 | 705971.3203 | ACTION | 5906.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5911.06 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5912.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5912.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5914.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 5914.065 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 5921.06 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5923.06 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5926.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5926.065 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5927.06 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5930.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5930.065 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 5930.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 5930.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 5932.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 5932.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5934.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5934.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5938.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5938.065 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5938.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5938.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5942.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5942.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5944.125 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5949.19 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5951.19 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5954.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5954.065 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5955.19 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5958.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5958.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 5964.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 5964.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5966.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 5966.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 5970.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 16 | 0 | ACTION | 5970.065 | MooredSubInstallation
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 5971.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 5971.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5972.255 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5973.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5973.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5977.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5977.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5977.32 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5979.32 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5980.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5980.565 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5983.32 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6000.385 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6004.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 6004.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6005.45 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6007.45 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6011.45 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6028.515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6033.58 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6035.58 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6039.58 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6056.645 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6061.71 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6063.71 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6067.71 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6076.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 6076.565 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 259.6753 | 2055762.987 | ACTION | 6076.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 105.1753 | 832637.987 | ACTION | 6076.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6082.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6082.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6084.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 6084.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6084.775 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6089.84 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6096.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6096.565 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6099.84 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6100.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6100.565 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 6100.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 6100.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 6102.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 6102.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6104.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6104.565 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6104.84 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6108.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6108.565 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6108.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6108.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6109.84 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6112.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6112.565 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6119.84 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6121.84 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6124.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6124.565 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6125.84 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6128.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6128.065 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6128.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6128.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6131.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6131.565 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6134.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 6134.565 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 6134.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 6134.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6135.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6135.065 | MooredSubInstallation
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 6141.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 6141.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6142.905 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6147.97 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6149.97 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6153.97 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6159.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 6159.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6171.035 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6176.1 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6178.1 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6182.1 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6199.165 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6204.23 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6206.23 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6210.23 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6227.295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6231.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 6231.065 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 259.6753 | 2055762.987 | ACTION | 6231.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 89.1753 | 705971.3203 | ACTION | 6231.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6232.36 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6234.36 | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6237.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6237.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6238.36 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6239.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 6239.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6251.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6251.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6255.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6255.065 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 6255.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 6255.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6255.425 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 6257.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 6257.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6259.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6259.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6260.49 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6262.49 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6263.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6263.065 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6263.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6263.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6266.49 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6267.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6267.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6279.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6279.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6282.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6282.565 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6283.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6283.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6283.555 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6288.62 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 6289.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 6289.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 6296.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 6296.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6298.62 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6302.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 6302.565 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6303.62 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6308.62 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6318.62 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6320.62 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 40 | 0 | ACTION | 6322.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 40 | 0 | ACTION | 6322.565 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6324.62 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6326.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6326.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6329.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6329.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6341.685 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6346.75 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6348.75 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6352.75 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6353.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 6353.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6369.815 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6374.88 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6376.88 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6380.88 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6397.945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6403.01 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6405.01 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6409.01 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6425.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 6425.565 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 283.6753 | 2245762.987 | ACTION | 6425.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 129.1753 | 1022637.987 | ACTION | 6425.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6426.075 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6431.14 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6433.14 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6433.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 6433.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6445.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6445.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6449.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6449.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6453.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6453.565 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 36 | 150000 | ACTION | 6469.14 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6470.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 6470.565 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6473.14 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 64 | 506666.6667 | ACTION | 6489.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 64 | 506666.6667 | ACTION | 6489.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 36 | 0 | ACTION | 6489.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 36 | 0 | ACTION | 6489.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6490.205 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6493.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6493.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6495.27 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6495.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6495.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6497.27 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6497.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6497.565 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6501.27 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6509.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6509.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6513.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6513.065 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 6513.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 6513.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 6515.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 6515.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6516.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6516.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6518.335 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6520.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6520.065 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6521.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6521.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6523.4 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6533.4 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6538.4 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6541.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6541.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6543.4 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6544.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 6544.065 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 6547.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 6547.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6553.4 | MooringSystemInstallation
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 6554.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 6554.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6555.4 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6559.4 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6576.465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6581.53 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6583.53 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6587.53 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6604.595 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6609.66 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6611.66 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6615.66 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6616.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 6616.065 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 319.6753 | 2530762.987 | ACTION | 6616.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 61.1753 | 484304.6537 | ACTION | 6616.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6622.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6622.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6624.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 6624.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6632.725 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6636.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6636.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6637.79 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6638.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 6638.565 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6639.79 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6640.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6640.065 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 6640.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 6640.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 6642.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 6642.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6643.79 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6644.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6644.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 6652.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 8 | 0 | ACTION | 6652.065 | MooredSubInstallation
| Towing Group 2 | Delay | 10 | 79166.6667 | ACTION | 6652.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 10 | 79166.6667 | ACTION | 6652.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6656.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6656.065 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6658.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6658.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6660.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6660.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6660.855 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6665.92 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6667.92 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6671.92 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6672.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6672.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6675.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6675.565 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6678.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6678.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6679.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6679.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6682.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6682.565 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 6684.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 6684.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6688.985 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 6691.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 6691.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6694.05 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6696.05 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6700.05 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6706.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 6706.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6717.115 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6722.18 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6732.18 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6737.18 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6742.18 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6752.18 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6754.18 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6758.18 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6775.245 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6778.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 6778.565 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 223.6753 | 1770762.987 | ACTION | 6778.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 87.1753 | 690137.987 | ACTION | 6778.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6780.31 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6782.31 | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6784.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6784.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6786.31 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6786.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 6786.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6798.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6798.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6802.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6802.565 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 6802.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 6802.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6803.375 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 6804.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 6804.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6806.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 6806.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6806.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6806.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6808.44 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6810.44 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6810.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6810.565 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6810.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6810.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6814.44 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6814.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6814.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6826.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6826.565 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6830.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6830.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6831.505 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6836.57 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 6836.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 6836.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6838.57 | MooringSystemInstallation
| Towing Group 1 | Transit | 3 | 23750 | ACTION | 6839.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 3 | 23750 | ACTION | 6839.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6842.57 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 3 | 23750 | ACTION | 6842.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 3 | 23750 | ACTION | 6842.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 4.1429 | 32797.619 | ACTION | 6846.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 4.1429 | 32797.619 | ACTION | 6846.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 29 | 0 | ACTION | 6855.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 29 | 0 | ACTION | 6855.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6859.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6859.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6859.635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6864.7 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6866.7 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6870.7 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 6873.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 14 | 0 | ACTION | 6873.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6876.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6876.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6887.765 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6892.83 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6894.83 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6898.83 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6915.895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 41 | 0 | ACTION | 6917.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 41 | 0 | ACTION | 6917.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6920.96 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6921.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6921.065 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6930.96 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6935.96 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6940.96 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6945.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 6945.065 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 6950.96 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6952.96 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6956.96 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6974.025 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6974.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 6974.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6979.09 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6981.09 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6985.09 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7002.155 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7007.22 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7009.22 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7013.22 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7017.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 7017.065 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 325.6753 | 2578262.987 | ACTION | 7017.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 170.1753 | 1347221.3203 | ACTION | 7017.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 2 | Delay: No Substructure Storage Available | 42.5 | 0 | ACTION | 7017.065 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7023.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7023.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7025.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 7025.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7030.285 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7035.35 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7037.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7037.065 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7037.35 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7041.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7041.065 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 7041.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 7041.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7041.35 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 7043.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 7043.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7045.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7045.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7049.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7049.065 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7049.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7049.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7053.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7053.065 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7058.415 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7063.48 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7065.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7065.065 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7065.48 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7068.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7068.565 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7069.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7069.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7069.48 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7072.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7072.065 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 7075.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 7075.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7075.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7075.565 | MooredSubInstallation
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 7082.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 7082.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7086.545 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7091.61 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7093.61 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7097.61 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7099.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 7099.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7114.675 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7119.74 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 7129.74 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7134.74 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7142.565 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 7144.74 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7146.74 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7150.74 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7167.805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7171.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 7171.565 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 324.6753 | 2570346.3203 | ACTION | 7171.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 89.1753 | 705971.3203 | ACTION | 7171.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7172.87 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7174.87 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7177.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7177.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7178.87 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7179.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 7179.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 7185.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7191.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7191.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7195.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7195.565 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 7195.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 7195.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7195.935 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 7197.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 7197.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7199.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7199.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7203 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7203.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7203.565 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7203.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7203.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7207 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7207.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7207.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7219.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7219.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7223.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7223.065 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7223.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7223.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7224.065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7226.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7226.565 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7229.13 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 7229.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 7229.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7230.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7230.065 | MooredSubInstallation
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 7236.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 7236.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7254.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 7254.065 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7310.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7326.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 7326.065 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 243.6753 | 1929096.3203 | ACTION | 7326.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 89.1753 | 705971.3203 | ACTION | 7326.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7332.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7332.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7334.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 7334.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7346.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7346.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7350.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7350.065 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 7350.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 7350.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 7352.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 7352.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 7353.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7354.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7354.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7358.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7358.065 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7358.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7358.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7362.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7362.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7374.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7374.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7377.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7377.565 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7378.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7378.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7381.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7381.065 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 7384.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 7384.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7384.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7384.565 | MooredSubInstallation
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 7391.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 7391.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7408.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 7408.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 49 | 0 | ACTION | 7457.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 49 | 0 | ACTION | 7457.565 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7478.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 7521.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7529.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 7529.565 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 292.6753 | 2317012.987 | ACTION | 7529.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 138.1753 | 1093887.987 | ACTION | 7529.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 2 | Delay: No Substructure Storage Available | 8.5 | 0 | ACTION | 7529.565 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7535.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7535.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7537.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 7537.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7549.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7549.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7553.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7553.565 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 7553.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 7553.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 7555.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 7555.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7557.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7557.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7561.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7561.565 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7561.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7561.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7565.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7565.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7577.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7577.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7581.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7581.065 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7581.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7581.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7584.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7584.565 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 7587.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 7587.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7588.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7588.065 | MooredSubInstallation
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 7594.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 7594.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7612.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 7612.065 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7646.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7684.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 7684.065 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 292.6753 | 2317012.987 | ACTION | 7684.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 89.1753 | 705971.3203 | ACTION | 7684.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7690.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7690.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7692.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 7692.065 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 7697.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7704.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7704.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7708.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7708.065 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 7708.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 7708.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 7710.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 7710.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7712.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7712.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7716.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7716.065 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7716.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7716.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7720.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7720.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7732.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7732.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7735.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7735.565 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7736.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7736.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7739.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7739.065 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 7742.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 7742.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7742.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7742.565 | MooredSubInstallation
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 7749.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 7749.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7766.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 7766.565 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7814.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7838.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 7838.565 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 243.6753 | 1929096.3203 | ACTION | 7838.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 89.1753 | 705971.3203 | ACTION | 7838.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7844.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7844.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7846.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 7846.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7858.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7858.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7862.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7862.565 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 7862.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 7862.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 7864.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 7864.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 7865.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7866.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7866.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7870.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7870.565 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7870.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7870.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7874.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7874.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7886.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7886.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7890.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7890.065 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7890.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7890.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7893.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7893.565 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 3 | 23750 | ACTION | 7893.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 3 | 23750 | ACTION | 7893.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7897.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7897.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7921.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 7921.065 | MooredSubInstallation
| Towing Group 1 | Delay | 66 | 522500 | ACTION | 7959.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 66 | 522500 | ACTION | 7959.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 3 | 23750 | ACTION | 7962.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 3 | 23750 | ACTION | 7962.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 7969.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 7969.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7982.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7993.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 7993.065 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 243.6753 | 1929096.3203 | ACTION | 7993.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 23.1753 | 183471.3203 | ACTION | 7993.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7999.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7999.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8001.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 8001.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8013.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8013.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8017.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8017.065 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 8017.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 8017.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 8019.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 8019.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8021.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8021.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8025.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8025.065 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8025.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8025.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8029.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8029.065 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 8033.565 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 118750 | ACTION | 8040.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 118750 | ACTION | 8040.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8041.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8041.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 8053.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 12 | 0 | ACTION | 8053.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8056.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8056.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8060.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8060.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8063.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8063.565 | MooredSubInstallation
| Towing Group 3 | Delay | 35 | 277083.3333 | ACTION | 8075.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 35 | 277083.3333 | ACTION | 8075.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 39583.3333 | ACTION | 8080.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 39583.3333 | ACTION | 8080.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 8086.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 8086.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8087.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 8087.565 | MooredSubInstallation
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 8093.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 8093.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8150.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8159.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 8159.565 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 189.6753 | 1501596.3203 | ACTION | 8159.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 66.1753 | 523887.987 | ACTION | 8159.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8165.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8165.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8167.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 8167.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8179.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8179.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8183.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8183.565 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 8183.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 8183.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 8185.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 8185.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8187.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8187.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8191.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8191.565 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8191.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8191.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8195.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8195.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 8201.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8207.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8207.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 8209.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 2 | 0 | ACTION | 8209.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8213.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8213.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8216.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8216.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8220.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8220.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8244.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 8244.065 | MooredSubInstallation
| Towing Group 2 | Delay | 100 | 791666.6667 | ACTION | 8291.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 100 | 791666.6667 | ACTION | 8291.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 8311.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 8311.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8316.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 8316.065 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 222.6753 | 1762846.3203 | ACTION | 8316.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 8317.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 8317.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8318.565 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8322.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8324.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 8324.065 | MooredSubInstallation
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 8324.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 8324.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8330.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8336.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8336.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8340.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8340.065 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 8340.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 8342.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8344.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8344.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8348.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8348.065 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8348.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 8349.0715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 8351.0715 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8352.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8352.065 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 55416.6667 | ACTION | 8355.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8364.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8364.065 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 8369.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 8380.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 16 | 0 | ACTION | 8380.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8383.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8383.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8387.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8387.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8390.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8390.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8414.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 8414.565 | MooredSubInstallation
| Towing Group 2 | Delay | 132 | 1045000 | ACTION | 8483.0715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 128 | 1013333.3333 | ACTION | 8483.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8486.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8486.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 8486.565 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 161.6753 | 1279929.6537 | ACTION | 8486.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8489.0715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8492.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 39583.3333 | ACTION | 8494.0715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 87083.3333 | ACTION | 8494.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8494.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 8494.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8506.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8506.565 | MooredSubInstallation
| Towing Group 2 | Delay | 14 | 110833.3333 | ACTION | 8508.0715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 14 | 110833.3333 | ACTION | 8508.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 15833.3333 | ACTION | 8510.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8510.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8510.565 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 8510.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 8512.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8514.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8514.565 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 8516.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8518.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8518.565 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8518.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8522.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8522.565 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 118750 | ACTION | 8523.0715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 8523.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 8529.0715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8529.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8534.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8534.565 | MooredSubInstallation
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 8536.2144 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 8537.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8538.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8538.065 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 8538.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8541.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8541.565 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 8544.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 8547.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 8549.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7 | 55416.6667 | ACTION | 8551.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 3 | 23750 | ACTION | 8552.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 1 | 7916.6667 | ACTION | 8552.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 0.14286 | 1130.9524 | ACTION | 8552.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 8556.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 15 | 0 | ACTION | 8556.565 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8558.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8560.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8560.065 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 8578.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8584.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 8584.065 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 8584.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 8591.7144 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8654.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8656.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 8656.065 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 119.8506 | 948817.6407 | ACTION | 8656.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 103.1753 | 816804.6537 | ACTION | 8656.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8662.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8662.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8664.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 8664.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8676.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8676.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8680.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8680.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8684.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8684.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8688.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8688.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8692.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8692.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8704.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8704.065 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 8705.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8707.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8707.565 | MooredSubInstallation
0.5 | Array Cable Installation Vessel | Mobilize | 72 | 337500 | ACTION | 8711.6247 | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 8715.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 8 | 0 | ACTION | 8715.565 | MooredSubInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 56250 | ACTION | 8717.6247 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8719.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8719.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8722.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8722.565 | MooredSubInstallation
| Towing Group 2 | Delay | 64 | 506666.6667 | ACTION | 8726.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 64 | 506666.6667 | ACTION | 8726.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 8744.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 8744.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 8746.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 8746.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8746.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 8746.565 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8752.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8752.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 8755.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 8755.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8818.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 8818.565 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 226.8506 | 1795900.974 | ACTION | 8818.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8822.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8826.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 8826.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8838.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8838.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8842.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8842.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8846.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8846.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8850.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8850.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8854.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8854.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8866.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8866.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8870.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8870.065 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 8873.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8873.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8873.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8877.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8877.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8901.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 8901.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8973.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 8973.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8981.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 8981.065 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8990.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8993.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8993.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8997.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8997.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9001.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9001.065 | MooredSubInstallation
| Towing Group 1 | Delay | 185 | 1464583.3333 | ACTION | 9003.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9005.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9005.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9009.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9009.065 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9009.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 255 | 2018750 | ACTION | 9010.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 255 | 2018750 | ACTION | 9010.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 39583.3333 | ACTION | 9015.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 39583.3333 | ACTION | 9015.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9021.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9021.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 9024.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 3 | 0 | ACTION | 9024.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9027.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9027.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9031.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9031.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9034.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9034.565 | MooredSubInstallation
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 9041.565 | MooredSubInstallation
| Towing Group 1 | Delay | 41 | 324583.3333 | ACTION | 9050.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 42 | 332500 | ACTION | 9057.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 42 | 332500 | ACTION | 9057.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9058.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 9058.565 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 9068.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 95000 | ACTION | 9069.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 95000 | ACTION | 9069.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 59 | 467083.3333 | ACTION | 9127.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 59 | 467083.3333 | ACTION | 9128.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 59 | 467083.3333 | ACTION | 9128.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 9129.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9130.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 9130.565 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 9134.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 9134.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 418 | 3918750 | ACTION | 9135.6247 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9135.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9138.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 9138.565 | MooredSubInstallation
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 9141.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 9141.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Transit | 6 | 56250 | ACTION | 9141.6247 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9147.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9147.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9150.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9150.565 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 126666.6667 | ACTION | 9151.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9154.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9154.565 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9158.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9158.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9158.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9162.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9162.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9166.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9166.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 9172.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 6 | 0 | ACTION | 9172.565 | MooredSubInstallation
| Towing Group 2 | Delay | 33 | 261250 | ACTION | 9180.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 33 | 261250 | ACTION | 9180.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9184.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9184.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9188.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9188.065 | MooredSubInstallation
| Towing Group 1 | Delay | 37 | 292916.6667 | ACTION | 9188.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9191.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9191.565 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 31666.6667 | ACTION | 9192.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9195.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9195.065 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 5 | 39583.3333 | ACTION | 9197.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 9198.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 9198.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 2 | Substructure Assembly | 168 | 0 | ACTION | 9209.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9219.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 9219.065 | MooredSubInstallation
| Towing Group 2 | Delay | 44 | 348333.3333 | ACTION | 9242.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 44 | 348333.3333 | ACTION | 9242.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 45 | 356250 | ACTION | 9242.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 1 | 7916.6667 | ACTION | 9243.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 9244.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 9244.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9250.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9250.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 109 | 1021875 | ACTION | 9250.6247 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 9250.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Transit | 2.6957 | 25271.7391 | ACTION | 9253.3204 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 9255.3204 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 9256.3204 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9256.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 9261.8204 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 9267.3204 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 9268.3204 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9270.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9270.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 9275.0715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 9276.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 9276.5715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 9277.0715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9283.0715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 9283.7144 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 9283.7144 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 16.0261 | 150244.4853 | ACTION | 9284.3465 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 9285.3465 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9289.7144 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9289.7144 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 9290.8465 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9291.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 9291.065 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 9296.3465 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 9298.3465 | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9299.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 9299.065 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 9299.3465 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9303.0715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 9307.8962 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 9307.8962 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 9309.0715 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 9309.8962 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 9309.8962 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9311.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9311.065 | MooredSubInstallation
| Towing Group 1 | Transit | 4 | 31666.6667 | ACTION | 9313.0715 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9315.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9315.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9319.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9319.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9323.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9323.065 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9326.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9327.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9327.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9339.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9339.065 | MooredSubInstallation
| Towing Group 1 | Delay | 29 | 229583.3333 | ACTION | 9342.0715 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9342.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9342.565 | MooredSubInstallation
| Towing Group 1 | Transit | 3.1429 | 24880.9524 | ACTION | 9345.2144 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9346.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9346.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9349.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9349.565 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9351.2144 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 37 | 0 | ACTION | 9386.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 37 | 0 | ACTION | 9386.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9410.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 9410.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 9437.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Delay | 27 | 0 | ACTION | 9437.565 | MooredSubInstallation
| Towing Group 1 | Delay | 117 | 926250 | ACTION | 9468.2144 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 166 | 1314166.6667 | ACTION | 9475.8962 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 166 | 1314166.6667 | ACTION | 9475.8962 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9481.8962 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9481.8962 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 9486.3962 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 9488.3962 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9494.3962 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 196 | 1837500 | ACTION | 9495.3465 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 9500.8465 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9501.8962 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9501.8962 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 9506.3465 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 9507.3465 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 9507.8962 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 9507.8962 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9509.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 9509.565 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9514.3962 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 9515.039 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 9515.039 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9517.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Move Substructure | 8 | 0 | ACTION | 9517.565 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 9520.3962 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9521.039 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9521.039 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 16.0261 | 150244.4853 | ACTION | 9523.3725 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 9524.3725 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 9527.539 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9529.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9529.565 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 9529.8725 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9533.539 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9533.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9533.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9537.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9537.565 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 9539.2208 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 9539.2208 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9541.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9541.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9545.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9545.565 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 9551.7208 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9557.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9557.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9561.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9561.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9564.565 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9564.565 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9568.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9568.065 | MooredSubInstallation
| Towing Group 1 | Delay | 17 | 134583.3333 | ACTION | 9568.7208 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 30 | 237500 | ACTION | 9569.2208 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 30 | 237500 | ACTION | 9569.2208 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 9570.7208 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 9571.2208 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 9571.2208 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9576.7208 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9577.2208 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9577.2208 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9592.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Mechanical Completion | 24 | 0 | ACTION | 9592.065 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9596.7208 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9597.2208 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9597.2208 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 9602.7208 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 9603.2208 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 9603.2208 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 9609.8637 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 9610.3637 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 9610.3637 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 101 | 946875 | ACTION | 9630.8725 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 9636.3725 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 9638.3725 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 9639.3725 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 9644.8725 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 9650.3725 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 9651.3725 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 18750 | ACTION | 9653.3725 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9664.065 | MooredSubInstallation
| Turbine Assembly Line 2 | Electrical Completion | 72 | 0 | ACTION | 9664.065 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 54.2013 | 429093.6147 | ACTION | 9664.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 53.7013 | 425135.2814 | ACTION | 9664.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9670.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9670.065 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9672.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9684.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9688.065 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 9688.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 9688.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 9690.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 9690.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9692.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9696.065 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9696.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9696.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9700.065 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 53 | 496875 | ACTION | 9706.3725 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 2.9378 | 27542.3219 | ACTION | 9709.3104 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 9710.3104 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9712.065 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9715.565 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 9715.8104 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9716.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9716.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9719.065 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 9721.3104 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 9722.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 9722.2468 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9722.565 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 9723.3104 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 9724.3104 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 7.1429 | 56547.619 | ACTION | 9729.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.1429 | 56547.619 | ACTION | 9729.3897 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 9729.8104 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 9735.3104 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 9736.3104 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 9741.2482 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 9742.2482 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9746.565 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 9747.7482 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 9753.2482 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 9755.2482 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 9756.2482 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 9761.7482 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 9767.2482 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 9768.2482 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 9773.1861 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 9774.1861 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 9779.6861 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 9785.1861 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 9787.1861 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 9788.1861 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 9793.6861 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 9799.1861 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 9800.1861 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 28125 | ACTION | 9803.1861 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9818.565 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 208.2013 | 1648260.2814 | ACTION | 9818.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 5 | 39583.3333 | ACTION | 9823.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9829.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 25 | 197916.6667 | ACTION | 9854.565 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 18.1818 | 143939.3939 | ACTION | 9872.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 72 | 570000 | ACTION | 9944.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 9946.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9952.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 155 | 1453125 | ACTION | 9958.1861 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.9378 | 18167.3219 | ACTION | 9960.1239 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 9961.1239 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 9966.6239 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 9972.1239 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9972.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 9974.1239 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 9975.1239 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 9978.7468 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 9980.6239 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 7.1429 | 56547.619 | ACTION | 9985.8897 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 9986.1239 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 60 | 562500 | ACTION | 10046.1239 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 10047.1239 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 10052.0618 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 10053.0618 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 154 | 1443750 | ACTION | 10207.0618 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 10212.5618 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 10218.0618 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 10220.0618 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 10221.0618 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 10226.5618 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 10232.0618 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 10233.0618 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 10237.9996 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 10238.9996 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 10244.4996 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 10249.9996 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 10251.9996 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 10252.9996 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 37 | 346875 | ACTION | 10289.9996 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 10295.4996 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 10300.9996 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 10301.9996 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 28125 | ACTION | 10304.9996 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 196 | 1837500 | ACTION | 10500.9996 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.9378 | 18167.3219 | ACTION | 10502.9375 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 10503.9375 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 10509.4375 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 10514.9375 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 10516.9375 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 10517.9375 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 10523.4375 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 10528.9375 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 10529.9375 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 10534.8753 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 10535.8753 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 10541.3753 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 52 | 487500 | ACTION | 10593.3753 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 10598.8753 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 10600.8753 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 10601.8753 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 10607.3753 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 10612.8753 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 10613.8753 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 10618.8132 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 10619.8132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 10625.3132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 10630.8132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 10632.8132 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 10633.8132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 10639.3132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 10644.8132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 193 | 1809375 | ACTION | 10837.8132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 10838.8132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 10843.751 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 10844.751 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 10850.251 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 10855.751 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 10857.751 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 10858.751 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 10864.251 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 10869.751 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 10870.751 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 10875.6889 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 10876.6889 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 10882.1889 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 53 | 496875 | ACTION | 10935.1889 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 10940.6889 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 10942.6889 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 10943.6889 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 10949.1889 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 10954.6889 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 10955.6889 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 10960.6267 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 10961.6267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 10967.1267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 10972.6267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 10974.6267 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 10975.6267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 10981.1267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 10986.6267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 10987.6267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 10992.5646 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 10993.5646 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 10999.0646 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11004.5646 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 11006.5646 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11007.5646 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 11013.0646 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11018.5646 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 11019.5646 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 11024.5024 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 74 | 693750 | ACTION | 11098.5024 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11099.5024 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 184 | 1725000 | ACTION | 11283.5024 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 11289.0024 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11294.5024 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 11296.5024 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11297.5024 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 11303.0024 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11308.5024 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 11309.5024 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 11314.4403 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11315.4403 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 11320.9403 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11326.4403 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 11328.4403 | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 39 | 365625 | ACTION | 11367.4403 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11368.4403 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 11373.9403 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11379.4403 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 11380.4403 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 28125 | ACTION | 11383.4403 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 106 | 993750 | ACTION | 11489.4403 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.9378 | 18167.3219 | ACTION | 11491.3781 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11492.3781 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 11497.8781 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11503.3781 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 11505.3781 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11506.3781 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 11511.8781 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11517.3781 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 11518.3781 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 11523.316 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11524.316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 11529.816 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11535.316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 11537.316 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11538.316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 11543.816 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11549.316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 11550.316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 11555.2538 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11556.2538 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 11561.7538 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11567.2538 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 18 | 168750 | ACTION | 11585.2538 | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 11587.2538 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11588.2538 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 7 | 65625 | ACTION | 11595.2538 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 11600.7538 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11606.2538 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 11607.2538 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 11612.1917 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11613.1917 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 11618.6917 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11624.1917 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 11626.1917 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11627.1917 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 11632.6917 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 146 | 1368750 | ACTION | 11778.6917 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11784.1917 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 11785.1917 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 11790.1295 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11791.1295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 11796.6295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11802.1295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 126 | 1181250 | ACTION | 11928.1295 | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 11930.1295 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11931.1295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 11936.6295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11942.1295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 11943.1295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 11948.0674 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11949.0674 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 11954.5674 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11960.0674 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 11962.0674 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11963.0674 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 11968.5674 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 11974.0674 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 11975.0674 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 11980.0052 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 11981.0052 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 69 | 646875 | ACTION | 12050.0052 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12055.5052 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12061.0052 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12063.0052 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12064.0052 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12069.5052 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 254 | 2381250 | ACTION | 12323.5052 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12329.0052 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 12330.0052 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 76 | 712500 | ACTION | 12406.0052 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 12410.943 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12411.943 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12417.443 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12422.943 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12424.943 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12425.943 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12431.443 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12436.943 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 12437.943 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 12442.8809 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12443.8809 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12449.3809 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 161 | 1509375 | ACTION | 12610.3809 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12615.8809 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12617.8809 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12618.8809 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12624.3809 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12629.8809 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 12630.8809 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 12635.8187 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12636.8187 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12642.3187 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 11 | 103125 | ACTION | 12653.3187 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12658.8187 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12660.8187 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12661.8187 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12667.3187 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12672.8187 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 12673.8187 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 12678.7566 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12679.7566 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12685.2566 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12690.7566 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12692.7566 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12693.7566 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12699.2566 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12704.7566 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 12705.7566 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 12710.6944 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12711.6944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12717.1944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12722.6944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12724.6944 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12725.6944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12731.1944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12736.6944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 12737.6944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 12742.6323 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12743.6323 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 132 | 1237500 | ACTION | 12875.6323 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12881.1323 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12886.6323 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12888.6323 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12889.6323 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12895.1323 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12900.6323 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 12901.6323 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 12906.5701 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12907.5701 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12913.0701 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12918.5701 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12920.5701 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12921.5701 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12927.0701 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12932.5701 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 12933.5701 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 12938.508 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12939.508 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12945.008 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12950.508 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12952.508 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12953.508 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12959.008 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12964.508 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 12965.508 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 12970.4458 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12971.4458 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12976.9458 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12982.4458 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12984.4458 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12985.4458 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12990.9458 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12996.4458 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 12997.4458 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 13002.3837 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13003.3837 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13008.8837 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 101 | 946875 | ACTION | 13109.8837 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13115.3837 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13117.3837 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13118.3837 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13123.8837 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13129.3837 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13130.3837 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 13135.3215 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13136.3215 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13141.8215 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13147.3215 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13149.3215 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13150.3215 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13155.8215 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 7 | 65625 | ACTION | 13162.8215 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13168.3215 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13169.3215 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 13174.2594 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13175.2594 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13180.7594 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13186.2594 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13188.2594 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13189.2594 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13194.7594 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13200.2594 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13201.2594 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 13206.1972 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13207.1972 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13212.6972 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13218.1972 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13220.1972 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13221.1972 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13226.6972 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13232.1972 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13233.1972 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 13238.1351 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13239.1351 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13244.6351 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13250.1351 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13252.1351 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13253.1351 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13258.6351 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 72 | 675000 | ACTION | 13330.6351 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13336.1351 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13337.1351 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 13342.0729 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13343.0729 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 184 | 1725000 | ACTION | 13527.0729 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13532.5729 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13538.0729 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13540.0729 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13541.0729 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13546.5729 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13552.0729 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13553.0729 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 13558.0108 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13559.0108 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13564.5108 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13570.0108 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13572.0108 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13573.0108 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13578.5108 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13584.0108 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13585.0108 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 28125 | ACTION | 13588.0108 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 85 | 796875 | ACTION | 13673.0108 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.9378 | 18167.3219 | ACTION | 13674.9486 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13675.9486 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13681.4486 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13686.9486 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13688.9486 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13689.9486 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13695.4486 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13700.9486 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13701.9486 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 13706.8865 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13707.8865 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13713.3865 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13718.8865 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13720.8865 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13721.8865 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13727.3865 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13732.8865 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13733.8865 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 13738.8243 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13739.8243 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13745.3243 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13750.8243 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13752.8243 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13753.8243 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13759.3243 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13764.8243 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13765.8243 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 13770.7622 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13771.7622 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13777.2622 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13782.7622 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13784.7622 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13785.7622 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13791.2622 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13796.7622 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13797.7622 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 13802.7 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13803.7 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13809.2 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13814.7 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13816.7 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13817.7 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13823.2 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13828.7 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13829.7 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 13834.6378 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13835.6378 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13841.1378 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13846.6378 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13848.6378 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13849.6378 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13855.1378 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13860.6378 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13861.6378 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 13866.5757 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13867.5757 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13873.0757 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13878.5757 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13880.5757 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13881.5757 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13887.0757 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13892.5757 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13893.5757 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 13898.5135 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13899.5135 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13905.0135 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13910.5135 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13912.5135 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13913.5135 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13919.0135 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13924.5135 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13925.5135 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 13930.4514 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13931.4514 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13936.9514 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 91 | 853125 | ACTION | 14027.9514 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14033.4514 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14035.4514 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14036.4514 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14041.9514 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14047.4514 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14048.4514 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14053.3892 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14054.3892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14059.8892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14065.3892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14067.3892 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14068.3892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14073.8892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14079.3892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14080.3892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14085.3271 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14086.3271 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14091.8271 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14097.3271 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14099.3271 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14100.3271 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14105.8271 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14111.3271 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14112.3271 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14117.2649 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14118.2649 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14123.7649 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14129.2649 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14131.2649 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14132.2649 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14137.7649 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14143.2649 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14144.2649 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14149.2028 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14150.2028 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14155.7028 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14161.2028 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14163.2028 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14164.2028 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14169.7028 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14175.2028 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14176.2028 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14181.1406 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14182.1406 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14187.6406 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14193.1406 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14195.1406 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14196.1406 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14201.6406 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14207.1406 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14208.1406 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14213.0785 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14214.0785 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 148 | 1387500 | ACTION | 14362.0785 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14367.5785 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14373.0785 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14375.0785 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14376.0785 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14381.5785 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14387.0785 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14388.0785 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14393.0163 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14394.0163 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14399.5163 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14405.0163 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14407.0163 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14408.0163 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14413.5163 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14419.0163 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14420.0163 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14424.9542 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14425.9542 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14431.4542 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14436.9542 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14438.9542 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14439.9542 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14445.4542 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14450.9542 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14451.9542 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14456.892 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14457.892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14463.392 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14468.892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14470.892 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14471.892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14477.392 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14482.892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14483.892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 28125 | ACTION | 14486.892 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 14 | 131250 | ACTION | 14500.892 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.9378 | 18167.3219 | ACTION | 14502.8299 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14503.8299 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 9 | 84375 | ACTION | 14512.8299 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14518.3299 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14523.8299 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14525.8299 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14526.8299 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14532.3299 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14537.8299 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14538.8299 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14543.7677 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14544.7677 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14550.2677 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14555.7677 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14557.7677 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14558.7677 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14564.2677 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14569.7677 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14570.7677 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14575.7056 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14576.7056 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14582.2056 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14587.7056 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14589.7056 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14590.7056 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 21 | 196875 | ACTION | 14611.7056 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14617.2056 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 8 | 75000 | ACTION | 14625.2056 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14630.7056 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14631.7056 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 12.0467 | 112937.754 | ACTION | 14643.7523 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14644.7523 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14650.2523 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14655.7523 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14657.7523 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14658.7523 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14664.2523 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14669.7523 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14670.7523 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 12.0467 | 112937.754 | ACTION | 14682.7989 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14683.7989 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14689.2989 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14694.7989 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14696.7989 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14697.7989 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14703.2989 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14708.7989 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14709.7989 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8.3095 | 77901.6126 | ACTION | 14718.1085 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14719.1085 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14724.6085 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14730.1085 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14732.1085 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14733.1085 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14738.6085 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14744.1085 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14745.1085 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8.3095 | 77901.6126 | ACTION | 14753.418 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14754.418 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14759.918 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14765.418 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14767.418 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14768.418 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14773.918 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14779.418 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14780.418 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.4336 | 50939.9102 | ACTION | 14785.8516 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14786.8516 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14792.3516 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14797.8516 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14799.8516 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14800.8516 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14806.3516 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14811.8516 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14812.8516 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.4336 | 50939.9102 | ACTION | 14818.2851 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14819.2851 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14824.7851 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14830.2851 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 8.6957 | 81521.7391 | ACTION | 14838.9808 | ArrayCableInstallation | ArrayCableInstallation | FALSE