## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | include_onshore_construction | max_waveheight | max_windspeed | transit_speed | num_vessels | num_ahts_vessels
0.5 | Export Cable Installation Vessel | Mobilize | 72 | 450000 | ACTION | 0 | ExportCableInstallation
1 | Mooring System Installation Vessel | Mobilize | 168 | 700000 | ACTION | 0 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Load Cable | 6 | 75000 | ACTION | 6 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 21.1351 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 23.1351 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 27.1351 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 44.2001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 49.2651 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 51.2651 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 55.2651 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 72.3301 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 77.3951 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 79.3951 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 83.3951 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 88 | 1100000 | ACTION | 94 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Tow Plow | 0.4 | 5000 | ACTION | 94.4 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Pull Winch | 0.4 | 5000 | ACTION | 94.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Prepare Cable | 1 | 12500 | ACTION | 95.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 100.4601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 101.3 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 105.5251 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 106.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 107.5251 | MooringSystemInstallation
| Export Cable Installation Vessel | Lower Cable | 1 | 12500 | ACTION | 107.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 111.5251 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 128.5901 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 133.6551 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 135.6551 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 139.6551 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 156.7201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 50 | 625000 | ACTION | 157.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 161.7851 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 163.7851 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 167.7851 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 184.8501 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 189.9151 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 201.0502 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 206.0502 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 211.0502 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 222.1853 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 224.1853 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 228.1853 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 245.2503 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 26 | 108333.3333 | ACTION | 271.2503 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 276.3153 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 278.3153 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 282.3153 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 299.3803 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 304.4453 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 306.4453 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 310.4453 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 164 | 2050000 | ACTION | 321.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 327.5103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 332.5753 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 334.5753 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 16 | 200000 | ACTION | 337.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 338.5753 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 1 | 12500 | ACTION | 338.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 355.6403 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 17 | 212500 | ACTION | 355.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 360.7053 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 362.7053 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 366.7053 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 383.7703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 388.8353 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 390.8353 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 394.8353 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 40 | 500000 | ACTION | 395.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 411.9003 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 416.9653 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 24 | 300000 | ACTION | 419.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 428.1004 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 433.1004 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substation Assembly Line 1 | Substation Substructure Assembly | 0 | 0 | ACTION | 436.5993 | FloatingSubstationInstallation
| Substation Assembly Line 1 | Attach Topside | 24 | 0 | ACTION | 460.5993 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay: Waiting on Substation Assembly | 24 | 100000 | ACTION | 460.5993 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 156 | 650000 | ACTION | 589.1004 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 129 | 537500 | ACTION | 589.5993 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 594.1004 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 605.2355 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 607.2355 | MooringSystemInstallation
| Floating Substation Installation Vessel | Tow Substation to Site | 18.5585 | 77327.0833 | ACTION | 608.1578 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 610.1578 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 611.2355 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 34 | 141666.6667 | ACTION | 645.2355 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 43 | 179166.6667 | ACTION | 653.1578 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 659.1578 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 662.3005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 663.1578 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 667.3655 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 669.3655 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 251 | 3137500 | ACTION | 670.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 673.3655 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 16.065 | 66937.5 | ACTION | 679.2228 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 684.2878 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 19 | 237500 | ACTION | 689.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 690.4305 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 695.4955 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 697.4955 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 701.4955 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 12 | 150000 | ACTION | 701.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 706.2878 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 718.2878 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 718.5605 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 722.2878 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 723.6255 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 725.6255 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 729.6255 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 16.065 | 66937.5 | ACTION | 738.3528 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 743.4178 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 746.6905 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 751.7555 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 753.7555 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 757.7555 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 765.4178 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 73 | 912500 | ACTION | 774.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 774.8205 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Check Mooring Lines | 11 | 45833.3333 | ACTION | 776.4178 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay | 1 | 4166.6667 | ACTION | 777.4178 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 1 | 4166.6667 | ACTION | 778.4178 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 779.8855 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 781.8855 | MooringSystemInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 782.4178 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 785.8855 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 16.065 | 66937.5 | ACTION | 798.4828 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 802.9505 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 803.5478 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 808.0155 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 819.1506 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 824.1506 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 829.1506 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 35 | 145833.3333 | ACTION | 838.5478 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 840.2857 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 842.2857 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 846.2857 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 78 | 975000 | ACTION | 852.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 860.5478 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 863.3507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 868.4157 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 16 | 200000 | ACTION | 868.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 870.4157 | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 872.5478 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 874.4157 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 9 | 112500 | ACTION | 877.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 2 | 25000 | ACTION | 879.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 883.6829 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 891.4807 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 896.5457 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 898.5457 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 902.5457 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 919.6107 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 924.6757 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 926.6757 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 930.6757 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 56 | 700000 | ACTION | 935.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 947.7407 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 952.8057 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 954.8057 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 23 | 287500 | ACTION | 958.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 958.8057 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 975.8707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 980.9357 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 982.9357 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 986.9357 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 24 | 100000 | ACTION | 1010.9357 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1028.0007 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1033.0657 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 1044.2008 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1049.2008 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1054.2008 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 1065.3359 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 107 | 1337500 | ACTION | 1065.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1067.3359 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1071.3359 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1088.4009 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1093.4659 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1095.4659 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1099.4659 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 49 | 612500 | ACTION | 1114.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1116.5309 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1121.5959 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1123.5959 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 66 | 275000 | ACTION | 1189.5959 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1193.5959 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 89 | 370833.3333 | ACTION | 1282.5959 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1299.6609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1304.7259 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1306.7259 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 194 | 2425000 | ACTION | 1308.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1310.7259 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1327.7909 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 19 | 237500 | ACTION | 1327.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Delay | 1 | 12500 | ACTION | 1328.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1332.8559 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1334.8559 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1338.8559 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1355.9209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1360.9859 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1362.9859 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1366.9859 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1384.0509 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1389.1159 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 63 | 787500 | ACTION | 1391.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 1400.251 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1405.251 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1410.251 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 1421.3861 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1423.3861 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1427.3861 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 42 | 525000 | ACTION | 1433.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1444.4511 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1449.5161 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1451.5161 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1455.5161 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 34 | 425000 | ACTION | 1467.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Delay | 1 | 12500 | ACTION | 1468.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 2 | 25000 | ACTION | 1470.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1472.5811 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1477.6461 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1479.6461 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1483.6461 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1500.7111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 31 | 387500 | ACTION | 1501.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1505.7761 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1507.7761 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1511.7761 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 25 | 312500 | ACTION | 1526.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1528.8411 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 29 | 120833.3333 | ACTION | 1557.8411 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1562.9061 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1564.9061 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1568.9061 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1585.9711 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 64 | 800000 | ACTION | 1590.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1591.0361 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1593.0361 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1597.0361 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1614.1011 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1619.1661 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 39 | 487500 | ACTION | 1629.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 1630.3012 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1635.3012 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1640.3012 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 1651.4363 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1653.4363 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 27 | 337500 | ACTION | 1656.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1657.4363 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 2 | 25000 | ACTION | 1658.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Delay | 2 | 25000 | ACTION | 1660.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 6 | 75000 | ACTION | 1666.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1674.5013 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1679.5663 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1681.5663 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1685.5663 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 30 | 375000 | ACTION | 1696.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1702.6313 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1707.6963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1709.6963 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1713.6963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 26.9147 | 336433.2719 | ACTION | 1723.7147 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Position Onsite | 2 | 25000 | ACTION | 1725.7147 | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1730.7613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 1731.2147 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1735.8263 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 1736.7147 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1737.8263 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1741.8263 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Transit | 9.6827 | 121033.6957 | ACTION | 1746.3974 | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1758.8913 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1763.9563 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1765.9563 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1769.9563 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1787.0213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1792.0863 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1794.0863 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1798.0863 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1815.1513 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1820.2163 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 1831.3514 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1836.3514 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1841.3514 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 1852.4865 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1854.4865 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1858.4865 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1875.5515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1880.6165 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1882.6165 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1886.6165 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1903.6815 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1908.7465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1910.7465 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1914.7465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1931.8115 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1936.8765 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1938.8765 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1942.8765 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1959.9415 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1965.0065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1967.0065 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1971.0065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1988.0715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1993.1365 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1995.1365 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1999.1365 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2016.2015 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2021.2665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 2032.4016 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2037.4016 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2042.4016 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 2053.5367 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2055.5367 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2059.5367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 114 | 475000 | ACTION | 2173.5367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2190.6017 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2195.6667 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 46 | 191666.6667 | ACTION | 2241.6667 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2243.6667 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2247.6667 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2264.7317 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2269.7967 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2271.7967 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2275.7967 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2292.8617 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2297.9267 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2299.9267 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2303.9267 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 51 | 212500 | ACTION | 2354.9267 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2371.9917 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2377.0567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2379.0567 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2383.0567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2400.1217 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2405.1867 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2407.1867 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2411.1867 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2428.2517 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2433.3167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 2444.4518 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2449.4518 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2454.4518 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 2465.5869 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2467.5869 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2471.5869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 31 | 129166.6667 | ACTION | 2502.5869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2519.6519 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2524.7169 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2526.7169 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2530.7169 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2547.7819 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2552.8469 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2554.8469 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2558.8469 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2575.9119 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2580.9769 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2582.9769 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2586.9769 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2604.0419 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2609.1069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2611.1069 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2615.1069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2632.1719 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2637.2369 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 14 | 58333.3333 | ACTION | 2651.2369 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2653.2369 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2657.2369 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2674.3019 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2679.3669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 2690.502 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2695.502 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2700.502 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 2710.502 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 14 | 58333.3333 | ACTION | 2724.502 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 1.1351 | 4729.5833 | ACTION | 2725.6371 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2727.6371 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2731.6371 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2748.7021 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2753.7671 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2755.7671 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2759.7671 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2776.8321 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2781.8971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2783.8971 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2787.8971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 50 | 208333.3333 | ACTION | 2837.8971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2854.9621 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2860.0271 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2862.0271 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2866.0271 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2883.0921 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2888.1571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2890.1571 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2894.1571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2911.2221 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2916.2871 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2918.2871 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2922.2871 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2939.3521 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2944.4171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 2955.5522 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2960.5522 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2965.5522 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 2976.6873 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2978.6873 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2982.6873 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 85 | 354166.6667 | ACTION | 3067.6873 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3084.7523 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3089.8173 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3091.8173 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3095.8173 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3112.8823 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3117.9473 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3119.9473 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3123.9473 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3141.0123 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3146.0773 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3148.0773 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3152.0773 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3169.1423 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 38 | 158333.3333 | ACTION | 3207.1423 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3212.2073 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3214.2073 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3218.2073 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3235.2723 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3240.3373 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3242.3373 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3246.3373 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3263.4023 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3268.4673 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 3279.6024 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3284.6024 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3289.6024 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 3300.7375 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3302.7375 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3306.7375 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3323.8025 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3328.8675 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3330.8675 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3334.8675 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3351.9325 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3356.9975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3358.9975 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3362.9975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3380.0625 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3385.1275 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3387.1275 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3391.1275 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3408.1925 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3413.2575 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3415.2575 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3419.2575 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3436.3225 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3441.3875 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3443.3875 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3447.3875 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3464.4525 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3469.5175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 3480.6526 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3485.6526 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3490.6526 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 3501.7877 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3503.7877 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3507.7877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3524.8527 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3529.9177 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3531.9177 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3535.9177 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3552.9827 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3558.0477 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3560.0477 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3564.0477 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3581.1127 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3586.1777 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3588.1777 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3592.1777 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3609.2427 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3614.3077 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3616.3077 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3620.3077 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3637.3727 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3642.4377 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3644.4377 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3648.4377 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3665.5027 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3670.5677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 3681.7028 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3686.7028 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3691.7028 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 3702.8379 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3704.8379 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3708.8379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 20 | 83333.3333 | ACTION | 3728.8379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3745.9029 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3750.9679 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3752.9679 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3756.9679 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3774.0329 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3779.0979 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3781.0979 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3785.0979 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3802.1629 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3807.2279 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3809.2279 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3813.2279 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3830.2929 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3835.3579 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3837.3579 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3841.3579 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3858.4229 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3863.4879 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3865.4879 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3869.4879 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3886.5529 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3891.6179 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 3902.753 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3907.753 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3912.753 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 3923.8881 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3925.8881 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3929.8881 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3946.9531 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3952.0181 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3954.0181 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3958.0181 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3975.0831 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3980.1481 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3982.1481 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3986.1481 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4003.2131 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4008.2781 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4010.2781 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4014.2781 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4031.3431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4036.4081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4038.4081 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4042.4081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4059.4731 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4064.5381 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4066.5381 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4070.5381 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4087.6031 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4092.6681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4098.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 4098.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 4103.8032 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4106.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4118.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4122.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 20 | 83333.3333 | ACTION | 4123.8032 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4126.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4128.8032 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4130.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4133.8032 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4134.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 4144.9383 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4146.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4146.9383 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4150.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4150.9383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4153.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4157.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4168.0033 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4173.0683 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4175.0683 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4179.0683 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4181.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4196.1333 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4201.1983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4203.1983 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4207.1983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4224.2633 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4229.3283 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4231.3283 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4235.3283 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4252.3933 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4253.0908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 322.5 | 2553125 | ACTION | 4253.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4257.4583 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4259.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4259.4583 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4263.4583 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4266.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 4266.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4274.5908 | MooredSubInstallation
| Towing Group 1 | Delay | 17 | 134583.3333 | ACTION | 4276.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4280.5233 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4285.5883 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4286.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4287.5883 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4290.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4291.5883 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4294.5908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 4296.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 4305.5908 | MooredSubInstallation
| Towing Group 1 | Delay | 11 | 87083.3333 | ACTION | 4307.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4308.6533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 4309.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4309.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4313.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4313.7183 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4315.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 4324.8534 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4329.8534 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4334.8534 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8 | 33333.3333 | ACTION | 4342.8534 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 22 | 91666.6667 | ACTION | 4364.8534 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 1 | 4166.6667 | ACTION | 4365.8534 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 60 | 0 | ACTION | 4373.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 10 | 41666.6667 | ACTION | 4375.8534 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2.1351 | 8896.25 | ACTION | 4377.9885 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4379.9885 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4383.9885 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 69 | 546250 | ACTION | 4384.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4385.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4389.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4392.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4396.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4401.0535 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 4404.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4406.1185 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4408.1185 | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 4410.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4412.1185 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 4418.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4420.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4429.1835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4434.2485 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4434.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4436.2485 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4440.2485 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4457.3135 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4462.3785 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4464.3785 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4468.3785 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4485.4435 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4490.5085 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4492.0908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 561.5 | 4445208.3333 | ACTION | 4492.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4492.5085 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4496.5085 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4500.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4512.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4513.5735 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4518.6385 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4520.6385 | MooringSystemInstallation
| Towing Group 2 | Delay | 29 | 229583.3333 | ACTION | 4521.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 9 | 0 | ACTION | 4521.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4524.6385 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4525.0908 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4527.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4529.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4541.7035 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4546.7685 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 20 | 158333.3333 | ACTION | 4547.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 18 | 0 | ACTION | 4547.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4551.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4555.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 4557.9036 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4562.9036 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4567.0908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 4567.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4567.9036 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 4569.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 4571.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4574.5908 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4575.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4578.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 4579.0387 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4581.0387 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4585.0387 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 4595.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 19 | 0 | ACTION | 4597.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4600.5908 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 4601.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4602.1037 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4602.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4607.1687 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4609.1687 | MooringSystemInstallation
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 4609.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4613.1687 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4624.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4630.2337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4635.2987 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4637.2987 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4641.2987 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4658.3637 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4663.4287 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4665.4287 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4669.4287 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4686.4937 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4691.5587 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4693.5587 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4696.5908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 766 | 6064166.6667 | ACTION | 4696.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4697.5587 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4702.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4704.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4714.6237 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4716.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 4717.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4719.6887 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4721.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4721.6887 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4725.6887 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 17 | 0 | ACTION | 4738.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4742.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4742.7537 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4746.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4747.8187 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4750.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 4758.9538 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4763.9538 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4768.9538 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4770.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 4780.0889 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4782.0889 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4786.0889 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4803.1539 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4808.2189 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4810.2189 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4814.2189 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4831.2839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4836.3489 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4838.3489 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4842.3489 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4859.4139 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 158 | 1250833.3333 | ACTION | 4860.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 110 | 0 | ACTION | 4860.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4864.4789 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4866.4789 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4870.4789 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4872.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4876.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4879.5908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 4880.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 4882.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4883.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4887.5439 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4888.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4892.6089 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4894.6089 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4898.6089 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4907.0908 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 4908.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 4914.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4915.6739 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4920.7389 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4922.7389 | MooringSystemInstallation
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 4922.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4926.7389 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4938.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4943.8039 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4948.8689 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 4960.004 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4965.004 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4970.004 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4979.0908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 560.8007 | 4439672.3728 | ACTION | 4979.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 4981.1391 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4983.1391 | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4985.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4987.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4987.1391 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4999.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5003.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5004.2041 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 5005.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5007.0908 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 5007.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5009.2691 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5011.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5011.2691 | MooringSystemInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5013.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5015.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5015.2691 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5027.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5030.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5032.3341 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5033.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5034.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5037.3991 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5037.5908 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 5039.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5039.3991 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5043.3991 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 5047.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5060.4641 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5061.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5065.5291 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5067.5291 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5071.5291 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5088.5941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5093.6591 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5095.6591 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5099.6591 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5106.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5116.7241 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5121.7891 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5123.7891 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5127.7891 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5133.5908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 524.3007 | 4150714.0395 | ACTION | 5133.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5139.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5141.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5144.8541 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5149.9191 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5153.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5157.5908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 5159.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 5161.0542 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5161.5908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 5161.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5165.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5166.0542 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5167.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5169.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5171.0542 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5181.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 5182.1893 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5184.1893 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5185.0908 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5187.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5188.1893 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5188.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5192.0908 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 5193.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 5201.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5205.2543 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5210.3193 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5212.3193 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5216.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5216.3193 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5233.3843 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5238.4493 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5240.4493 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5244.4493 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5261.5143 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5266.5793 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5268.5793 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5272.5793 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5274.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5288.0908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 365.3007 | 2891964.0395 | ACTION | 5288.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5289.6443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5294.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5294.7093 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5296.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5296.7093 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5300.7093 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5308.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5312.0908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 5314.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5316.0908 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 5316.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5317.7743 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5320.0908 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5322.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5322.8393 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5324.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5324.8393 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5328.8393 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5336.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 5340.0908 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5342.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5343.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5345.9043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5347.0908 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 5348.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5350.9693 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 5356.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 5362.1044 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5367.1044 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5372.1044 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 5383.2395 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5385.2395 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5389.2395 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5406.3045 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5411.3695 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 65 | 0 | ACTION | 5412.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5413.3695 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5415.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5417.3695 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5434.4345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5439.4995 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5439.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5441.4995 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5442.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5445.4995 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5462.5645 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5467.6295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5469.6295 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5473.6295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5490.6945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5495.7595 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5497.7595 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5501.7595 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5511.5908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 464.3007 | 3675714.0395 | ACTION | 5511.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5517.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5518.8245 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5519.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5523.8895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5525.8895 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5529.8895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5531.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5535.5908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 5537.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5539.5908 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 5539.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5543.5908 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5545.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5546.9545 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5547.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5552.0195 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5559.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5563.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 5563.1546 | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5565.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5566.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5568.1546 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5570.0908 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 5571.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5573.1546 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 5579.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 5584.2897 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5586.2897 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5590.2897 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5594.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5607.3547 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5610.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5612.4197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5614.4197 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5618.4197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5635.4847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5640.5497 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5642.5497 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5646.5497 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5663.6147 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5666.0908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 464.3007 | 3675714.0395 | ACTION | 5666.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5668.6797 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5670.6797 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5674.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5674.6797 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 9 | 71250 | ACTION | 5675.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5681.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5686.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5690.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5691.7447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5694.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5696.8097 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5698.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5698.8097 | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 5701.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5702.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5702.8097 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 5703.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5709.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5714.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5717.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5719.8747 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5721.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5724.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5724.9397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5726.9397 | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5729.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5730.9397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 5735.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 5743.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5748.0047 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5748.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5753.0697 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 5764.2048 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5769.2048 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5774.2048 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5778.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 5785.3399 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5787.3399 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5791.3399 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5808.4049 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 64 | 0 | ACTION | 5812.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5813.4699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5815.4699 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5819.4699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5836.5349 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5841.5999 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5843.5999 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5847.5999 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5864.6649 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5869.7299 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5871.7299 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5875.7299 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5884.5908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 528.3007 | 4182380.7062 | ACTION | 5884.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5890.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5892.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5892.7949 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5897.8599 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5899.8599 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5903.8599 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5904.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5908.5908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 5910.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5912.5908 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 5912.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5916.5908 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5918.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5920.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5920.9249 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5925.9899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5927.9899 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5931.9899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5932.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5936.0908 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5938.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5939.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5943.0908 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 5944.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5946.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5949.0549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 5952.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5954.1199 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 5965.255 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5967.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5970.255 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5975.255 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 5986.3901 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5988.3901 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5992.3901 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6009.4551 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6014.5201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6016.5201 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6020.5201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6037.5851 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6039.0908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 459.3007 | 3636130.7062 | ACTION | 6039.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6042.6501 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6044.6501 | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6045.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6047.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6048.6501 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6059.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6063.0908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 6065.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6065.7151 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6067.0908 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 6067.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6070.7801 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6071.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6072.7801 | MooringSystemInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6073.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6075.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6076.7801 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6087.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6090.5908 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6093.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6093.8451 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6094.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6097.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6098.9101 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 6099.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6100.9101 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6104.9101 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 6107.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6114.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6121.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6121.9751 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6127.0401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6129.0401 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6133.0401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6150.1051 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6155.1701 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 6166.3052 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6171.3052 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6176.3052 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 6187.4403 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6189.4403 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6193.4403 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6193.5908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 450.3007 | 3564880.7062 | ACTION | 6193.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6199.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6201.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6210.5053 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6213.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6215.5703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6217.5703 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6217.5908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 6219.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6221.5703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6221.5908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 6221.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6225.5908 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6227.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6229.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6238.6353 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6241.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6243.7003 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6245.7003 | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6247.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6249.7003 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 6253.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 6261.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6266.7653 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6271.8303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6273.8303 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6277.8303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6282.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6294.8953 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 9 | 37500 | ACTION | 6303.8953 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 63 | 0 | ACTION | 6304.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6308.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6308.9603 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6310.9603 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6311.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6314.9603 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 6315.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6319.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6332.0253 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6337.0903 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6339.0903 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6343.0903 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6343.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6360.1553 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6365.2203 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 6376.3554 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6381.3554 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6386.3554 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 6397.4905 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6399.4905 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6403.4905 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6415.0908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 462.3007 | 3659880.7062 | ACTION | 6415.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6420.5555 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6421.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6423.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6425.6205 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6427.6205 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6431.6205 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6435.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6439.0908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 6441.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6443.0908 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 6443.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6447.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6448.6855 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6449.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6450.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6451.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6453.7505 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6455.7505 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6459.7505 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6463.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6466.5908 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6469.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6470.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6473.5908 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 6475.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6476.8155 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6481.8805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 6483.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6483.8805 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6487.8805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6497.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6504.9455 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6510.0105 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6512.0105 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6516.0105 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6533.0755 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6538.1405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6540.1405 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6544.1405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6561.2055 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6566.2705 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 2 | 8333.3333 | ACTION | 6568.2705 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6569.5908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 462.3007 | 3659880.7062 | ACTION | 6569.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6577.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 19 | 79166.6667 | ACTION | 6587.2705 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2 | 8333.3333 | ACTION | 6589.2705 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6589.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 1 | 4166.6667 | ACTION | 6590.2705 | MooringSystemInstallation
| Towing Group 1 | Delay | 21 | 166250 | ACTION | 6590.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6593.5908 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6596.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 7.1351 | 29729.5833 | ACTION | 6597.4056 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6597.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6601.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6602.4056 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6605.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6607.4056 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 3 | 12500 | ACTION | 6610.4056 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 3 | 12500 | ACTION | 6613.4056 | MooringSystemInstallation
| Towing Group 1 | Delay | 17 | 134583.3333 | ACTION | 6613.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6617.5908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6618.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6621.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.1351 | 33896.25 | ACTION | 6621.5407 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6623.5407 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6624.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6627.5407 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6628.0908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 6633.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 6635.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6641.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6644.6057 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6649.6707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6651.6707 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6652.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6655.6707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6661.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 6667.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6672.7357 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 6675.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6677.8007 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6679.8007 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6683.8007 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6700.8657 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6705.9307 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6707.9307 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6711.9307 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6724.0908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 462.3007 | 3659880.7062 | ACTION | 6724.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6732.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6744.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6748.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6752.0908 | MooredSubInstallation
| Towing Group 2 | Delay | 32 | 253333.3333 | ACTION | 6756.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6756.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 45 | 187500 | ACTION | 6756.9307 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6760.0908 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6762.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6772.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6773.9957 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6775.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6779.0607 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6779.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6781.0607 | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 6782.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6782.5908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 6784.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6785.0607 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6786.5908 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6790.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6802.1257 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6806.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6807.1907 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6809.1907 | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 19 | 150416.6667 | ACTION | 6809.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 34 | 141666.6667 | ACTION | 6843.1907 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6847.1907 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6864.2557 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 58 | 459166.6667 | ACTION | 6867.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7916.6667 | ACTION | 6868.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6869.3207 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 6874.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6878.5908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 395.3007 | 3129464.0395 | ACTION | 6878.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 6880.4558 | MooringSystemInstallation
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 6882.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6884.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6885.4558 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6886.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6890.4558 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6898.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 6901.5909 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6902.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6903.5909 | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 6904.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6906.5908 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 6906.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6907.5909 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6910.5908 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6912.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6914.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6924.6559 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6926.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6929.7209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6930.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6931.7209 | MooringSystemInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6932.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6933.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6935.7209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6937.0908 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 6938.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 6946.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6952.7859 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6954.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6957.8509 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6959.8509 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6961.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6963.8509 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6980.9159 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6985.9809 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6987.9809 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6991.9809 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7009.0459 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7014.1109 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7016.1109 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7033.0908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 357.3007 | 2828630.7062 | ACTION | 7033.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7041.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7053.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7057.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7061.0908 | MooredSubInstallation
| Towing Group 1 | Delay | 31 | 245416.6667 | ACTION | 7064.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 48 | 200000 | ACTION | 7064.1109 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7065.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7068.1109 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7069.0908 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7070.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 7081.0908 | MooredSubInstallation
| Towing Group 1 | Delay | 11 | 87083.3333 | ACTION | 7081.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7085.1759 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7090.2409 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7092.2409 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7093.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7096.2409 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7096.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7100.0908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 7101.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7103.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7113.3059 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7118.3709 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7122.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7127.5908 | MooredSubInstallation
| Towing Group 1 | Delay | 27 | 213750 | ACTION | 7128.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 7129.506 | MooringSystemInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 7130.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7134.506 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7136.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7139.506 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 7150.6411 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7152.6411 | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7156.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7156.6411 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 7162.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 7170.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7173.7061 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7178.7711 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7180.7711 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7184.7711 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7199.5908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 317.3007 | 2511964.0395 | ACTION | 7199.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7201.8361 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7205.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7206.9011 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7207.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7208.9011 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7212.9011 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7219.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7223.5908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 7225.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7227.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7231.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7235.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 28 | 116666.6667 | ACTION | 7240.9011 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7247.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7251.0908 | MooredSubInstallation
| Towing Group 2 | Delay | 28 | 221666.6667 | ACTION | 7253.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7254.5908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 7255.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7257.9661 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7258.0908 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7261.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7263.0311 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7265.0311 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7269.0311 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7281.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7282.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7286.0961 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 7287.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7290.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7291.1611 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7293.1611 | MooringSystemInstallation
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 7295.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7297.1611 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7314.2261 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7319.2911 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7321.2911 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7325.2911 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7342.3561 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7347.4211 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7354.0908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 407.3007 | 3224464.0395 | ACTION | 7354.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 7358.5562 | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7360.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7362.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7363.5562 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7368.5562 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7374.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7378.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 7379.6913 | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 7380.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7381.6913 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7382.0908 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 7382.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7385.6913 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7386.0908 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7388.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7390.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7402.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7402.7563 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7405.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7407.8213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7408.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7409.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7409.8213 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7412.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7413.8213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 7414.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 7422.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7430.8863 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7435.9513 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7436.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7437.9513 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7441.9513 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7458.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7459.0163 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7464.0813 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7466.0813 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7470.0813 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7487.1463 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7492.2113 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7494.2113 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7498.2113 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7508.5908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 338.3007 | 2678214.0395 | ACTION | 7508.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7514.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7515.2763 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7516.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7520.3413 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7522.3413 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7526.3413 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7528.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7532.5908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 7534.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7536.5908 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 7536.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7540.5908 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7542.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7543.4063 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7544.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7548.4713 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7556.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 7559.6064 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7560.0908 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7562.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7563.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7564.6064 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7567.0908 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 7568.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7569.6064 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 7576.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 7580.7415 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7582.7415 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7586.7415 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7591.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7603.8065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7608.8715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7610.8715 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7614.8715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7626.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7631.9365 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7637.0015 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7639.0015 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7643.0015 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7660.0665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7663.0908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 367.3007 | 2907797.3728 | ACTION | 7663.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7665.1315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7667.1315 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7669.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7671.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7671.1315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7683.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7687.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7688.1965 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 7689.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7691.0908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 7691.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7693.2615 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7695.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7695.2615 | MooringSystemInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7697.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7699.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7699.2615 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7711.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7714.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7716.3265 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7717.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7718.0908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7721.3915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7721.5908 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 7723.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7723.3915 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7727.3915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 7731.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7744.4565 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7745.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7749.5215 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 7760.6566 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7765.6566 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11.1351 | 46396.25 | ACTION | 7776.7917 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7778.7917 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7782.7917 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7794.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7799.8567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7804.9217 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7806.9217 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7810.9217 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7817.5908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 395.3007 | 3129464.0395 | ACTION | 7817.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7823.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7825.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7827.9867 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7833.0517 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7835.0517 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7837.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7839.0517 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7841.5908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 7843.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7845.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7849.5908 | MooredSubInstallation
| Towing Group 3 | Delay | 9 | 71250 | ACTION | 7852.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7853.5908 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 7854.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7856.1167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 3 | 23750 | ACTION | 7857.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 7858.5908 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7861.1817 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7863.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7870.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7874.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7877.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7881.0908 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7883.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 7889.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 7897.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7905.0908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7962.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7977.0908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 400.3007 | 3169047.3728 | ACTION | 7977.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7983.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7985.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7997.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8001.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8005.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8009.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8013.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8025.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8028.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8032.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 8040.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8043.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8067.5908 | MooredSubInstallation
| Towing Group 1 | Delay | 116 | 918333.3333 | ACTION | 8099.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 8119.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 8121.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8127.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8130.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8139.5908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 408.3007 | 3232380.7062 | ACTION | 8139.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8145.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 8147.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8147.5908 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 8153.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8159.5908 | MooredSubInstallation
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 8161.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8163.5908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 8165.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8167.5908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 8167.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8171.5908 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8173.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8175.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8187.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8191.0908 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 8193.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8194.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8198.0908 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 8199.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 8207.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8222.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8294.0908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 396.3007 | 3137380.7062 | ACTION | 8294.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8298.5908 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8300.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8302.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8314.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8318.0908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 8320.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8322.0908 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 8322.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8326.0908 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8328.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8330.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8342.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8345.5908 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 8348.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8349.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8352.5908 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 8354.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 8362.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8376.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 25 | 0 | ACTION | 8401.5908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8466.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8473.5908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 312.3007 | 2472380.7062 | ACTION | 8473.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8479.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8481.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8493.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 8494.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8498.5908 | MooredSubInstallation
| Towing Group 1 | Delay | 22 | 174166.6667 | ACTION | 8501.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8502.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8506.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8510.5908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 8521.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8522.5908 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 8523.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8526.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8529.5908 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8529.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8533.0908 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 8549.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 8555.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8557.0908 | MooredSubInstallation
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 8563.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8629.0908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 421.3007 | 3335297.3728 | ACTION | 8629.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8634.5908 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8635.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8637.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8649.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8653.0908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 8655.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8657.0908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 8657.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8661.0908 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8663.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8665.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8677.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8680.5908 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 8683.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8684.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8687.5908 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 8689.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 8697.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8711.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8783.5908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 421.3007 | 3335297.3728 | ACTION | 8783.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8789.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8791.5908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8802.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8803.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8807.5908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 8809.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8811.5908 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 8811.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8815.5908 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8817.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8819.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8831.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8835.0908 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 8837.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8838.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8842.0908 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 8843.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 8851.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8866.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8938.0908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 374.3007 | 2963214.0395 | ACTION | 8938.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8944.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8946.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8958.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 8962.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8966.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8970.0908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8970.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8974.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 8985.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8989.0908 | MooredSubInstallation
| Towing Group 1 | Delay | 51 | 403750 | ACTION | 8995.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9001.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9004.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9008.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9011.5908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 9015.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 9017.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9035.5908 | MooredSubInstallation
| Towing Group 1 | Delay | 48 | 380000 | ACTION | 9065.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9071.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9091.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 9097.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 9105.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9107.5908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 410.3007 | 3248214.0395 | ACTION | 9107.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9113.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9115.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9127.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9131.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9135.5908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9138.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9139.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9143.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9155.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9159.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9162.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9166.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9190.0908 | MooredSubInstallation
| Towing Group 2 | Delay | 141 | 1116250 | ACTION | 9254.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9262.0908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 410.3007 | 3248214.0395 | ACTION | 9262.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9268.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9270.0908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 9274.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9282.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9286.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9290.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9294.0908 | MooredSubInstallation
| Towing Group 3 | Delay | 28 | 221666.6667 | ACTION | 9296.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9298.0908 | MooredSubInstallation
| Towing Group 2 | Delay | 30 | 237500 | ACTION | 9304.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9306.5908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 9306.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9310.0908 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9312.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9313.5908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 9316.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9317.0908 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 9318.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9320.5908 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9324.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9332.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 9338.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9344.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9344.5908 | MooredSubInstallation
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 9346.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 9350.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 9358.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9416.5908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 311.3007 | 2464464.0395 | ACTION | 9416.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9422.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9424.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9436.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9440.5908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 9442.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9444.5908 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 9444.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9448.5908 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9450.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9452.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9464.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9468.0908 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9470.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9471.5908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9474.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9475.0908 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 9476.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 9484.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9499.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9571.0908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 224.3007 | 1775714.0395 | ACTION | 9571.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9577.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9579.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9591.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9595.0908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 9597.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9599.0908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 9599.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9603.0908 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9605.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9607.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9619.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9622.5908 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9625.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9626.0908 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 9631.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 9632.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9635.5908 | MooredSubInstallation
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 9639.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9642.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9659.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9731.5908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 373.3007 | 2955297.3728 | ACTION | 9731.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9739.5908 | MooredSubInstallation
| Towing Group 3 | Delay | 18 | 142500 | ACTION | 9749.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9751.5908 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9755.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9755.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9759.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9763.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9767.5908 | MooredSubInstallation
| Towing Group 3 | Delay | 16 | 126666.6667 | ACTION | 9771.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 9771.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9783.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 9789.5908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 9791.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9793.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9796.5908 | MooredSubInstallation
| Towing Group 3 | Delay | 8 | 63333.3333 | ACTION | 9799.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9800.0908 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 9801.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9807.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9810.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9824.0908 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9827.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 9833.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 9841.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9896.0908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 411.3007 | 3256130.7062 | ACTION | 9896.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9902.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9904.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9916.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9920.0908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 9922.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9924.0908 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 9924.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9928.0908 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9930.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9932.0908 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 9933.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 34 | 0 | ACTION | 9966.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9978.0908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9978.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9981.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9985.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9988.5908 | MooredSubInstallation
| Towing Group 1 | Delay | 56 | 443333.3333 | ACTION | 9989.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 134583.3333 | ACTION | 10006.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 10012.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10012.5908 | MooredSubInstallation
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 10020.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10084.5908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 445.3007 | 3525297.3728 | ACTION | 10084.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 10090.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10092.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10104.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10108.5908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 10110.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 1 | 7916.6667 | ACTION | 10111.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10112.5908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 10113.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10116.5908 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 10119.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10120.5908 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 55416.6667 | ACTION | 10126.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10132.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 10137.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10141.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10144.5908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10146.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10148.0908 | MooredSubInstallation
| Towing Group 2 | Delay | 44 | 348333.3333 | ACTION | 10170.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10172.0908 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 102916.6667 | ACTION | 10183.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 10189.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 10197.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10244.0908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 402.3007 | 3184880.7062 | ACTION | 10244.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 8 | 63333.3333 | ACTION | 10252.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10252.0908 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 10258.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10264.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10268.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10272.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10276.0908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 10278.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10280.0908 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 10280.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 10286.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10292.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10295.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10299.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10302.5908 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 10306.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 10312.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10314.5908 | MooredSubInstallation
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 10320.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10326.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10398.5908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 378.3007 | 2994880.7062 | ACTION | 10398.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 10404.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10406.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10418.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10422.5908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 10424.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10426.5908 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 10426.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10430.5908 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 10432.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10434.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10446.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10450.0908 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 10452.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10453.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10457.0908 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 10458.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 10466.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10481.0908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10482.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10553.0908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 355.3007 | 2812797.3728 | ACTION | 10553.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 10559.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10561.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10573.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10577.0908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 10579.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10581.0908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 10581.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10585.0908 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 10587.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10589.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10601.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10604.5908 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 10607.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10608.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10611.5908 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 10613.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 10621.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10635.5908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10650.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10707.5908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 387.3007 | 3066130.7062 | ACTION | 10707.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 3 | 23750 | ACTION | 10710.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10715.5908 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 10716.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10727.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10731.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10735.5908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 10736.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10739.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10743.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10755.5908 | MooredSubInstallation
| Towing Group 3 | Delay | 20 | 158333.3333 | ACTION | 10756.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 10758.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10759.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10762.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10766.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10790.0908 | MooredSubInstallation
| Towing Group 3 | Delay | 49 | 387916.6667 | ACTION | 10807.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 10813.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10818.5908 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 10833.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 10839.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 10847.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10862.0908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 395.3007 | 3129464.0395 | ACTION | 10862.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 10868.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10870.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10882.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10886.0908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 10888.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10890.0908 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 10890.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10894.0908 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 10896.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10898.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10910.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10913.5908 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 10916.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10917.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10920.5908 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 10922.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 10930.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10944.5908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10986.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11016.5908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 395.3007 | 3129464.0395 | ACTION | 11016.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11022.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11024.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11036.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11040.5908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 11042.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11044.5908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 11044.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11048.5908 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11050.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11052.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11064.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11068.0908 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11070.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11071.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11075.0908 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 11076.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 11084.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11099.0908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11154.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11171.0908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 323.3007 | 2559464.0395 | ACTION | 11171.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11177.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11179.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11191.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11195.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11199.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11203.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11207.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 11212.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11224.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 11238.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11241.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11245.0908 | MooredSubInstallation
| Towing Group 3 | Delay | 71 | 562083.3333 | ACTION | 11248.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11248.5908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 11268.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11272.5908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11322.5908 | MooredSubInstallation
| Towing Group 3 | Delay | 69 | 546250 | ACTION | 11337.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 11339.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11344.5908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 414.3007 | 3279880.7062 | ACTION | 11344.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11345.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11350.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11352.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11364.5908 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11365.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11368.5908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 11370.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 11371.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11372.5908 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 11372.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11376.5908 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11378.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 11379.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11380.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11392.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11396.0908 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11398.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 11404.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 11412.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 23 | 0 | ACTION | 11419.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11422.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11426.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11450.0908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11490.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11522.0908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 437.3007 | 3461964.0395 | ACTION | 11522.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11528.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11530.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11542.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11546.0908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 11548.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11550.0908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 11550.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11554.0908 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11556.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11558.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11570.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 11574.0908 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11576.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11577.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11581.0908 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 11582.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11584.5908 | MooredSubInstallation
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 11590.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11608.5908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11658.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11680.5908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 301.3007 | 2385297.3728 | ACTION | 11680.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11686.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11688.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11700.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11704.5908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 11706.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11708.5908 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 11708.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11712.5908 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11714.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11716.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11728.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11732.0908 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11734.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11735.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11739.0908 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 11740.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 11748.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11763.0908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11826.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11835.0908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 422.3007 | 3343214.0395 | ACTION | 11835.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11843.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11855.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 41 | 0 | ACTION | 11896.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11900.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11904.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11908.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11912.0908 | MooredSubInstallation
| Towing Group 1 | Delay | 80 | 633333.3333 | ACTION | 11915.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11921.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11924.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11927.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11931.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11934.5908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 11941.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 11943.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11949.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11958.5908 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11969.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 11975.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 11983.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11994.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12030.5908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 440.3007 | 3485714.0395 | ACTION | 12030.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12036.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12038.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12050.5908 | MooredSubInstallation
| Towing Group 2 | Delay | 18 | 142500 | ACTION | 12054.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 12054.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12058.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12062.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12066.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12070.5908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 12074.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 12076.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 4 | 31666.6667 | ACTION | 12080.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 12081.5908 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12086.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12093.5908 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 55416.6667 | ACTION | 12093.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 11 | 87083.3333 | ACTION | 12104.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 102916.6667 | ACTION | 12117.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 2 | 15833.3333 | ACTION | 12119.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 13 | 102916.6667 | ACTION | 12132.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 41 | 0 | ACTION | 12134.5908 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 4 | 31666.6667 | ACTION | 12136.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12138.0908 | MooredSubInstallation
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 12144.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 12153.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12156.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12160.0908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12162.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12184.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12256.0908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 507.3007 | 4016130.7062 | ACTION | 12256.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12262.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12264.0908 | MooredSubInstallation
| Towing Group 3 | Delay | 6 | 47500 | ACTION | 12268.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12276.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12280.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12284.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12288.0908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 12288.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 12290.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12292.0908 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12296.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12304.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12307.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12311.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12314.5908 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 12316.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 12322.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 12330.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12330.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12338.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12410.5908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 427.3007 | 3382797.3728 | ACTION | 12410.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 7 | 55416.6667 | ACTION | 12417.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12418.5908 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12423.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12430.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12434.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12438.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12442.5908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 12443.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 12445.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12446.5908 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12451.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12458.5908 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 63333.3333 | ACTION | 12459.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12498.5908 | MooredSubInstallation
| Towing Group 1 | Delay | 54 | 427500 | ACTION | 12513.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 95000 | ACTION | 12525.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 2 | 15833.3333 | ACTION | 12527.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 6 | 47500 | ACTION | 12533.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 4 | 31666.6667 | ACTION | 12537.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 12545.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12666.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 258 | 0 | ACTION | 12716.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12720.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 12727.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12730.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12734.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12758.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12830.0908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 685.3007 | 5425297.3728 | ACTION | 12830.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12834.5908 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12836.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12838.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12850.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 12853.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12857.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 43 | 0 | ACTION | 12900.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12904.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 12906.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12910.0908 | MooredSubInstallation
| Towing Group 2 | Delay | 90 | 712500 | ACTION | 12926.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 12926.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12930.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12942.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12945.5908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 12946.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 12948.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12949.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12952.5908 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12954.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 12974.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12976.5908 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 12980.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 12988.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13002.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13048.5908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 718.3007 | 5686547.3728 | ACTION | 13048.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13056.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13068.5908 | MooredSubInstallation
| Towing Group 3 | Delay | 21 | 166250 | ACTION | 13069.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 13069.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13073.5908 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13075.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13077.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13081.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13085.5908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 13095.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13097.5908 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 13097.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13101.0908 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13103.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13104.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13108.0908 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13123.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 13129.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13132.0908 | MooredSubInstallation
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 13137.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13170.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13204.0908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 658.3007 | 5211547.3728 | ACTION | 13204.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13210.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13212.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13224.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13228.0908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 13230.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13232.0908 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 13232.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13236.0908 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13238.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13240.0908 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 39583.3333 | ACTION | 13243.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13338.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 115 | 0 | ACTION | 13355.0908 | MooredSubInstallation
| Towing Group 1 | Delay | 112 | 886666.6667 | ACTION | 13355.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13367.0908 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 118750 | ACTION | 13370.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13370.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13374.0908 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 13376.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13377.5908 | MooredSubInstallation
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 13384.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13401.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13473.5908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 485.3007 | 3841964.0395 | ACTION | 13473.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13479.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13481.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13493.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13497.5908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 13499.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13501.5908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 13501.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13505.5908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13506.5908 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13507.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13509.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13521.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13525.0908 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13527.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13528.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13532.0908 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 13533.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 13541.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13556.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13628.0908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 490.3007 | 3881547.3728 | ACTION | 13628.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13634.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13636.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13648.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13652.0908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 13654.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13656.0908 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 13656.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13660.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 13662.0908 | MooredSubInstallation
| Towing Group 3 | Delay | 6 | 47500 | ACTION | 13662.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13666.0908 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13668.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13674.5908 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 63333.3333 | ACTION | 13676.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 1 | 7916.6667 | ACTION | 13677.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 15833.3333 | ACTION | 13679.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 10 | 79166.6667 | ACTION | 13689.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 55416.6667 | ACTION | 13696.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 99 | 0 | ACTION | 13765.0908 | MooredSubInstallation
| Towing Group 3 | Delay | 69 | 546250 | ACTION | 13765.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 13768.3365 | MooredSubInstallation | [5 empty] | 3 | 1
0.5 | Array Cable Installation Vessel | Mobilize | 72 | 337500 | ACTION | 13769.9503 | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 13774.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Load Cable | 6 | 56250 | ACTION | 13775.9503 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13777.0908 | MooredSubInstallation
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 13782.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 13789.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 15 | 140625 | ACTION | 13790.9503 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13792.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13796.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Transit | 9.6827 | 90775.2717 | ACTION | 13800.633 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13802.633 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13803.633 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 11 | 103125 | ACTION | 13814.633 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13820.133 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13825.633 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13826.633 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 28125 | ACTION | 13829.633 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Delay | 43 | 0 | ACTION | 13839.0908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13842.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13842.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 13 | 121875 | ACTION | 13842.633 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 13.0261 | 122119.4853 | ACTION | 13855.659 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13856.659 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 7 | 65625 | ACTION | 13863.659 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13866.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13869.159 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13938.5908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 554.3007 | 4388214.0395 | ACTION | 13938.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13946.5908 | MooredSubInstallation
| Towing Group 1 | Delay | 19 | 150416.6667 | ACTION | 13957.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13958.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 93 | 871875 | ACTION | 13962.159 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13962.5908 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13963.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13967.659 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13969.659 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13970.659 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13976.159 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 13977.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13981.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 6 | 56250 | ACTION | 13982.159 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13985.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13987.659 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13988.659 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 1 | 9375 | ACTION | 13989.659 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 14001.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14005.5908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14010.5908 | MooredSubInstallation
| Towing Group 1 | Delay | 62 | 490833.3333 | ACTION | 14025.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 20 | 0 | ACTION | 14025.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 44 | 412500 | ACTION | 14033.659 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14037.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14041.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14044.5908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 14045.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 14047.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14048.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 15.0261 | 140869.4853 | ACTION | 14048.6851 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14049.6851 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14053.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14055.1851 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14060.6851 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14062.6851 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14063.6851 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14069.1851 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14072.0908 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14073.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14074.6851 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14075.6851 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 14079.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14080.623 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14081.623 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14087.123 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 14087.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14092.623 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14094.623 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14095.623 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14101.123 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14106.623 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14107.623 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14112.5608 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14113.5608 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14119.0608 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14124.5608 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14126.5608 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14127.5608 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14133.0608 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14138.5608 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14139.5608 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14144.0908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 602.3007 | 4768214.0395 | ACTION | 14144.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14144.4987 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14145.4987 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14150.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14150.9987 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14152.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14156.4987 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14158.4987 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14159.4987 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14164.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14164.9987 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14168.0908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 14170.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14170.4987 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14171.4987 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14172.0908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 14172.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14176.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14176.4365 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14177.4365 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14178.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14178.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14180.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14182.9365 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 7 | 65625 | ACTION | 14189.9365 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14192.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14195.4365 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14197.4365 | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 14198.0908 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14198.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14198.4365 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14201.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14203.9365 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 14204.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14209.4365 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14210.4365 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 14212.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14215.3744 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14216.3744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 18 | 0 | ACTION | 14219.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14221.8744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14223.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14226.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14227.3744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14229.3744 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14230.3744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14235.8744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14241.3744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14242.3744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14247.3122 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14248.3122 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14250.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14253.8122 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14259.3122 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14261.3122 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14262.3122 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14267.8122 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14273.3122 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14274.3122 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14279.2501 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14280.2501 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14285.7501 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14291.2501 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14293.2501 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14294.2501 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14299.7501 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14305.2501 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14306.2501 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14311.1879 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14312.1879 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14317.6879 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14322.5908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 540.3007 | 4277380.7062 | ACTION | 14322.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14323.1879 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14325.1879 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14326.1879 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14328.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14330.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14331.6879 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14337.1879 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14338.1879 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14342.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14343.1258 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14344.1258 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14346.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14346.5908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 14348.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14349.6258 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14350.5908 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 14350.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14354.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14355.1258 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14356.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14357.1258 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14358.1258 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14358.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14363.6258 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14369.1258 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14370.1258 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14370.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14374.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14375.0636 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14376.0636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14376.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14377.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14381.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14381.5636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 14382.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14387.0636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14389.0636 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14390.0636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 14390.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14395.5636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14401.0636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14402.0636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14405.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14407.0015 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14408.0015 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14413.5015 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14419.0015 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14421.0015 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14422.0015 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14427.5015 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14433.0015 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14434.0015 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14438.9393 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14439.9393 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14445.4393 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14450.9393 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14452.9393 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14453.9393 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14459.4393 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14464.9393 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14465.9393 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14470.8771 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14471.8771 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14477.0908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 389.3007 | 3081964.0395 | ACTION | 14477.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14477.3771 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14482.8771 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14483.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14484.8771 | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14485.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14485.8771 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14491.3771 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14496.8771 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14497.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14497.8771 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14501.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14502.815 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 14503.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14503.815 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14505.0908 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 14505.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14509.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14509.315 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14511.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14513.0908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14514.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14514.815 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14516.815 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14517.815 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14523.315 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14525.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14528.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14528.815 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14529.815 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14531.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14532.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14534.7528 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14535.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14535.7528 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 14537.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14541.2528 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 14545.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14546.7528 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14548.7528 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14549.7528 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14555.2528 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14559.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14560.7528 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14561.7528 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14566.6907 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14567.6907 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14573.1907 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 4 | 37500 | ACTION | 14577.1907 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14582.6907 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14584.6907 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14585.6907 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14631.5908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 419.3007 | 3319464.0395 | ACTION | 14631.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14637.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14639.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14651.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 69 | 646875 | ACTION | 14654.6907 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14655.5908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 14657.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14659.5908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 14659.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14660.1907 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14663.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14665.6907 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14665.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14666.6907 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14667.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14671.6285 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14672.6285 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14678.1285 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14679.5908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14682.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14683.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14683.6285 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14685.6285 | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14685.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14686.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14686.6285 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14690.0908 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 14691.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14692.1285 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14697.6285 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14698.6285 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 14699.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14703.5664 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14704.5664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14710.0664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14714.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14715.5664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14717.5664 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14718.5664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14724.0664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14729.5664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14730.5664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14735.5042 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14736.5042 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14742.0042 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 7 | 65625 | ACTION | 14749.0042 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14754.5042 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14756.5042 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14757.5042 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 73 | 0 | ACTION | 14787.0908 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14850.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14859.0908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 468.3007 | 3707380.7062 | ACTION | 14859.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14867.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14879.0908 | MooredSubInstallation
| Towing Group 3 | Delay | 23 | 182083.3333 | ACTION | 14882.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 14882.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14886.0908 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14888.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 131 | 1228125 | ACTION | 14888.5042 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14890.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14894.0042 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14894.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14898.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14899.5042 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14900.5042 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 18750 | ACTION | 14902.5042 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 14908.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14910.0908 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 14910.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 14914.0908 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14916.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14917.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14921.0908 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14936.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 14942.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 41 | 384375 | ACTION | 14943.5042 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 2.9378 | 27542.3219 | ACTION | 14946.4421 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14947.4421 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 14950.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 17 | 159375 | ACTION | 14964.4421 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14969.9421 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14975.4421 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14977.4421 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14978.4421 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14983.9421 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14989.4421 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14990.4421 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 14995.3799 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14996.3799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 91 | 0 | ACTION | 15012.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 16 | 150000 | ACTION | 15012.3799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15015.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15017.8799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15018.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15039.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 50 | 468750 | ACTION | 15067.8799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15073.3799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15075.3799 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15076.3799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15081.8799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15087.3799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15088.3799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 15093.3178 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15094.3178 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15099.8178 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15105.3178 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15107.3178 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15108.3178 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15111.5908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 566.3007 | 4483214.0395 | ACTION | 15111.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15113.8178 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15117.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15119.3178 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15119.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15120.3178 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 15125.2556 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15126.2556 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15131.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15131.7556 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15135.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15137.2556 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 15137.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15139.2556 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15139.5908 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 15139.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15140.2556 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15143.5908 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15145.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15147.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15159.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15163.0908 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 15165.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15166.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15170.0908 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 15171.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 34 | 318750 | ACTION | 15174.2556 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15179.7556 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 15179.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15185.2556 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15186.2556 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15186.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 15191.1935 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15192.1935 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15194.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15197.6935 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15203.1935 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15205.1935 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15206.1935 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15211.6935 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15217.1935 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15218.1935 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 15223.1313 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15224.1313 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15229.6313 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15235.1313 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15237.1313 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15238.1313 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15243.6313 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15249.1313 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15250.1313 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 15255.0692 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15256.0692 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15261.5692 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15266.0908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 566.3007 | 4483214.0395 | ACTION | 15266.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15267.0692 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15269.0692 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15270.0692 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15272.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15274.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15275.5692 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15281.0692 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15282.0692 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15286.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 15287.007 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15288.007 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15290.0908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 15292.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15293.507 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15294.0908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 15294.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15298.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15299.007 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15300.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15301.007 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15302.007 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15302.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15307.507 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15313.007 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15314.007 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15314.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15317.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 15318.9449 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15319.9449 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 15320.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15321.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15324.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15325.4449 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 15326.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15330.9449 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15332.9449 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15333.9449 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 15334.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15339.4449 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15344.9449 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15345.9449 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15348.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 15350.8827 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15351.8827 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15357.3827 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15362.8827 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15364.8827 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15365.8827 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15371.3827 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15376.8827 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15377.8827 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 15382.8206 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15383.8206 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15389.3206 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15394.8206 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15396.8206 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15397.8206 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15403.3206 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15408.8206 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15409.8206 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 15414.7584 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15420.5908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 470.3007 | 3723214.0395 | ACTION | 15420.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15426.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15428.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15440.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15444.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 15460.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15464.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15468.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15472.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15484.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 15485.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15489.0908 | MooredSubInstallation
| Towing Group 3 | Delay | 64 | 506666.6667 | ACTION | 15490.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15492.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15496.0908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 15510.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15520.0908 | MooredSubInstallation
| Towing Group 3 | Delay | 12 | 95000 | ACTION | 15522.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 15524.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15530.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 15550.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 15556.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 15564.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 161 | 1509375 | ACTION | 15575.7584 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15576.7584 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 6 | 56250 | ACTION | 15582.7584 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15588.2584 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15592.0908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 412.3007 | 3264047.3728 | ACTION | 15592.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15593.7584 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15595.7584 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15596.7584 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15598.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15600.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15602.2584 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15607.7584 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15608.7584 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15612.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 15613.6963 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15614.6963 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15616.0908 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 15618.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15620.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15620.1963 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 15620.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15624.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15625.6963 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15626.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15627.6963 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15628.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15628.6963 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15634.1963 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15639.6963 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15640.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15640.6963 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15643.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 15645.6341 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 15646.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15646.6341 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15647.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15650.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15652.1341 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 15652.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15657.6341 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15659.6341 | ArrayCableInstallation
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 15660.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15660.6341 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15666.1341 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15671.6341 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15672.6341 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15674.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 15677.5719 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15678.5719 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15684.0719 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15689.5719 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15691.5719 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15692.5719 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15698.0719 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15703.5719 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15704.5719 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 15709.5098 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15710.5098 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15716.0098 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15721.5098 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15723.5098 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15724.5098 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15730.0098 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15735.5098 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15736.5098 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 15741.4476 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15746.5908 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 412.3007 | 3264047.3728 | ACTION | 15746.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15752.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15754.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15766.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15770.5908 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 15772.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 32 | 300000 | ACTION | 15773.4476 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15774.4476 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15774.5908 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 15774.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15778.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15779.9476 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15780.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15782.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15785.4476 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15787.4476 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15788.4476 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15793.9476 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15794.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15798.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15799.4476 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15800.4476 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 15800.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 28125 | ACTION | 15803.4476 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 15806.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 10 | 0 | ACTION | 15808.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15811.5908 | MooredSubInstallation
| Towing Group 2 | Transit | 7.9536 | 62966.3393 | ACTION | 15814.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 15827.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15831.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 32 | 300000 | ACTION | 15835.4476 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.9378 | 18167.3219 | ACTION | 15837.3855 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15855.0908 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 20 | 187500 | ACTION | 15857.3855 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15858.3855 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 18 | 168750 | ACTION | 15876.3855 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15881.8855 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15887.3855 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15889.3855 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15890.3855 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15927.0908 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 362.3007 | 2868214.0395 | ACTION | 15927.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15933.0908 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15935.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15947.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15951.0908 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 15953.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15955.0908 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 15955.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15959.0908 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15961.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15963.0908 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 63333.3333 | ACTION | 15969.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 1 | 7916.6667 | ACTION | 15970.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 71250 | ACTION | 15979.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 5 | 39583.3333 | ACTION | 15984.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 15987.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 49 | 0 | ACTION | 16012.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16024.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 16038.0908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16041.5908 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16045.0908 | MooredSubInstallation
| Towing Group 3 | Delay | 59 | 467083.3333 | ACTION | 16046.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16048.5908 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 16052.3365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 7.9536 | 62966.3393 | ACTION | 16060.2901 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 179 | 1678125 | ACTION | 16069.3855 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16072.5908 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16074.8855 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16080.3855 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16081.3855 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 16086.3233 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16087.3233 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16092.8233 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16098.3233 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16100.3233 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16101.3233 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 24 | 225000 | ACTION | 16125.3233 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16130.8233 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16136.3233 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16137.3233 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16144.5908 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 484.3007 | 3834047.3728 | ACTION | 16144.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 16150.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 17 | 134583.3333 | ACTION | 16167.5908 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 20.2456 | 160277.9545 | ACTION | 16187.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 16189.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 16195.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 16215.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 16221.8365 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.9536 | 62966.3393 | ACTION | 16229.7901 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 111 | 1040625 | ACTION | 16248.3233 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 16253.2612 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16254.2612 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16259.7612 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16265.2612 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16267.2612 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16268.2612 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16273.7612 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16279.2612 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16280.2612 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 16285.199 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16286.199 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16291.699 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16297.199 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16299.199 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16300.199 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16305.699 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16311.199 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16312.199 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 16317.1369 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16318.1369 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16323.6369 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16329.1369 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16331.1369 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16332.1369 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16337.6369 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16343.1369 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16344.1369 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 16349.0747 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16350.0747 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16355.5747 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16361.0747 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16363.0747 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16364.0747 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16369.5747 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16375.0747 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16376.0747 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 16381.0126 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16382.0126 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16387.5126 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16393.0126 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16395.0126 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16396.0126 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16401.5126 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16407.0126 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16408.0126 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 16412.9504 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 35 | 328125 | ACTION | 16447.9504 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16448.9504 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16454.4504 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16459.9504 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16461.9504 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16462.9504 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16468.4504 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16473.9504 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16474.9504 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 16479.8883 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16480.8883 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16486.3883 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16491.8883 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16493.8883 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16494.8883 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16500.3883 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16505.8883 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16506.8883 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 16511.8261 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16512.8261 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16518.3261 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16523.8261 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16525.8261 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16526.8261 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16532.3261 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16537.8261 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16538.8261 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 16543.764 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16544.764 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16550.264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16555.764 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16557.764 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16558.764 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16564.264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16569.764 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16570.764 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 28125 | ACTION | 16573.764 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 87 | 815625 | ACTION | 16660.764 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.9378 | 18167.3219 | ACTION | 16662.7018 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16663.7018 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16669.2018 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16674.7018 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16676.7018 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16677.7018 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16683.2018 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16688.7018 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16689.7018 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 18750 | ACTION | 16691.7018 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 146 | 1368750 | ACTION | 16837.7018 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 2.9378 | 27542.3219 | ACTION | 16840.6397 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16841.6397 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16847.1397 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16852.6397 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16854.6397 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16855.6397 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16861.1397 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16866.6397 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16867.6397 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 16872.5775 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16873.5775 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 34 | 318750 | ACTION | 16907.5775 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16913.0775 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 42 | 393750 | ACTION | 16955.0775 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16960.5775 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16962.5775 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16963.5775 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16969.0775 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16974.5775 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16975.5775 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 16980.5154 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16981.5154 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16987.0154 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16992.5154 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16994.5154 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16995.5154 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 543 | 5090625 | ACTION | 17538.5154 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 17544.0154 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 17549.5154 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 17550.5154 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 17555.4532 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 17556.4532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 17561.9532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 17567.4532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 17569.4532 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 17570.4532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 17575.9532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 17581.4532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 17582.4532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 17587.3911 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 17588.3911 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 17593.8911 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 17599.3911 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 17601.3911 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 17602.3911 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 17607.8911 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 93 | 871875 | ACTION | 17700.8911 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 17706.3911 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 17707.3911 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 37500 | ACTION | 17711.3911 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 341 | 3196875 | ACTION | 18052.3911 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 0.93785 | 8792.3219 | ACTION | 18053.3289 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18054.3289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18059.8289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18065.3289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18067.3289 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18068.3289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 37 | 346875 | ACTION | 18105.3289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18110.8289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18116.3289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18117.3289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 18122.2667 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 9 | 84375 | ACTION | 18131.2667 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18132.2667 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 4 | 37500 | ACTION | 18136.2667 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18141.7667 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18147.2667 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18149.2667 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18150.2667 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18155.7667 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18161.2667 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18162.2667 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 18167.2046 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18168.2046 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18173.7046 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18179.2046 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18181.2046 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18182.2046 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18187.7046 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18193.2046 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18194.2046 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 18199.1424 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18200.1424 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18205.6424 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18211.1424 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18213.1424 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18214.1424 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18219.6424 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18225.1424 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18226.1424 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 18231.0803 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18232.0803 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18237.5803 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18243.0803 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18245.0803 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18246.0803 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 186 | 1743750 | ACTION | 18432.0803 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18437.5803 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18443.0803 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18444.0803 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 18449.0181 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18450.0181 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 4 | 37500 | ACTION | 18454.0181 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18459.5181 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 79 | 740625 | ACTION | 18538.5181 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18544.0181 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18546.0181 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18547.0181 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 260 | 2437500 | ACTION | 18807.0181 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18812.5181 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18818.0181 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18819.0181 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 12.0467 | 112937.754 | ACTION | 18831.0648 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18832.0648 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18837.5648 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18843.0648 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18845.0648 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18846.0648 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18851.5648 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18857.0648 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18858.0648 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 12.0467 | 112937.754 | ACTION | 18870.1115 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18871.1115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18876.6115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18882.1115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18884.1115 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18885.1115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18890.6115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 25 | 234375 | ACTION | 18915.6115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18921.1115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18922.1115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8 | 75000 | ACTION | 18930.1115 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 32 | 300000 | ACTION | 18962.1115 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 0.30951 | 2901.6126 | ACTION | 18962.421 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18963.421 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 37 | 346875 | ACTION | 19000.421 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19005.921 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19011.421 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19013.421 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19014.421 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19019.921 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19025.421 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19026.421 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8.3095 | 77901.6126 | ACTION | 19034.7305 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19035.7305 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19041.2305 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19046.7305 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19048.7305 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19049.7305 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19055.2305 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 48 | 450000 | ACTION | 19103.2305 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19108.7305 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19109.7305 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.4336 | 50939.9102 | ACTION | 19115.1641 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19116.1641 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19121.6641 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19127.1641 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19129.1641 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19130.1641 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19135.6641 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19141.1641 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19142.1641 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.4336 | 50939.9102 | ACTION | 19147.5977 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19148.5977 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19154.0977 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 133 | 1246875 | ACTION | 19287.0977 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19292.5977 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 9.6827 | 90775.2717 | ACTION | 19302.2804 | ArrayCableInstallation | ArrayCableInstallation | FALSE