## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | location | phase_name | max_waveheight | max_windspeed | transit_speed | num_vessels | num_ahts_vessels
0.5 | Export Cable Installation Vessel | Mobilize | 72 | 180000 | ACTION | 0 | ExportCableInstallation
| Onshore Construction | Onshore Construction | 0 | 1665604.3526 | ACTION | 0 | ExportCableInstallation | Landfall
1 | Mooring System Installation Vessel | Mobilize | 168 | 700000 | ACTION | 0 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 6 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 5 | 20833.3333 | ACTION | 15 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 45 | 187500 | ACTION | 60 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 77 | 385000 | ACTION | 83 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Tow Plow | 0.4 | 2000 | ACTION | 83.4 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Pull Winch | 0.4 | 2000 | ACTION | 83.8 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 84.8 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 90.3 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Transit | 38.2759 | 159482.9167 | ACTION | 98.2759 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 100.2759 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 104.2759 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 16 | 66666.6667 | ACTION | 120.2759 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 137.3409 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 142.4059 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 144.4059 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 148.4059 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 165.4709 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 170.5359 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 172.5359 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 176.5359 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 193.6009 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 198.6659 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 200.6659 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 204.6659 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 19 | 79166.6667 | ACTION | 223.6659 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 240.7309 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 153 | 765000 | ACTION | 243.3 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 245.7959 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 247.7959 | MooringSystemInstallation
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 248.8 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 249.8 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 251.7959 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 10 | 50000 | ACTION | 259.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Delay | 44 | 183333.3333 | ACTION | 295.7959 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 312.8609 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 317.9259 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 319.9259 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 323.9259 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 340.9909 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 346.0559 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 389.3318 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 394.3318 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 399.3318 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 156 | 780000 | ACTION | 415.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 442.6077 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 444.6077 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 29 | 145000 | ACTION | 444.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 448.6077 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 465.6727 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 470.7377 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 472.7377 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 476.7377 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 493.8027 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 498.8677 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 500.8677 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 504.8677 | MooringSystemInstallation |  | MooringSystemInstallation
| Substation Assembly Line 1 | Substation Substructure Assembly | 0 | 0 | ACTION | 507.9273 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 26 | 108333.3333 | ACTION | 530.8677 | MooringSystemInstallation |  | MooringSystemInstallation
| Substation Assembly Line 1 | Attach Topside | 24 | 0 | ACTION | 531.9273 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay: Waiting on Completed Assembly | 24 | 100000 | ACTION | 531.9273 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 547.9327 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 552.9977 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 109 | 545000 | ACTION | 553.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 554.9977 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 558.9977 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 9 | 45000 | ACTION | 562.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 576.0627 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 581.1277 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 594.1277 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 596.1277 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 600.1277 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 617.1927 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 622.2577 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 624.2577 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 628.2577 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 76 | 316666.6667 | ACTION | 704.2577 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 721.3227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 3 | 12500 | ACTION | 724.3227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 729.3877 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 772.6636 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 777.6636 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 782.6636 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 55 | 229166.6667 | ACTION | 837.6636 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 306 | 1275000 | ACTION | 837.9273 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 880.9395 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 882.9395 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 324 | 1620000 | ACTION | 886.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 886.9395 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 904.0045 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 909.0695 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Tow Substation to Site | 72.1265 | 300527.0833 | ACTION | 910.0538 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 911.0695 | MooringSystemInstallation
| Floating Substation Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 912.0538 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 28 | 140000 | ACTION | 914.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 915.0695 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 918.0538 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 922.0538 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 932.1345 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 49 | 204166.6667 | ACTION | 971.0538 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 39 | 162500 | ACTION | 971.1345 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 976.1995 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 978.1995 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 982.1995 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 16.065 | 66937.5 | ACTION | 987.1188 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 992.1838 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 999.2645 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1004.3295 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1006.3295 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1010.3295 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 99 | 495000 | ACTION | 1013.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1014.1838 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 6 | 30000 | ACTION | 1019.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1026.1838 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1027.3945 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1030.1838 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1032.4595 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1034.4595 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1038.4595 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 16.065 | 66937.5 | ACTION | 1046.2488 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1051.3138 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1055.5245 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1060.5895 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 41 | 205000 | ACTION | 1060.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1062.5895 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1066.5895 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1073.3138 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1083.6545 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1085.3138 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1088.7195 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1089.3138 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 29 | 145000 | ACTION | 1089.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 16.065 | 66937.5 | ACTION | 1105.3788 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1110.4438 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 1117.4438 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 1118.4438 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay | 5 | 20833.3333 | ACTION | 1123.4438 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 3 | 12500 | ACTION | 1126.4438 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 1131.9954 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1136.9954 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 14 | 58333.3333 | ACTION | 1140.4438 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1141.9954 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 18 | 75000 | ACTION | 1158.4438 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 75 | 375000 | ACTION | 1164.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 1165.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1170.4438 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 1185.2713 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1187.2713 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 24 | 120000 | ACTION | 1189.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1191.2713 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1208.3363 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1213.4013 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 1213.7197 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1215.4013 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1219.4013 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1236.4663 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1241.5313 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 52 | 260000 | ACTION | 1241.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1243.5313 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1247.5313 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1264.5963 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1269.6613 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1271.6613 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1275.6613 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 1282.6613 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1299.7263 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 1306.7263 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1311.7913 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1313.7913 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1317.7913 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 1328.7913 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1345.8563 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 109 | 545000 | ACTION | 1350.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1350.9213 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1352.9213 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1356.9213 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1373.9863 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1379.0513 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 40 | 200000 | ACTION | 1390.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 1422.3272 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1427.3272 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1432.3272 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2 | 8333.3333 | ACTION | 1434.3272 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 18 | 75000 | ACTION | 1452.3272 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 12 | 50000 | ACTION | 1464.3272 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 32 | 133333.3333 | ACTION | 1496.3272 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 29.2759 | 121982.9167 | ACTION | 1525.6031 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1527.6031 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1531.6031 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1548.6681 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1553.7331 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1555.7331 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1559.7331 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 178 | 890000 | ACTION | 1568.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1576.7981 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1581.8631 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1583.8631 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 19 | 95000 | ACTION | 1587.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1587.8631 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1604.9281 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1609.9931 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1611.9931 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1615.9931 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1633.0581 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1638.1231 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1640.1231 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1644.1231 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 67 | 335000 | ACTION | 1654.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1661.1881 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1666.2531 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1668.2531 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1672.2531 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 28.5723 | 142861.6352 | ACTION | 1683.3723 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1689.3181 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1694.3831 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Transit | 37.6312 | 188156.087 | ACTION | 1721.0035 | ExportCableInstallation
| Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 1727.0035 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 1737.659 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1742.659 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1747.659 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 41 | 205000 | ACTION | 1768.0035 | ExportCableInstallation
| Export Cable Installation Vessel | Transit | 12 | 60000 | ACTION | 1780.0035 | ExportCableInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 1790.9349 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1792.9349 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1796.9349 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1813.9999 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 35 | 175000 | ACTION | 1815.0035 | ExportCableInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1819.0649 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1821.0649 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1825.0649 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Transit | 25.6312 | 128156.087 | ACTION | 1840.6348 | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1842.1299 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1842.6348 | ExportCableInstallation
| Export Cable Installation Vessel | Raise Cable | 0.5 | 2500 | ACTION | 1843.1348 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1847.1949 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1849.1949 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1853.1949 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1870.2599 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1875.3249 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1877.3249 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1881.3249 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Splice Cable | 48 | 240000 | ACTION | 1891.1348 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1892.1348 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1898.3899 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1903.4549 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1905.4549 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1909.4549 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1926.5199 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1931.5849 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1933.5849 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1937.5849 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1954.6499 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1959.7149 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 83.9431 | 419715.5392 | ACTION | 1976.0779 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1978.0779 | ExportCableInstallation
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1983.5779 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1989.0779 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Transit | 2 | 10000 | ACTION | 1991.0779 | ExportCableInstallation
| Export Cable Installation Vessel | Delay | 5 | 25000 | ACTION | 1996.0779 | ExportCableInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 2002.9908 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2007.9908 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2012.9908 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Transit | 35.6312 | 178156.087 | ACTION | 2031.7091 | ExportCableInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 2056.2667 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2058.2667 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2062.2667 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2079.3317 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2084.3967 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2086.3967 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2090.3967 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2107.4617 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2112.5267 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2114.5267 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2118.5267 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2135.5917 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2140.6567 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2142.6567 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2146.6567 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2163.7217 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2168.7867 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2170.7867 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2174.7867 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2191.8517 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2196.9167 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2198.9167 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 27 | 112500 | ACTION | 2225.9167 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2229.9167 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 29 | 120833.3333 | ACTION | 2258.9167 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2275.9817 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2281.0467 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 2324.3226 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2329.3226 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2334.3226 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 2377.5985 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2379.5985 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2383.5985 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2400.6635 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2405.7285 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2407.7285 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2411.7285 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2428.7935 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2433.8585 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2435.8585 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2439.8585 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2456.9235 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2461.9885 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2463.9885 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2467.9885 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2485.0535 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2490.1185 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2492.1185 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2496.1185 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2513.1835 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2518.2485 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2520.2485 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2524.2485 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2541.3135 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2546.3785 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 2589.6544 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2594.6544 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2599.6544 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 2642.9303 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2644.9303 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2648.9303 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2665.9953 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2671.0603 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2673.0603 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2677.0603 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2694.1253 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2699.1903 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2701.1903 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2705.1903 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2722.2553 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2727.3203 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2729.3203 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2733.3203 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2750.3853 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2755.4503 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2757.4503 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2761.4503 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2778.5153 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2783.5803 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2785.5803 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2789.5803 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2806.6453 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2811.7103 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 2854.9862 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2859.9862 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2864.9862 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 2908.2621 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2910.2621 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2914.2621 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2931.3271 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2936.3921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2938.3921 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2942.3921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2959.4571 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2964.5221 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2966.5221 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2970.5221 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2987.5871 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2992.6521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2994.6521 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2998.6521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3015.7171 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3020.7821 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3022.7821 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3026.7821 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3043.8471 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3048.9121 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3050.9121 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3054.9121 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3071.9771 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3077.0421 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 3120.318 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3125.318 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3130.318 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 3173.5939 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3175.5939 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3179.5939 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3196.6589 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3201.7239 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3203.7239 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3207.7239 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3224.7889 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3229.8539 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3231.8539 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3235.8539 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3252.9189 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3257.9839 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3259.9839 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3263.9839 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3281.0489 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3286.1139 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3288.1139 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3292.1139 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3309.1789 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3314.2439 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3316.2439 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3320.2439 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3337.3089 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3342.3739 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 3385.6498 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3390.6498 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3395.6498 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 35 | 145833.3333 | ACTION | 3430.6498 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 3441.6498 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.2759 | 34482.9167 | ACTION | 3449.9257 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3451.9257 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3455.9257 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3472.9907 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3478.0557 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3480.0557 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3484.0557 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3501.1207 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3506.1857 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3508.1857 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3512.1857 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3529.2507 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3534.3157 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3536.3157 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3540.3157 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3557.3807 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3562.4457 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3564.4457 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3568.4457 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3585.5107 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3590.5757 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3592.5757 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3596.5757 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3613.6407 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3618.7057 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 3661.9816 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3666.9816 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3671.9816 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 3715.2575 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3717.2575 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3721.2575 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3738.3225 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3743.3875 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3745.3875 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3749.3875 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3766.4525 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3771.5175 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3773.5175 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3777.5175 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3794.5825 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3799.6475 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3801.6475 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3805.6475 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3822.7125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3827.7775 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3829.7775 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3833.7775 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3850.8425 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3855.9075 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3857.9075 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3861.9075 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3878.9725 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3884.0375 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 3927.3134 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3932.3134 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3937.3134 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 3980.5893 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3982.5893 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3986.5893 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4003.6543 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4008.7193 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4010.7193 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4014.7193 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4031.7843 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4036.8493 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4038.8493 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4042.8493 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4059.9143 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4064.9793 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4066.9793 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4070.9793 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4088.0443 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4093.1093 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4095.1093 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4099.1093 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4116.1743 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4121.2393 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4123.2393 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4127.2393 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4144.3043 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4149.3693 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 4192.6452 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4197.6452 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4202.6452 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 4245.9211 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4247.9211 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4251.9211 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4268.9861 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4274.0511 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4276.0511 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4280.0511 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4297.1161 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4302.1811 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4304.1811 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4308.1811 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4325.2461 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4330.3111 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4332.3111 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4336.3111 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4353.3761 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4358.4411 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4360.4411 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4364.4411 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4381.5061 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4386.5711 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4388.5711 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4392.5711 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4409.6361 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4414.7011 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 4457.977 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4462.977 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4467.977 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 26 | 108333.3333 | ACTION | 4493.977 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 4501.977 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 6 | 25000 | ACTION | 4507.977 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 4509.977 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 11.2759 | 46982.9167 | ACTION | 4521.2529 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4523.2529 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4527.2529 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4544.3179 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4549.3829 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4551.3829 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4555.3829 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4572.4479 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4577.5129 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4579.5129 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4583.5129 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4600.5779 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4605.6429 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4607.6429 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4611.6429 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4628.7079 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4633.7729 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4635.7729 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4639.7729 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4656.8379 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4661.9029 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4663.9029 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4667.9029 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4684.9679 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4690.0329 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 4733.3088 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4738.3088 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4743.3088 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 4786.5847 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4788.5847 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4792.5847 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4809.6497 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4814.7147 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4816.7147 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4820.7147 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4837.7797 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4842.8447 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4844.8447 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4848.8447 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4865.9097 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4870.9747 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4872.9747 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4876.9747 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4894.0397 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4899.1047 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4901.1047 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4905.1047 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4922.1697 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4927.2347 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4929.2347 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4933.2347 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4950.2997 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4955.3647 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 4998.6406 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5003.6406 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5008.6406 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 5051.9165 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5053.9165 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5057.9165 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5074.9815 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5080.0465 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5082.0465 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5086.0465 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5103.1115 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5108.1765 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5110.1765 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5114.1765 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5131.2415 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5136.3065 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5138.3065 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5142.3065 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5159.3715 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5164.4365 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5166.4365 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5170.4365 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5187.5015 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5192.5665 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5194.5665 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5198.5665 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5215.6315 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5220.6965 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 5263.9724 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5268.9724 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5273.9724 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 5317.2483 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5319.2483 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5323.2483 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5340.3133 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5345.3783 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5347.3783 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5351.3783 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5368.4433 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5373.5083 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5375.5083 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5379.5083 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5396.5733 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5401.6383 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5403.6383 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5407.6383 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5424.7033 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5429.7683 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5431.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 5431.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5431.7683 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5435.7683 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5439.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5451.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5452.8333 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5455.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5457.8983 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5459.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5459.8983 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5463.8983 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5471.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5474.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5478.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5480.9633 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5481.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5486.0283 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5505.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 5529.3042 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5534.3042 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5539.3042 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 5582.5801 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5584.5801 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5588.5801 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5599.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5605.6451 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5610.7101 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5612.7101 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5616.7101 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 112 | 0 | ACTION | 5617.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5633.7751 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5638.8401 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5640.8401 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5644.8401 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5661.9051 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5666.9701 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5668.9701 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5672.9701 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5689.8076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 426.5 | 2843333.3333 | ACTION | 5689.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5690.0351 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5695.1001 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5695.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5697.1001 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5697.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5701.1001 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5709.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5713.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5717.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5718.1651 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5723.2301 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5725.2301 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5729.2301 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5729.8076 | MooredSubInstallation
| Towing Group 1 | Delay | 48 | 320000 | ACTION | 5743.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5746.2951 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5751.3601 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 28 | 0 | ACTION | 5757.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5761.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5764.8076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5767.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5768.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5792.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 5794.636 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5799.636 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5804.636 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 5805.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 5807.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5813.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5833.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 5839.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 5847.9119 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5849.9119 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5853.9119 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5864.3076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 601 | 4006666.6667 | ACTION | 5864.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5870.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5870.9769 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5872.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5876.0419 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5878.0419 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5882.0419 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5884.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5888.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5892.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5899.1069 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5904.1719 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5904.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5906.1719 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5907.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5910.1719 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5911.3076 | MooredSubInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 5911.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5914.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5927.2369 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 5932.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5932.3019 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 5934.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5934.3019 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5935.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5938.3019 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5938.8076 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5940.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5955.3669 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5960.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5960.4319 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5962.4319 | MooringSystemInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 5966.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5966.4319 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5983.4969 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5988.5619 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5990.5619 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5994.5619 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6010.8076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 747.5 | 4983333.3333 | ACTION | 6010.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6011.6269 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6016.6919 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6016.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6018.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6030.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6034.8076 | MooredSubInstallation
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 6038.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 22 | 146666.6667 | ACTION | 6038.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 6038.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6042.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6054.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6058.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 6059.9678 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6061.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6064.9678 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6065.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6069.9678 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6089.3076 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 6100.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 6102.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6103.3076 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6108.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 6113.2437 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6115.2437 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6119.2437 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6128.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 6134.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6136.3087 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6141.3737 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6143.3737 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6147.3737 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6161.3076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 249.5508 | 1663671.9048 | ACTION | 6161.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6164.4387 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6167.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6169.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6169.5037 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6171.5037 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6175.5037 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6181.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6185.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6189.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6192.5687 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6197.6337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6199.6337 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6201.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6203.6337 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6204.8076 | MooredSubInstallation
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 6206.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6208.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6211.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6220.6987 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6225.7637 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6227.7637 | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 6229.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 6231.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6231.7637 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6235.8076 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6237.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6248.8287 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6253.8937 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6255.8937 | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6257.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6259.8937 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 6263.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6271.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6276.9587 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6282.0237 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6307.8076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 269.5508 | 1797005.2381 | ACTION | 6307.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6313.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6315.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 6325.2996 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6327.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6330.2996 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6331.8076 | MooredSubInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 6335.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6335.2996 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6335.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6347.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6351.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6354.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6358.3076 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 6375.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 6377.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 6378.5755 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6380.5755 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6382.3076 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6383.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6384.5755 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 13333.3333 | ACTION | 6385.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 1 | 6666.6667 | ACTION | 6386.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6401.6405 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 120000 | ACTION | 6404.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 2 | 13333.3333 | ACTION | 6406.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6406.7055 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6408.7055 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6412.7055 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Delay | 10 | 66666.6667 | ACTION | 6416.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 3 | 20000 | ACTION | 6419.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 2 | 13333.3333 | ACTION | 6421.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 1 | 6666.6667 | ACTION | 6422.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6429.7705 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6434.8355 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6439.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6454.3076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 247.5508 | 1650338.5714 | ACTION | 6454.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6462.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 35 | 145833.3333 | ACTION | 6469.8355 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6471.8355 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6474.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6475.8355 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 6489.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6492.9005 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6493.3076 | MooredSubInstallation
| Towing Group 3 | Delay | 40 | 266666.6667 | ACTION | 6494.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 6494.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6497.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6497.9655 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6499.9655 | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6500.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6503.9655 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6509.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6512.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6516.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6519.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6521.0305 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6526.0955 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6528.0955 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6532.0955 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6543.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6549.1605 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6554.2255 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6556.2255 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6560.2255 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 6562.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 6564.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6570.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6577.2905 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6582.3555 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6590.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 6596.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6607.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6615.8076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 280.5508 | 1870338.5714 | ACTION | 6615.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6621.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6623.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 6625.6314 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6630.6314 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6635.6314 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6635.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6639.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6643.8076 | MooredSubInstallation
| Towing Group 1 | Delay | 30 | 200000 | ACTION | 6651.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 6651.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6663.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6667.3076 | MooredSubInstallation
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 6668.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6670.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6674.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 6678.9073 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6680.9073 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6684.9073 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6698.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6701.9723 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6707.0373 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6709.0373 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6713.0373 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 6713.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 6715.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6721.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6730.1023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6735.1673 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6737.1673 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6741.1673 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6741.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 6747.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6758.2323 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6763.2973 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6765.2973 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6769.2973 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6770.3076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 275.5508 | 1837005.2381 | ACTION | 6770.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6775.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 5 | 0 | ACTION | 6775.3076 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6776.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6783.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6786.3623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6791.4273 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6793.4273 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6795.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6797.4273 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6799.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6803.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6814.4923 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6815.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6818.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6819.5573 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 6819.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6821.5573 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6822.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6825.5573 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 6838.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 6840.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6842.6223 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6847.6873 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Delay | 12 | 80000 | ACTION | 6852.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 33 | 0 | ACTION | 6855.3076 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6858.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6858.8076 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6878.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6882.8076 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 6884.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 6890.9632 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6895.9632 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6900.9632 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6943.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 6944.2391 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6946.2391 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6950.2391 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6954.8076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 286.5508 | 1910338.5714 | ACTION | 6954.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 6956.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6960.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6962.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6967.3041 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6972.3691 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6974.3691 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6974.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6978.3691 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6978.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6982.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6994.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6995.4341 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6998.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7000.4991 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7001.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7002.4991 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7005.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7006.4991 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 7022.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7023.5641 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 7024.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7028.6291 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7029.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7030.6291 | MooringSystemInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7030.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7034.6291 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7050.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7051.6941 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 7056.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7056.7591 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7058.7591 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7062.7591 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7079.8241 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7084.8891 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7086.8891 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7090.8891 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7101.3076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 281.5508 | 1877005.2381 | ACTION | 7101.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7107.9541 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7111.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 10 | 0 | ACTION | 7111.3076 | MooredSubInstallation
| Towing Group 1 | Delay | 11 | 73333.3333 | ACTION | 7112.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7113.0191 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7118.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7119.3076 | MooredSubInstallation
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 7128.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7131.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7135.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7139.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7151.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7154.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 7156.295 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7158.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7161.295 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7161.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7166.295 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 7180.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 7182.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7185.8076 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7188.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7208.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 7209.5709 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7211.5709 | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 7214.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7215.5709 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7232.6359 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7237.7009 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7239.7009 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7243.7009 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7257.8076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 301.5508 | 2010338.5714 | ACTION | 7257.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7260.7659 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7263.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7265.8309 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7267.8309 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7271.8309 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7279.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 7279.3076 | MooredSubInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 7286.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7287.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7288.8959 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7293.9609 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7295.9609 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7299.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7299.9609 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7303.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7307.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7317.0259 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7319.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7322.0909 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7322.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7324.0909 | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 7325.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7326.3076 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 7327.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7328.0909 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7329.8076 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7333.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7345.1559 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7350.2209 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7352.2209 | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7353.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7353.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7356.2209 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 7359.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7373.2859 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7378.3509 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 7421.6268 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7425.8076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 297.0508 | 1980338.5714 | ACTION | 7425.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7426.6268 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7431.6268 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 7431.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7431.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7447.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 7447.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 19 | 79166.6667 | ACTION | 7450.6268 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7455.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7467.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7471.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7475.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 41 | 0 | ACTION | 7516.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7528.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 79 | 329166.6667 | ACTION | 7529.6268 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7531.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7535.3076 | MooredSubInstallation
| Towing Group 3 | Delay | 105 | 700000 | ACTION | 7536.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7538.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 24.2759 | 101149.5833 | ACTION | 7553.9027 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7555.9027 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7559.9027 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7562.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7576.9677 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7582.0327 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7584.0327 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7588.0327 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 7598.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 7600.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7605.0977 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7606.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7610.1627 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7612.1627 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7615.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7616.1627 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7626.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 7632.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7633.2277 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7634.8076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 348.5508 | 2323671.9048 | ACTION | 7634.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7638.2927 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7640.2927 | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7640.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7642.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7644.2927 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7654.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7658.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7661.3577 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7662.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7666.4227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7668.4227 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7672.4227 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7674.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 7681.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7685.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7688.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7689.4877 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7692.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7694.5527 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7696.5527 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7700.5527 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 7704.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 66 | 440000 | ACTION | 7706.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7716.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7717.6177 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7722.6827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 7765.9586 | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 7768.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 7770.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7770.9586 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7775.9586 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7783.3076 | MooredSubInstallation
| Towing Group 1 | Delay | 13 | 86666.6667 | ACTION | 7783.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7788.3076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 356.5508 | 2377005.2381 | ACTION | 7788.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7789.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7794.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7796.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7808.3076 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7809.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7812.3076 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 7815.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7816.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 7819.2345 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7821.2345 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7825.2345 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7828.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7831.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7835.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7838.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7842.2995 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7847.3645 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7849.3645 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7853.3645 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 7856.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 7858.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7862.8076 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7864.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7870.4295 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7875.4945 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7877.4945 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7881.4945 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7884.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 7887.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 7890.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7898.5595 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7903.6245 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7905.6245 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7909.6245 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7934.8076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 230.0508 | 1533671.9048 | ACTION | 7934.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7951.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 16.5 | 0 | ACTION | 7951.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 44 | 183333.3333 | ACTION | 7953.6245 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7959.3076 | MooredSubInstallation
| Towing Group 3 | Delay | 25 | 166666.6667 | ACTION | 7959.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 7962.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7965.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7970.6895 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7971.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7975.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7975.7545 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7977.7545 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7979.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7981.7545 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7991.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7994.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7998.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7998.8195 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8001.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8003.8845 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8005.8845 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8009.8845 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8025.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8026.9495 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 8027.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 8029.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8032.0145 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8035.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 26666.6667 | ACTION | 8039.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 19 | 79166.6667 | ACTION | 8051.0145 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 8059.0145 | MooringSystemInstallation
| Towing Group 3 | Delay | 35 | 233333.3333 | ACTION | 8074.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 24.2759 | 101149.5833 | ACTION | 8083.2904 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8088.2904 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 106666.6667 | ACTION | 8090.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8093.2904 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 8096.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8097.8076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 210.0508 | 1400338.5714 | ACTION | 8097.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8103.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8119.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 8119.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8127.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 8136.5663 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8138.5663 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8139.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8142.5663 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8143.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8147.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8159.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8159.6313 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8162.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8164.6963 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8166.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8166.6963 | MooringSystemInstallation
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 8168.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8169.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8170.6963 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8187.7613 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8192.8263 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8193.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8194.8263 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8198.8263 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 60 | 250000 | ACTION | 8258.8263 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8265.8076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 303.5508 | 2023671.9048 | ACTION | 8265.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8275.8913 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8280.9563 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8282.9563 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8286.9563 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8287.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 8287.3076 | MooredSubInstallation
| Towing Group 1 | Delay | 188 | 1253333.3333 | ACTION | 8291.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 26 | 173333.3333 | ACTION | 8291.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8295.3076 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8297.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8304.0213 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8307.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8309.0863 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8311.0863 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8311.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8315.0863 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8315.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8327.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8330.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8332.1513 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8334.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8337.2163 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8337.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8339.2163 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8343.2163 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 8353.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8361.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8433.8076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 265.0508 | 1767005.2381 | ACTION | 8433.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8455.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 8455.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 114 | 475000 | ACTION | 8457.2163 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8463.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8474.2813 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8475.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8479.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8479.3463 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Delay | 129 | 860000 | ACTION | 8482.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 49 | 326666.6667 | ACTION | 8482.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8483.3076 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 8484.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8488.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8490.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 20000 | ACTION | 8493.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8495.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 8498.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8501.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8505.3076 | MooredSubInstallation
| Towing Group 1 | Delay | 14 | 93333.3333 | ACTION | 8507.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8508.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 8522.6222 | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 113333.3333 | ACTION | 8524.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8527.6222 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 8530.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8532.6222 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8532.8076 | MooredSubInstallation
| Towing Group 2 | Delay | 255 | 1700000 | ACTION | 8552.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 64 | 426666.6667 | ACTION | 8552.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 8575.8981 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8577.8981 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8581.8981 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8598.9631 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 8602.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8604.0281 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8604.8076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 2.0508 | 13671.9048 | ACTION | 8604.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8606.0281 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8610.0281 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8610.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 8614.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 8614.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 8616.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 8616.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8622.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8622.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8623.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 18.5 | 0 | ACTION | 8623.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8627.0931 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8631.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8632.1581 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8634.1581 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8638.1581 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 8642.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 8642.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8643.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8647.3076 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 8648.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 8648.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8651.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8655.2231 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8660.2881 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8662.2881 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8663.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 8664.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8667.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8671.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8674.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 23 | 95833.3333 | ACTION | 8685.2881 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8689.2881 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8698.8076 | MooredSubInstallation
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 8720.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 8720.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 37 | 154166.6667 | ACTION | 8726.2881 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8743.3531 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8748.4181 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8750.4181 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8754.4181 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8770.8076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 50.0508 | 333671.9048 | ACTION | 8770.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8791.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 20.5 | 0 | ACTION | 8791.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8799.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 49 | 204166.6667 | ACTION | 8803.4181 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8811.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8815.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8819.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8820.4831 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8831.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8834.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8838.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8841.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8865.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8937.8076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 217.0508 | 1447005.2381 | ACTION | 8937.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8959.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 8959.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8967.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8979.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8983.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8987.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8999.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 183 | 762500 | ACTION | 9003.4831 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 9007.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9008.5481 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9010.5481 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9010.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9014.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9014.5481 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9017.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9041.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 36 | 150000 | ACTION | 9050.5481 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Delay | 286 | 1906666.6667 | ACTION | 9056.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 119 | 793333.3333 | ACTION | 9056.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9062.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9062.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9067.6131 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9072.6781 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 3 | 12500 | ACTION | 9075.6781 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 34 | 141666.6667 | ACTION | 9109.6781 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9113.8076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9127.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 9127.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9135.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9147.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 40.2759 | 167816.25 | ACTION | 9149.954 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9151.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9154.954 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9155.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9167.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 9 | 0 | ACTION | 9176.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9179.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 26 | 108333.3333 | ACTION | 9180.954 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9183.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9185.954 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9186.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 18 | 75000 | ACTION | 9203.954 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9210.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 35 | 145833.3333 | ACTION | 9238.954 | MooringSystemInstallation
| Towing Group 1 | Delay | 632 | 4213333.3333 | ACTION | 9242.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 180 | 1200000 | ACTION | 9242.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 180 | 1200000 | ACTION | 9242.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 25.2759 | 105316.25 | ACTION | 9264.2299 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9266.2299 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9270.2299 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9282.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9287.2949 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9292.3599 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9294.3599 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9295.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 12.5 | 0 | ACTION | 9295.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9298.3599 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9303.3076 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 9304.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 9304.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 9304.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 9306.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 9306.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 9306.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9315.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9319.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9323.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9335.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 9339.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 44 | 183333.3333 | ACTION | 9342.3599 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9342.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9346.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9349.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9359.4249 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 36 | 0 | ACTION | 9385.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9409.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 9436.8076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9463.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 109 | 454166.6667 | ACTION | 9468.4249 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9473.4899 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9475.4899 | MooringSystemInstallation
| Towing Group 1 | Delay | 169 | 1126666.6667 | ACTION | 9475.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 169 | 1126666.6667 | ACTION | 9475.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 169 | 1126666.6667 | ACTION | 9475.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9479.4899 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9481.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9481.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9481.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9496.5549 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9501.6199 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9501.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9501.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9501.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9503.6199 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9507.6199 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 9507.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 9507.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 9507.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9508.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9516.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9524.6849 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9528.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9529.7499 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9531.7499 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9532.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9535.7499 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9536.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9548.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9552.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9552.8149 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9555.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9557.8799 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9559.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9559.8799 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9563.8799 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 9579.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 9579.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 9579.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9580.9449 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9583.3076 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9585.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9585.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9585.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9586.0099 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 9629.2858 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9631.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9634.2858 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9639.2858 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 9647.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 9647.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 9647.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 9649.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 9649.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 9649.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9655.3076 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9655.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9655.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9655.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9663.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9675.3076 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9675.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9675.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9675.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9679.3076 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 9681.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 9681.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 9681.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 9682.5617 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9683.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9684.5617 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9688.5617 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9695.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9698.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9702.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9705.6267 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9705.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9710.6917 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9712.6917 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9716.6917 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9729.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9733.7567 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9738.8217 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9740.8217 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9744.8217 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 9753.7061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 9753.7061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 9753.7061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9759.7061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9761.8867 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9766.9517 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9768.9517 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9772.9517 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9790.0167 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9795.0817 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9797.0817 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9799.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9801.0817 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9801.8076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 48.1016 | 320677.1429 | ACTION | 9801.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9807.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9809.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9818.1467 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 9821.5288 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9821.8076 | MooredSubInstallation
| Towing Group 1 | Delay | 1 | 6666.6667 | ACTION | 9822.5288 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 9822.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9823.2117 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 9824.5288 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9825.2117 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9826.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9829.2117 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9830.5288 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9830.8076 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 46666.6667 | ACTION | 9837.5288 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9846.2767 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 22 | 0 | ACTION | 9852.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 9854.2767 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9859.3417 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9864.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9868.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9871.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9875.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 34 | 141666.6667 | ACTION | 9893.3417 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9899.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 46 | 191666.6667 | ACTION | 9939.3417 | MooringSystemInstallation
| Towing Group 1 | Delay | 107 | 713333.3333 | ACTION | 9944.5288 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 9.2759 | 38649.5833 | ACTION | 9948.6176 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9953.6176 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 86666.6667 | ACTION | 9957.5288 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9958.6176 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 9963.5288 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9967.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9971.3076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 217.6016 | 1450677.1429 | ACTION | 9971.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9977.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9979.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9991.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 9993.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9997.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 10001.8935 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 10012.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10016.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 10022.8935 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10024.8935 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10028.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10028.8935 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 10035.6553 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 10036.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10039.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10043.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10045.9585 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10046.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10051.0235 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10053.0235 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10057.0235 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10070.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10074.0885 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10079.1535 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10081.1535 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10085.1535 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 27 | 112500 | ACTION | 10112.1535 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10129.2185 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10134.2835 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10135.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10136.2835 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10142.8076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 107.1524 | 714349.0476 | ACTION | 10142.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10150.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10162.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 17 | 0 | ACTION | 10179.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10183.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10187.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 54 | 225000 | ACTION | 10190.2835 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10194.2835 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Delay | 390 | 2600000 | ACTION | 10197.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 55 | 366666.6667 | ACTION | 10197.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 221 | 1473333.3333 | ACTION | 10198.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10199.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10203.3076 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10203.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10206.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10210.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10211.3485 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10216.4135 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10218.4135 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10222.4135 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10234.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10239.4785 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10244.5435 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10246.5435 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10250.5435 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 10259.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 10260.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 10261.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 10262.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 10265.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10267.6085 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10267.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 10267.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10268.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10272.6735 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10273.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10287.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10288.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10293.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 10293.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 10294.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 10299.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10303.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10306.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10314.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 43.2759 | 180316.25 | ACTION | 10315.9494 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10320.9494 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 5 | 20833.3333 | ACTION | 10325.9494 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10326.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10330.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10334.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10346.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 10353.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 30 | 125000 | ACTION | 10355.9494 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10356.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10360.3076 | MooredSubInstallation
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 10365.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 10366.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 10367.3076 | MooredSubInstallation
| Towing Group 2 | Delay | 3 | 20000 | ACTION | 10368.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10370.8076 | MooredSubInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 10371.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10374.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 28 | 116666.6667 | ACTION | 10383.9494 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10394.8076 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 20 | 83333.3333 | ACTION | 10403.9494 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 10.2759 | 42816.25 | ACTION | 10414.2253 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10416.2253 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10420.2253 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 28 | 116666.6667 | ACTION | 10448.2253 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Delay | 85 | 566666.6667 | ACTION | 10459.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10465.2903 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10466.8076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 100.5508 | 670338.5714 | ACTION | 10466.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10470.3553 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10471.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 4.5 | 0 | ACTION | 10471.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10472.3553 | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10472.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10476.3553 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10479.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10491.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10493.4203 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10495.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10498.4853 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10499.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10500.4853 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10504.4853 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10511.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10514.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10518.3076 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10521.5503 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 10521.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10521.8076 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 10523.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10526.6153 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10529.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 10534.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 10536.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10542.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 100000 | ACTION | 10544.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 13333.3333 | ACTION | 10544.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10545.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 17 | 0 | ACTION | 10562.8076 | MooredSubInstallation
| Towing Group 2 | Delay | 38 | 253333.3333 | ACTION | 10582.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 38 | 253333.3333 | ACTION | 10582.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 33333.3333 | ACTION | 10587.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 10593.5796 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 120000 | ACTION | 10600.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 10606.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10634.8076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 263.0508 | 1753671.9048 | ACTION | 10634.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10639.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 4.5 | 0 | ACTION | 10639.3076 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10640.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10647.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10659.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10663.3076 | MooredSubInstallation
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 10665.7061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10667.3076 | MooredSubInstallation
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 10678.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10679.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 82 | 0 | ACTION | 10761.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10764.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10768.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10771.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10795.8076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10807.3076 | MooredSubInstallation
| Towing Group 1 | Delay | 184 | 1226666.6667 | ACTION | 10824.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10867.8076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 202.1016 | 1347343.8095 | ACTION | 10867.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10873.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10875.8076 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 10886.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10887.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 10895.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10899.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10903.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10915.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10919.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10922.8076 | MooredSubInstallation
| Towing Group 1 | Delay | 38 | 253333.3333 | ACTION | 10924.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 51 | 340000 | ACTION | 10924.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10926.3076 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 10926.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10932.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10950.3076 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10952.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 10958.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10975.3076 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 10986.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 10988.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10994.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11014.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 11020.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11022.3076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 343.5508 | 2290338.5714 | ACTION | 11022.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11028.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11030.3076 | MooredSubInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 11030.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11042.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11046.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11050.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11062.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 11069.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11072.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11076.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11079.8076 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 11090.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 11092.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 11092.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11098.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11103.8076 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11118.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 11124.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11143.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11175.8076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 145.0508 | 967005.2381 | ACTION | 11175.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11183.8076 | MooredSubInstallation
0.5 | Array Cable Installation Vessel | Mobilize | 72 | 180000 | ACTION | 11189.7823 | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 11195.7823 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11195.8076 | MooredSubInstallation
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 11196.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 11201.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11205.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 11216.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11220.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11232.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11236.3076 | MooredSubInstallation
| Towing Group 1 | Delay | 61 | 406666.6667 | ACTION | 11236.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11239.8076 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11242.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11243.3076 | MooredSubInstallation
| Towing Group 1 | Delay | 22 | 146666.6667 | ACTION | 11264.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11267.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 88 | 440000 | ACTION | 11283.7823 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11311.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Transit | 37.6312 | 188156.087 | ACTION | 11321.4135 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11323.4135 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11324.4135 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 11326.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 11328.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11334.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11339.3076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 246.5508 | 1643671.9048 | ACTION | 11339.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11345.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11347.3076 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11354.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 2 | 13333.3333 | ACTION | 11356.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 2 | 13333.3333 | ACTION | 11358.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11359.3076 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 4 | 26666.6667 | ACTION | 11362.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11363.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11367.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 43 | 215000 | ACTION | 11367.4135 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11372.9135 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11378.4135 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11379.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11379.4135 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | ACTION | 11383.4135 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Delay | 54 | 0 | ACTION | 11433.3076 | MooredSubInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 11434.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11436.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11440.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11443.8076 | MooredSubInstallation
| Towing Group 2 | Delay | 116 | 773333.3333 | ACTION | 11461.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11467.8076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11479.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 106 | 530000 | ACTION | 11489.4135 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 6.9462 | 34731.0783 | ACTION | 11496.3597 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11497.3597 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11502.8597 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11508.3597 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11510.3597 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11511.3597 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11516.8597 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11522.3597 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 11523.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11523.3597 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 11525.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11531.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 11534.3059 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11535.3059 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11539.8076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 343.5508 | 2290338.5714 | ACTION | 11539.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11540.8059 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11545.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11546.3059 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11547.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11548.3059 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11549.3059 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11551.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11554.8059 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 11557.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11559.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11560.3059 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11561.3059 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11563.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11567.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 7 | 35000 | ACTION | 11568.3059 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11579.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 11580.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11584.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 17 | 85000 | ACTION | 11585.3059 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11587.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 3.9462 | 19731.0783 | ACTION | 11589.2521 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11590.2521 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 5 | 25000 | ACTION | 11595.2521 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11600.7521 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 11600.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11604.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11606.2521 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 11607.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11608.2521 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11609.2521 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 11609.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11614.7521 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11615.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11620.2521 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11621.2521 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11628.3076 | MooredSubInstallation
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 11629.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 11632.1983 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11633.1983 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11635.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 11641.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11647.3076 | MooredSubInstallation
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 11713.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 88 | 0 | ACTION | 11716.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 146 | 730000 | ACTION | 11779.1983 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11784.6983 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11788.3076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 353.5508 | 2357005.2381 | ACTION | 11788.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11790.1983 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11792.1983 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11793.1983 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11794.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11796.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11798.6983 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11808.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 11813.3076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11815.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11817.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 24 | 0 | ACTION | 11841.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11845.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 47 | 0 | ACTION | 11892.3076 | MooredSubInstallation
| Towing Group 1 | Delay | 110 | 733333.3333 | ACTION | 11904.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11904.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11907.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11911.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11914.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 130 | 650000 | ACTION | 11928.6983 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11934.1983 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11935.1983 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11938.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 11946.1446 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11947.1446 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11952.6446 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11958.1446 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11960.1446 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11961.1446 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 11966.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11966.6446 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 11968.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11972.1446 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11973.1446 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11974.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11983.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 11984.0908 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11994.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 4 | 26666.6667 | ACTION | 11998.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12010.8076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 381.5508 | 2543671.9048 | ACTION | 12010.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12018.8076 | MooredSubInstallation
| Towing Group 2 | Delay | 15 | 100000 | ACTION | 12025.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 28 | 186666.6667 | ACTION | 12026.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 2 | 13333.3333 | ACTION | 12028.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12030.8076 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12031.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12034.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12038.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 66 | 330000 | ACTION | 12050.0908 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12050.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12051.0908 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12054.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12056.5908 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12057.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12061.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12062.0908 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12064.0908 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12065.0908 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12085.3076 | MooredSubInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 12100.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 65 | 0 | ACTION | 12150.3076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12151.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12222.3076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 508.5508 | 3390338.5714 | ACTION | 12222.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12228.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12230.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12242.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 36 | 0 | ACTION | 12278.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12282.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 12295.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12299.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 19 | 0 | ACTION | 12318.3076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12319.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 258 | 1290000 | ACTION | 12323.0908 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12328.5908 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12330.3076 | MooredSubInstallation
| Towing Group 2 | Delay | 361 | 2406666.6667 | ACTION | 12392.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 165 | 1100000 | ACTION | 12393.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 65 | 0 | ACTION | 12395.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12398.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12402.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12405.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 78 | 390000 | ACTION | 12406.5908 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12412.0908 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12413.0908 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 12424.037 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12425.037 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12429.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12430.537 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12436.037 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12438.037 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12439.037 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12444.537 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12450.037 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 12454.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 12455.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 12456.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 12457.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 13 | 86666.6667 | ACTION | 12469.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 13 | 86666.6667 | ACTION | 12470.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12475.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12476.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12487.3076 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12495.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12496.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 1 | 6666.6667 | ACTION | 12496.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 1 | 6666.6667 | ACTION | 12497.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12501.8076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 401.5508 | 2677005.2381 | ACTION | 12501.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12509.8076 | MooredSubInstallation
| Towing Group 2 | Delay | 17 | 113333.3333 | ACTION | 12513.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 12 | 80000 | ACTION | 12513.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 17 | 113333.3333 | ACTION | 12514.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 5 | 33333.3333 | ACTION | 12518.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 5 | 33333.3333 | ACTION | 12519.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12519.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12521.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12525.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 12527.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12531.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12543.8076 | MooredSubInstallation
| Towing Group 1 | Delay | 63 | 420000 | ACTION | 12582.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 41 | 0 | ACTION | 12584.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12588.3076 | MooredSubInstallation
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 12590.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 12591.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12591.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12595.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 160 | 800000 | ACTION | 12610.037 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12611.037 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12619.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 12621.9832 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12622.9832 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12628.4832 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12633.9832 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12635.9832 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12636.9832 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12642.4832 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 12644.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 12646.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12652.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 11 | 55000 | ACTION | 12653.4832 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12655.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12658.9832 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12659.9832 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 12670.9294 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12671.9294 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12672.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12677.4294 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 12678.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12682.9294 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12684.9294 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12685.9294 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12691.3076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 100.5508 | 670338.5714 | ACTION | 12691.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12691.4294 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12696.9294 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12697.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12697.9294 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12699.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 12708.8756 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12709.8756 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12711.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12715.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12715.3756 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12719.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12720.8756 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12722.8756 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12723.8756 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12729.3756 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12731.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12734.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12734.8756 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12735.8756 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9 | 45000 | ACTION | 12744.8756 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 12750.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 105 | 700000 | ACTION | 12802.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 70 | 0 | ACTION | 12804.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12808.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12811.8076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12823.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12835.8076 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 12864.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 12866.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12872.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 131 | 655000 | ACTION | 12875.8756 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.9462 | 9731.0783 | ACTION | 12877.8218 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12878.8218 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12884.3218 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12889.8218 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12891.8218 | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12892.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12892.8218 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 12898.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12898.3218 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12903.8218 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12904.8218 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12907.8076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 316.5508 | 2110338.5714 | ACTION | 12907.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12913.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 12915.7681 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12915.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12916.7681 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12922.2681 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12927.7681 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12927.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12929.7681 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12930.7681 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12931.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12935.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12936.2681 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12941.7681 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12942.7681 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12947.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12951.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 12953.7143 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12954.7143 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12954.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12958.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12960.2143 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12965.7143 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12967.7143 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12968.7143 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 12970.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12974.2143 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 12975.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 12977.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12979.7143 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12980.7143 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12982.3076 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12983.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12991.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 12991.6605 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12992.6605 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12998.1605 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13003.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13003.6605 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13005.6605 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13006.6605 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 13009.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13054.3076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 303.5508 | 2023671.9048 | ACTION | 13054.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13062.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13074.3076 | MooredSubInstallation
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 13081.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 49 | 326666.6667 | ACTION | 13103.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 29 | 0 | ACTION | 13103.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13107.3076 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13109.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 104 | 520000 | ACTION | 13110.6605 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13111.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13116.1605 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13121.6605 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13122.6605 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13123.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13126.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13130.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 13133.6067 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13133.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13134.6067 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13140.1067 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13145.6067 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13147.6067 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13148.6067 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13154.1067 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13157.8076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13159.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 9 | 45000 | ACTION | 13163.1067 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13168.6067 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13169.6067 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 13171.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 13173.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13179.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 13180.5529 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13181.5529 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13187.0529 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13192.5529 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13194.5529 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13195.5529 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13199.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13201.0529 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 13205.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13206.5529 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13207.5529 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 13218.4991 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13219.4991 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13224.9991 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13229.8076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 259.5508 | 1730338.5714 | ACTION | 13229.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13230.4991 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13232.4991 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13233.4991 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13235.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13237.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13238.9991 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13244.4991 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13245.4991 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13249.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13253.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 13256.4454 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13257.4454 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13257.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13262.9454 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 13277.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 50 | 0 | ACTION | 13307.8076 | MooredSubInstallation
| Towing Group 2 | Delay | 73 | 486666.6667 | ACTION | 13308.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13319.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13323.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13326.8076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13327.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13330.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 68 | 340000 | ACTION | 13330.9454 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13336.4454 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13338.4454 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13339.4454 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13354.3076 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 13370.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 13372.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13378.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 10 | 66666.6667 | ACTION | 13388.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13426.3076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 344.5508 | 2297005.2381 | ACTION | 13426.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 42 | 280000 | ACTION | 13430.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 5 | 33333.3333 | ACTION | 13431.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13434.3076 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13437.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 10 | 66666.6667 | ACTION | 13440.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13446.3076 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 13446.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13450.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13454.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13466.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13469.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13473.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13476.8076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13495.3076 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 13499.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13500.8076 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 13501.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13507.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 13518.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13527.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 188 | 940000 | ACTION | 13527.4454 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13532.9454 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 13533.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13538.4454 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13539.4454 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 13550.3916 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13551.3916 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13556.8916 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13562.3916 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13564.3916 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13565.3916 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13570.8916 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13572.8076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 295.5508 | 1970338.5714 | ACTION | 13572.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13576.3916 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13577.3916 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13578.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13580.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 13588.3378 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13592.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13596.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13600.8076 | MooredSubInstallation
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 13605.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 47 | 0 | ACTION | 13647.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13659.8076 | MooredSubInstallation
| Towing Group 1 | Delay | 82 | 546666.6667 | ACTION | 13660.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13663.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 13665.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13669.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13672.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 85 | 425000 | ACTION | 13673.3378 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13674.3378 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13676.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13679.8378 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13685.3378 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13687.3378 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13688.3378 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13693.8378 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13699.3378 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13700.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13700.3378 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 13711.284 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13712.284 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13717.784 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 13722.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13723.284 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 13724.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13725.284 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13726.284 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13730.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13731.784 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13737.284 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13738.284 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 13749.2302 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13750.2302 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13750.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13755.7302 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 13756.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13761.2302 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13763.2302 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13764.2302 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13769.7302 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13772.3076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 253.5508 | 1690338.5714 | ACTION | 13772.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13775.2302 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13776.2302 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13778.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13780.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 13787.1764 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13788.1764 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13792.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13793.6764 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13796.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13799.1764 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13800.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13801.1764 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13802.1764 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13807.6764 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13812.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13813.1764 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13814.1764 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13815.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13819.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13822.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 13825.1227 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13826.1227 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 13828.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13831.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13831.6227 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13837.1227 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13839.1227 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13840.1227 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 13840.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 13842.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13845.6227 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13846.8076 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13848.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13851.1227 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13852.1227 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 13863.0689 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13864.0689 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13868.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13869.5689 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 13874.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13875.0689 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13877.0689 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13878.0689 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13883.5689 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13889.0689 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13890.0689 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 13901.0151 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13902.0151 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13907.5151 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13913.0151 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13915.0151 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13916.0151 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13918.8076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 313.5508 | 2090338.5714 | ACTION | 13918.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13921.5151 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13924.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13926.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13927.0151 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13928.0151 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13938.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 13938.9613 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13939.9613 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13942.8076 | MooredSubInstallation
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 13946.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13946.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13958.8076 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 13986.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13999.3076 | MooredSubInstallation
| Towing Group 3 | Delay | 26 | 173333.3333 | ACTION | 14012.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 14014.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14020.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 68 | 0 | ACTION | 14026.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 88 | 440000 | ACTION | 14027.9613 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14030.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14033.4613 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14033.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14037.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14038.9613 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14040.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14040.9613 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14041.9613 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 14046.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14047.4613 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14052.9613 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14053.9613 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14061.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 14064.9075 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14065.9075 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14071.4075 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14076.9075 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14078.9075 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14079.9075 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14085.4075 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14090.9075 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14091.9075 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 14102.8537 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14103.8537 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14109.3537 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14114.8537 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14116.8537 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14117.8537 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 14118.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14123.3537 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14128.8537 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14129.8537 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14133.3076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 304.5508 | 2030338.5714 | ACTION | 14133.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14139.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 14140.7999 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14141.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14141.7999 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14147.2999 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14152.7999 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14153.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14154.7999 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14155.7999 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14157.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14161.2999 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14161.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14166.7999 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14167.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14167.7999 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14173.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14176.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 14178.7462 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14179.7462 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14180.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14183.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14185.2462 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14190.7462 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14192.7462 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14193.7462 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14199.2462 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 14201.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 14203.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14204.7462 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14205.7462 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14207.8076 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14209.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 14216.6924 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14217.6924 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14229.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 4 | 26666.6667 | ACTION | 14233.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 1 | 6666.6667 | ACTION | 14234.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 1 | 6666.6667 | ACTION | 14235.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 6 | 40000 | ACTION | 14241.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 1 | 6666.6667 | ACTION | 14242.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14279.8076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 333.5508 | 2223671.9048 | ACTION | 14279.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14285.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14287.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14299.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14303.8076 | MooredSubInstallation
| Towing Group 2 | Delay | 20 | 133333.3333 | ACTION | 14305.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14307.8076 | MooredSubInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 14314.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14319.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14323.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14326.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14330.3076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14335.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14354.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 145 | 725000 | ACTION | 14362.6924 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 14367.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14368.1924 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 14369.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14373.6924 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14375.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14375.6924 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14376.6924 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14382.1924 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14387.6924 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14388.6924 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14395.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 14399.6386 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14400.6386 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 14401.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14406.1386 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14411.6386 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14413.6386 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14414.6386 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14420.1386 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14425.6386 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14426.3076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 307.5508 | 2050338.5714 | ACTION | 14426.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14426.6386 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14432.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14434.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14446.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14450.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14454.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 36.6512 | 183255.8368 | ACTION | 14463.2898 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14464.2898 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14466.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14469.7898 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14469.8076 | MooredSubInstallation
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 14473.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14475.2898 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 12 | 60000 | ACTION | 14487.2898 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 14494.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 14496.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 14 | 70000 | ACTION | 14501.2898 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14502.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14503.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Transit | 5 | 25000 | ACTION | 14506.2898 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 40 | 0 | ACTION | 14509.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 7 | 35000 | ACTION | 14513.2898 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14513.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14516.8076 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14522.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 14528.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Transit | 20.6312 | 103156.087 | ACTION | 14533.921 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14540.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Transit | 37.6312 | 188156.087 | ACTION | 14571.5522 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 14577.5522 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 18 | 90000 | ACTION | 14595.5522 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 14600.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 17 | 85000 | ACTION | 14612.5522 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14612.8076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 298.5508 | 1990338.5714 | ACTION | 14612.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14618.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Transit | 8 | 40000 | ACTION | 14620.5522 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14620.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 5 | 25000 | ACTION | 14625.5522 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14632.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14636.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Transit | 11.6312 | 58156.087 | ACTION | 14637.1834 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14639.1834 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14640.1834 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14640.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14645.6834 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14651.1834 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14652.1834 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14652.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14656.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14659.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14663.3076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14671.3076 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 14680.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 14682.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14687.3076 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14688.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 36.6512 | 183255.8368 | ACTION | 14688.8346 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14689.8346 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14695.3346 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14700.8346 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14702.8346 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14703.8346 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14708.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14709.3346 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 14714.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14714.8346 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14715.8346 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 14726.7808 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14727.7808 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14733.2808 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14738.7808 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14740.7808 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14741.7808 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14747.2808 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14752.7808 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14753.7808 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14759.3076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 285.5508 | 1903671.9048 | ACTION | 14759.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 14764.727 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14765.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14765.727 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14767.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14771.227 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14776.727 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14778.727 | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14779.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14779.727 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14783.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14785.227 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 14786.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14787.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14790.727 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14791.727 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14799.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 14802.6732 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14802.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14803.6732 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14806.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14809.1732 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14809.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14814.6732 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14816.6732 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14817.6732 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14823.1732 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 14827.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14828.6732 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 14829.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14829.6732 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14833.8076 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14835.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14839.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 14840.6194 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14841.6194 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 3 | 15000 | ACTION | 14844.6194 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14850.1194 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14855.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14855.6194 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Check Mooring Lines | 2 | 13333.3333 | ACTION | 14857.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 1 | 6666.6667 | ACTION | 14858.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 6 | 30000 | ACTION | 14861.6194 | ArrayCableInstallation
| Towing Group 2 | Check Mooring Lines | 4 | 26666.6667 | ACTION | 14862.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14863.6194 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14864.6194 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14870.1194 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14875.6194 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14876.6194 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 6 | 30000 | ACTION | 14882.6194 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 6 | 30000 | ACTION | 14888.6194 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 10000 | ACTION | 14890.6194 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 3 | 15000 | ACTION | 14893.6194 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 10000 | ACTION | 14895.6194 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14905.8076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 305.5508 | 2037005.2381 | ACTION | 14905.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14911.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14913.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14925.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14929.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14933.8076 | MooredSubInstallation
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 14934.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 33 | 220000 | ACTION | 14944.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14945.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14949.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14952.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14956.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 73 | 365000 | ACTION | 14968.6194 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 0.94622 | 4731.0783 | ACTION | 14969.5657 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14970.5657 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14976.0657 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14980.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14981.5657 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14983.5657 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14984.5657 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14990.0657 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 15006.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15007.3076 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 15008.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15014.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 28 | 140000 | ACTION | 15018.0657 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15023.5657 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15024.5657 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 15034.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 15035.5119 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15036.5119 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 15040.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15042.0119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15047.5119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15049.5119 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15050.5119 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15052.3076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 265.5508 | 1770338.5714 | ACTION | 15052.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15056.0119 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15058.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15060.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15061.5119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15062.5119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 8 | 40000 | ACTION | 15070.5119 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15072.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 15078.3076 | MooredSubInstallation
| Towing Group 1 | Delay | 23 | 153333.3333 | ACTION | 15081.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15082.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15086.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15098.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15101.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15105.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15108.8076 | MooredSubInstallation
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 15112.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 44 | 220000 | ACTION | 15114.5119 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 2.9462 | 14731.0783 | ACTION | 15117.4581 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15118.4581 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15123.9581 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15129.4581 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15131.4581 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15132.4581 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15132.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15137.9581 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 15143.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15143.4581 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15144.4581 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 15145.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15151.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 15155.4043 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15156.4043 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 15171.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 18 | 90000 | ACTION | 15174.4043 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15175.3076 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 15177.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15179.9043 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15185.4043 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15187.4043 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15188.4043 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15193.9043 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15199.4043 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15200.4043 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15204.8076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 270.5508 | 1803671.9048 | ACTION | 15204.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15210.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 15211.3505 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15212.3505 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15212.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15217.8505 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15223.3505 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15224.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15225.3505 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15226.3505 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15228.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15231.8505 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15232.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15237.3505 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15238.3505 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15244.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 8 | 40000 | ACTION | 15246.3505 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15248.3076 | MooredSubInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 15249.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 3 | 15000 | ACTION | 15249.3505 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15251.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 2.9462 | 14731.0783 | ACTION | 15252.2967 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15253.2967 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15255.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15258.7967 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15264.2967 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15266.2967 | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 15272.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 15274.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15279.3076 | MooredSubInstallation
| Towing Group 2 | Delay | 46 | 306666.6667 | ACTION | 15320.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15326.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 64 | 320000 | ACTION | 15330.2967 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15331.2967 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15336.7967 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15342.2967 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15343.2967 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15343.3076 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 15346.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15351.3076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 238.5508 | 1590338.5714 | ACTION | 15351.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 15352.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 15354.243 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15355.243 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15357.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15359.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15371.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15375.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15379.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 35 | 175000 | ACTION | 15390.243 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15391.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15394.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15395.743 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15398.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15401.243 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15401.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15403.243 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15404.243 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15409.743 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15415.243 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15416.243 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 15419.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 15421.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 15424.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15425.8076 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15427.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 15427.1892 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15428.1892 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15433.6892 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15439.1892 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15441.1892 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15442.1892 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 15447.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15447.6892 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 15453.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15453.1892 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15454.1892 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 15465.1354 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15466.1354 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15471.6354 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15477.1354 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15479.1354 | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15497.8076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 248.5508 | 1657005.2381 | ACTION | 15497.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15503.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15505.8076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15511.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15517.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15521.8076 | MooredSubInstallation
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 15525.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15525.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 49 | 245000 | ACTION | 15528.1354 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15529.1354 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15534.6354 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15537.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15540.1354 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15541.1354 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15541.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15544.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15548.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 15552.0816 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15553.0816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15558.5816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15564.0816 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 15565.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15566.0816 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15567.0816 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 15567.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15572.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15572.5816 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15573.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 40000 | ACTION | 15579.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 34 | 0 | ACTION | 15606.3076 | MooredSubInstallation
| Towing Group 1 | Delay | 58 | 386666.6667 | ACTION | 15637.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 93333.3333 | ACTION | 15651.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 16 | 106666.6667 | ACTION | 15667.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 15673.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15678.3076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 253.5508 | 1690338.5714 | ACTION | 15678.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15679.3076 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15684.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15686.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15698.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15702.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15706.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 134 | 670000 | ACTION | 15706.5816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15712.0816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15713.0816 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15718.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15721.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 15724.0278 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15725.0278 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15725.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15728.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15730.5278 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15736.0278 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15738.0278 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15739.0278 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15744.5278 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 15745.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 15746.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 15748.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15750.0278 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15751.0278 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15752.8076 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15754.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 7 | 35000 | ACTION | 15758.0278 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 15774.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 15780.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 29 | 145000 | ACTION | 15787.0278 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 3.9462 | 19731.0783 | ACTION | 15790.974 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15791.974 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15797.474 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15802.974 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15804.974 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15805.974 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15824.8076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 299.5508 | 1997005.2381 | ACTION | 15824.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 8 | 53333.3333 | ACTION | 15832.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15832.8076 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15838.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15844.8076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15847.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15848.8076 | MooredSubInstallation
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 15852.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15852.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15864.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15868.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15871.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15875.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15899.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 21 | 0 | ACTION | 15920.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15992.3076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 246.5508 | 1643671.9048 | ACTION | 15992.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16000.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16012.3076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16015.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16016.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16020.3076 | MooredSubInstallation
| Towing Group 3 | Delay | 191 | 1273333.3333 | ACTION | 16029.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 38 | 253333.3333 | ACTION | 16030.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16032.3076 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 16036.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 16039.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16042.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 240 | 1200000 | ACTION | 16045.974 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16046.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16049.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16051.474 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16056.974 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 16057.974 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 16068.9202 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16069.9202 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16073.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16075.4202 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16080.9202 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 16082.9202 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16083.9202 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16089.4202 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 16091.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 16093.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16094.9202 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 16095.9202 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 16098.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 16099.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 16100.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 8 | 40000 | ACTION | 16103.9202 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 16106.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 93333.3333 | ACTION | 16113.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 53333.3333 | ACTION | 16114.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 9 | 60000 | ACTION | 16122.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 9 | 60000 | ACTION | 16123.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 40000 | ACTION | 16128.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 16134.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 80000 | ACTION | 16135.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 36 | 180000 | ACTION | 16139.9202 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 16141.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 2.9462 | 14731.0783 | ACTION | 16142.8665 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16143.8665 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16145.8076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 293.5508 | 1957005.2381 | ACTION | 16145.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16149.3665 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 16151.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16153.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16154.8665 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 16156.8665 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16157.8665 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16163.3665 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16165.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16169.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16173.8076 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16183.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16185.8076 | MooredSubInstallation
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 16206.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 23 | 0 | ACTION | 16208.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16212.3076 | MooredSubInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 16213.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16215.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16219.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16243.3076 | MooredSubInstallation
| Towing Group 2 | Delay | 106 | 706666.6667 | ACTION | 16257.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16315.3076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 108.5508 | 723671.9048 | ACTION | 16315.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 16319.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 16321.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 16321.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16323.3076 | MooredSubInstallation
| Towing Group 2 | Delay | 10 | 66666.6667 | ACTION | 16331.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 11 | 73333.3333 | ACTION | 16332.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16335.3076 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 16337.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16339.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16343.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 185 | 925000 | ACTION | 16348.3665 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16351.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16353.8665 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 16354.8665 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16355.3076 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 16357.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16358.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16362.3076 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 16363.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 16365.8127 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16366.8127 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 4 | 20000 | ACTION | 16370.8127 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 16374.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16376.3127 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16377.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16381.8127 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 16383.8127 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16384.8127 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16390.3127 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 16394.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16395.8127 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 16396.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 16396.8127 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16401.8076 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 16402.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 16407.7589 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16408.7589 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16414.2589 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16419.7589 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 16421.7589 | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 16422.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16422.7589 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 16428.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16428.2589 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16433.7589 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 16434.7589 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 16435.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 16445.7051 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16446.7051 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16452.2051 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16473.8076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 260.5508 | 1737005.2381 | ACTION | 16473.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 16479.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16481.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 33 | 165000 | ACTION | 16485.2051 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16490.7051 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 16492.7051 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16493.7051 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16493.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16497.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16499.2051 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 16500.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16501.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16504.7051 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 16505.7051 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16513.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.9462 | 54731.0783 | ACTION | 16516.6513 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16517.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16517.6513 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16519.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16520.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16523.1513 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16524.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16528.6513 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 16530.6513 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16531.6513 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16537.1513 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 16541.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 16543.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16548.3076 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 16549.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 19 | 95000 | ACTION | 16556.1513 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16561.6513 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 16562.6513 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 16569.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 16575.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 31.1609 | 155804.7007 | ACTION | 16593.8123 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16594.8123 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16600.3123 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16605.8123 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16620.3076 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 184.5508 | 1230338.5714 | ACTION | 16620.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 16626.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16628.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16640.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Transit | 36 | 180000 | ACTION | 16641.8123 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16644.3076 | MooredSubInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 16647.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16648.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 8 | 40000 | ACTION | 16649.8123 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 1.6312 | 8156.087 | ACTION | 16651.4435 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 16657.4435 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16660.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16663.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16667.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16670.8076 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 16688.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 16690.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16694.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Transit | 37.6312 | 188156.087 | ACTION | 16695.0747 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 16696.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 16697.0747 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16698.0747 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16703.5747 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 16716.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 16722.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 32 | 160000 | ACTION | 16735.5747 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16741.0747 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 16742.0747 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16766.8076 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 266.5508 | 1777005.2381 | ACTION | 16766.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 16772.8076 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 31.1609 | 155804.7007 | ACTION | 16773.2356 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16774.2356 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16774.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16779.7356 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16785.2356 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16786.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 16787.2356 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16788.2356 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16790.8076 | MooredSubInstallation
| Towing Group 2 | Transit | 72.1265 | 480843.3333 | ACTION | 16794.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16794.8076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16806.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 22 | 110000 | ACTION | 16810.2356 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16810.3076 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16813.8076 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16815.7356 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16817.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16821.2356 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 16822.2356 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 16834.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 16836.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16841.3076 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 20 | 100000 | ACTION | 16842.2356 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 16842.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 16862.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 22 | 110000 | ACTION | 16864.2356 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 16868.6304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.7305 | 28652.6168 | ACTION | 16869.9662 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16870.9662 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16876.4662 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16881.9662 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 16883.9662 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16884.9662 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16890.4662 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16895.9662 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16913.3076 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 265.5508 | 1770338.5714 | ACTION | 16913.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 16919.3076 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 72.1265 | 480843.3333 | ACTION | 16940.7569 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 54 | 270000 | ACTION | 16949.9662 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 16950.9662 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 25.7305 | 128652.6168 | ACTION | 16976.6967 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16977.6967 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 61.8227 | 412151.4286 | ACTION | 16981.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 16983.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16983.1967 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16988.6967 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 16989.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 16990.6967 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16991.6967 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16997.1967 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 17002.6967 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 17003.6967 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 17009.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 7 | 35000 | ACTION | 17010.6967 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Check Mooring Lines | 5 | 33333.3333 | ACTION | 17014.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 29 | 193333.3333 | ACTION | 17043.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 1 | 6666.6667 | ACTION | 17044.1304 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 48 | 240000 | ACTION | 17058.6967 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 13.4247 | 67123.3856 | ACTION | 17072.1214 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 17073.1214 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 17078.6214 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 17084.1214 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 17086.1214 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 17087.1214 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 72.1265 | 480843.3333 | ACTION | 17116.2569 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 131 | 655000 | ACTION | 17218.1214 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 17223.6214 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 17229.1214 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 17230.1214 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 20.4247 | 102123.3856 | ACTION | 17250.546 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 17251.546 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 17257.046 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 17262.546 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 17264.546 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 17265.546 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 17271.046 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 17276.546 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 17277.546 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 15.4418 | 77208.7962 | ACTION | 17292.9878 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 17293.9878 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 17299.4878 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 17304.9878 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 17306.9878 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 17307.9878 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 17313.4878 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 17318.9878 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 17319.9878 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 15.4418 | 77208.7962 | ACTION | 17335.4296 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 17336.4296 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 17341.9296 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 17347.4296 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 17349.4296 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 17350.4296 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 17355.9296 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 17361.4296 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 17362.4296 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | ACTION | 17365.4296 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 107 | 535000 | ACTION | 17472.4296 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 8.6072 | 43036.03 | ACTION | 17481.0368 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 17482.0368 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 17487.5368 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 17493.0368 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 17495.0368 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 17496.0368 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 17501.5368 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 17507.0368 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 17508.0368 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | ACTION | 17511.0368 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 53 | 265000 | ACTION | 17564.0368 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 8.6072 | 43036.03 | ACTION | 17572.644 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 17573.644 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 17579.144 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 17584.644 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 37.6312 | 188156.087 | ACTION | 17622.2752 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 2 | 10000 | ACTION | 17624.2752 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 65 | 325000 | ACTION | 17689.2752 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 35.6312 | 178156.087 | ACTION | 17724.9064 | ArrayCableInstallation |  | ArrayCableInstallation