## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | location | phase_name | max_waveheight | max_windspeed | transit_speed | num_vessels | num_ahts_vessels
0.5 | Export Cable Installation Vessel | Mobilize | 72 | 180000 | ACTION | 0 | ExportCableInstallation
| Onshore Construction | Onshore Construction | 0 | 1665604.3526 | ACTION | 0 | ExportCableInstallation | Landfall
1 | Mooring System Installation Vessel | Mobilize | 168 | 700000 | ACTION | 0 | MooringSystemInstallation
| Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 6 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 7 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 17 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 21.3349 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 23.3349 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 27.3349 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 43.4949 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 47.6549 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 49.6549 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 53.6549 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 69.8149 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 73.9749 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 75.9749 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 79.9749 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 96.1349 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 100.2949 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 102.2949 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 106.2949 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 107 | 535000 | ACTION | 113 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Tow Plow | 0.4 | 2000 | ACTION | 113.4 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Pull Winch | 0.4 | 2000 | ACTION | 113.8 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 114.8 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 120.3 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 122.4549 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 125.8 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 126.6149 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 126.8 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 128.6149 | MooringSystemInstallation
| Substation Assembly Line 1 | Substation Substructure Assembly | 0 | 0 | ACTION | 130.5654 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 132.6149 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 148.7749 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 24 | 120000 | ACTION | 150.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 152.9349 | MooringSystemInstallation |  | MooringSystemInstallation
| Substation Assembly Line 1 | Attach Topside | 24 | 0 | ACTION | 154.5654 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay: Waiting on Completed Assembly | 24 | 100000 | ACTION | 154.5654 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 154.9349 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 22 | 91666.6667 | ACTION | 176.5654 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 22 | 91666.6667 | ACTION | 176.9349 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 180.9349 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Tow Substation to Site | 7.2248 | 30103.4722 | ACTION | 183.7902 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 185.7902 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 19 | 79166.6667 | ACTION | 199.9349 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 216.0949 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 220.2549 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 224.5898 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 39 | 162500 | ACTION | 224.7902 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 229.5898 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 230.7902 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 234.5898 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 234.7902 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 86 | 430000 | ACTION | 236.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 238.9247 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 240.9247 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 244.9247 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 9 | 45000 | ACTION | 245.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 249.9502 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 254.1102 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 30 | 125000 | ACTION | 274.9247 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 30 | 125000 | ACTION | 284.1102 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 45 | 225000 | ACTION | 290.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 291.0847 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 295.2447 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 297.2447 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 301.2447 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 306.1102 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 317.4047 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 318.1102 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 321.5647 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 322.1102 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 323.5647 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 327.5647 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 337.2702 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 341.4302 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 343.7247 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 347.8847 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 349.8847 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 353.8847 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 363.4302 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 370.0447 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 374.2047 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 375.4302 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 376.2047 | MooringSystemInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 379.4302 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 380.2047 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 394.5902 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 396.3647 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 398.7502 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 400.5247 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 402.5247 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 406.5247 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 123.6922 | 618460.7554 | ACTION | 414.4922 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 416.4922 | ExportCableInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 420.7502 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 421.9922 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 422.6847 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 426.8447 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 431.1796 | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 432.7502 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 436.1796 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 437.0851 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 441.1796 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 445.5145 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 24 | 100000 | ACTION | 469.5145 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 471.5145 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 1 | 4166.6667 | ACTION | 472.5145 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 476.5145 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 492.6745 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 496.8345 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 498.8345 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 502.8345 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 91 | 455000 | ACTION | 512.9922 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 518.4922 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 518.9945 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 522.2616 | ExportCableInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 523.1545 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 525.1545 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 529.1545 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 545.3145 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 549.4745 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 551.4745 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 555.4745 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 571.6345 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 575.7945 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 577.7945 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 581.7945 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 597.9545 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 602.1145 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 604.1145 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 608.1145 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 624.2745 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 628.4345 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 632.7694 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 26 | 108333.3333 | ACTION | 658.7694 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 663.7694 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 38 | 158333.3333 | ACTION | 701.7694 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 706.7694 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 711.1043 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 713.1043 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 717.1043 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 39 | 162500 | ACTION | 756.1043 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 772.2643 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 776.4243 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 778.4243 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 782.4243 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 798.5843 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 802.7443 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 804.7443 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 808.7443 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 824.9043 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 829.0643 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 831.0643 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 835.0643 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 851.2243 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 855.3843 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 857.3843 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 861.3843 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 24 | 100000 | ACTION | 885.3843 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 901.5443 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 905.7043 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 907.7043 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 911.7043 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 927.8643 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 932.0243 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 936.3592 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 941.3592 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 946.3592 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 950.6941 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 952.6941 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 956.6941 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 972.8541 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 977.0141 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 979.0141 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 983.0141 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 999.1741 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1003.3341 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1005.3341 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1009.3341 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1025.4941 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1029.6541 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1031.6541 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1035.6541 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1051.8141 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1055.9741 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1057.9741 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1061.9741 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1078.1341 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1082.2941 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1084.2941 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1088.2941 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1104.4541 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1108.6141 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1112.949 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1117.949 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1122.949 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1127.2839 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1129.2839 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1133.2839 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1149.4439 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1153.6039 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1155.6039 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1159.6039 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1175.7639 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1179.9239 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1181.9239 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1185.9239 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 6 | 25000 | ACTION | 1191.9239 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1208.0839 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1212.2439 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1214.2439 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1218.2439 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 42 | 175000 | ACTION | 1260.2439 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1276.4039 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1280.5639 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1282.5639 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1286.5639 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1302.7239 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1306.8839 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1308.8839 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1312.8839 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1329.0439 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1333.2039 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1337.5388 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1342.5388 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1347.5388 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1351.8737 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1353.8737 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1357.8737 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1374.0337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1378.1937 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1380.1937 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1384.1937 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1400.3537 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1404.5137 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1406.5137 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 18 | 75000 | ACTION | 1424.5137 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1428.5137 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1444.6737 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1448.8337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1450.8337 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1454.8337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 22 | 91666.6667 | ACTION | 1476.8337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1492.9937 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1497.1537 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1499.1537 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1503.1537 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 32 | 133333.3333 | ACTION | 1535.1537 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1551.3137 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 1572.3137 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1576.4737 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1578.4737 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1582.4737 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1598.6337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1602.7937 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1607.1286 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1612.1286 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1617.1286 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 1 | 4166.6667 | ACTION | 1618.1286 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 43 | 179166.6667 | ACTION | 1661.1286 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 3.3349 | 13895.4167 | ACTION | 1664.4635 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1666.4635 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1670.4635 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1686.6235 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1690.7835 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1692.7835 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1696.7835 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1712.9435 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1717.1035 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1719.1035 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1723.1035 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1739.2635 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1743.4235 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1745.4235 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1749.4235 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1765.5835 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1769.7435 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1771.7435 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1775.7435 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1791.9035 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1796.0635 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1798.0635 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1802.0635 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1818.2235 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1822.3835 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1826.7184 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1831.7184 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1836.7184 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1841.0533 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1843.0533 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1847.0533 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 12 | 50000 | ACTION | 1859.0533 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1875.2133 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1879.3733 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1881.3733 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 36 | 150000 | ACTION | 1917.3733 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1921.3733 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1937.5333 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1941.6933 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1943.6933 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1947.6933 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 17 | 70833.3333 | ACTION | 1964.6933 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1980.8533 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1985.0133 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1987.0133 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1991.0133 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2007.1733 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2011.3333 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2013.3333 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2017.3333 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2033.4933 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2037.6533 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2039.6533 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2043.6533 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2059.8133 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2063.9733 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2068.3082 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2073.3082 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2078.3082 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2082.6431 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2084.6431 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2088.6431 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2104.8031 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2108.9631 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2110.9631 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2114.9631 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 31 | 129166.6667 | ACTION | 2145.9631 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2162.1231 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2166.2831 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2168.2831 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2172.2831 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2188.4431 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2192.6031 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2194.6031 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2198.6031 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 26 | 108333.3333 | ACTION | 2224.6031 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2240.7631 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 2248.7631 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2252.9231 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2254.9231 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 2262.9231 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2266.9231 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2283.0831 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2287.2431 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2289.2431 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2293.2431 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2309.4031 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2313.5631 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2317.898 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2322.898 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2327.898 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2 | 8333.3333 | ACTION | 2329.898 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 9 | 37500 | ACTION | 2338.898 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2.3349 | 9728.75 | ACTION | 2341.2329 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2343.2329 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2347.2329 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 46 | 191666.6667 | ACTION | 2393.2329 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2409.3929 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2413.5529 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2415.5529 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2419.5529 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2435.7129 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2439.8729 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2441.8729 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2445.8729 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2462.0329 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2466.1929 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 40 | 166666.6667 | ACTION | 2506.1929 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2508.1929 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2512.1929 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2528.3529 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2532.5129 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2534.5129 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2538.5129 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2554.6729 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2558.8329 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2560.8329 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2564.8329 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 48 | 200000 | ACTION | 2612.8329 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2628.9929 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2633.1529 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2637.4878 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2642.4878 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2647.4878 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2651.8227 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2653.8227 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2657.8227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2673.9827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2678.1427 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2680.1427 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2684.1427 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2700.3027 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2704.4627 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2706.4627 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2710.4627 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2726.6227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2730.7827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2732.7827 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2736.7827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2752.9427 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2757.1027 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2759.1027 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2763.1027 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2779.2627 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2783.4227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2785.4227 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2789.4227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2805.5827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2809.7427 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2814.0776 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2819.0776 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2824.0776 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2828.4125 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2830.4125 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2834.4125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2850.5725 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2854.7325 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2856.7325 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2860.7325 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2876.8925 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2881.0525 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2883.0525 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2887.0525 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2903.2125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2907.3725 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2909.3725 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2913.3725 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2929.5325 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2933.6925 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2935.6925 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2939.6925 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2955.8525 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2960.0125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2962.0125 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2966.0125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2982.1725 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2986.3325 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2990.6674 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2995.6674 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3000.6674 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3005.0023 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3007.0023 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3011.0023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3027.1623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3031.3223 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3033.3223 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3037.3223 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3053.4823 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3057.6423 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3059.6423 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3063.6423 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3079.8023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3083.9623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3085.9623 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3089.9623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3106.1223 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3110.2823 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3112.2823 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3116.2823 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3132.4423 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3136.6023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3138.6023 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3142.6023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3158.7623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3162.9223 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3167.2572 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3172.2572 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3177.2572 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3181.5921 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3183.5921 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3187.5921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3203.7521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3207.9121 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3209.9121 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3213.9121 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3230.0721 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3234.2321 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3236.2321 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3240.2321 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3256.3921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3260.5521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3262.5521 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3266.5521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3282.7121 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3286.8721 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3288.8721 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3292.8721 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3309.0321 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3313.1921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3315.1921 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3319.1921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3335.3521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3339.5121 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2 | 8333.3333 | ACTION | 3341.5121 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 48 | 200000 | ACTION | 3389.5121 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2.3349 | 9728.75 | ACTION | 3391.847 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3396.847 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3401.847 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4 | 16666.6667 | ACTION | 3405.847 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 45 | 187500 | ACTION | 3450.847 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 0.3349 | 1395.4167 | ACTION | 3451.1819 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3453.1819 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3457.1819 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3473.3419 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3477.5019 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3479.5019 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3483.5019 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3499.6619 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3503.8219 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3505.8219 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3509.8219 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3525.9819 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3530.1419 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3532.1419 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3536.1419 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3552.3019 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3556.4619 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3558.4619 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3562.4619 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3578.6219 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3582.7819 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3584.7819 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3588.7819 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3604.9419 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3609.1019 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3613.4368 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3618.4368 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3623.4368 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 3 | 12500 | ACTION | 3626.4368 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3650.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 3650.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3658.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3670.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 3683.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3687.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 88 | 366666.6667 | ACTION | 3714.4368 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 1.3349 | 5562.0833 | ACTION | 3715.7717 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3717.7717 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3721.7717 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 26 | 108333.3333 | ACTION | 3747.7717 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3763.9317 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3768.0917 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3770.0917 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3774.0917 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 88 | 0 | ACTION | 3775.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3779.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3790.2517 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 3791.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3794.4117 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3796.4117 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 9 | 0 | ACTION | 3800.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3800.4117 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3803.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3807.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3810.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3816.5717 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3818.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3820.7317 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3822.7317 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3826.7317 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3834.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3842.8917 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3847.0517 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3849.0517 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3853.0517 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3869.2117 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3873.3717 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3875.3717 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3879.3717 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 61 | 0 | ACTION | 3895.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 30 | 125000 | ACTION | 3909.3717 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3925.5317 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3929.6917 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3934.0266 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3939.0266 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3944.0266 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3948.3615 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3950.3615 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3954.3615 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 3967.3615 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 3967.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 485.5 | 3236666.6667 | ACTION | 3967.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3975.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 9 | 60000 | ACTION | 3976.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 3982.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3983.5215 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3986.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3987.6815 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3987.8791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 3989.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3989.6815 | MooringSystemInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 3991.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3991.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3993.6815 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3995.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 3997.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4007.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4009.8415 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4011.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4014.0015 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4014.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4016.0015 | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 4017.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4018.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4020.0015 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 4023.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 4030.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4036.1615 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 4040.1615 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4042.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4044.3215 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4046.3215 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4050.3215 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4066.4815 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4070.6415 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4072.6415 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4076.6415 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4092.8015 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4096.9615 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4098.9615 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4102.9615 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4114.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 632 | 4213333.3333 | ACTION | 4114.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4119.1215 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4120.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4122.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4123.2815 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 4126.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4127.6164 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4132.6164 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4134.3791 | MooredSubInstallation
| Towing Group 2 | Delay | 10 | 66666.6667 | ACTION | 4136.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 4137.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4137.6164 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 4138.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4141.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4141.9513 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4143.9513 | MooringSystemInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4144.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4145.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4147.9513 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 40000 | ACTION | 4150.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4154.3791 | MooredSubInstallation
| Towing Group 2 | Delay | 10 | 66666.6667 | ACTION | 4160.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 4161.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4164.1113 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4168.2713 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4170.2713 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4173.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4174.2713 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 93333.3333 | ACTION | 4174.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4176.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4180.3791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 4180.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4183.8791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 4187.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4190.4313 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4194.5913 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4196.5913 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4200.5913 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4207.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4216.7513 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4220.9113 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4222.9113 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4226.9113 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4243.0713 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4247.2313 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4249.2313 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4253.2313 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4269.3913 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4273.5513 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4275.5513 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4279.5513 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4279.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 797.5 | 5316666.6667 | ACTION | 4279.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4285.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4287.8791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 4292.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 4294.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4295.7113 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4299.8713 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4299.8791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4300.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4303.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4304.2062 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4307.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4309.2062 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4314.2062 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4318.5411 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4319.8791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 4320.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4320.5411 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4322.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4323.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4324.5411 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 4326.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4326.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4330.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 4333.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4340.7011 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4344.8611 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4346.8611 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4350.8611 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4354.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4367.0211 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4371.1811 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4373.1811 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4377.1811 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4393.3411 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4397.5011 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4399.5011 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4403.5011 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4419.6611 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4423.8211 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4425.8211 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4426.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 396.0825 | 2640549.6825 | ACTION | 4426.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4429.8211 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4432.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4434.3791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 4438.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 4440.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4445.9811 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4446.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4450.1411 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4452.1411 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4456.1411 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4472.3011 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4476.4611 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 33 | 0 | ACTION | 4479.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4480.796 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4483.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4485.796 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4490.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4490.796 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4495.1309 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4497.1309 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4501.1309 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Delay | 61 | 406666.6667 | ACTION | 4501.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 19 | 0 | ACTION | 4502.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4506.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4507.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4517.2909 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4521.4509 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4523.4509 | MooringSystemInstallation
| Towing Group 1 | Delay | 19 | 126666.6667 | ACTION | 4526.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4527.4509 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 13333.3333 | ACTION | 4528.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 4 | 26666.6667 | ACTION | 4532.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 20000 | ACTION | 4535.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 2 | 13333.3333 | ACTION | 4537.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 32 | 0 | ACTION | 4538.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4543.6109 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4547.7709 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4549.7709 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4550.3791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 100000 | ACTION | 4552.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4553.7709 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 4558.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 4565.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4569.9309 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4574.0909 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4576.0909 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4580.0909 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4596.2509 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4600.4109 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4602.4109 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4606.4109 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4622.5709 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4626.7309 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4628.7309 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4632.7309 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 87 | 0 | ACTION | 4637.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4640.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4644.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4647.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4648.8909 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4653.0509 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4657.3858 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4658.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4662.3858 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4667.3858 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4671.7207 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4671.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4673.7207 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4677.7207 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4693.8807 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4698.0407 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4700.0407 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4704.0407 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4720.2007 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4724.3607 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4726.3607 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4730.3607 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4743.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 556.0825 | 3707216.3492 | ACTION | 4743.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4746.5207 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4749.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4750.6807 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4751.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4752.6807 | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 4756.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4756.6807 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 4758.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4763.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4764.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4767.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4771.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4772.8407 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4777.0007 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 93333.3333 | ACTION | 4778.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4779.0007 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 4782.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4783.0007 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Delay | 5 | 33333.3333 | ACTION | 4783.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 40000 | ACTION | 4789.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4794.8791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 4795.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4799.1607 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 4802.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4803.3207 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4805.3207 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 4808.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4809.3207 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4812.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4815.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4819.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4825.4807 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4826.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4829.6407 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4833.9756 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4838.9756 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4843.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4843.9756 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4848.3105 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4850.3105 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4854.3105 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4870.4705 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4874.6305 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4876.6305 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4880.6305 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4896.7905 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4900.9505 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4902.9505 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4906.9505 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4915.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 582.0825 | 3880549.6825 | ACTION | 4915.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4921.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4923.1105 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4923.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4927.2705 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 4927.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4929.2705 | MooringSystemInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 4929.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4933.2705 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4935.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4935.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4939.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4943.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4949.4305 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4953.5905 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4955.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 4955.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4955.5905 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4958.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4959.5905 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 4961.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4962.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4965.8791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 4968.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4975.7505 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4979.9105 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4981.9105 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4985.9105 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4989.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4994.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5002.0705 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5006.2305 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5010.5654 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5015.5654 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5020.5654 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5024.9003 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5026.9003 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5030.9003 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5047.0603 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5051.2203 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5053.2203 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5057.2203 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5061.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 496.0825 | 3307216.3492 | ACTION | 5061.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5067.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5069.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5073.3803 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 5074.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 5076.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5077.5403 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5079.5403 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5081.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5082.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5083.5403 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5085.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5089.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5099.7003 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5101.8791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5102.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5103.8603 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5105.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5105.8603 | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 5108.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5108.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5109.8603 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 5115.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 5120.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5124.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5126.0203 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5130.1803 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5132.1803 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5136.1803 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5148.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5152.3403 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5156.5003 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5158.5003 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5162.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5162.5003 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5178.6603 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5182.8203 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5187.1552 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5192.1552 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5197.1552 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5201.4901 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5203.4901 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5207.4901 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5220.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 418.0825 | 2787216.3492 | ACTION | 5220.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5223.6501 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5226.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5227.8101 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5228.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5229.8101 | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 5232.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5233.8101 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 5234.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5240.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5240.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5244.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5248.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5249.9701 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5254.1301 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5256.1301 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5260.1301 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5260.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5260.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5263.8791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 5266.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5267.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5270.8791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 5273.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5276.2901 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5280.4501 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5282.4501 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5286.4501 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5294.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5302.6101 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5306.7701 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5308.7701 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5312.7701 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5328.9301 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5330.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5333.0901 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5335.0901 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5339.0901 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5355.2501 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5359.4101 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5363.745 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5366.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 398.0825 | 2653883.0159 | ACTION | 5366.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5368.745 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5372.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5373.745 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5374.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5378.0799 | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 5379.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5380.0799 | MooringSystemInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 5381.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5384.0799 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5386.8791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5387.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5390.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5394.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5400.2399 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5404.3999 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5406.3999 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5406.8791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5407.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5410.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5410.3999 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 5413.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5413.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5417.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 5420.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5426.5599 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5430.7199 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5432.7199 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5436.7199 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5441.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5452.8799 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5457.0399 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5459.0399 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5463.0399 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5479.1999 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5483.3599 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5485.3599 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5489.3599 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5498.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5505.5199 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5509.6799 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5511.6799 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5513.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 398.0825 | 2653883.0159 | ACTION | 5513.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5515.6799 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5519.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5521.3791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 5525.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 5527.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5531.8399 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5533.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5533.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5535.9999 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5537.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5540.3348 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5541.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5545.3348 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5550.3348 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5553.3791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5553.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5554.6697 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5556.6697 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5556.8791 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 5559.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5560.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5560.6697 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5563.8791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 5566.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5576.8297 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5580.9897 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5582.9897 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5586.9897 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5587.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5603.1497 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5607.3097 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5609.3097 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5613.3097 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5629.4697 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5633.6297 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5635.6297 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5639.6297 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5655.7897 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5659.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 386.0825 | 2573883.0159 | ACTION | 5659.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5659.9497 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5661.9497 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5665.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5665.9497 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5666.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5667.8791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 5672.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 5674.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5679.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5680.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5682.1097 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5683.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5686.2697 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5687.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5688.2697 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5692.2697 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5699.8791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5700.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5703.3791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 5706.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5706.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5708.4297 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5710.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5712.5897 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 5713.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5716.9246 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5721.9246 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5726.9246 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5731.2595 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5733.2595 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5734.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5737.2595 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5753.4195 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5757.5795 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5759.5795 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5763.5795 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5779.7395 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5783.8995 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5785.8995 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 55 | 0 | ACTION | 5789.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5789.8995 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5806.0595 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5810.2195 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5812.2195 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5816.2195 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5832.3795 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5834.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5836.5395 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5838.5395 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5842.5395 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5858.6995 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5861.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 441.0825 | 2940549.6825 | ACTION | 5861.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5862.8595 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5864.8595 | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5867.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5868.8595 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5869.3791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 5873.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 5875.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5881.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5881.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5885.0195 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5885.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5889.1795 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5889.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5893.5144 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5898.5144 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5901.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5901.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5903.5144 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5904.8791 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 5907.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5907.8493 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5909.8493 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 5910.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5913.8493 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5914.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 5914.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5917.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5930.0093 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5934.1693 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5936.1693 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5940.1693 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5941.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5956.3293 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5960.4893 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5962.4893 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5966.4893 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5982.6493 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5986.8093 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5988.8093 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5992.8093 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6002.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6008.9693 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6013.1293 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6013.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 447.0825 | 2980549.6825 | ACTION | 6013.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6015.1293 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6019.1293 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6019.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6021.8791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 6026.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 6028.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6033.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6034.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6035.2893 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6037.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6039.4493 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6041.4493 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6041.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6045.4493 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6053.8791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6054.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6057.3791 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 6060.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6060.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6061.6093 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6064.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6065.7693 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 6067.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6070.1042 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6075.1042 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6080.1042 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6084.4391 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6086.4391 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6088.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6090.4391 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6106.5991 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6110.7591 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6112.7591 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6116.7591 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6132.9191 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6137.0791 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6139.0791 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6143.0791 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6159.2391 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6160.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 447.0825 | 2980549.6825 | ACTION | 6160.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6163.3991 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6165.3991 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6166.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6168.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6169.3991 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6170.3791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 6172.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 6174.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6180.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6180.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6184.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6185.5591 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6188.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6189.7191 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6191.7191 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6195.7191 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6200.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6200.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6203.8791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 6206.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6207.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6210.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6211.8791 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 6213.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6216.0391 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6218.0391 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6222.0391 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6234.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6238.1991 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6242.3591 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6246.694 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6251.694 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6256.694 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6261.0289 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6263.0289 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6267.0289 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6283.1889 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6287.3489 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6289.3489 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6293.3489 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6306.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 392.0825 | 2613883.0159 | ACTION | 6306.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6309.5089 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6312.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6313.6689 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6314.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6315.6689 | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 6319.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6319.6689 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 6321.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6326.8791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6327.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6330.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6334.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6335.8289 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6338.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6339.9889 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6341.9889 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6345.9889 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6346.8791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6347.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6350.3791 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 6353.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6353.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6357.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 6360.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6362.1489 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6366.3089 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6368.3089 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6372.3089 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6381.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 19 | 79166.6667 | ACTION | 6391.3089 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6407.4689 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6411.6289 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6413.6289 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6417.6289 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6433.7889 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6437.9489 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6442.2838 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6447.2838 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6452.2838 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6453.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 386.0825 | 2573883.0159 | ACTION | 6453.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6456.6187 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6458.6187 | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6459.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6461.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6462.6187 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 6465.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 6467.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6473.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6473.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6477.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6478.7787 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6481.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6482.9387 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6484.9387 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6488.9387 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6493.3791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6493.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6496.8791 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 6499.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6500.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6503.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6505.0987 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6506.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 6506.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6509.2587 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6511.2587 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6515.2587 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6527.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6531.4187 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6535.5787 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6537.5787 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6541.5787 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6557.7387 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6561.8987 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6563.8987 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6567.8987 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6584.0587 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6588.2187 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6590.2187 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6594.2187 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6599.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 386.0825 | 2573883.0159 | ACTION | 6599.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 3 | 20000 | ACTION | 6602.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6607.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6608.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6610.3787 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6614.5387 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 6615.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 6617.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6618.8736 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6619.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6623.8736 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 6627.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6628.8736 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Delay | 12 | 80000 | ACTION | 6629.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6631.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6633.2085 | MooringSystemInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6635.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6635.2085 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6635.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6639.2085 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 10 | 66666.6667 | ACTION | 6645.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 6650.8791 | MooredSubInstallation
| Towing Group 2 | Delay | 8 | 53333.3333 | ACTION | 6653.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6655.3685 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6659.5285 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6661.5285 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6662.8791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 10 | 66666.6667 | ACTION | 6663.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6665.5285 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 6669.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6674.3791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 6676.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 6678.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6681.6885 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6682.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6685.8485 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6685.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6687.8485 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6691.8485 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 21 | 0 | ACTION | 6706.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6708.0085 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6710.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6712.1685 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6714.1685 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6718.1685 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6734.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 38 | 158333.3333 | ACTION | 6756.1685 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6772.3285 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6776.4885 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6778.4885 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6782.4885 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6798.6485 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6802.8085 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6804.8085 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6806.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 446.0825 | 2973883.0159 | ACTION | 6806.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6808.8085 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6812.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6814.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6824.9685 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6826.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6829.1285 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Delay | 17 | 113333.3333 | ACTION | 6829.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6830.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6833.4634 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6834.3791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 6835.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 6837.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6838.4634 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6842.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6842.7983 | MooringSystemInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6843.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6844.7983 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6846.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6848.7983 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6849.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6853.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6856.8791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6863.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6864.9583 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6869.1183 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 6869.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6871.1183 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6875.1183 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 6876.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6880.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6891.2783 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6895.4383 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6897.4383 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6901.4383 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 43 | 179166.6667 | ACTION | 6944.4383 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6952.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 446.0825 | 2973883.0159 | ACTION | 6952.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6958.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6960.5983 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6960.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6964.7583 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 6965.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 6967.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6972.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6973.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6976.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6980.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6992.8791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6993.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6996.3791 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 6999.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6999.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7003.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 7006.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7010.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7027.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7099.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 423.0825 | 2820549.6825 | ACTION | 7099.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7107.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7119.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7123.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7127.3791 | MooredSubInstallation
| Towing Group 2 | Delay | 36 | 240000 | ACTION | 7135.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7139.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7141.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7142.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7146.3791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 7147.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 7149.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7149.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7155.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7173.8791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7175.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7178.3791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 7181.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 7188.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7245.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 369.0825 | 2460549.6825 | ACTION | 7245.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7253.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 18 | 120000 | ACTION | 7263.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7265.8791 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7269.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7269.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7273.8791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 7276.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 7278.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7284.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7285.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7289.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7292.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7296.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7304.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 7310.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 7317.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7320.3791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7346.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7392.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 386.0825 | 2573883.0159 | ACTION | 7392.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7400.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7412.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7416.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7420.3791 | MooredSubInstallation
| Towing Group 1 | Delay | 35 | 233333.3333 | ACTION | 7427.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7432.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7433.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7435.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7439.3791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 7439.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 7441.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7442.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7447.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7466.8791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7467.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 7473.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 7480.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7514.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7538.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 350.0825 | 2333883.0159 | ACTION | 7538.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7544.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7546.8791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 7551.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 7553.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7558.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7559.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7562.8791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 46666.6667 | ACTION | 7566.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7566.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7578.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7582.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 7588.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7591.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7595.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7619.3791 | MooredSubInstallation
| Towing Group 2 | Delay | 72 | 480000 | ACTION | 7638.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 86666.6667 | ACTION | 7651.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 7657.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 7664.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7682.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7691.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 374.0825 | 2493883.0159 | ACTION | 7691.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7697.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7699.3791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 7703.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 7705.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7711.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7711.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7715.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7719.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7731.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7731.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7734.8791 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 7737.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7738.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7741.8791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 7744.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7765.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7837.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 357.0825 | 2380549.6825 | ACTION | 7837.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7843.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 7850.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7850.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 12.5 | 0 | ACTION | 7850.3791 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 7852.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7858.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7858.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7870.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7874.3791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7878.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7878.3791 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 7884.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7890.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 7891.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 39 | 0 | ACTION | 7929.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7932.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7936.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7939.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7963.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8018.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8035.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 371.5825 | 2477216.3492 | ACTION | 8035.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8041.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8043.8791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 8048.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 8050.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8055.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8056.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8059.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8063.8791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 53333.3333 | ACTION | 8064.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8075.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 17 | 0 | ACTION | 8092.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8096.3791 | MooredSubInstallation
| Towing Group 2 | Delay | 35 | 233333.3333 | ACTION | 8099.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8099.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8103.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 80000 | ACTION | 8111.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 8117.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 8124.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8127.3791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8186.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8199.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 454.5825 | 3030549.6825 | ACTION | 8199.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8205.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8207.3791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 8211.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 8213.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8219.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8219.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8223.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8227.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8239.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 8239.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8242.8791 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 8245.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8246.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8249.8791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 8252.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8273.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8345.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 454.5825 | 3030549.6825 | ACTION | 8345.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8351.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8354.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 8.5 | 0 | ACTION | 8354.3791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 8358.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 8360.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8362.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8366.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8374.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8378.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8382.3791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 8386.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 8392.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8394.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8397.8791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 8399.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8401.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8404.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8428.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8500.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 376.5825 | 2510549.6825 | ACTION | 8500.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8522.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 8522.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8530.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8542.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8546.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8550.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8562.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8565.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8569.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8572.8791 | MooredSubInstallation
| Towing Group 2 | Delay | 76 | 506666.6667 | ACTION | 8576.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8582.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 8589.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 8591.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8596.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8597.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 40000 | ACTION | 8603.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8668.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 416.0825 | 2773883.0159 | ACTION | 8668.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8690.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 8690.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8698.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8710.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8714.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8718.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8730.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8733.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8737.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8740.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 8754.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8778.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 28 | 0 | ACTION | 8806.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8858.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8878.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 479.5825 | 3197216.3492 | ACTION | 8878.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8886.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8898.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8902.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8906.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8918.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8922.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8925.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 8931.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8935.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8959.3791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9026.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9031.3791 | MooredSubInstallation
| Towing Group 3 | Delay | 366 | 2440000 | ACTION | 9034.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 156 | 1040000 | ACTION | 9034.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 432 | 2880000 | ACTION | 9035.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9039.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9040.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9040.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 9047.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 9047.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 93333.3333 | ACTION | 9049.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 9049.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 9049.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9051.3791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 9055.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9055.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9055.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9055.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9059.3791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 9062.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9068.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9071.3791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 9074.4894 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9074.8791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9075.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9075.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 9076.4894 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 2 | 13333.3333 | ACTION | 9077.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 2 | 13333.3333 | ACTION | 9077.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 9078.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9082.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9085.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9109.8791 | MooredSubInstallation
| Towing Group 2 | Delay | 56 | 373333.3333 | ACTION | 9132.4894 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 56 | 373333.3333 | ACTION | 9133.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 56 | 373333.3333 | ACTION | 9133.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 4 | 26666.6667 | ACTION | 9137.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 4 | 26666.6667 | ACTION | 9137.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9138.4894 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 9144.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 9144.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9158.4894 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 9164.4894 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 9171.7142 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9181.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 37.5825 | 250549.6825 | ACTION | 9181.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9194.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 12.5 | 0 | ACTION | 9194.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9202.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9214.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9218.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9222.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9234.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9237.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9241.3791 | MooredSubInstallation
| Towing Group 3 | Delay | 63 | 420000 | ACTION | 9244.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9244.8791 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9250.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 9257.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 9259.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9265.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9268.8791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9285.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 9291.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 9298.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9340.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 196.5825 | 1310549.6825 | ACTION | 9340.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9346.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 9353.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 9355.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9361.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9362.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 9362.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9370.3791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 100000 | ACTION | 9376.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9382.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9386.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9390.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9402.3791 | MooredSubInstallation
| Towing Group 1 | Delay | 27 | 180000 | ACTION | 9403.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9405.8791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 33333.3333 | ACTION | 9408.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9409.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9412.8791 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 9414.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 9421.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9436.8791 | MooredSubInstallation
0.5 | Array Cable Installation Vessel | Mobilize | 72 | 180000 | ACTION | 9447.8379 | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 9453.8379 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9508.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 337.1649 | 2247766.0317 | ACTION | 9508.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 1 | 6666.6667 | ACTION | 9509.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9515.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 9522.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 9524.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9530.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9530.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 9530.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 20000 | ACTION | 9533.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9538.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9550.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9554.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9558.3791 | MooredSubInstallation
| Towing Group 2 | Delay | 29 | 193333.3333 | ACTION | 9562.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9570.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9573.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9577.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 113333.3333 | ACTION | 9579.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9580.8791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 9585.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 9592.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9604.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9676.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 378.5825 | 2523883.0159 | ACTION | 9676.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9698.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 9698.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9706.3791 | MooredSubInstallation
| Towing Group 3 | Delay | 39 | 260000 | ACTION | 9715.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9718.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9721.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9722.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9726.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 274 | 1370000 | ACTION | 9727.8379 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 9728.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 9730.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 9731.6074 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 9733.6074 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9734.6074 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9736.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9738.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9740.1074 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9741.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9745.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9745.6074 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 9746.6074 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9748.8791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9756.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 9756.5984 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9757.5984 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 9762.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9763.0984 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 9769.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9772.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 76 | 0 | ACTION | 9848.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9866.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 123 | 615000 | ACTION | 9886.0984 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9891.5984 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 9893.5984 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9894.5984 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9900.0984 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9905.5984 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 9906.5984 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | ACTION | 9910.5984 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9920.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 499.5825 | 3330549.6825 | ACTION | 9920.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9926.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9928.8791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 9933.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 9935.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9940.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9941.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9944.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9948.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 41 | 205000 | ACTION | 9951.5984 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 5.991 | 29954.8442 | ACTION | 9957.5893 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9958.5893 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9960.8791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9961.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9964.0893 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9964.3791 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 9967.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9967.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9969.5893 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9971.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 9971.5893 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9972.5893 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 9974.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9978.0893 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9983.5893 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 9984.5893 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 9994.5803 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9995.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9995.5803 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10001.0803 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 10 | 50000 | ACTION | 10011.0803 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10016.5803 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10018.5803 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10019.5803 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10025.0803 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10030.5803 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10031.5803 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10034.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 10041.5713 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10042.5713 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10048.0713 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10053.5713 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10055.5713 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10056.5713 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10062.0713 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10067.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 475.0825 | 3167216.3492 | ACTION | 10067.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10067.5713 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10068.5713 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10073.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10075.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 10078.5622 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10079.5622 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 10079.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 10081.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10085.0622 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10087.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10087.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10090.5622 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10091.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10092.5622 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10093.5622 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10095.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10099.0622 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10104.5622 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10105.5622 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10107.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10107.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10110.8791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 10113.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10114.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 10115.5532 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10116.5532 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10117.8791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 10120.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10122.0532 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10141.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 17 | 0 | ACTION | 10158.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 73 | 365000 | ACTION | 10195.0532 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10200.5532 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10202.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10202.5532 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10203.5532 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10209.0532 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10230.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 461.5825 | 3077216.3492 | ACTION | 10230.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10238.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10250.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10254.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10258.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 36 | 240000 | ACTION | 10266.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10270.8791 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10272.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 64 | 320000 | ACTION | 10273.0532 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10274.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10277.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10278.5532 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 10279.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10279.5532 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 10281.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10281.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10287.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 8 | 40000 | ACTION | 10287.5532 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 60000 | ACTION | 10296.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10305.3791 | MooredSubInstallation
| Towing Group 3 | Delay | 43 | 286666.6667 | ACTION | 10339.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 46666.6667 | ACTION | 10346.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 7 | 46666.6667 | ACTION | 10353.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 26666.6667 | ACTION | 10357.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 10363.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 10370.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10370.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10377.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 403.0825 | 2687216.3492 | ACTION | 10377.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 93 | 465000 | ACTION | 10380.5532 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.991 | 9954.8442 | ACTION | 10382.5442 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10383.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10383.5442 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10385.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10397.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10401.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10405.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10417.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10420.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10424.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10427.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10451.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 96 | 640000 | ACTION | 10479.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 10485.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 10487.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 106 | 530000 | ACTION | 10489.5442 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10493.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10495.0442 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10500.5442 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10502.5442 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10503.5442 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10509.0442 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10513.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 2 | 13333.3333 | ACTION | 10515.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10523.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 403.0825 | 2687216.3492 | ACTION | 10523.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10538.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 14.5 | 0 | ACTION | 10538.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10546.3791 | MooredSubInstallation
| Towing Group 1 | Delay | 35 | 233333.3333 | ACTION | 10550.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 27 | 180000 | ACTION | 10550.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 4 | 26666.6667 | ACTION | 10554.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10556.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10558.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 10561.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10562.3791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 10563.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 10565.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10566.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10578.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10581.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10585.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10588.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10612.8791 | MooredSubInstallation
| Towing Group 2 | Delay | 74 | 493333.3333 | ACTION | 10639.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 135 | 675000 | ACTION | 10644.0442 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10645.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10649.5442 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10650.5442 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 7 | 35000 | ACTION | 10657.5442 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10665.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 1 | 6666.6667 | ACTION | 10666.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10684.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 314.5825 | 2097216.3492 | ACTION | 10684.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 10 | 66666.6667 | ACTION | 10694.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 29 | 193333.3333 | ACTION | 10695.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 5 | 33333.3333 | ACTION | 10700.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10700.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10706.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 10706.3791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 10707.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 10707.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 10709.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10714.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10715.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10726.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10730.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10734.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10735.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 78 | 390000 | ACTION | 10735.5442 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 2.991 | 14954.8442 | ACTION | 10738.5352 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10739.5352 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 10741.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10746.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 10748.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10749.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10753.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10756.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10780.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 71 | 355000 | ACTION | 10810.5352 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10816.0352 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10821.5352 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10823.5352 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10824.5352 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10852.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 291.0825 | 1940549.6825 | ACTION | 10852.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10874.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 10874.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10882.3791 | MooredSubInstallation
| Towing Group 1 | Delay | 32 | 213333.3333 | ACTION | 10884.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10890.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10894.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 72 | 360000 | ACTION | 10896.5352 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 10897.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10898.3791 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 10899.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10902.0352 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10902.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10905.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10907.5352 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10908.5352 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10914.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10917.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 10918.5261 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10919.5261 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10921.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10924.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10925.0261 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10925.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10930.5261 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 10931.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10932.5261 | ArrayCableInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 10938.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10948.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 24 | 120000 | ACTION | 10956.5261 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10957.5261 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10963.0261 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 10975.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11042.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11047.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 340.5825 | 2270549.6825 | ACTION | 11047.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 4 | 26666.6667 | ACTION | 11051.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11055.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11057.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 98 | 490000 | ACTION | 11061.0261 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 11064.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 11066.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11066.5261 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11067.5261 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11067.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11071.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11072.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11075.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11077.5171 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11078.5171 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11084.0171 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11087.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11091.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11092.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11094.8791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 11098.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11098.3791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 11105.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11122.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 50 | 250000 | ACTION | 11134.0171 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11139.5171 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11141.5171 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11142.5171 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11148.0171 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11153.5171 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11154.5171 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11164.5081 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11165.5081 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11171.0081 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 59 | 0 | ACTION | 11181.3791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11210.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 64 | 320000 | ACTION | 11235.0081 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11240.5081 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11242.5081 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11243.5081 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11249.0081 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11253.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 505.0825 | 3367216.3492 | ACTION | 11253.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11254.5081 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11255.5081 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11259.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11261.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11265.499 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 11265.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11266.499 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 11267.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11271.999 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11273.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11273.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11277.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11277.499 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11279.499 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11280.499 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11281.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11285.999 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 113333.3333 | ACTION | 11290.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11293.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11296.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11300.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11303.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11327.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 55 | 366666.6667 | ACTION | 11345.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 20000 | ACTION | 11348.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 11354.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 11361.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 86 | 430000 | ACTION | 11371.999 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11377.499 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11378.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11378.499 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11388.49 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11389.49 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11394.99 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11399.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 461.5825 | 3077216.3492 | ACTION | 11399.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11407.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11419.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11423.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11427.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11439.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11443.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11446.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11450.3791 | MooredSubInstallation
| Towing Group 1 | Delay | 59 | 393333.3333 | ACTION | 11458.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11464.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 75 | 375000 | ACTION | 11469.99 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 11471.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 11473.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11474.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11475.49 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11477.49 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11478.49 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11479.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11483.99 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11489.49 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11490.49 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11499.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11500.481 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11501.481 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 11505.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11506.981 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 11512.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11512.481 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11514.481 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11515.481 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11520.981 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11526.481 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11527.481 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11537.4719 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11538.4719 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11546.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11546.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 441.0825 | 2940549.6825 | ACTION | 11546.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11554.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11566.3791 | MooredSubInstallation
| Towing Group 2 | Delay | 21 | 140000 | ACTION | 11567.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11570.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11573.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11574.3791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 11579.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 11581.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11586.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11587.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11589.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11593.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11596.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 60 | 300000 | ACTION | 11598.4719 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11603.9719 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11607.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11609.4719 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11611.4719 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11612.4719 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 11613.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 11620.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11620.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11692.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 331.0825 | 2207216.3492 | ACTION | 11692.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11698.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 11705.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 11707.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11713.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11714.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 11714.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11722.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 114 | 570000 | ACTION | 11726.4719 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11731.9719 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11733.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11734.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11737.4719 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11738.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11738.4719 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 11739.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11742.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 11746.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11748.4629 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11749.4629 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11754.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11754.9629 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11757.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11760.4629 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11761.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11762.4629 | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 35 | 0 | ACTION | 11796.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11799.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11823.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11882.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 131 | 655000 | ACTION | 11893.4629 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11894.4629 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11895.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 383.5825 | 2557216.3492 | ACTION | 11895.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11899.9629 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11901.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11903.8791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 11908.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 11910.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11915.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11919.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 11921.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 12 | 80000 | ACTION | 11922.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11925.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11928.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 53333.3333 | ACTION | 11936.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11937.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 5 | 33333.3333 | ACTION | 11941.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 60000 | ACTION | 11950.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 11 | 73333.3333 | ACTION | 11961.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 20000 | ACTION | 11964.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 31 | 0 | ACTION | 11968.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 70 | 350000 | ACTION | 11969.9629 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 11970.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11972.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11975.4629 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11975.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11976.4629 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 11977.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11979.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11986.4539 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11987.4539 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11992.9539 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11998.4539 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12000.4539 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12001.4539 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12003.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12006.9539 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12012.4539 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12013.4539 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9 | 45000 | ACTION | 12022.4539 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12050.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 43 | 215000 | ACTION | 12065.4539 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 0.99097 | 4954.8442 | ACTION | 12066.4448 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12067.4448 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12072.9448 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12075.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 454.5825 | 3030549.6825 | ACTION | 12075.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12078.4448 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12080.4448 | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12081.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12081.4448 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12083.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12086.9448 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 12087.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 12089.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12092.4448 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12093.4448 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12095.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12095.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12099.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12103.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12103.4358 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12104.4358 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12109.9358 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12115.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12115.4358 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12115.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12117.4358 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12118.4358 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12118.8791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 12121.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12122.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12123.9358 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12125.8791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 12128.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 22 | 110000 | ACTION | 12145.9358 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12149.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12151.4358 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12152.4358 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12162.4268 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12163.4268 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12168.9268 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12174.4268 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12176.4268 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12177.4268 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12182.9268 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12188.4268 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12189.4268 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 8 | 40000 | ACTION | 12197.4268 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12218.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12221.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 475.5825 | 3170549.6825 | ACTION | 12221.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12229.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12241.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 31 | 0 | ACTION | 12272.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 55 | 366666.6667 | ACTION | 12276.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12276.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12280.8791 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12282.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12292.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 15 | 100000 | ACTION | 12297.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 12304.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 12306.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 6 | 40000 | ACTION | 12312.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12318.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 134 | 670000 | ACTION | 12331.4268 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.991 | 9954.8442 | ACTION | 12333.4177 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12334.4177 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 113333.3333 | ACTION | 12335.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 7 | 46666.6667 | ACTION | 12342.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 20000 | ACTION | 12345.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 12351.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 21 | 105000 | ACTION | 12355.4177 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 12358.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12360.9177 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 8 | 40000 | ACTION | 12368.9177 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12374.4177 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12376.4177 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12377.4177 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12382.9177 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12386.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12388.4177 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12389.4177 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12399.4087 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12400.4087 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12405.9087 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12411.4087 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12413.4087 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12414.4087 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12419.9087 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12425.4087 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12426.4087 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12436.3997 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12437.3997 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12442.8997 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12448.3997 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12450.3997 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12451.3997 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 14 | 70000 | ACTION | 12465.3997 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12470.8997 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12476.3997 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12477.3997 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 10000 | ACTION | 12479.3997 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12554.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 300 | 0 | ACTION | 12592.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12596.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12599.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 12610.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12614.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 140 | 700000 | ACTION | 12619.3997 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | ACTION | 12622.3997 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 3 | 15000 | ACTION | 12625.3997 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 4.991 | 24954.8442 | ACTION | 12630.3907 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12631.3907 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12636.8907 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12638.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12642.3907 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12644.3907 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12645.3907 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12650.8907 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12656.3907 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12657.3907 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12667.3816 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12668.3816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12673.8816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12679.3816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12681.3816 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12682.3816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12687.8816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12693.3816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12694.3816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12704.3726 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12705.3726 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12710.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 733.0825 | 4887216.3492 | ACTION | 12710.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12710.8726 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12716.3726 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12716.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12718.3726 | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12718.3791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12722.3791 | MooredSubInstallation
| Towing Group 1 | Delay | 13 | 86666.6667 | ACTION | 12729.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12730.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12734.3791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 12735.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 12737.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12738.3791 | MooredSubInstallation
| Towing Group 1 | Delay | 15 | 100000 | ACTION | 12752.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 12753.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12758.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12765.3791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 53333.3333 | ACTION | 12766.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 85 | 0 | ACTION | 12850.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12853.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12857.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12860.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12884.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 122 | 813333.3333 | ACTION | 12888.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12890.3791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 80000 | ACTION | 12900.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 12906.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 12913.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 202 | 1010000 | ACTION | 12920.3726 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12921.3726 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12926.8726 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12932.3726 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12933.3726 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12943.3636 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12944.3636 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12949.8636 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12955.3636 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12956.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 828.0825 | 5520549.6825 | ACTION | 12956.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12957.3636 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12958.3636 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12962.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12963.8636 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12964.8791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 12969.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12969.3636 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12970.3636 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 12971.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12976.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12977.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12980.3545 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12980.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12981.3545 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12984.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12986.8545 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12992.3545 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12994.3545 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12995.3545 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12996.8791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12997.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13000.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13000.8545 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 13003.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13003.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13006.3545 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13007.3545 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13007.3791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 13010.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13017.3455 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13018.3455 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13023.8455 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13029.3455 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13031.3455 | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13031.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13032.3455 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13037.8455 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13043.3455 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13044.3455 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13054.3365 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13055.3365 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13058.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13060.8365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13066.3365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13068.3365 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13069.3365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13074.8365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13080.3365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13081.3365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13091.3274 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13092.3274 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13097.8274 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13103.3274 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13103.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 745.0825 | 4967216.3492 | ACTION | 13103.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13111.3791 | MooredSubInstallation
| Towing Group 3 | Delay | 10 | 66666.6667 | ACTION | 13113.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 13 | 65000 | ACTION | 13116.3274 | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13118.3274 | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13119.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13123.3791 | MooredSubInstallation
| Towing Group 3 | Delay | 45 | 300000 | ACTION | 13164.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 41 | 0 | ACTION | 13164.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13168.3791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 13170.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13172.3791 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 13172.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13178.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 26666.6667 | ACTION | 13182.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 4 | 26666.6667 | ACTION | 13186.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 13333.3333 | ACTION | 13188.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 1 | 6666.6667 | ACTION | 13189.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 20000 | ACTION | 13192.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 19 | 126666.6667 | ACTION | 13211.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 13333.3333 | ACTION | 13213.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13226.3791 | MooredSubInstallation
| Towing Group 3 | Delay | 45 | 300000 | ACTION | 13258.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 6666.6667 | ACTION | 13259.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 1 | 6666.6667 | ACTION | 13260.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 89 | 0 | ACTION | 13261.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 149 | 745000 | ACTION | 13267.3274 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13268.3274 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 53333.3333 | ACTION | 13268.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13273.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13273.8274 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 13274.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13279.3274 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13280.3274 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 13281.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13290.3184 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13291.3184 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13296.8184 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13302.3184 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 10 | 50000 | ACTION | 13312.3184 | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 39 | 0 | ACTION | 13312.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13314.3184 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13315.3184 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13315.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 43 | 215000 | ACTION | 13358.3184 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13363.8184 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13369.3184 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13370.3184 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13380.3094 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13381.3094 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13386.8094 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13392.3094 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13394.3094 | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13394.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13395.3094 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13400.8094 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13406.3094 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13407.3094 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 92 | 0 | ACTION | 13407.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13411.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 18 | 0 | ACTION | 13429.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13432.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 27 | 135000 | ACTION | 13434.3094 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13456.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 87 | 435000 | ACTION | 13521.3094 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | ACTION | 13525.3094 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13528.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 615.0825 | 4100549.6825 | ACTION | 13528.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 9 | 45000 | ACTION | 13534.3094 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13534.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13536.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.6959 | 23479.6026 | ACTION | 13539.0053 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13540.0053 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 13541.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 13543.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13545.5053 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13548.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13549.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13551.0053 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13552.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 13554.7748 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13556.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 13558.5443 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13562.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 13564.5443 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 13568.3137 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13568.8791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13569.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13570.3137 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13571.3137 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13572.3791 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 13575.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13575.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13576.8137 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13579.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 13582.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13582.3137 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13583.3137 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13603.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 35.6959 | 178479.6026 | ACTION | 13619.0096 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13620.0096 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13625.5096 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13631.0096 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13633.0096 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13634.0096 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13639.5096 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13645.0096 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13646.0096 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13656.0006 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13657.0006 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13662.5006 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13668.0006 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13670.0006 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13671.0006 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13675.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 665.0825 | 4433883.0159 | ACTION | 13675.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13676.5006 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13681.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13682.0006 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13683.0006 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13683.3791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 13687.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 13689.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13692.9916 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13693.9916 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13695.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13695.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13699.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13699.4916 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13703.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13704.9916 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13706.9916 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13707.9916 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 5 | 25000 | ACTION | 13712.9916 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13715.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13715.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13718.4916 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13718.8791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 13721.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13722.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13723.9916 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13724.9916 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13725.8791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 13728.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13730.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13734.9826 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13735.9826 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13741.4826 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13746.9826 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13748.9826 | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13749.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13749.9826 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13755.4826 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13760.9826 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13761.9826 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13771.9735 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13772.9735 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13778.4735 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13783.9735 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13785.9735 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13786.9735 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13792.4735 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13797.9735 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13798.9735 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13808.9645 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13809.9645 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13815.4645 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13820.9645 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13821.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 540.0825 | 3600549.6825 | ACTION | 13821.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13822.9645 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13823.9645 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13827.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13829.4645 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13829.8791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 13834.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13834.9645 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 13836.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 2 | 10000 | ACTION | 13836.9645 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13837.9645 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 13838.9645 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13841.8791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13842.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 13333.3333 | ACTION | 13844.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 1 | 6666.6667 | ACTION | 13845.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 6666.6667 | ACTION | 13846.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 13855.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13859.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13863.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 18 | 120000 | ACTION | 13864.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13875.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 13880.8791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 113333.3333 | ACTION | 13881.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13884.3791 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 13887.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13887.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13891.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 13894.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13898.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13915.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 114 | 570000 | ACTION | 13952.9645 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 8.991 | 44954.8442 | ACTION | 13961.9555 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13962.9555 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13968.4555 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13973.9555 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13975.9555 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13976.9555 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13982.4555 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13987.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 405.0825 | 2700549.6825 | ACTION | 13987.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13987.9555 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13988.9555 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13993.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13995.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13998.9464 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 13999.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13999.9464 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 14001.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14005.4464 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14007.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14007.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14010.9464 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14011.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14012.9464 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14013.9464 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14015.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14019.4464 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14024.9464 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14025.9464 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14027.3791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14027.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14030.8791 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 14033.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14035.9374 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14036.9374 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 14040.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14042.4374 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 4 | 20000 | ACTION | 14046.4374 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 18 | 0 | ACTION | 14048.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14051.9374 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14052.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14053.9374 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14054.9374 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14055.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14060.4374 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14065.9374 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14066.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14066.9374 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14076.9284 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14077.9284 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14079.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14083.4284 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14088.9284 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14090.9284 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14091.9284 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 53 | 265000 | ACTION | 14144.9284 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14150.4284 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14151.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 423.0825 | 2820549.6825 | ACTION | 14151.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14155.9284 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14156.9284 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14157.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14159.8791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 14164.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 14166.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14166.9193 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14167.9193 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14171.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14172.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14173.4193 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14175.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14178.9193 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14179.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14180.9193 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14181.9193 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14187.4193 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14191.8791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14192.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14192.9193 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14193.9193 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14195.3791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 14198.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14198.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14202.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14203.9103 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14204.9103 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 14205.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14210.4103 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14215.9103 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14217.9103 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14218.9103 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14226.3791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14234.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 25 | 125000 | ACTION | 14243.9103 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14249.4103 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14254.9103 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14255.9103 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14265.9013 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14266.9013 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14272.4013 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14277.9013 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14279.9013 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14280.9013 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14286.4013 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14291.9013 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14292.9013 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14298.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 404.0825 | 2693883.0159 | ACTION | 14298.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14302.8922 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14303.8922 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14304.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14306.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14309.3922 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 14310.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 14312.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14314.8922 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14316.8922 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14317.8922 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14318.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14318.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14322.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14323.3922 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14326.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14328.8922 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14329.8922 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14338.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14338.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14339.8832 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14340.8832 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14341.8791 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 14344.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14345.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14346.3832 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14348.8791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 14351.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14351.8832 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14353.8832 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14354.8832 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14360.3832 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14365.8832 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14366.8832 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14372.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14376.8742 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14377.8742 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14383.3742 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14388.8742 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14390.8742 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14391.8742 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14397.3742 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14402.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 47 | 235000 | ACTION | 14444.3742 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14444.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 404.0825 | 2693883.0159 | ACTION | 14444.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14449.8742 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14450.8742 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14450.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14452.8791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 14457.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 14459.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14460.8652 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14461.8652 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14464.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14465.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14467.3652 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14468.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14472.8652 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14472.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14474.8652 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14475.8652 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14481.3652 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14484.8791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14485.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14486.8652 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14487.8652 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14488.3791 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 14491.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14491.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14495.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14497.8561 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 14498.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14498.8561 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14504.3561 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14509.8561 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14511.8561 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14512.8561 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14518.3561 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14519.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14523.8561 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14524.8561 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5 | 25000 | ACTION | 14529.8561 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 3 | 15000 | ACTION | 14532.8561 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 10000 | ACTION | 14534.8561 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14570.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 49 | 245000 | ACTION | 14583.8561 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 2.991 | 14954.8442 | ACTION | 14586.8471 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14587.8471 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14591.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 386.0825 | 2573883.0159 | ACTION | 14591.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14593.3471 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14597.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14598.8471 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14599.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14600.8471 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14601.8471 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 14603.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 14605.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14607.3471 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14611.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14611.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14612.8471 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14613.8471 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14615.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14619.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14623.8381 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14624.8381 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14630.3381 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14631.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14631.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14634.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14635.8381 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 14637.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14637.8381 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14638.8381 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 14642.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14644.3381 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 14644.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14646.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14649.8381 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14649.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14650.8381 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14660.829 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14661.829 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14667.329 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14672.829 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14673.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14674.829 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14675.829 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14681.329 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14686.829 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14687.829 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14697.82 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14698.82 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14704.32 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14709.82 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14711.82 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14712.82 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14718.32 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14723.82 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14724.82 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14734.811 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14735.811 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14738.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14741.311 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14745.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 394.0825 | 2627216.3492 | ACTION | 14745.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14746.811 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14748.811 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14749.811 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14751.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14753.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14755.311 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 14758.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 14760.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14760.811 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14761.811 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14765.8791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14766.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14769.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14773.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14785.8791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14786.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14789.3791 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 14792.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14792.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 34 | 170000 | ACTION | 14795.811 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14796.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 14799.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 12 | 60000 | ACTION | 14807.811 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14820.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 14 | 70000 | ACTION | 14821.811 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 18.2057 | 91028.4666 | ACTION | 14840.0167 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14841.0167 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14846.5167 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14852.0167 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 14855.7861 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 14861.7861 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 14865.5556 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14867.5556 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14868.5556 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14874.0556 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14879.5556 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14880.5556 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14892.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 394.0825 | 2627216.3492 | ACTION | 14892.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14898.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14900.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 20 | 100000 | ACTION | 14900.5556 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 14904.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 14906.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14912.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14912.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14916.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14920.3791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 73333.3333 | ACTION | 14923.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14932.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 14937.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14940.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 24 | 160000 | ACTION | 14947.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 14955.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 56 | 280000 | ACTION | 14956.5556 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 60000 | ACTION | 14956.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14959.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 6 | 30000 | ACTION | 14962.5556 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 14962.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 14964.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 5 | 25000 | ACTION | 14967.5556 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14967.8791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 14969.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 4.2057 | 21028.4666 | ACTION | 14971.7613 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14972.7613 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 18 | 90000 | ACTION | 14990.7613 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14991.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14996.2613 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15001.7613 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15003.7613 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15004.7613 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15010.2613 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 8 | 40000 | ACTION | 15018.2613 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15023.7613 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15024.7613 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 17 | 85000 | ACTION | 15041.7613 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15063.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 419.0825 | 2793883.0159 | ACTION | 15063.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15071.8791 | MooredSubInstallation
| Towing Group 2 | Delay | 15 | 100000 | ACTION | 15078.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15083.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15084.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15087.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15091.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 15094.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15106.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15110.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15113.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15117.3791 | MooredSubInstallation
| Towing Group 2 | Delay | 43 | 286666.6667 | ACTION | 15127.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 15134.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 15136.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15141.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15142.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 102 | 510000 | ACTION | 15143.7613 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 7.7753 | 38876.3827 | ACTION | 15151.5366 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15152.5366 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15158.0366 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 15162.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15163.5366 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15165.5366 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15166.5366 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 15168.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15172.0366 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 15175.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15177.5366 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15178.5366 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 24.7753 | 123876.3827 | ACTION | 15203.3119 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15204.3119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15209.8119 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15213.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 414.0825 | 2760549.6825 | ACTION | 15213.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15215.3119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15217.3119 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15218.3119 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15219.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15221.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15223.8119 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 15225.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 15227.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15229.3119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15230.3119 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15233.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15233.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15237.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15241.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 19.4694 | 97347.1515 | ACTION | 15249.7813 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15250.7813 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15253.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 15253.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15256.2813 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15256.8791 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 15259.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15260.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15261.7813 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15263.7813 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15263.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15264.7813 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 15266.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15270.2813 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15275.7813 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15276.7813 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15287.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 19.4694 | 97347.1515 | ACTION | 15296.2507 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15297.2507 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15302.7507 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15308.2507 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15310.2507 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15311.2507 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15316.7507 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15322.2507 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15323.2507 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 14.4865 | 72432.5621 | ACTION | 15337.7372 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15338.7372 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15344.2372 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15349.7372 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15351.7372 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15352.7372 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15358.2372 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15359.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 390.0825 | 2600549.6825 | ACTION | 15359.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15363.7372 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15364.7372 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15365.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 15372.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 15374.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 14.4865 | 72432.5621 | ACTION | 15379.2237 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15380.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15380.2237 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15385.7237 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15391.2237 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15393.2237 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15394.2237 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15399.7237 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 15400.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15405.2237 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 15406.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15406.2237 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 15413.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.652 | 53259.7959 | ACTION | 15416.8757 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15417.8757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15423.3757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15428.8757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15430.8757 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15431.8757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15437.3757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15442.8757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15443.8757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.652 | 53259.7959 | ACTION | 15454.5277 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15455.5277 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15461.0277 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15466.5277 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 15470.2971 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 15474.0666 | ArrayCableInstallation |  | ArrayCableInstallation