## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | location | phase_name | max_waveheight | max_windspeed | transit_speed | num_vessels | num_ahts_vessels
0.5 | Export Cable Installation Vessel | Mobilize | 72 | 180000 | ACTION | 0 | ExportCableInstallation
| Onshore Construction | Onshore Construction | 0 | 1665604.3526 | ACTION | 0 | ExportCableInstallation | Landfall
1 | Mooring System Installation Vessel | Mobilize | 168 | 700000 | ACTION | 0 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 6 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 14.3349 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 16.3349 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 20.3349 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 36.4949 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 40.6549 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 42.6549 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 46.6549 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 62.8149 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 66.9749 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 68.9749 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 72.9749 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 89.1349 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 93.2949 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 88 | 440000 | ACTION | 94 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Tow Plow | 0.4 | 2000 | ACTION | 94.4 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Pull Winch | 0.4 | 2000 | ACTION | 94.8 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 95.2949 | MooringSystemInstallation
| Export Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 95.8 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 99.2949 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 101.3 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 106.8 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 107.8 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 115.4549 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 119.6149 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 121.6149 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 125.6149 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 141.7749 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 145.9349 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 147.9349 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 151.9349 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 50 | 250000 | ACTION | 157.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 168.0949 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 172.2549 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 176.5898 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 181.5898 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 186.5898 | MooringSystemInstallation |  | MooringSystemInstallation
| Substation Assembly Line 1 | Substation Substructure Assembly | 0 | 0 | ACTION | 187.3154 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 190.9247 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 192.9247 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 196.9247 | MooringSystemInstallation |  | MooringSystemInstallation
| Substation Assembly Line 1 | Attach Topside | 24 | 0 | ACTION | 211.3154 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay: Waiting on Completed Assembly | 24 | 100000 | ACTION | 211.3154 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 213.0847 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 217.2447 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Tow Substation to Site | 7.2248 | 30103.4722 | ACTION | 218.5402 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 219.2447 | MooringSystemInstallation
| Floating Substation Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 220.5402 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 223.2447 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 226.5402 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 230.5402 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 239.4047 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 243.5647 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 245.5647 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 40 | 166666.6667 | ACTION | 270.5402 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 26 | 108333.3333 | ACTION | 271.5647 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 275.5647 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 285.7002 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 289.8602 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 291.7247 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 295.8847 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 297.8602 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 297.8847 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 301.8847 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 318.0447 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 319.8602 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 164 | 820000 | ACTION | 321.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 322.2047 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 324.2047 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 328.2047 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 331.8602 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 335.8602 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 16 | 80000 | ACTION | 337.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 338.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 344.3647 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 348.5247 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 350.5247 | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 351.0202 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 354.5247 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 355.1802 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 17 | 85000 | ACTION | 355.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 370.6847 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 374.8447 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 377.1802 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 379.1796 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 384.1796 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 389.1796 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 389.1802 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 393.1802 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 393.5145 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 395.5145 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 40 | 200000 | ACTION | 395.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 399.5145 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 408.3402 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 412.5002 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 415.6745 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 24 | 120000 | ACTION | 419.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 419.8345 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 421.8345 | MooringSystemInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 13 | 54166.6667 | ACTION | 425.5002 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 425.8345 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 164 | 683333.3333 | ACTION | 589.8345 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 169 | 704166.6667 | ACTION | 594.5002 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 9 | 37500 | ACTION | 603.5002 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 605.9945 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 610.1545 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 7 | 29166.6667 | ACTION | 610.5002 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 612.1545 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 616.1545 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 29 | 120833.3333 | ACTION | 645.1545 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 42 | 175000 | ACTION | 652.5002 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 5 | 20833.3333 | ACTION | 657.5002 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 661.3145 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 661.8351 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 665.4745 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 667.4745 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 251 | 1255000 | ACTION | 670.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 671.4745 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 687.6345 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 19 | 95000 | ACTION | 689.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 691.7945 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 693.7945 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 697.7945 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 12 | 60000 | ACTION | 701.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 713.9545 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 718.1145 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 720.1145 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 724.1145 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 30.6922 | 153460.7554 | ACTION | 732.4922 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 734.4922 | ExportCableInstallation
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 739.9922 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 740.2745 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 744.4345 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 745.4922 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 748.7694 | MooringSystemInstallation
| Export Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 749.2616 | ExportCableInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 753.7694 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 758.7694 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 763.1043 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 765.1043 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 769.1043 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 785.2643 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 789.4243 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 791.4243 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 795.4243 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 811.5843 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 815.7443 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 817.7443 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 821.7443 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 837.9043 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 842.0643 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 844.0643 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 848.0643 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 864.2243 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 868.3843 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 870.3843 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 874.3843 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 890.5443 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 894.7043 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 896.7043 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 900.7043 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 916.8643 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 921.0243 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 925.3592 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 930.3592 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 935.3592 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 939.6941 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 941.6941 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 945.6941 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 961.8541 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 966.0141 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 968.0141 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 972.0141 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 988.1741 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 992.3341 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 994.3341 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 998.3341 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 12 | 50000 | ACTION | 1010.3341 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1026.4941 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1030.6541 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1032.6541 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1036.6541 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1052.8141 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1056.9741 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1058.9741 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1062.9741 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1079.1341 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1083.2941 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1085.2941 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1089.2941 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1105.4541 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1109.6141 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1113.949 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1118.949 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1123.949 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2 | 8333.3333 | ACTION | 1125.949 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 64 | 266666.6667 | ACTION | 1189.949 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2.3349 | 9728.75 | ACTION | 1192.2839 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1194.2839 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1198.2839 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 84 | 350000 | ACTION | 1282.2839 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1298.4439 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1302.6039 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1304.6039 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1308.6039 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1324.7639 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1328.9239 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1330.9239 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1334.9239 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1351.0839 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1355.2439 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1357.2439 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1361.2439 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1377.4039 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1381.5639 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1383.5639 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1387.5639 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1403.7239 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1407.8839 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1409.8839 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1413.8839 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1430.0439 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1434.2039 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1438.5388 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1443.5388 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1448.5388 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1452.8737 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1454.8737 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1458.8737 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1475.0337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1479.1937 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1481.1937 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1485.1937 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1501.3537 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1505.5137 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1507.5137 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1511.5137 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1527.6737 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1531.8337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1533.8337 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 18 | 75000 | ACTION | 1551.8337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1555.8337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 1557.8337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1573.9937 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1578.1537 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1580.1537 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1584.1537 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1600.3137 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1604.4737 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1606.4737 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1610.4737 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1626.6337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1630.7937 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1635.1286 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1640.1286 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1645.1286 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1649.4635 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1651.4635 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1655.4635 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1671.6235 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1675.7835 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1677.7835 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1681.7835 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1697.9435 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1702.1035 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1704.1035 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1708.1035 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1724.2635 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1728.4235 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1730.4235 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1734.4235 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1750.5835 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1754.7435 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1756.7435 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1760.7435 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1776.9035 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1781.0635 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1783.0635 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1787.0635 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1803.2235 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1807.3835 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1811.7184 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1816.7184 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1821.7184 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1826.0533 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1828.0533 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1832.0533 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1848.2133 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1852.3733 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1854.3733 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1858.3733 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1874.5333 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1878.6933 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1880.6933 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1884.6933 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1900.8533 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1905.0133 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1907.0133 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1911.0133 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1927.1733 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1931.3333 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1933.3333 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1937.3333 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1953.4933 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1957.6533 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1959.6533 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1963.6533 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1979.8133 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1983.9733 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1988.3082 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1993.3082 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1998.3082 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2002.6431 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2004.6431 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2008.6431 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2024.8031 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2028.9631 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2030.9631 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2034.9631 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2051.1231 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2055.2831 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2057.2831 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2061.2831 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 112 | 466666.6667 | ACTION | 2173.2831 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2189.4431 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2193.6031 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2195.6031 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 46 | 191666.6667 | ACTION | 2241.6031 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2245.6031 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2261.7631 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2265.9231 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2267.9231 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2271.9231 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2288.0831 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2292.2431 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2294.2431 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2298.2431 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 56 | 233333.3333 | ACTION | 2354.2431 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2370.4031 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2374.5631 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2378.898 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2383.898 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2388.898 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2393.2329 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2395.2329 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2399.2329 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2415.3929 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2419.5529 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2421.5529 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2425.5529 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2441.7129 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2445.8729 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2447.8729 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2451.8729 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2468.0329 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2472.1929 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2474.1929 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 28 | 116666.6667 | ACTION | 2502.1929 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2506.1929 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2522.3529 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2526.5129 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2528.5129 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2532.5129 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2548.6729 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2552.8329 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2554.8329 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2558.8329 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2574.9929 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2579.1529 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2583.4878 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2588.4878 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2593.4878 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2597.8227 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2599.8227 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2603.8227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2619.9827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2624.1427 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2626.1427 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2630.1427 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 2651.1427 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2667.3027 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2671.4627 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2673.4627 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2677.4627 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2693.6227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2697.7827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2699.7827 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2703.7827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 2724.7827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2740.9427 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2745.1027 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2747.1027 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2751.1027 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2767.2627 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2771.4227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2773.4227 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2777.4227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2793.5827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2797.7427 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2802.0776 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 35 | 145833.3333 | ACTION | 2837.0776 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2842.0776 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2847.0776 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2851.4125 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2853.4125 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2857.4125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2873.5725 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2877.7325 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2879.7325 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2883.7325 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2899.8925 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2904.0525 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2906.0525 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2910.0525 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2926.2125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2930.3725 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2932.3725 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2936.3725 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2952.5325 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2956.6925 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2958.6925 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2962.6925 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2978.8525 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2983.0125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2985.0125 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2989.0125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 78 | 325000 | ACTION | 3067.0125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3083.1725 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3087.3325 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3091.6674 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3096.6674 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3101.6674 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3106.0023 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3108.0023 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3112.0023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3128.1623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3132.3223 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3134.3223 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3138.3223 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3154.4823 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3158.6423 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3160.6423 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3164.6423 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 43 | 179166.6667 | ACTION | 3207.6423 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3223.8023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3227.9623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3229.9623 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3233.9623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3250.1223 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3254.2823 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3256.2823 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3260.2823 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3276.4423 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3280.6023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3282.6023 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3286.6023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3302.7623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3306.9223 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3311.2572 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3316.2572 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3321.2572 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3325.5921 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3327.5921 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3331.5921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3347.7521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3351.9121 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3353.9121 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3357.9121 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3374.0721 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3378.2321 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3380.2321 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3384.2321 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3400.3921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3404.5521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3406.5521 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3410.5521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3426.7121 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3430.8721 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3432.8721 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3436.8721 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3453.0321 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3457.1921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3459.1921 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3463.1921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3479.3521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3483.5121 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3487.847 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3492.847 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3497.847 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3502.1819 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3504.1819 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3508.1819 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3524.3419 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3528.5019 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3530.5019 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3534.5019 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3550.6619 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3554.8219 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3556.8219 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3560.8219 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3576.9819 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3581.1419 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3583.1419 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3587.1419 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3603.3019 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3607.4619 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3609.4619 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3613.4619 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3629.6219 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3633.7819 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3635.7819 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3639.7819 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3646.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 3646.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3654.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3655.9419 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3660.1019 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3664.4368 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3666.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3669.4368 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3674.4368 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3678.7717 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3680.7717 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3684.7717 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 22 | 0 | ACTION | 3688.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3692.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3700.9317 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3705.0917 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3707.0917 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3711.0917 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 17 | 70833.3333 | ACTION | 3728.0917 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 43 | 0 | ACTION | 3735.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3739.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3744.2517 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3748.4117 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3750.4117 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 3751.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3754.4117 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 3757.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3760.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3770.5717 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3774.7317 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 3774.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3776.7317 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3778.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3780.7317 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3781.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3796.8917 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3801.0517 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3803.0517 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3805.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3807.0517 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3814.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3823.2117 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3827.3717 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3829.3717 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3833.3717 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3849.5317 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3853.6917 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3858.0266 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3863.0266 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3868.0266 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3872.3615 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3874.3615 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 3877.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 399.5 | 2663333.3333 | ACTION | 3877.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3878.3615 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 3883.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3885.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 6 | 40000 | ACTION | 3889.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3894.5215 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 3896.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3897.8791 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 3898.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3898.6815 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3900.6815 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3901.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 3904.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3904.6815 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3905.8791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 80000 | ACTION | 3916.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 3917.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 2 | 13333.3333 | ACTION | 3918.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3920.8415 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3925.0015 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 53333.3333 | ACTION | 3926.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3927.0015 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 3929.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3931.0015 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 3932.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 3939.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3947.1615 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3951.3215 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3953.3215 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3957.3215 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3973.4815 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3977.6415 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3979.6415 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3982.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3983.6415 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3999.8015 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4003.9615 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4005.9615 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4009.9615 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4026.1215 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4030.2815 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4034.6164 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4039.6164 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 112 | 0 | ACTION | 4041.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4044.6164 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4045.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4048.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4048.9513 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4050.9513 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4052.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4054.9513 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4071.1113 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4075.2713 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4076.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4077.2713 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4081.2713 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4097.4313 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4101.5913 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4103.5913 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4107.5913 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 35 | 0 | ACTION | 4111.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 16 | 66666.6667 | ACTION | 4123.5913 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4139.7513 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4143.9113 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4145.9113 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4149.9113 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4150.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4166.0713 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4170.2313 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4172.2313 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4176.2313 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4183.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 705 | 4700000 | ACTION | 4183.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4189.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4191.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4192.3913 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 4195.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4196.5513 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 4197.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4198.5513 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4202.5513 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4203.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4203.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4207.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4211.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4218.7113 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4222.8713 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4223.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 4223.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4226.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4227.2062 | MooringSystemInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 4229.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 4230.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4232.2062 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4234.3791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 4236.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4237.2062 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4237.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4241.5411 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4243.5411 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4247.5411 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4261.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4263.7011 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4267.8611 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4269.8611 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4273.8611 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4290.0211 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4294.1811 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4296.1811 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4300.1811 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4316.3411 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4318.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4320.5011 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4322.5011 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4326.5011 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4333.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 855.5 | 5703333.3333 | ACTION | 4333.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4341.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4353.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 19 | 0 | ACTION | 4372.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 49 | 204166.6667 | ACTION | 4375.5011 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4376.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4380.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 50 | 333333.3333 | ACTION | 4383.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4389.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4391.6611 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4392.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4395.8211 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 4396.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4396.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4397.8211 | MooringSystemInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 4398.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4399.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4401.8211 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4403.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4404.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4417.9811 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4422.1411 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 4424.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4424.1411 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4427.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4428.1411 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 4430.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 4437.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4444.3011 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4448.4611 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4452.796 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4457.796 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4462.796 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4467.1309 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4469.1309 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4473.1309 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4486.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4489.2909 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4493.4509 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4495.4509 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4499.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 560.0825 | 3733883.0159 | ACTION | 4499.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4499.4509 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4507.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4515.6109 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4519.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4519.7709 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Delay | 22 | 146666.6667 | ACTION | 4521.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 4521.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4521.7709 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4525.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4525.7709 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4527.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4529.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4541.9309 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4546.0909 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Delay | 20 | 133333.3333 | ACTION | 4547.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 18 | 0 | ACTION | 4547.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4548.0909 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4552.0909 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 4553.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 4555.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4559.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4561.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4568.2509 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 4571.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4572.4109 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4574.4109 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4574.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4578.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4578.4109 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 4581.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 4587.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4594.5709 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 4594.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 19 | 0 | ACTION | 4597.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4598.7309 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4600.7309 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4600.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4604.7309 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4620.8909 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4624.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4625.0509 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4629.3858 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4634.3858 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4639.3858 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4643.7207 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4645.7207 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4649.7207 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4654.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4665.8807 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4670.0407 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4672.0407 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4676.0407 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4692.2007 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4696.3607 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4696.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 460.0825 | 3067216.3492 | ACTION | 4696.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4698.3607 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4702.3607 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4704.8791 | MooredSubInstallation
| Towing Group 2 | Delay | 20 | 133333.3333 | ACTION | 4716.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4716.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4718.5207 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4720.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4722.6807 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4722.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4724.6807 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4728.6807 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 17 | 0 | ACTION | 4737.8791 | MooredSubInstallation
| Towing Group 2 | Delay | 15 | 100000 | ACTION | 4737.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4741.8791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 4744.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4744.8407 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 4746.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4749.0007 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4751.0007 | MooringSystemInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4752.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4753.8791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 13333.3333 | ACTION | 4754.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4755.0007 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Delay | 9 | 60000 | ACTION | 4763.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4771.1607 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 60000 | ACTION | 4772.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4775.3207 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4777.3207 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4781.3207 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Delay | 13 | 86666.6667 | ACTION | 4785.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 60000 | ACTION | 4794.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 3 | 20000 | ACTION | 4797.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4797.4807 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Check Mooring Lines | 1 | 6666.6667 | ACTION | 4798.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4801.6407 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4805.9756 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4810.9756 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Delay | 14 | 93333.3333 | ACTION | 4812.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4815.9756 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Check Mooring Lines | 5 | 33333.3333 | ACTION | 4817.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4820.3105 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4822.3105 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4822.3791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 4824.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4826.3105 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4842.4705 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4846.6305 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4848.6305 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4852.6305 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 111 | 0 | ACTION | 4864.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4868.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4868.7905 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4871.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4872.9505 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4874.9505 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4875.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4878.9505 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4895.1105 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4899.2705 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4899.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4901.2705 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4905.2705 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4921.4305 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4925.5905 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4927.5905 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4931.5905 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4947.7505 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4951.9105 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4953.9105 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4957.9105 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4971.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 534.0825 | 3560549.6825 | ACTION | 4971.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4974.0705 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4977.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4978.2305 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4979.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4982.5654 | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 4983.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 4985.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4987.5654 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4990.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4991.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4991.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4992.5654 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4995.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4996.9003 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4998.9003 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4999.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5002.9003 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5011.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5011.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 5017.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5019.0603 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5023.2203 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 5024.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5025.2203 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 5026.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5029.2203 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5029.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5033.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5036.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5045.3803 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5049.5403 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5051.5403 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5055.5403 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5060.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5071.7003 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5075.8603 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5077.8603 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5081.8603 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5098.0203 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5102.1803 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5104.1803 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5108.1803 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5124.3403 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5128.5003 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5130.5003 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5132.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 538.0825 | 3587216.3492 | ACTION | 5132.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5134.5003 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5138.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5140.8791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 5145.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 5147.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5150.6603 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5152.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5153.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5154.8203 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5156.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5158.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5159.1552 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5160.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5164.1552 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5169.1552 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5172.8791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5173.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5173.4901 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5175.4901 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5176.3791 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 5179.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5179.4901 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5179.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5183.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 5186.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5195.6501 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5199.8101 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5201.8101 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5205.8101 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5207.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5221.9701 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5226.1301 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5228.1301 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5232.1301 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5248.2901 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5252.4501 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5254.4501 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5258.4501 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5274.6101 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5278.7701 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5279.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 455.0825 | 3033883.0159 | ACTION | 5279.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5280.7701 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5284.7701 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5285.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5287.3791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 5291.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 5293.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5299.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5299.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5300.9301 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5303.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5305.0901 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5307.0901 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5307.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5311.0901 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5319.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5319.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5322.8791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 5325.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5326.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5326.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5327.2501 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5331.4101 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 5332.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5335.745 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 5340.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5340.745 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5343.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5345.745 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5350.0799 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5352.0799 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5356.0799 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5367.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5372.2399 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5376.3999 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5378.3999 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5382.3999 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5398.5599 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5402.7199 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5404.7199 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5408.7199 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5424.8799 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5429.0399 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5431.0399 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5435.0399 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5439.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 415.0825 | 2767216.3492 | ACTION | 5439.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5445.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5447.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5451.1999 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 5452.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 5454.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5455.3599 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5457.3599 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5459.8791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5460.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5461.3599 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5463.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5467.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5477.5199 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5479.8791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5480.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5481.6799 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5483.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5483.6799 | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 5486.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5486.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5487.6799 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5490.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 5493.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5494.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5503.8399 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5507.9999 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5512.3348 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5514.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5517.3348 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5522.3348 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5526.6697 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5528.6697 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5532.6697 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5548.8297 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5552.9897 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5554.9897 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5558.9897 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5575.1497 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5579.3097 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5581.3097 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5585.3097 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5586.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 400.0825 | 2667216.3492 | ACTION | 5586.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5592.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5594.3791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 5598.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 5600.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5601.4697 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5605.6297 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5606.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5606.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5607.6297 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5610.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5611.6297 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5614.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5626.3791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5626.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5627.7897 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5629.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5631.9497 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 5632.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5633.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5633.9497 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5636.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5637.9497 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 5639.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5654.1097 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5658.2697 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5660.2697 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5660.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5662.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5664.2697 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5680.4297 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5684.5897 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5688.9246 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5693.9246 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5698.9246 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5703.2595 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5705.2595 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5709.2595 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5725.4195 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5729.5795 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5731.5795 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5732.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 400.0825 | 2667216.3492 | ACTION | 5732.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5735.5795 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5738.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5740.8791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 5745.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 5747.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5751.7395 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5752.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5753.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5755.8995 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5756.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5757.8995 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5760.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5761.8995 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5772.8791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5773.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5778.0595 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 5779.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5782.2195 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5784.2195 | MooringSystemInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 5786.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5788.2195 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5804.3795 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5808.5395 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5810.5395 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5814.5395 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 56 | 0 | ACTION | 5828.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5830.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5830.6995 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5832.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5834.8595 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5835.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5836.8595 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5839.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5840.8595 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5857.0195 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5861.1795 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5863.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5865.5144 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5870.5144 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5875.5144 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5879.8493 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5881.8493 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5885.8493 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5902.0093 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5906.1693 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5908.1693 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5912.1693 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5928.3293 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5932.4893 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5934.4893 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5935.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 442.0825 | 2947216.3492 | ACTION | 5935.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5938.4893 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5941.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5943.3791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 5947.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 5949.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5954.6493 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5955.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5955.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5958.8093 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5959.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5960.8093 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5963.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5964.8093 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5975.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5975.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5978.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5980.9693 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 5981.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5982.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5985.1293 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5985.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5987.1293 | MooringSystemInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 5988.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5991.1293 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5998.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6007.2893 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6009.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6011.4493 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6013.4493 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6017.4493 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6033.6093 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6037.7693 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6042.1042 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6047.1042 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6052.1042 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6056.4391 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6058.4391 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6062.4391 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6078.5991 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6081.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 442.0825 | 2947216.3492 | ACTION | 6081.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6082.7591 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6084.7591 | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6087.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6088.7591 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6089.8791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 6094.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 6096.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6101.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6102.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6104.9191 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6105.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6109.0791 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6109.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6111.0791 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6115.0791 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6121.8791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6122.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6125.3791 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 6128.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6128.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6131.2391 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6132.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 6135.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6135.3991 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6137.3991 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6141.3991 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6156.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6157.5591 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6161.7191 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6163.7191 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6166.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6167.7191 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6183.8791 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6188.0391 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6190.0391 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6194.0391 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6210.1991 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6214.3591 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6218.694 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6223.694 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6228.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 442.0825 | 2947216.3492 | ACTION | 6228.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6228.694 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6233.0289 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6234.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6235.0289 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6236.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6239.0289 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 6240.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 6242.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6248.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6248.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6252.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6255.1889 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6256.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6259.3489 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6261.3489 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6265.3489 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6268.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6268.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 6274.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6281.5089 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 6281.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6285.6689 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6287.6689 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6291.6689 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 12 | 50000 | ACTION | 6303.6689 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 36 | 0 | ACTION | 6304.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6307.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6311.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 6315.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6318.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6319.8289 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6323.9889 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6325.9889 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6329.9889 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6334.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6342.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6346.1489 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6350.3089 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6352.3089 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6356.3089 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6372.4689 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6376.6289 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6378.6289 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6382.6289 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6398.7889 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6402.9489 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6407.2838 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6412.2838 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6414.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 426.0825 | 2840549.6825 | ACTION | 6414.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6417.2838 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6420.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6421.6187 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6422.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6423.6187 | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 6427.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6427.6187 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 6429.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6434.8791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6435.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6438.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6442.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6443.7787 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6447.9387 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6449.9387 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6453.9387 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6454.8791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6455.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6458.3791 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 6461.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6461.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6465.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 6468.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6470.0987 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6474.2587 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6476.2587 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6480.2587 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6489.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6496.4187 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6500.5787 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6502.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6502.5787 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6506.5787 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6522.7387 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6526.8987 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6528.8987 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6532.8987 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6549.0587 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6553.2187 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6555.2187 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6559.2187 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6561.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 426.0825 | 2840549.6825 | ACTION | 6561.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6569.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6581.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 6583.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6587.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 31 | 129166.6667 | ACTION | 6590.2187 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6591.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6603.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6606.3787 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 6613.3787 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 6614.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6617.5387 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6617.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 57 | 380000 | ACTION | 6618.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6621.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6621.8736 | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6624.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6624.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6626.8736 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 6630.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6631.8736 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 6632.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6636.2085 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6638.2085 | MooringSystemInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6638.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6642.2085 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6648.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6658.3685 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6658.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6662.5285 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6664.5285 | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 6664.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6668.5285 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6670.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 6671.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6684.6885 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6688.8485 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6690.8485 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6694.8485 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6711.0085 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6715.1685 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6717.1685 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6720.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 439.0825 | 2927216.3492 | ACTION | 6720.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6721.1685 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6728.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6740.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6744.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6748.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 35 | 145833.3333 | ACTION | 6756.1685 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6760.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6764.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6767.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6771.3791 | MooredSubInstallation
| Towing Group 2 | Delay | 51 | 340000 | ACTION | 6771.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6772.3285 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6776.4885 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6777.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6778.4885 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6782.4885 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 6784.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 6786.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6792.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6795.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6798.6485 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6802.8085 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6804.8085 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6808.8085 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 113333.3333 | ACTION | 6809.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6838.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 35 | 145833.3333 | ACTION | 6843.8085 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6859.9685 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6864.1285 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Delay | 58 | 386666.6667 | ACTION | 6867.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6867.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 399.0825 | 2660549.6825 | ACTION | 6867.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6868.4634 | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 20000 | ACTION | 6870.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6873.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6873.4634 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6875.3791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 6876.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6877.7983 | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 6879.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6879.7983 | MooringSystemInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 6881.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 6883.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6883.7983 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6887.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6887.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6891.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6895.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6899.9583 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6904.1183 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6906.1183 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6907.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6907.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6910.1183 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6910.8791 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 6913.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6914.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6917.8791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 6920.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6926.2783 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6930.4383 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6932.4383 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6936.4383 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6941.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6952.5983 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6956.7583 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7006.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7013.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 342.0825 | 2280549.6825 | ACTION | 7013.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7021.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7033.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7037.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7041.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7053.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 31 | 0 | ACTION | 7084.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7088.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7091.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7095.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7119.3791 | MooredSubInstallation
| Towing Group 1 | Delay | 114 | 760000 | ACTION | 7127.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7133.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 7140.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 7142.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7148.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7168.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 7174.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7174.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 7181.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7191.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 308.0825 | 2053883.0159 | ACTION | 7191.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7197.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7199.3791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 7203.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 7205.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7211.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7211.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7215.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7219.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 53333.3333 | ACTION | 7219.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7231.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7234.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7238.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7241.8791 | MooredSubInstallation
| Towing Group 2 | Delay | 34 | 226666.6667 | ACTION | 7253.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 80000 | ACTION | 7265.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7265.8791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 7271.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 7278.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7337.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 417.0825 | 2780549.6825 | ACTION | 7337.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7342.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7343.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7345.8791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 7350.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 7352.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7357.8791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7358.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7361.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7365.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7377.8791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7378.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7381.3791 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 7384.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7384.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7388.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 7391.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7412.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7484.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 303.0825 | 2020549.6825 | ACTION | 7484.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7490.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7492.3791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 7496.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 7498.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7504.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7504.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 20000 | ACTION | 7507.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7508.3791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7510.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7512.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7524.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7527.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 21 | 140000 | ACTION | 7528.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7531.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7534.8791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 113333.3333 | ACTION | 7545.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 7551.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 7558.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7558.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7630.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 352.0825 | 2347216.3492 | ACTION | 7630.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7636.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7638.8791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 7643.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 7645.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7650.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7651.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7654.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7658.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7670.8791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7671.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7674.3791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 7677.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7677.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7678.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7681.3791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 7684.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7705.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7777.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 386.0825 | 2573883.0159 | ACTION | 7777.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7783.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7785.3791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 7789.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 7791.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7797.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7797.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7801.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7805.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7817.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7817.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7820.8791 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 7823.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7824.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7827.8791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 7830.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7846.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7851.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7923.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 365.0825 | 2433883.0159 | ACTION | 7923.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7931.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7943.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7947.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7951.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7963.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 7976.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7980.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7983.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7987.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8011.3791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8014.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8083.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 399.0825 | 2660549.6825 | ACTION | 8083.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8091.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8103.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8107.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8111.3791 | MooredSubInstallation
| Towing Group 1 | Delay | 194 | 1293333.3333 | ACTION | 8117.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 35 | 233333.3333 | ACTION | 8118.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8123.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8123.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8124.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8126.8791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 8130.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8130.3791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 8130.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 8132.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 8132.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8133.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8138.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8138.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8157.8791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 8158.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 8158.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 8164.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 8164.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 8171.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 8171.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8182.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8229.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 399.0825 | 2660549.6825 | ACTION | 8229.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8235.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8237.8791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 8242.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 8244.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8249.8791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8250.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8253.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8257.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8269.8791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 8270.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8273.3791 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 8276.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8276.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8280.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 8283.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8304.3791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8350.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8376.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 205.0825 | 1367216.3492 | ACTION | 8376.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8384.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8396.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 8404.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8408.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8412.3791 | MooredSubInstallation
| Towing Group 1 | Delay | 45 | 300000 | ACTION | 8421.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8424.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8427.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8427.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8431.3791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 8433.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8434.8791 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 8435.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8441.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8458.8791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 8461.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 8467.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 8474.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8518.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8530.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 359.0825 | 2393883.0159 | ACTION | 8530.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8536.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8538.8791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 8543.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 8545.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8550.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8551.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8554.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8558.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8570.8791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 8571.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8574.3791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 8577.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8577.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8581.3791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 8584.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8605.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8677.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 394.0825 | 2627216.3492 | ACTION | 8677.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8683.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8686.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 9 | 0 | ACTION | 8686.3791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 8689.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 8691.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8694.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8697.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8706.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8710.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8714.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 8717.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 8723.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8726.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8729.8791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 8730.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8733.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8736.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8760.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8832.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 358.0825 | 2387216.3492 | ACTION | 8832.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8838.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 8845.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 8847.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 7 | 46666.6667 | ACTION | 8854.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8854.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 8854.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8860.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8862.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8874.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8878.3791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 8880.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8882.3791 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 8886.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 8893.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8894.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8897.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8901.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8904.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8928.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 49 | 0 | ACTION | 8977.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9022.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9049.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 465.5825 | 3103883.0159 | ACTION | 9049.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9057.8791 | MooredSubInstallation
| Towing Group 2 | Delay | 15 | 100000 | ACTION | 9064.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9069.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9070.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9073.8791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 9077.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9077.8791 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 9079.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9085.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9089.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9093.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9096.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9100.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9105.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 4 | 26666.6667 | ACTION | 9109.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9124.3791 | MooredSubInstallation
| Towing Group 2 | Delay | 66 | 440000 | ACTION | 9175.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 2 | 13333.3333 | ACTION | 9177.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 9184.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9190.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9196.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 465.5825 | 3103883.0159 | ACTION | 9196.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9204.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9216.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9220.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9224.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9236.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 9242.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9245.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9249.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9252.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 67 | 446666.6667 | ACTION | 9263.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9269.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9276.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 36 | 240000 | ACTION | 9305.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 9311.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 9313.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9319.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9339.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 9345.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9348.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 455.5825 | 3037216.3492 | ACTION | 9348.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 9352.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9358.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 9.5 | 0 | ACTION | 9358.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9366.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9378.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9382.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9386.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9398.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9401.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9405.3791 | MooredSubInstallation
| Towing Group 1 | Delay | 58 | 386666.6667 | ACTION | 9406.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 9411.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9412.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9414.8791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 9419.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 9421.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9427.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9438.8791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9447.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 9453.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 9460.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9510.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 326.5825 | 2177216.3492 | ACTION | 9510.8791 | MooredSubInstallation | [5 empty] | 2 | 1
0.5 | Array Cable Installation Vessel | Mobilize | 72 | 180000 | ACTION | 9514.8379 | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9516.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 9520.8379 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 9523.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 3 | 15000 | ACTION | 9523.8379 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 9525.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9526.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 15.5 | 0 | ACTION | 9526.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 9527.6074 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 9529.6074 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9530.6074 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9531.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9534.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9536.1074 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9541.6074 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 9542.6074 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9546.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9550.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9551.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 9552.5984 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9553.5984 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9554.3791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 9557.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9559.0984 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 9564.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9564.5984 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9566.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 9566.5984 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9567.5984 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9569.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9573.0984 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9573.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9576.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9578.5984 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 9579.5984 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 9589.5893 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9590.5893 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9596.0893 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9600.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9601.5893 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 9603.5893 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9604.5893 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9610.0893 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9615.5893 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 9616.5893 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 9626.5803 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9627.5803 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 25 | 125000 | ACTION | 9652.5803 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9658.0803 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9663.5803 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 9665.5803 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9666.5803 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9672.0803 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9672.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 320.0825 | 2133883.0159 | ACTION | 9672.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9677.5803 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 9678.5803 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9678.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 9685.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 9687.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 9688.5713 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9689.5713 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9693.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9694.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 9694.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9695.0713 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9700.5713 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9702.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 9702.5713 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9703.5713 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9709.0713 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9713.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9714.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9714.5713 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 9715.5713 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9718.3791 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 9719.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9722.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 9725.5622 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 9726.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9726.5622 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9732.0622 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 9749.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9761.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9764.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 24 | 0 | ACTION | 9788.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9792.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9795.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 87 | 435000 | ACTION | 9819.0622 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9819.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9824.5622 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 9826.5622 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9827.5622 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9833.0622 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9838.5622 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 9839.5622 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 10000 | ACTION | 9841.5622 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9862.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9891.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 431.5825 | 2877216.3492 | ACTION | 9891.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9897.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9899.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 6 | 40000 | ACTION | 9903.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 9910.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9911.8791 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 9912.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9915.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9918.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9919.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9931.8791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 100000 | ACTION | 9933.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 36 | 0 | ACTION | 9967.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9971.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9974.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9978.3791 | MooredSubInstallation
| Towing Group 1 | Delay | 56 | 373333.3333 | ACTION | 9989.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 33333.3333 | ACTION | 9994.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 156 | 780000 | ACTION | 9997.5622 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 10000.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10002.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 7.991 | 39954.8442 | ACTION | 10005.5532 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10006.5532 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 10007.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10012.0532 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10017.5532 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10019.5532 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10020.5532 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10030.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10074.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 510.0825 | 3400549.6825 | ACTION | 10074.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10080.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10082.3791 | MooredSubInstallation
| Towing Group 2 | Delay | 14 | 93333.3333 | ACTION | 10094.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10094.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10098.3791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 10100.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10102.3791 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 10102.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 9 | 60000 | ACTION | 10111.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10114.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10117.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10117.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10121.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10124.8791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 60000 | ACTION | 10126.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10148.8791 | MooredSubInstallation
| Towing Group 2 | Delay | 44 | 293333.3333 | ACTION | 10170.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 158 | 790000 | ACTION | 10178.5532 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 73333.3333 | ACTION | 10181.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10184.0532 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 10187.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10189.5532 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10190.5532 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | ACTION | 10194.5532 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 10194.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10198.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10220.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 494.5825 | 3297216.3492 | ACTION | 10220.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10228.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10240.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10244.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10248.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 40 | 266666.6667 | ACTION | 10260.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10260.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10264.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10266.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10267.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10271.3791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 10273.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 10275.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 86 | 430000 | ACTION | 10280.5532 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10281.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.991 | 29954.8442 | ACTION | 10286.5442 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10287.5442 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10293.0442 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10295.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10298.5442 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10300.5442 | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10301.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10301.5442 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10307.0442 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 10307.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10312.5442 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10313.5442 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 10314.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 10323.5352 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10324.5352 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10330.0352 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10335.5352 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10337.5352 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10338.5352 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10344.0352 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10349.5352 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10350.5352 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 10360.5261 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10361.5261 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10366.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10367.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 360.0825 | 2400549.6825 | ACTION | 10367.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10373.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10375.3791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 10379.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 20 | 100000 | ACTION | 10381.5261 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 10381.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10387.0261 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10387.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10387.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10391.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10392.5261 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10394.5261 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10395.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10395.5261 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10401.0261 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10406.5261 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10407.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10407.5261 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10407.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10410.8791 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 10413.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10414.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 10417.5171 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10417.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10418.5171 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 10420.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10424.0171 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10429.5171 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10431.5171 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10432.5171 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10438.0171 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10441.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10443.5171 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10444.5171 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 10454.5081 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10455.5081 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10461.0081 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10466.5081 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10468.5081 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10469.5081 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10475.0081 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10513.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 319.0825 | 2127216.3492 | ACTION | 10513.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 13 | 86666.6667 | ACTION | 10526.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10532.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10534.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 20.5 | 0 | ACTION | 10534.3791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 10539.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 10541.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10542.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10547.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10554.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10558.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10562.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10567.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 10573.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10574.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10577.8791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 10580.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10581.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10584.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 118 | 590000 | ACTION | 10593.0081 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10598.5081 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10599.5081 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10608.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 10609.499 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10610.499 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10615.999 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10621.499 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10623.499 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10624.499 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10629.999 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10635.499 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10636.499 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 10646.49 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10647.49 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10652.99 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 24 | 120000 | ACTION | 10676.99 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10680.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 366.5825 | 2443883.0159 | ACTION | 10680.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10682.49 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10684.49 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10685.49 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10686.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 10693.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 10695.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10701.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 6666.6667 | ACTION | 10702.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10702.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 10702.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10710.3791 | MooredSubInstallation
| Towing Group 3 | Delay | 15 | 100000 | ACTION | 10717.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10722.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10726.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10730.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 113333.3333 | ACTION | 10734.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10742.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10745.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10749.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10752.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 23 | 153333.3333 | ACTION | 10757.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 13333.3333 | ACTION | 10759.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 4 | 26666.6667 | ACTION | 10763.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10776.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 45 | 300000 | ACTION | 10808.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 2 | 13333.3333 | ACTION | 10810.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 10817.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 154 | 770000 | ACTION | 10839.49 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10844.99 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10848.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 428.0825 | 2853883.0159 | ACTION | 10848.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10850.49 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10851.49 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10854.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 10861.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 10861.481 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10862.481 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 10863.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10867.981 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10869.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10870.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 10870.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10873.481 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10875.481 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10876.481 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10878.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10881.981 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10887.481 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10888.481 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10889.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10890.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10894.3791 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 10895.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10898.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 10898.4719 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10899.4719 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 10902.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10904.9719 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10910.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10910.4719 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10912.4719 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10913.4719 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10913.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10917.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10918.9719 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10920.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10924.4719 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10925.4719 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 10935.4629 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10936.4629 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10941.9629 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10944.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 42 | 210000 | ACTION | 10983.9629 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10989.4629 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10991.4629 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10992.4629 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10997.9629 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11003.4629 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11004.4629 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11014.4539 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11015.4539 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11016.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 436.5825 | 2910549.6825 | ACTION | 11016.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11020.9539 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11022.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11026.4539 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11028.4539 | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 11029.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11029.4539 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 11031.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11034.9539 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11037.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11038.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 11038.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11040.4539 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11041.4539 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11046.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11051.4448 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11052.4448 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11057.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11057.9448 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11058.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11062.3791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 11063.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11063.4448 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11065.4448 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11066.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11066.4448 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 11070.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11071.9448 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11077.4448 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11078.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11078.4448 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11081.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11085.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11088.4358 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11088.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11112.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 60 | 300000 | ACTION | 11148.4358 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11149.4358 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11154.9358 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11160.4358 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11162.4358 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11163.4358 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11168.9358 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11184.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 367.5825 | 2450549.6825 | ACTION | 11184.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11206.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 11206.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11214.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11226.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11230.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11234.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11246.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11249.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11253.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11256.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11280.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 152 | 1013333.3333 | ACTION | 11336.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11342.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 11349.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 181 | 905000 | ACTION | 11349.9358 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 11351.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11352.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 450.5825 | 3003883.0159 | ACTION | 11352.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11355.4358 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11356.4358 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11357.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11358.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 11365.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11366.4268 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 11367.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11367.4268 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11373.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11374.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 11374.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11377.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11382.3791 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 11383.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 11390.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11393.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11394.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11398.3791 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 11399.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11402.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 11406.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11414.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 11419.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11422.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11426.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 11441.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11444.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11468.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 111 | 555000 | ACTION | 11478.4268 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11483.9268 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11489.4268 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11491.4268 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11492.4268 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11497.9268 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 21 | 105000 | ACTION | 11518.9268 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11524.4268 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11525.4268 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11535.4177 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11536.4177 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11540.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 470.5825 | 3137216.3492 | ACTION | 11540.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11541.9177 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11542.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 1.5 | 0 | ACTION | 11542.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11546.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11547.4177 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11549.4177 | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11550.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11550.4177 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 11553.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 11555.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 5 | 25000 | ACTION | 11555.4177 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11560.9177 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11561.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11562.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11566.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11566.4177 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11567.4177 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11570.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | ACTION | 11570.4177 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11581.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 11 | 55000 | ACTION | 11581.4177 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11582.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11585.8791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 11587.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 6.991 | 34954.8442 | ACTION | 11588.4087 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11589.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11589.4087 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11592.8791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 11594.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11616.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11688.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 298.5825 | 1990549.6825 | ACTION | 11688.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 105 | 525000 | ACTION | 11694.4087 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11694.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11699.9087 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 11701.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 11703.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11705.4087 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11707.4087 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11708.4087 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11709.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11710.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 11710.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11713.9087 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11718.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11719.4087 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11720.4087 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11729.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11730.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11730.3997 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11731.3997 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11734.3791 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 11735.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11736.8997 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11738.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 11742.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11742.3997 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11744.3997 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11745.3997 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11750.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11750.8997 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11753.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11756.3997 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11757.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11757.3997 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11760.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11767.3907 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11768.3907 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11773.8907 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11779.3907 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11781.3907 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11782.3907 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11784.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11787.8907 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11793.3907 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11794.3907 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11804.3816 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11805.3816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 14 | 70000 | ACTION | 11819.3816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11824.8816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11830.3816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11832.3816 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11833.3816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11838.8816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11844.3816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11845.3816 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | ACTION | 11849.3816 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11856.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 450.5825 | 3003883.0159 | ACTION | 11856.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11878.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 11878.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11886.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11898.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11902.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11906.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11918.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11921.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 68 | 453333.3333 | ACTION | 11924.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11925.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11928.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11930.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 11937.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 11939.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11945.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 100 | 500000 | ACTION | 11949.3816 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11952.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.991 | 29954.8442 | ACTION | 11955.3726 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11956.3726 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11961.8726 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11965.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11967.3726 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11969.3726 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11970.3726 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 11971.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11975.8726 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 11978.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11981.3726 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11982.3726 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11992.3636 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11993.3636 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11998.8636 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12004.3636 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12006.3636 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12007.3636 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12012.8636 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12018.3636 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12019.3636 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12024.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 430.5825 | 2870549.6825 | ACTION | 12024.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12029.3545 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12030.3545 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12030.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12035.8545 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 12037.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 12039.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12041.3545 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12043.3545 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12044.3545 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12045.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12046.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 12046.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 33333.3333 | ACTION | 12050.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 4 | 26666.6667 | ACTION | 12054.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12054.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 17 | 85000 | ACTION | 12061.3545 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12066.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12066.8545 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 100000 | ACTION | 12069.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12070.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12074.3791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 12075.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 12081.3791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 12082.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12093.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 41 | 0 | ACTION | 12134.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12137.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 12152.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12156.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12159.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 108 | 540000 | ACTION | 12174.8545 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12180.3545 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12181.3545 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12183.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12191.3455 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12192.3455 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12197.8455 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12203.3455 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12205.3455 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12206.3455 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12211.8455 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12214.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12217.3455 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12218.3455 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12228.3365 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12229.3365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12234.8365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12240.3365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12242.3365 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12243.3365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12248.8365 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12255.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 513.5825 | 3423883.0159 | ACTION | 12255.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12261.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12263.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 10 | 66666.6667 | ACTION | 12271.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12275.8791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 12278.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12279.8791 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 12280.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12283.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 36 | 180000 | ACTION | 12284.8365 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12286.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12290.3365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12291.3365 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12295.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12299.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12301.3274 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12302.3274 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12302.8791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12306.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12306.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12307.8274 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 12312.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 12319.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12330.3791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12382.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 91 | 455000 | ACTION | 12398.8274 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12402.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 424.0825 | 2827216.3492 | ACTION | 12402.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12404.3274 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12406.3274 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12407.3274 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12408.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12410.3791 | MooredSubInstallation
| Towing Group 1 | Delay | 9 | 60000 | ACTION | 12417.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 15 | 75000 | ACTION | 12422.3274 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12422.3791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 12423.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 12425.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12426.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12427.8274 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12430.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12431.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12433.3274 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12434.3274 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12442.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12444.3184 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12445.3184 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12445.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12449.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12450.8184 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12451.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12452.8791 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 12457.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 12464.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 32 | 0 | ACTION | 12484.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12508.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12550.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12580.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 498.5825 | 3323883.0159 | ACTION | 12580.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 4 | 26666.6667 | ACTION | 12584.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12588.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12590.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12600.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 57 | 0 | ACTION | 12657.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12661.8791 | MooredSubInstallation
| Towing Group 2 | Delay | 72 | 480000 | ACTION | 12662.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12665.8791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 12669.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 12671.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 42 | 0 | ACTION | 12707.8791 | MooredSubInstallation
| Towing Group 2 | Delay | 47 | 313333.3333 | ACTION | 12718.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12718.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12719.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12724.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 13333.3333 | ACTION | 12726.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 12726.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12730.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12733.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12737.3791 | MooredSubInstallation
| Towing Group 2 | Delay | 29 | 193333.3333 | ACTION | 12755.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12761.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 120000 | ACTION | 12773.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 12779.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 12786.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 347 | 1735000 | ACTION | 12797.8184 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12803.3184 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12805.3184 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12806.3184 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12811.8184 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12817.3184 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12818.3184 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 12819.3184 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 2 | 10000 | ACTION | 12821.3184 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 12822.3184 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 3 | 15000 | ACTION | 12825.3184 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | ACTION | 12829.3184 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 2 | 10000 | ACTION | 12831.3184 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12833.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 514.0825 | 3427216.3492 | ACTION | 12833.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 3.991 | 19954.8442 | ACTION | 12835.3094 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12836.3094 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12839.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12841.3791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 12845.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 12847.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12853.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12857.3791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12886.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 43 | 0 | ACTION | 12900.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12904.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 22 | 0 | ACTION | 12926.3791 | MooredSubInstallation
| Towing Group 3 | Delay | 83 | 553333.3333 | ACTION | 12930.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12936.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12938.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12941.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12945.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 111 | 555000 | ACTION | 12947.3094 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12948.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12952.8094 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12956.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12958.3094 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12960.3094 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12961.3094 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 12962.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12966.8094 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 12969.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12972.3094 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12972.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12973.3094 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 16 | 80000 | ACTION | 12989.3094 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13044.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 580.0825 | 3867216.3492 | ACTION | 13044.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13052.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13054.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13064.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 13068.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 28 | 186666.6667 | ACTION | 13072.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13072.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13076.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13078.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 13085.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 13087.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13088.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13092.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13093.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13095.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 107 | 535000 | ACTION | 13096.3094 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13099.3791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13113.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 19.6959 | 98479.6026 | ACTION | 13116.0053 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13117.0053 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 13119.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13122.5053 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13123.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 13126.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13128.0053 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 13131.7748 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 13135.5443 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 13141.5443 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 13145.3137 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13147.3137 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13148.3137 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13153.8137 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13159.3137 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 34 | 170000 | ACTION | 13193.3137 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13194.3137 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13195.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 409.0825 | 2727216.3492 | ACTION | 13195.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13201.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13203.3791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 13207.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 13209.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13215.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13215.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13219.3791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13222.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13223.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 34 | 170000 | ACTION | 13228.3137 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 13229.3137 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.6959 | 8479.6026 | ACTION | 13231.0096 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13232.0096 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13235.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13235.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 13241.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 13248.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 125 | 625000 | ACTION | 13357.0096 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 124 | 0 | ACTION | 13359.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13362.5096 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13362.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13366.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13368.0096 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13369.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13370.0096 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13371.0096 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13376.5096 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13382.0096 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13383.0096 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13390.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13393.0006 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13393.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13394.0006 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13399.5006 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13405.0006 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13407.0006 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13408.0006 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13413.5006 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13419.0006 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13420.0006 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13429.9916 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13430.9916 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13436.4916 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 17 | 85000 | ACTION | 13453.4916 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13458.9916 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13460.9916 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13461.9916 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13465.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 496.0825 | 3307216.3492 | ACTION | 13465.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13467.4916 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13471.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13472.9916 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13473.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13473.9916 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 13478.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 13480.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13483.9826 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13484.9826 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13485.8791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13486.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13489.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13490.4826 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13493.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13495.9826 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13497.9826 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13498.9826 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13504.4826 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13505.8791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13506.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13509.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13509.9826 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13510.9826 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 13512.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13512.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13516.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 13519.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13520.9735 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13521.9735 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13527.4735 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13532.9735 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13534.9735 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13535.9735 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13540.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13541.4735 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13546.9735 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13547.9735 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13557.9645 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13558.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13558.9645 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13564.4645 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13569.9645 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13571.9645 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13572.9645 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13578.4645 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13583.9645 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13584.9645 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13594.9555 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13595.9555 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13601.4555 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13606.9555 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13608.9555 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13609.9555 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13612.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 486.0825 | 3240549.6825 | ACTION | 13612.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13615.4555 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13618.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13620.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13620.9555 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13621.9555 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 13624.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 13626.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13631.9464 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13632.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13632.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13632.9464 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13636.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13638.4464 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13640.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13643.9464 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13645.9464 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13646.9464 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13652.3791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13652.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 13658.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 13665.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13726.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 137 | 0 | ACTION | 13789.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 143 | 715000 | ACTION | 13789.9464 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13792.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13795.4464 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13796.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13800.9464 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13801.9464 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 6 | 30000 | ACTION | 13807.9464 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 6 | 30000 | ACTION | 13813.9464 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 3.991 | 19954.8442 | ACTION | 13817.9374 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13818.9374 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13824.4374 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 43 | 0 | ACTION | 13839.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 18 | 90000 | ACTION | 13842.4374 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13842.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13847.9374 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13849.9374 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13850.9374 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 12 | 60000 | ACTION | 13862.9374 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13866.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13868.4374 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13894.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13938.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 690.0825 | 4600549.6825 | ACTION | 13938.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13946.8791 | MooredSubInstallation
| Towing Group 2 | Delay | 18 | 120000 | ACTION | 13956.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13958.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 94 | 470000 | ACTION | 13962.4374 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13962.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13962.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13967.9374 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13968.9374 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Delay | 14 | 93333.3333 | ACTION | 13976.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 13976.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13978.9284 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13979.9284 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13980.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 2 | 10000 | ACTION | 13981.9284 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 13983.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 13985.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13987.4284 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 44 | 0 | ACTION | 14024.8791 | MooredSubInstallation
| Towing Group 2 | Delay | 40 | 266666.6667 | ACTION | 14025.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14031.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 46 | 230000 | ACTION | 14033.4284 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14036.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14038.9284 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14040.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14040.9284 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14041.9284 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14043.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14047.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14047.4284 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14051.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14052.9284 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14053.9284 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 14057.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14062.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14063.9193 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 14064.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14064.9193 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14070.4193 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14071.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14075.9193 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14077.9193 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14078.9193 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14084.4193 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14089.9193 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14090.9193 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14100.9103 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14101.9103 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14107.4103 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14112.9103 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14114.9103 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14115.9103 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14121.4103 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14126.9103 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14127.9103 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14137.9013 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14138.9013 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14143.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 624.0825 | 4160549.6825 | ACTION | 14143.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14144.4013 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14149.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14149.9013 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14151.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14151.9013 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14152.9013 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 14155.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 14157.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14158.4013 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14163.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14163.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14163.9013 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14164.9013 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14167.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14171.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14174.8922 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14175.8922 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14181.3922 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14183.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14183.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 8 | 40000 | ACTION | 14189.3922 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 14189.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14194.8922 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 14196.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14196.8922 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14197.8922 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 14198.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14201.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14203.3922 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14208.8922 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14209.8922 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 17 | 0 | ACTION | 14218.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14219.8832 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14220.8832 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14222.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14225.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14226.3832 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14230.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14231.8832 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14233.8832 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14234.8832 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14240.3832 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14245.8832 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14246.8832 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14249.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14256.8742 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14257.8742 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14263.3742 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14268.8742 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14270.8742 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14271.8742 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14277.3742 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14282.8742 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14283.8742 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14293.8652 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14294.8652 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14300.3652 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14305.8652 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14307.8652 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14308.8652 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14314.3652 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14319.8652 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14320.8652 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14321.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 656.0825 | 4373883.0159 | ACTION | 14321.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14327.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14329.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14330.8561 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14331.8561 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 14334.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 14336.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14337.3561 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14341.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14342.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14342.8561 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14344.8561 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14345.8561 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14345.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14349.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14351.3561 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14356.8561 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14357.8561 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14361.8791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14362.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14365.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14367.8471 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 14368.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14368.8471 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14368.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14372.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14374.3471 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 14375.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14379.8471 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14381.8471 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14382.8471 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14388.3471 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14393.8471 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14394.8471 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14396.3791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14398.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14404.8381 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14405.8381 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14411.3381 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14416.8381 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14418.8381 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14419.8381 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14425.3381 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14430.8381 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14431.8381 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14441.829 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14442.829 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14448.329 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14453.829 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14455.829 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14456.829 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14462.329 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14467.829 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14468.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 404.0825 | 2693883.0159 | ACTION | 14468.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14468.829 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14474.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14476.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14478.82 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14479.82 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 14480.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 14482.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14485.32 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14488.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14488.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14490.82 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14492.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14492.82 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14493.82 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14496.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14499.32 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14504.82 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14505.82 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14508.3791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14508.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14511.8791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 14514.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14515.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14515.811 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14516.811 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14518.8791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 14521.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14522.311 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14527.811 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14529.811 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14530.811 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14536.311 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14541.811 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14542.811 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14542.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14566.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 30.2057 | 151028.4666 | ACTION | 14573.0167 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14574.0167 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 3 | 15000 | ACTION | 14577.0167 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14582.5167 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14614.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 418.0825 | 2787216.3492 | ACTION | 14614.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14622.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 12 | 80000 | ACTION | 14626.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14632.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14634.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14638.8791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 14639.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 14641.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14642.8791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14647.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 72 | 360000 | ACTION | 14654.5167 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14654.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14658.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14660.0167 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14661.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 14663.7861 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14665.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14667.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 14669.7861 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 14673.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 14673.5556 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14675.5556 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14676.5556 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 14680.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14682.0556 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14687.5556 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14688.5556 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14689.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 30.2057 | 151028.4666 | ACTION | 14718.7613 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14719.7613 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14725.2613 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14730.7613 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14732.7613 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14733.7613 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14734.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14739.2613 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14744.7613 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14745.7613 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 14746.7613 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 3 | 15000 | ACTION | 14749.7613 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 11 | 55000 | ACTION | 14760.7613 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14761.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 386.0825 | 2573883.0159 | ACTION | 14761.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14769.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14781.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 43 | 0 | ACTION | 14824.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14828.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 38 | 0 | ACTION | 14866.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14870.3791 | MooredSubInstallation
| Towing Group 1 | Delay | 121 | 806666.6667 | ACTION | 14882.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 14882.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14888.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 128 | 640000 | ACTION | 14888.7613 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14894.3791 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 14894.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 14896.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 12.7753 | 63876.3827 | ACTION | 14901.5366 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14902.5366 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14902.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 20 | 0 | ACTION | 14914.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14917.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14921.3791 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14922.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 14928.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 14935.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 41 | 205000 | ACTION | 14943.5366 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14949.0366 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 15 | 75000 | ACTION | 14964.0366 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14969.5366 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14971.5366 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14972.5366 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14978.0366 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14983.5366 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14984.5366 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 16 | 80000 | ACTION | 15000.5366 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Delay | 91 | 0 | ACTION | 15012.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 12 | 60000 | ACTION | 15012.5366 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15015.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 8.7753 | 43876.3827 | ACTION | 15021.3119 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15039.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 46 | 230000 | ACTION | 15067.3119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15068.3119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15073.8119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15079.3119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15081.3119 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15082.3119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15087.8119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15093.3119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15094.3119 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15111.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 590.0825 | 3933883.0159 | ACTION | 15111.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 19.4694 | 97347.1515 | ACTION | 15113.7813 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15114.7813 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15117.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15119.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15120.2813 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 15124.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15125.7813 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 15126.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15127.7813 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15128.7813 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15131.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15132.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15134.2813 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15135.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15139.7813 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15139.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15140.7813 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5 | 25000 | ACTION | 15145.7813 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15151.8791 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 15152.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 15153.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15157.3791 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 15158.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15160.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15164.3791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 48165.5556 | ACTION | 15165.2967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 29 | 145000 | ACTION | 15174.7813 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15188.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 14.4694 | 72347.1515 | ACTION | 15189.2507 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15190.2507 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15195.7507 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15201.2507 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15203.2507 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15204.2507 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15209.7507 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15215.2507 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15216.2507 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 14.4865 | 72432.5621 | ACTION | 15230.7372 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15231.7372 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15237.2372 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15242.7372 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15244.7372 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15245.7372 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15251.2372 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15256.7372 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15257.7372 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15260.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 580.0825 | 3867216.3492 | ACTION | 15260.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15266.3791 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15268.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 14.4865 | 72432.5621 | ACTION | 15272.2237 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 3 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 15272.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15273.2237 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 15274.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15278.7237 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15280.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15280.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15284.2237 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15284.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15286.2237 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15287.2237 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15288.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15292.7237 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15298.2237 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15299.2237 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15300.3791 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 15300.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15303.8791 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 15306.5719 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15307.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.652 | 53259.7959 | ACTION | 15309.8757 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15310.8757 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15310.8791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 48165.5556 | ACTION | 15313.7967 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15316.3757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15321.8757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15323.8757 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15324.8757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15330.3757 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15334.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15335.8757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15336.8757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.652 | 53259.7959 | ACTION | 15347.5277 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15348.5277 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15354.0277 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15359.5277 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 15363.2971 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 15367.0666 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15406.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 471.0825 | 3140549.6825 | ACTION | 15406.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15412.8791 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 6.1927 | 41284.7619 | ACTION | 15419.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 15421.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15427.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 33333.3333 | ACTION | 15432.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 91 | 606666.6667 | ACTION | 15523.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 100000 | ACTION | 15538.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 15544.0719 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 7.2248 | 48165.5556 | ACTION | 15551.2967 | MooredSubInstallation | [5 empty] | 2 | 1