## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | location | phase_name | max_waveheight | max_windspeed | transit_speed | num_vessels | num_ahts_vessels
0.5 | Export Cable Installation Vessel | Mobilize | 72 | 180000 | ACTION | 0 | ExportCableInstallation
| Onshore Construction | Onshore Construction | 0 | 1665604.3526 | ACTION | 0 | ExportCableInstallation | Landfall
1 | Mooring System Installation Vessel | Mobilize | 168 | 700000 | ACTION | 0 | MooringSystemInstallation
| Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 6 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Delay | 43 | 179166.6667 | ACTION | 43 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 48 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 53 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 61.9117 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 57 | 285000 | ACTION | 63 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Tow Plow | 0.4 | 2000 | ACTION | 63.4 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Pull Winch | 0.4 | 2000 | ACTION | 63.8 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 63.9117 | MooringSystemInstallation
| Export Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 64.8 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 67.9117 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 70.3 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 75.8 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 76.8 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 84.4767 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 89.0417 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 91.0417 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 17 | 85000 | ACTION | 93.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 95.0417 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 111.6067 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 116.1717 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 118.1717 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 122.1717 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 138.7367 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 143.3017 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 145.3017 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 149.3017 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 60 | 300000 | ACTION | 153.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 165.8667 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 170.4317 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 172.4317 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 20 | 83333.3333 | ACTION | 192.4317 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 196.4317 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 212.9967 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 217.5617 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 219.5617 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 223.5617 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 17 | 70833.3333 | ACTION | 240.5617 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 103 | 515000 | ACTION | 256.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 257.1267 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 261.6917 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 270.6034 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 275.6034 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 19 | 95000 | ACTION | 275.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Export Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 276.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 280.6034 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 289.5151 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 291.5151 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 295.5151 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 312.0801 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 316.6451 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 318.6451 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 322.6451 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 339.2101 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 64 | 320000 | ACTION | 340.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 343.7751 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 345.7751 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 349.7751 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 9 | 45000 | ACTION | 349.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 350.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 366.3401 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 370.9051 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 372.9051 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 376.9051 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 186 | 775000 | ACTION | 562.9051 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 228 | 1140000 | ACTION | 578.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 579.4701 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 584.0351 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 586.0351 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 590.0351 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 17 | 85000 | ACTION | 595.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Delay | 46 | 191666.6667 | ACTION | 636.0351 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 652.6001 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 657.1651 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 659.1651 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 39 | 162500 | ACTION | 698.1651 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 702.1651 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 718.7301 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 723.2951 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 130 | 650000 | ACTION | 725.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 732.2068 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 7 | 35000 | ACTION | 732.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 737.2068 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 8 | 40000 | ACTION | 740.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 742.2068 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 751.1185 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 753.1185 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 14 | 70000 | ACTION | 754.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 757.1185 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 773.6835 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 778.2485 | MooringSystemInstallation |  | MooringSystemInstallation
| Substation Assembly Line 1 | Substation Substructure Assembly | 0 | 0 | ACTION | 785.0632 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 789.2485 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 791.2485 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 16 | 66666.6667 | ACTION | 807.2485 | MooringSystemInstallation |  | MooringSystemInstallation
| Substation Assembly Line 1 | Attach Topside | 24 | 0 | ACTION | 809.0632 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay: Waiting on Completed Assembly | 24 | 100000 | ACTION | 809.0632 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 811.2485 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 816.0632 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 5 | 20833.3333 | ACTION | 816.2485 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Tow Substation to Site | 14.8528 | 61886.8056 | ACTION | 830.916 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 832.8135 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 832.916 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 837.3785 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 838.916 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 839.3785 | MooringSystemInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 842.916 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 843.3785 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 850.916 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 851.3785 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.565 | 64854.1667 | ACTION | 866.481 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 867.9435 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 871.046 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 872.5085 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 874.5085 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 878.5085 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 15 | 62500 | ACTION | 886.046 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 888.046 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 139 | 695000 | ACTION | 893.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Connect Mooring Lines | 7 | 29166.6667 | ACTION | 895.046 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 895.0735 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 899.6385 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 901.6385 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 905.6385 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 907.046 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 911.046 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 922.2035 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.565 | 64854.1667 | ACTION | 926.611 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 926.7685 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 33 | 165000 | ACTION | 926.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 928.7685 | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 931.176 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 932.7685 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 933.176 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 2 | 8333.3333 | ACTION | 935.176 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 58 | 241666.6667 | ACTION | 990.7685 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1007.3335 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1011.8985 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 83 | 345833.3333 | ACTION | 1018.176 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1020.8102 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1025.8102 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1030.8102 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 19 | 79166.6667 | ACTION | 1037.176 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1039.7219 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1041.7219 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1045.7219 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 18 | 75000 | ACTION | 1055.176 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 1056.176 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1062.2869 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1066.8519 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1068.176 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 142 | 710000 | ACTION | 1068.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1068.8519 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | ACTION | 1071.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1072.176 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1072.8519 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 69 | 287500 | ACTION | 1141.176 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 70 | 291666.6667 | ACTION | 1142.8519 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.565 | 64854.1667 | ACTION | 1156.741 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1159.4169 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1161.306 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1163.9819 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1165.9819 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1169.9819 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 104 | 520000 | ACTION | 1175.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1183.306 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1186.5469 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 12 | 60000 | ACTION | 1187.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1191.1119 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 9 | 37500 | ACTION | 1192.306 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1193.1119 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1197.1119 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 23 | 95833.3333 | ACTION | 1220.1119 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 37 | 154166.6667 | ACTION | 1229.306 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 3 | 12500 | ACTION | 1232.306 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1236.6769 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1241.2177 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1241.2419 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1243.2419 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1247.2419 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1263.8069 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1268.3719 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 82 | 410000 | ACTION | 1269.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1270.3719 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1274.3719 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1290.9369 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 21.5723 | 107861.6352 | ACTION | 1291.3723 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1295.5019 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 1299.1216 | ExportCableInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1304.4136 | MooringSystemInstallation
| Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 1305.1216 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1309.4136 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 1312.8709 | ExportCableInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1314.4136 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1314.8709 | ExportCableInstallation
| Export Cable Installation Vessel | Raise Cable | 0.5 | 2500 | ACTION | 1315.3709 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1323.3253 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1325.3253 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1329.3253 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1345.8903 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1350.4553 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1352.4553 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1356.4553 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 32 | 133333.3333 | ACTION | 1388.4553 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1405.0203 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1409.5853 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1411.5853 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1415.5853 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1432.1503 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1436.7153 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1438.7153 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1442.7153 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1459.2803 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1463.8453 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1465.8453 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1469.8453 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 28 | 116666.6667 | ACTION | 1497.8453 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1514.4103 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 30 | 125000 | ACTION | 1544.4103 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1548.9753 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1550.9753 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1554.9753 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1571.5403 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1576.1053 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1585.017 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1590.017 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1595.017 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1603.9287 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1605.9287 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1609.9287 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1626.4937 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1631.0587 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1633.0587 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 1654.0587 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1658.0587 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1674.6237 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1679.1887 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1681.1887 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1685.1887 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1701.7537 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1706.3187 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1708.3187 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1712.3187 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1728.8837 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1733.4487 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1735.4487 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1739.4487 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 1746.4487 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1763.0137 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1767.5787 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1769.5787 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1773.5787 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1790.1437 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1794.7087 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1803.6204 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1808.6204 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1813.6204 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1822.5321 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1824.5321 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1828.5321 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 15 | 62500 | ACTION | 1843.5321 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1860.0971 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1864.6621 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1866.6621 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1870.6621 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1887.2271 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1891.7921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1893.7921 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1897.7921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1914.3571 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1918.9221 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1920.9221 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1924.9221 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1941.4871 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1946.0521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1948.0521 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1952.0521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 57 | 237500 | ACTION | 2009.0521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2025.6171 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2030.1821 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 2037.1821 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2039.1821 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2043.1821 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 79 | 329166.6667 | ACTION | 2122.1821 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2138.7471 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2143.3121 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2152.2238 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2157.2238 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2162.2238 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2171.1355 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2173.1355 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2177.1355 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 51 | 212500 | ACTION | 2228.1355 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2244.7005 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2249.2655 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2251.2655 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2255.2655 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 96 | 400000 | ACTION | 2351.2655 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2367.8305 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 44 | 183333.3333 | ACTION | 2411.8305 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2416.3955 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2418.3955 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2422.3955 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2438.9605 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2443.5255 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2445.5255 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2449.5255 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2466.0905 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2470.6555 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2472.6555 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2476.6555 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2493.2205 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2497.7855 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2499.7855 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2503.7855 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2520.3505 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2524.9155 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2533.8272 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2538.8272 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2543.8272 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2552.7389 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2554.7389 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2558.7389 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2575.3039 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2579.8689 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2581.8689 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2585.8689 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2602.4339 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 2609.4339 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2613.9989 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2615.9989 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2619.9989 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2636.5639 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2641.1289 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2643.1289 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2647.1289 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2663.6939 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2668.2589 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2670.2589 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2674.2589 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2690.8239 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2695.3889 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2697.3889 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2701.3889 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2717.9539 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2722.5189 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2731.4306 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2736.4306 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2741.4306 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2750.3423 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2752.3423 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2756.3423 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2772.9073 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2777.4723 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2779.4723 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2783.4723 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2800.0373 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2804.6023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2806.6023 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2810.6023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2827.1673 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2831.7323 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2833.7323 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2837.7323 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2854.2973 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2858.8623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2860.8623 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2864.8623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2881.4273 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2885.9923 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2887.9923 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2891.9923 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 1580 | 7900000 | ACTION | 2895.3709 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2908.5573 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2913.1223 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2922.034 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2927.034 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2932.034 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2940.9457 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2942.9457 | MooringSystemInstallation
| Export Cable Installation Vessel | Splice Cable | 48 | 240000 | ACTION | 2943.3709 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 2944.3709 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2946.9457 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 10 | 50000 | ACTION | 2954.3709 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2963.5107 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2968.0757 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2970.0757 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2974.0757 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2990.6407 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2995.2057 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2997.2057 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3001.2057 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3017.7707 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3022.3357 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3024.3357 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3028.3357 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 90 | 450000 | ACTION | 3044.3709 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3044.9007 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3049.4657 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3051.4657 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3055.4657 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 24 | 120000 | ACTION | 3068.3709 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3072.0307 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3076.5957 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3078.5957 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3082.5957 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 29 | 145000 | ACTION | 3097.3709 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3099.1607 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3103.7257 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3112.6374 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3117.6374 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 22.1326 | 110662.8041 | ACTION | 3119.5035 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 3121.5035 | ExportCableInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3122.6374 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 3127.0035 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3131.5491 | MooringSystemInstallation
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 3132.5035 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3133.5491 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3137.5491 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 3140.2528 | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3154.1141 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3158.6791 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3160.6791 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3164.6791 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3181.2441 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3185.8091 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3187.8091 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3191.8091 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3208.3741 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3212.9391 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3214.9391 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3218.9391 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3235.5041 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3240.0691 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3242.0691 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3246.0691 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 20 | 83333.3333 | ACTION | 3266.0691 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3282.6341 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3287.1991 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3289.1991 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3293.1991 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3309.7641 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3314.3291 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3323.2408 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3328.2408 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3333.2408 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3342.1525 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3344.1525 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3348.1525 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3364.7175 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3369.2825 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3371.2825 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3375.2825 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3391.8475 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3396.4125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3398.4125 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3402.4125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3418.9775 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3423.5425 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3425.5425 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3429.5425 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 3442.5425 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3459.1075 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 3466.1075 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3470.6725 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3472.6725 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3476.6725 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3493.2375 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3497.8025 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3499.8025 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3503.8025 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3520.3675 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3524.9325 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3533.8442 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3538.8442 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3543.8442 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3552.7559 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3554.7559 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3558.7559 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3575.3209 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3579.8859 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3581.8859 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3585.8859 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3602.4509 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3607.0159 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3609.0159 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3613.0159 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3629.5809 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3634.1459 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3636.1459 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3640.1459 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3656.7109 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3661.2759 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3663.2759 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3667.2759 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3683.8409 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3688.4059 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3690.4059 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3694.4059 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3710.9709 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3715.5359 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3724.4476 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3729.4476 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3734.4476 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3743.3593 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3745.3593 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3749.3593 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3765.9243 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3770.4893 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3772.4893 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3776.4893 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3793.0543 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3797.6193 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3799.6193 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3803.6193 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3820.1843 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3824.7493 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3826.7493 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3830.7493 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3847.3143 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3851.8793 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3853.8793 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3857.8793 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3874.4443 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3879.0093 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3881.0093 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3885.0093 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3901.5743 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3906.1393 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3915.051 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3920.051 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3925.051 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3933.9627 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3935.9627 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3939.9627 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3956.5277 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3961.0927 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3963.0927 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3967.0927 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 18 | 75000 | ACTION | 3985.0927 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4001.6577 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4006.2227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4008.2227 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4012.2227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4028.7877 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4033.3527 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4035.3527 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4039.3527 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4055.9177 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4060.4827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4062.4827 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4066.4827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4083.0477 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4087.6127 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4089.6127 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4093.6127 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4110.1777 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4114.7427 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4123.6544 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4128.6544 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4133.6544 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4142.5661 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4144.5661 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4148.5661 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4165.1311 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4169.6961 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4171.6961 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4175.6961 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4192.2611 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4196.8261 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4198.8261 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4202.8261 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4219.3911 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4223.9561 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4225.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 4225.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4225.9561 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4229.9561 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4233.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4245.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4246.5211 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4249.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4251.0861 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4253.0861 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4253.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4257.0861 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4265.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4268.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4272.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4273.6511 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4275.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4278.2161 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4280.2161 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4284.2161 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4299.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4300.7811 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4305.3461 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4314.2578 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4319.2578 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4324.2578 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4333.1695 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4335.1695 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4339.1695 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4355.7345 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4360.2995 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4362.2995 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4366.2995 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4371.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 314.5 | 2096666.6667 | ACTION | 4371.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4377.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4382.8645 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4387.4295 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4389.4295 | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 4390.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 4392.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4393.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 4393.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4393.4295 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4398.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4401.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4409.9945 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4413.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4414.5595 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4416.5595 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4417.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 4418.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4420.5595 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4421.1069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 4424.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4433.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4436.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4437.1245 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 4439.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4440.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4441.6895 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4443.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4443.6895 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4447.6895 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4464.2545 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4467.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4468.8195 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4470.8195 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4474.8195 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4491.3845 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4495.9495 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4504.8612 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4509.8612 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4514.8612 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4523.7729 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4525.7729 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4529.7729 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4539.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 482.5 | 3216666.6667 | ACTION | 4539.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4545.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4546.3379 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4550.9029 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4552.9029 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4556.9029 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 4558.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 4560.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4561.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 4561.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4566.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4569.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4573.4679 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4578.0329 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4580.0329 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4581.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4584.0329 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4585.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 4586.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4589.1069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 4592.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4600.5979 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4601.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4604.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4605.1629 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4607.1629 | MooringSystemInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 4607.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4608.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4611.1629 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4611.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4627.7279 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4632.2929 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4634.2929 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4635.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4638.2929 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4654.8579 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4659.4229 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4661.4229 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4665.4229 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4681.9879 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4686.5529 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4695.4646 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4700.4646 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4705.4646 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4707.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 650.5 | 4336666.6667 | ACTION | 4707.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4713.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4714.3763 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4716.3763 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4720.3763 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 4726.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 4728.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4729.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 4729.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4734.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4736.9413 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4737.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4741.5063 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4743.5063 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4747.5063 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4749.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4753.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 4754.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4757.1069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 4760.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4764.0713 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4768.6363 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4769.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4770.6363 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4772.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4774.6363 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 4775.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4776.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4779.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4791.2013 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4795.7663 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4797.7663 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4801.7663 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4803.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4818.3313 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4822.8963 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4824.8963 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4828.8963 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4845.4613 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4850.0263 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4852.0263 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4856.0263 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4872.5913 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4875.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 436.4162 | 2909441.1111 | ACTION | 4875.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4877.1563 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4881.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4886.068 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4891.068 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 4894.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4896.068 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 4896.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4897.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 4897.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4902.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4904.9797 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4905.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4906.9797 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4910.9797 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4917.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4921.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 4922.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4925.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4927.5447 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 4928.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4932.1097 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4934.1097 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4937.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4938.1097 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4940.6069 | MooredSubInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 4943.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4944.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 4949.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4952.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4954.6747 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4959.2397 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4961.2397 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4965.2397 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4976.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4981.8047 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4986.3697 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4988.3697 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4992.3697 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5008.9347 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5013.4997 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5015.4997 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5019.4997 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5036.0647 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5040.6297 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5042.6297 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5046.6297 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5048.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 441.4162 | 2942774.4444 | ACTION | 5048.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5054.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5063.1947 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5065.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 16.5 | 0 | ACTION | 5065.1069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 5067.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5067.7597 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 5069.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5073.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5075.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5076.6714 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5081.6714 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5085.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5086.6714 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5089.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5093.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5095.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5095.5831 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5097.5831 | MooringSystemInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 5101.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5101.5831 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5105.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5108.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5112.1069 | MooredSubInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 5116.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5118.1481 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 5119.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5122.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5122.7131 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5124.7131 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5128.7131 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5145.2781 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5146.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5149.8431 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5151.8431 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5155.8431 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5172.4081 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5176.9731 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5178.9731 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5182.9731 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5199.5381 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5204.1031 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5206.1031 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5210.1031 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5218.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 443.4162 | 2956107.7778 | ACTION | 5218.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5224.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5226.6681 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5231.2331 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5233.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 14.5 | 0 | ACTION | 5233.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5233.2331 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5237.2331 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 5237.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 5239.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5241.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5245.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5253.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5253.7981 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5257.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5258.3631 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5261.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5265.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5267.2748 | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 5271.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5272.2748 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5273.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5276.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5277.2748 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5280.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5283.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5286.1865 | MooringSystemInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 5286.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5288.1865 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5292.1865 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5307.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5308.7515 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5313.3165 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5315.3165 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5319.3165 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5335.8815 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5340.4465 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5342.4465 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5346.4465 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5363.0115 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5367.5765 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5369.5765 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5373.5765 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5379.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 436.4162 | 2909441.1111 | ACTION | 5379.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5385.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5390.1415 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5394.7065 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5396.7065 | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 5398.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 5400.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5400.7065 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5401.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 5401.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5406.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5409.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5417.2715 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5421.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5421.8365 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5423.8365 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5425.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5426.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5427.8365 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5429.1069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 5432.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5441.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5444.4015 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5444.6069 | MooredSubInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 5447.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5448.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5448.9665 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5451.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5457.8782 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5462.8782 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5467.8782 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5475.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5476.7899 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5478.7899 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5482.7899 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5499.3549 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5503.9199 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5505.9199 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5509.9199 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5526.4849 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5531.0499 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5533.0499 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5537.0499 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5547.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 431.4162 | 2876107.7778 | ACTION | 5547.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5553.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5553.6149 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5558.1799 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5560.1799 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5564.1799 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 5566.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 5568.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5569.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 5569.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5574.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5577.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5580.7449 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5585.3099 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5587.3099 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5589.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5591.3099 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5593.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5594.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5597.1069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 5600.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5607.8749 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5609.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5612.4399 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5612.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5614.4399 | MooringSystemInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 5615.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5616.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5618.4399 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5619.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5635.0049 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5639.5699 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5643.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5648.4816 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5653.4816 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5658.4816 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5667.3933 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5669.3933 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5673.3933 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5689.9583 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5694.5233 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5696.5233 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5700.5233 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5715.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 429.4162 | 2862774.4444 | ACTION | 5715.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5717.0883 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5721.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5721.6533 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5723.6533 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5727.6533 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 5734.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 5736.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5737.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 5737.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5742.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5744.2183 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5745.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5748.7833 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5750.7833 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5754.7833 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5757.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5761.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5762.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5765.1069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 5768.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5771.3483 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5775.9133 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5777.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5777.9133 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5780.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5781.9133 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 5783.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5784.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5787.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5798.4783 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5803.0433 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5805.0433 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5809.0433 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5811.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5825.6083 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5830.1733 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5839.085 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5844.085 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5849.085 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5857.9967 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5859.9967 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5863.9967 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5880.5617 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5883.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 436.4162 | 2909441.1111 | ACTION | 5883.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5885.1267 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5887.1267 | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5889.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5891.1267 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 5902.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 5904.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5905.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 5905.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5907.6917 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5910.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5912.2567 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5913.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5914.2567 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5918.2567 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5925.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5929.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5930.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5933.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5934.8217 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 5936.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5939.3867 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5941.3867 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5945.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5945.3867 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5948.6069 | MooredSubInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 5951.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5952.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5955.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5961.9517 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5966.5167 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5968.5167 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5972.5167 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5979.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5989.0817 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5993.6467 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5995.6467 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5999.6467 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6016.2117 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6020.7767 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6029.6884 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6034.6884 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6039.6884 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6048.6001 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6050.6001 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6051.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 436.4162 | 2909441.1111 | ACTION | 6051.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6054.6001 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6057.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 6070.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6071.1651 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 6072.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6073.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 6073.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6075.7301 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6077.7301 | MooringSystemInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6078.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6081.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6081.7301 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6093.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6097.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6098.2951 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6098.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6101.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6102.8601 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 6104.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6104.8601 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6108.8601 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6113.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6116.6069 | MooredSubInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 6119.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6125.4251 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 6128.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6129.9901 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6131.9901 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6132.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6135.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6135.9901 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6152.5551 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6157.1201 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6159.1201 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6159.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6163.1201 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6179.6851 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6184.2501 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6186.2501 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6190.2501 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6206.8151 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6211.3801 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6220.2918 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6225.2918 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6230.2918 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6231.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 448.4162 | 2989441.1111 | ACTION | 6231.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 2 | 13333.3333 | ACTION | 6233.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6239.2035 | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6239.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6241.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 9.5 | 0 | ACTION | 6241.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6241.2035 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6245.2035 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6249.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 6252.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 6254.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6260.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6261.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6261.7685 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6265.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6269.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6281.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6284.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6288.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 29 | 120833.3333 | ACTION | 6290.7685 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6291.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6295.3335 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Delay | 35 | 233333.3333 | ACTION | 6295.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6297.3335 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6301.3335 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 19 | 126666.6667 | ACTION | 6314.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6315.6069 | MooredSubInstallation
| Towing Group 3 | Delay | 3 | 20000 | ACTION | 6317.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6317.8985 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 6666.6667 | ACTION | 6318.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6322.4635 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 6324.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6324.4635 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6328.4635 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 6339.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6345.0285 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6349.5935 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6351.5935 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6355.5935 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6372.1585 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6376.7235 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6378.7235 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6382.7235 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6387.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 436.4162 | 2909441.1111 | ACTION | 6387.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6393.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6399.2885 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6403.8535 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6405.8535 | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 6406.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 6408.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6409.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 6409.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6409.8535 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6414.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6417.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6426.4185 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6429.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6430.9835 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6433.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6434.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6437.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6439.8952 | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 6440.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6444.8952 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6449.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6449.8952 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6452.6069 | MooredSubInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 6455.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6456.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6458.8069 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6459.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6460.8069 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6464.8069 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6481.3719 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6483.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6485.9369 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6487.9369 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6491.9369 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6508.5019 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6513.0669 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6515.0669 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6519.0669 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6535.6319 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6540.1969 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6542.1969 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6546.1969 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6555.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 436.4162 | 2909441.1111 | ACTION | 6555.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6561.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6562.7619 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6567.3269 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6569.3269 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6573.3269 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 6574.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 6576.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6577.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 6577.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6582.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6585.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6589.8919 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6594.4569 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6596.4569 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6597.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6600.4569 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6601.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6602.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6605.1069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 6608.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6617.0219 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6617.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6620.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6621.5869 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 6623.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6624.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6627.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6630.4986 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6635.4986 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6640.4986 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6649.4103 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6651.4103 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6651.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6655.4103 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6671.9753 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6676.5403 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6678.5403 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6682.5403 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6699.1053 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6703.6703 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6705.6703 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6709.6703 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6723.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 384.4162 | 2562774.4444 | ACTION | 6723.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6745.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 6745.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 43 | 179166.6667 | ACTION | 6752.6703 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6753.1069 | MooredSubInstallation
| Towing Group 3 | Delay | 34 | 226666.6667 | ACTION | 6757.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6763.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6765.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6769.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6769.2353 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6773.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6773.8003 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6775.8003 | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 6776.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 6778.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6779.8003 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6785.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6788.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6792.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6795.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6796.3653 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6800.9303 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6802.9303 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6806.9303 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6819.6069 | MooredSubInstallation
| Towing Group 3 | Delay | 44 | 293333.3333 | ACTION | 6822.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6823.4953 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6828.0603 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6828.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6830.0603 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6834.0603 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 10 | 66666.6667 | ACTION | 6838.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6850.6253 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6855.1903 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6864.102 | MooringSystemInstallation
| Towing Group 3 | Delay | 28 | 186666.6667 | ACTION | 6866.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6869.102 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6874.102 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 10 | 66666.6667 | ACTION | 6876.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 6882.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6883.0137 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6885.0137 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6889.0137 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6891.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 436.4162 | 2909441.1111 | ACTION | 6891.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 6897.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6897.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6905.5787 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6910.1437 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 6910.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6912.1437 | MooringSystemInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 6912.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6913.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 6913.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6916.1437 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6918.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6921.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6932.7087 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6933.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6937.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6937.2737 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 19 | 126666.6667 | ACTION | 6937.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6939.2737 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6941.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6943.2737 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 10 | 0 | ACTION | 6951.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 6956.2737 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6963.1069 | MooredSubInstallation
| Towing Group 1 | Delay | 27 | 180000 | ACTION | 6964.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 6666.6667 | ACTION | 6965.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6966.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6970.1069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 6971.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6972.8387 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 6986.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 34 | 0 | ACTION | 7004.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7007.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7031.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 31 | 0 | ACTION | 7062.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7081.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 139 | 579166.6667 | ACTION | 7111.8387 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7116.4037 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7118.4037 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7122.4037 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7134.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 511.4162 | 3409441.1111 | ACTION | 7134.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7138.9687 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7140.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7142.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7143.5337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7145.5337 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7149.5337 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 7153.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7154.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 7155.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7158.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7161.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7162.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7166.0987 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7170.6637 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7172.6637 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7174.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7176.6637 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7178.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7181.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7181.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7185.1069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 7187.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7193.2287 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7197.7937 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 7202.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 7206.7054 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7209.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7211.7054 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7216.7054 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 7225.6171 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7227.6171 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7231.6171 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7248.1821 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7249.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7252.7471 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7254.7471 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7258.7471 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7275.3121 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7279.8771 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7281.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 383.9162 | 2559441.1111 | ACTION | 7281.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7281.8771 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7285.8771 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7287.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7289.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 7299.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7301.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 7301.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7302.4421 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7305.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7307.0071 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7309.0071 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7309.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7313.0071 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7321.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7324.6069 | MooredSubInstallation
| Towing Group 3 | Delay | 24 | 160000 | ACTION | 7325.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7328.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7329.5721 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7331.6069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7331.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7334.1371 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 20000 | ACTION | 7334.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7336.1371 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7355.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 7357.1371 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7361.1371 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Delay | 28 | 186666.6667 | ACTION | 7362.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7377.7021 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 113333.3333 | ACTION | 7379.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7382.2671 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7384.2671 | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 7385.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7388.2671 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 7400.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7404.8321 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7409.3971 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7417.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 7418.3088 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7423.3088 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7427.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 441.4162 | 2942774.4444 | ACTION | 7427.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7428.3088 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7433.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7435.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 7437.2205 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7439.2205 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7443.2205 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 7446.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7447.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 7448.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7451.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7454.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7455.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 20000 | ACTION | 7457.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7459.7855 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7464.3505 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7466.3505 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 46 | 0 | ACTION | 7501.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 42 | 175000 | ACTION | 7508.3505 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7512.3505 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7513.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7517.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7520.6069 | MooredSubInstallation
| Towing Group 1 | Delay | 64 | 426666.6667 | ACTION | 7521.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7524.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7528.9155 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7533.4805 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7535.4805 | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 113333.3333 | ACTION | 7538.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7539.4805 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 7544.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7548.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7556.0455 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 7559.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7560.6105 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7562.6105 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7566.6105 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7583.1755 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7585.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 88 | 0 | ACTION | 7636.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 80 | 333333.3333 | ACTION | 7663.1755 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7667.7405 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7669.7405 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7673.7405 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7690.3055 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7694.8705 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7696.8705 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7700.8705 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7708.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 505.9162 | 3372774.4444 | ACTION | 7708.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7714.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7716.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7717.4355 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7722.0005 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 7726.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7728.1069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 7728.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 7730.9122 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7732.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7735.9122 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 6 | 25000 | ACTION | 7741.9122 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7753.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 25 | 0 | ACTION | 7757.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7761.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 31 | 129166.6667 | ACTION | 7772.9122 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7773.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 2.9117 | 12132.0833 | ACTION | 7775.8239 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7776.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 48 | 320000 | ACTION | 7776.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7777.8239 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7780.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7781.8239 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7782.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 33333.3333 | ACTION | 7787.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 53 | 0 | ACTION | 7833.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 54 | 225000 | ACTION | 7835.8239 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7836.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7852.3889 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7856.9539 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7858.9539 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7860.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7862.9539 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Delay | 76 | 506666.6667 | ACTION | 7863.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 20000 | ACTION | 7866.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7879.5189 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7884.0839 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7886.0839 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7890.0839 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7921.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 96 | 0 | ACTION | 7956.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8028.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 627.9162 | 4186107.7778 | ACTION | 8028.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8036.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8048.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8052.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8056.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8068.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8072.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8075.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 8078.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8082.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8089.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 203 | 845833.3333 | ACTION | 8093.0839 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Delay | 68 | 453333.3333 | ACTION | 8096.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 230 | 1533333.3333 | ACTION | 8096.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8102.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8106.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 80000 | ACTION | 8108.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 8109.6489 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 8114.2139 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 8114.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 8115.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 8117.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8123.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 6666.6667 | ACTION | 8124.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 8129.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 25 | 166666.6667 | ACTION | 8149.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 86666.6667 | ACTION | 8162.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 2 | 13333.3333 | ACTION | 8164.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 40000 | ACTION | 8170.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 8176.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8178.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 618.9162 | 4126107.7778 | ACTION | 8178.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8184.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8186.1069 | MooredSubInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 8191.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 8196.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8198.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 8198.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8202.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8204.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8206.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8218.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8221.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 8224.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8225.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8228.6069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 8230.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 8245.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8252.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8257.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8324.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 194.9162 | 1299441.1111 | ACTION | 8324.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8330.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8332.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 8343.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8344.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 8345.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8348.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8351.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8352.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8364.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 100000 | ACTION | 8366.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 20 | 0 | ACTION | 8384.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 20 | 133333.3333 | ACTION | 8386.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8388.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 33333.3333 | ACTION | 8391.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8391.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8395.1069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 8397.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 8412.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8419.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8425.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 43 | 0 | ACTION | 8462.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8534.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 342.9162 | 2286107.7778 | ACTION | 8534.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8540.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8542.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 8552.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8554.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 8554.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8558.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8560.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8562.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8574.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 8580.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 9 | 0 | ACTION | 8583.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8586.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 8586.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8590.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8593.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 8593.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8596.6069 | MooredSubInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 8601.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8620.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8692.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 446.9162 | 2979441.1111 | ACTION | 8692.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8698.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8700.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8712.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 8717.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8721.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8725.6069 | MooredSubInstallation
| Towing Group 1 | Delay | 38 | 253333.3333 | ACTION | 8736.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8737.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8741.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8744.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8748.1069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 8749.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 8751.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8757.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8761.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8772.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 8777.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 8783.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 8798.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8844.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 431.9162 | 2879441.1111 | ACTION | 8844.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8852.1069 | MooredSubInstallation
| Towing Group 2 | Delay | 20 | 133333.3333 | ACTION | 8864.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8864.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8868.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8870.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8872.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 8884.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8896.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8899.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 33 | 220000 | ACTION | 8903.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8903.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8906.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 8915.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 8917.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 18 | 0 | ACTION | 8924.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8929.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8948.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 67 | 446666.6667 | ACTION | 8984.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8990.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 80000 | ACTION | 9002.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 68 | 0 | ACTION | 9016.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 58 | 386666.6667 | ACTION | 9060.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 53333.3333 | ACTION | 9068.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 9074.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9088.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 486.9162 | 3246107.7778 | ACTION | 9088.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 9089.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9096.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9097.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9108.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9112.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 9126.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9130.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9142.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9146.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 67 | 0 | ACTION | 9213.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9216.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9220.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 34 | 0 | ACTION | 9254.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9265.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9278.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 28 | 0 | ACTION | 9306.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9378.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 579.9162 | 3866107.7778 | ACTION | 9378.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9386.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9398.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 9401.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9405.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9409.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9421.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9433.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 38 | 0 | ACTION | 9459.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9462.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9466.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 9469.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9472.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9496.6069 | MooredSubInstallation
| Towing Group 3 | Delay | 417 | 2780000 | ACTION | 9505.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 128 | 853333.3333 | ACTION | 9506.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9511.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9512.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 9524.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 9524.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 9526.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 9526.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9532.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9532.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9552.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9552.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 9558.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 9558.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9568.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 478.9162 | 3192774.4444 | ACTION | 9568.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 9573.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 9573.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9574.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9576.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 9587.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9588.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 9589.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9592.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9595.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9596.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9601.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9608.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9612.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9615.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9615.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9619.1069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 9621.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 9636.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9643.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9715.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 141.9162 | 946107.7778 | ACTION | 9715.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9721.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9723.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 9733.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9735.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 9735.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9739.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9741.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9743.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9755.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9758.6069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9761.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9762.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9765.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 9767.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9769.1069 | MooredSubInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 9782.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9789.6069 | MooredSubInstallation
0.5 | Array Cable Installation Vessel | Mobilize | 72 | 180000 | ACTION | 9805.6489 | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 9811.6489 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 9819.3982 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 9821.3982 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9822.3982 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9861.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 287.9162 | 1919441.1111 | ACTION | 9861.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9867.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9869.6069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 9880.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9881.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 9882.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9885.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9888.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9889.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 80000 | ACTION | 9900.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9937.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 51 | 0 | ACTION | 9940.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9952.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9956.1069 | MooredSubInstallation
| Towing Group 1 | Delay | 57 | 380000 | ACTION | 9957.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9959.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9963.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 142 | 710000 | ACTION | 9964.3982 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 53333.3333 | ACTION | 9965.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9969.8982 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 9971.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9975.3982 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 9976.3982 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 9986.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 9986.8166 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9987.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 9987.8166 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 9993.3166 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 9998.8166 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10000.8166 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10001.8166 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10007.3166 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10012.8166 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10013.8166 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | ACTION | 10016.8166 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 24 | 120000 | ACTION | 10040.8166 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 7.4185 | 37092.2749 | ACTION | 10048.2351 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10049.2351 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10059.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 422.9162 | 2819441.1111 | ACTION | 10059.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10067.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10079.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10083.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10087.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 10095.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10105.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10107.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10110.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10114.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10117.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10141.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 93 | 620000 | ACTION | 10152.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10158.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 35 | 0 | ACTION | 10176.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 79 | 526666.6667 | ACTION | 10237.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 195 | 975000 | ACTION | 10244.2351 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10248.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 465.9162 | 3106107.7778 | ACTION | 10248.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10249.7351 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 10249.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 10251.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10254.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10255.2351 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10256.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10257.2351 | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10257.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10258.2351 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10263.7351 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 10267.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10268.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10269.2351 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 10269.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10270.2351 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10272.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10273.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10275.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10276.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10277.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 10280.6535 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10281.6535 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 10283.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10287.1535 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10288.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10292.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10292.6535 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10294.6535 | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10295.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10295.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10295.6535 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 10298.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10299.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10301.1535 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 10301.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10306.6535 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10307.6535 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 10316.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 10318.072 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10319.072 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10323.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10324.572 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10330.072 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10332.072 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10333.072 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10338.572 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10344.072 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10345.072 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 6 | 30000 | ACTION | 10351.072 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Delay | 35 | 0 | ACTION | 10358.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 42 | 210000 | ACTION | 10393.072 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 4.4185 | 22092.2749 | ACTION | 10397.4904 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10398.4904 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10403.9904 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10409.4904 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10411.4904 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10412.4904 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10417.9904 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10423.4904 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10424.4904 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10430.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 443.9162 | 2959441.1111 | ACTION | 10430.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 10434.9089 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10435.9089 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10436.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10438.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10441.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10441.4089 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 10448.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10450.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 10450.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10454.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10456.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10458.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10470.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 10471.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10474.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 19 | 126666.6667 | ACTION | 10475.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 10490.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10494.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10497.6069 | MooredSubInstallation
| Towing Group 1 | Delay | 33 | 220000 | ACTION | 10508.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 6666.6667 | ACTION | 10509.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 10515.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10521.6069 | MooredSubInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 10530.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 112 | 560000 | ACTION | 10553.4089 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10558.9089 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 16 | 80000 | ACTION | 10574.9089 | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10576.9089 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10577.9089 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10583.4089 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10588.9089 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10589.9089 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10593.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 294.9162 | 1966107.7778 | ACTION | 10593.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10599.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 10600.3274 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10601.3274 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10601.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10606.8274 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10609.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10612.3274 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 10612.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10613.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10614.3274 | ArrayCableInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 10614.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10615.3274 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10617.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10620.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10620.8274 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10621.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10626.3274 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10627.3274 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10633.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10637.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 10637.7458 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10638.7458 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10640.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10640.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10644.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10644.2458 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 10646.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10649.7458 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10651.7458 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10652.7458 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10658.2458 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 10661.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10663.7458 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10664.7458 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10668.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 10675.1643 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10676.1643 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10681.6643 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10687.1643 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10740.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 423.9162 | 2826107.7778 | ACTION | 10740.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10746.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10748.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 10758.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10760.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 10760.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 75 | 375000 | ACTION | 10762.1643 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10764.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10764.1643 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10765.1643 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10766.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10768.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10770.6643 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10776.1643 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10777.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10777.1643 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10780.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 10785.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10786.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 10787.5827 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10788.5827 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10788.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10792.1069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 10792.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10794.0827 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10795.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10799.5827 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10801.5827 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10802.5827 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 10807.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10819.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 43 | 215000 | ACTION | 10845.5827 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10851.0827 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10856.5827 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10857.5827 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 10868.0012 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10869.0012 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10874.5012 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10880.0012 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10882.0012 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10883.0012 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10888.5012 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10891.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 360.9162 | 2406107.7778 | ACTION | 10891.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10894.0012 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10895.0012 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10897.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10899.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 10905.4196 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10906.4196 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 10910.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10911.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10911.9196 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 10912.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10915.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10917.4196 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10918.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10919.4196 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10919.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10920.4196 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10925.9196 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10931.4196 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10931.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10932.4196 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10935.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10938.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10938.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10942.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 10942.8381 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10943.8381 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 10944.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10945.1069 | MooredSubInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 10959.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10966.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 28 | 140000 | ACTION | 10971.8381 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10977.3381 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10982.8381 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10984.8381 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10985.8381 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10991.3381 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10996.8381 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10997.8381 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11008.2565 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11009.2565 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11014.7565 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11020.2565 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11022.2565 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11023.2565 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11028.7565 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11038.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 376.9162 | 2512774.4444 | ACTION | 11038.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 2 | 13333.3333 | ACTION | 11040.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11046.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11046.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11058.1069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 11058.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 11060.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11062.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11066.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11066.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 20000 | ACTION | 11069.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 41 | 0 | ACTION | 11107.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11113.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11119.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11122.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 56 | 373333.3333 | ACTION | 11125.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11126.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11129.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 104 | 520000 | ACTION | 11132.7565 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11138.2565 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11139.2565 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 113333.3333 | ACTION | 11142.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 2 | 13333.3333 | ACTION | 11144.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 7 | 35000 | ACTION | 11146.2565 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Delay | 20 | 0 | ACTION | 11149.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11173.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 11175.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11247.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 439.9162 | 2932774.4444 | ACTION | 11247.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11255.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11267.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11271.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11275.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11281.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11287.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 24 | 0 | ACTION | 11311.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11315.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11318.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11322.1069 | MooredSubInstallation
| Towing Group 3 | Delay | 75 | 500000 | ACTION | 11322.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 178 | 1186666.6667 | ACTION | 11322.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 4 | 26666.6667 | ACTION | 11326.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 182 | 910000 | ACTION | 11328.2565 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11328.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 3.4185 | 17092.2749 | ACTION | 11331.675 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11332.675 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11338.175 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 11341.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 11341.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 11343.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11343.675 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11345.675 | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11346.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11346.675 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11349.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11352.175 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11369.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 19 | 95000 | ACTION | 11371.175 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 11375.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11376.675 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11377.675 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11388.0935 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11389.0935 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 11390.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11418.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 458.9162 | 3059441.1111 | ACTION | 11418.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11426.1069 | MooredSubInstallation
| Towing Group 1 | Delay | 9 | 60000 | ACTION | 11427.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11433.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11438.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11442.1069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 11445.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11446.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 11447.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11449.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11453.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 66 | 330000 | ACTION | 11455.0935 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11458.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11460.5935 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11461.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11465.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11466.0935 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11468.0935 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11468.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11469.0935 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11473.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11474.5935 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 11479.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11492.6069 | MooredSubInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 11494.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 46 | 230000 | ACTION | 11520.5935 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11526.0935 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11527.0935 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11537.5119 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11538.5119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11544.0119 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11564.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 222.9162 | 1486107.7778 | ACTION | 11564.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11570.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11572.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 11583.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11584.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 11585.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 44 | 220000 | ACTION | 11588.0119 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11588.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11591.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11592.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11593.5119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11595.5119 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11596.5119 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11604.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 93333.3333 | ACTION | 11605.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11608.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11611.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11615.1069 | MooredSubInstallation
| Towing Group 2 | Delay | 10 | 66666.6667 | ACTION | 11615.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11617.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 40000 | ACTION | 11621.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 11627.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 42 | 210000 | ACTION | 11638.5119 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11639.1069 | MooredSubInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 11642.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11644.0119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 22 | 110000 | ACTION | 11666.0119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11671.5119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11672.5119 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11682.9304 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11683.9304 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11689.4304 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11694.9304 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11696.9304 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11697.9304 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11703.4304 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11708.9304 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11709.9304 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11711.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 320.9162 | 2139441.1111 | ACTION | 11711.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11717.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11719.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11720.3488 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11721.3488 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11726.8488 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 11729.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11731.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 11731.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11732.3488 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11734.3488 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11735.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11735.3488 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11737.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11739.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11740.8488 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11746.3488 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11747.3488 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11751.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11754.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11757.7673 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11757.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11758.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11758.7673 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11761.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 11763.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11764.2673 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11769.7673 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11771.7673 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11772.7673 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11778.2673 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 11778.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11783.7673 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11784.7673 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11785.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11785.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11795.1857 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11796.1857 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11801.6857 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11807.1857 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11809.1857 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11810.1857 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11815.6857 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11821.1857 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11822.1857 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11832.6042 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11833.6042 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11839.1042 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11844.6042 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11846.6042 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11847.6042 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11853.1042 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11857.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 362.9162 | 2419441.1111 | ACTION | 11857.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11858.6042 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11859.6042 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11863.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11865.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11870.0226 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11871.0226 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 11876.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11877.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 11878.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11881.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11885.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11897.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11901.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11904.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11908.1069 | MooredSubInstallation
| Towing Group 1 | Delay | 30 | 200000 | ACTION | 11908.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11914.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 10 | 66666.6667 | ACTION | 11924.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 6 | 40000 | ACTION | 11930.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11932.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 10 | 66666.6667 | ACTION | 11940.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 11946.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 78 | 390000 | ACTION | 11949.0226 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11953.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11954.5226 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11960.0226 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 11961.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11962.0226 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11963.0226 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11968.5226 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11974.0226 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11975.0226 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11985.4411 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11986.4411 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11991.9411 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11997.4411 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11999.4411 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12000.4411 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12004.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 361.9162 | 2412774.4444 | ACTION | 12004.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12005.9411 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12010.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12011.4411 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12012.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12012.4411 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 12022.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12022.8595 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12023.8595 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12024.1069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 12024.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12028.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12029.3595 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12030.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12032.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12034.8595 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12036.8595 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12037.8595 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12043.3595 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12044.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12047.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12048.8595 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12049.8595 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12050.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12051.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12054.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 12056.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12060.278 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12061.278 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12066.778 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 12071.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12072.278 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12074.278 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12075.278 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12078.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12080.778 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12086.278 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12087.278 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12097.6965 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12098.6965 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12104.1965 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12109.6965 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12111.6965 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12112.6965 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12118.1965 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12121.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12123.6965 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12124.6965 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12135.1149 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12136.1149 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12141.6149 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12147.1149 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12149.1149 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12150.1149 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12150.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 12150.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12155.6149 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12156.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12158.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12161.1149 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12162.1149 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 12169.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12170.6069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 12171.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12172.5334 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12173.5334 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12174.6069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12177.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12178.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12190.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12194.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12197.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12197.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12201.1069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 12203.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 30 | 150000 | ACTION | 12203.5334 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12209.0334 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12214.5334 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12216.5334 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12217.5334 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 12218.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12225.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 16 | 80000 | ACTION | 12233.5334 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12239.0334 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12244.5334 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12245.5334 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12255.9518 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12256.9518 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12262.4518 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12267.9518 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12269.9518 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12270.9518 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12276.4518 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12281.9518 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12282.9518 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12289.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12293.3703 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12294.3703 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12297.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 335.9162 | 2239441.1111 | ACTION | 12297.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12299.8703 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12303.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12305.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12305.3703 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 12315.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12317.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 12317.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 3 | 20000 | ACTION | 12320.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12321.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12325.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12326.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12337.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12340.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12344.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12346.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12347.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 43 | 215000 | ACTION | 12348.3703 | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12350.3703 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12351.3703 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 12352.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12356.8703 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12362.3703 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12363.3703 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 12367.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12371.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12373.7887 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12374.7887 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12380.2887 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12385.7887 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12387.7887 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12388.7887 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12394.2887 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12399.7887 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12400.7887 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12411.2072 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12412.2072 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12417.7072 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12423.2072 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12425.2072 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12426.2072 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12431.7072 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12437.2072 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12438.2072 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12443.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 12443.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12449.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12451.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12457.1069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 12462.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12463.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 12464.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12467.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12470.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12471.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 36.1234 | 180617.0334 | ACTION | 12474.3306 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12475.3306 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12480.8306 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12483.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12486.3306 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12487.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12490.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12490.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 12494.0799 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12494.1069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 12496.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 12501.8292 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 12507.8292 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 12511.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12518.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 31 | 155000 | ACTION | 12538.8292 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 12546.5785 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12548.5785 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12549.5785 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12555.0785 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12560.5785 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12561.5785 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 10000 | ACTION | 12563.5785 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 11 | 55000 | ACTION | 12574.5785 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12590.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 12590.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12596.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12598.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 34.1234 | 170617.0334 | ACTION | 12608.7019 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 12608.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12610.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 12610.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 5 | 25000 | ACTION | 12613.7019 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12614.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12614.7019 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12616.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12618.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12620.2019 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12625.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12625.7019 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12627.7019 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12628.7019 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12630.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12633.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12634.2019 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12636.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12637.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12639.7019 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12640.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12640.7019 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 12642.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12651.1204 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12652.1204 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12657.6204 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 12657.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12663.1204 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12664.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12665.1204 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12666.1204 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12671.6204 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12677.1204 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12678.1204 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12688.5388 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12689.5388 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12695.0388 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12700.5388 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12702.5388 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12703.5388 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12709.0388 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12714.5388 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12715.5388 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12725.9573 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12726.9573 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12732.4573 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12736.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 368.9162 | 2459441.1111 | ACTION | 12736.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12737.9573 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12739.9573 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12740.9573 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12742.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12744.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12756.6069 | MooredSubInstallation
| Towing Group 1 | Delay | 15 | 100000 | ACTION | 12757.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12760.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12764.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 29 | 145000 | ACTION | 12769.9573 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 12770.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 12772.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12775.4573 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12776.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12778.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12780.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12780.9573 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12781.9573 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12783.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12787.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12792.3757 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12793.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12793.3757 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12798.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 12804.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12811.1069 | MooredSubInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 12819.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 26 | 130000 | ACTION | 12819.3757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12824.8757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12830.3757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12832.3757 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12833.3757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12838.8757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12844.3757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12845.3757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12855.7942 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12856.7942 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12862.2942 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12867.7942 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12869.7942 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12870.7942 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12876.2942 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12881.7942 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12882.7942 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12883.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 12883.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12889.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12891.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12893.2126 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12894.2126 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12899.7126 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 12901.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12903.1069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 12903.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12905.2126 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12907.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12907.2126 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12908.2126 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12909.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12911.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12913.7126 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12919.2126 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12920.2126 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12923.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12926.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12929.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12930.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12930.6311 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12931.6311 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12933.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 12935.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12937.1311 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12942.6311 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12944.6311 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12945.6311 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 12950.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12951.1311 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12956.6311 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12957.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12957.6311 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12961.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12968.0496 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12969.0496 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 36 | 180000 | ACTION | 13005.0496 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13010.5496 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13016.0496 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13018.0496 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13019.0496 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13024.5496 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13029.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 13029.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13030.0496 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13031.0496 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13035.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13037.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13041.468 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13042.468 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13047.968 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 13048.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13049.6069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 13050.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13053.468 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13053.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13055.468 | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13056.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13056.468 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13057.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13061.968 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13067.468 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13068.468 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13069.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13073.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13076.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13076.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13078.8865 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13079.8865 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13080.1069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 13082.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13085.3865 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13090.8865 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13092.8865 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13093.8865 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 13097.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13099.3865 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13104.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13104.8865 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13105.8865 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13116.3049 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13117.3049 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13122.8049 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13128.3049 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13129.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13130.3049 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13131.3049 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13136.8049 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 27 | 135000 | ACTION | 13163.8049 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13169.3049 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13170.3049 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13176.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 356.9162 | 2379441.1111 | ACTION | 13176.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13180.7234 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13181.7234 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13182.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13184.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13187.2234 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13192.7234 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13194.7234 | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 13194.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13195.7234 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13196.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 13196.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13200.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13201.2234 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13202.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13204.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13206.7234 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13207.7234 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13216.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13218.1418 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13219.1418 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13219.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13222.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13223.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13224.6418 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13226.6069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 13228.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13230.1418 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13232.1418 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13233.1418 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13238.6418 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 13243.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13244.1418 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13245.1418 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13250.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13255.5603 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13256.5603 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13262.0603 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13267.5603 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13269.5603 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13270.5603 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13276.0603 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13281.5603 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13282.5603 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13292.9787 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13293.9787 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13297.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13299.4787 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13304.9787 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13306.9787 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13307.9787 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13313.4787 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13318.9787 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13319.9787 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13322.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 13322.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13328.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13330.3972 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13330.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13331.3972 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13336.8972 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 13341.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13342.3972 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13342.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 13343.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13344.3972 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13345.3972 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13346.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13349.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13350.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13350.8972 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13356.3972 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13357.3972 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13362.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13366.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13367.8156 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13368.8156 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13369.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 13375.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 13377.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13380.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13384.1069 | MooredSubInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 13390.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13408.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 64 | 320000 | ACTION | 13432.8156 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13438.3156 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13443.8156 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13445.8156 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13446.8156 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13452.3156 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13457.8156 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13458.8156 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13465.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13469.2341 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13470.2341 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13475.7341 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13480.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 382.9162 | 2552774.4444 | ACTION | 13480.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13481.2341 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13483.2341 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13484.2341 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13486.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13488.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13489.7341 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13495.2341 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13496.2341 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 13498.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13500.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 13500.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13504.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13506.6526 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13506.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13507.6526 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13508.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13513.1526 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13518.6526 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13520.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13520.6526 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13521.6526 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13523.6069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13526.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13527.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13527.1526 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13530.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13532.6526 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 13532.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13533.6526 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13544.071 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13545.071 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 13547.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13550.571 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13554.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13556.071 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13558.071 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13559.071 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13564.571 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 7 | 35000 | ACTION | 13571.571 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13577.071 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13578.071 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13588.4895 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13589.4895 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 10 | 50000 | ACTION | 13599.4895 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13604.9895 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13610.4895 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13612.4895 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13613.4895 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13618.9895 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13624.4895 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13625.4895 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13626.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 382.9162 | 2552774.4444 | ACTION | 13626.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13632.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13633.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13634.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13635.9079 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13636.9079 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13642.4079 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 13645.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13646.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 13647.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13647.9079 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13649.9079 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13650.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13650.9079 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13653.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13654.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13656.4079 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13661.9079 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13662.9079 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13666.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13670.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13673.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13673.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13677.1069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 13679.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 30.6332 | 153165.8973 | ACTION | 13693.5411 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 13694.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13694.5411 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13700.0411 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13701.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13705.5411 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 13713.2904 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 13719.2904 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 13727.0397 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13729.0397 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13730.0397 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13735.5397 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13741.0397 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13742.0397 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 30.6332 | 153165.8973 | ACTION | 13772.6729 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13773.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 382.9162 | 2552774.4444 | ACTION | 13773.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13773.6729 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13779.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13779.1729 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13781.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13784.6729 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13786.6729 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13787.6729 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 13791.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13793.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13793.1729 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 13793.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13797.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13798.6729 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13799.6729 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13799.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13801.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13801.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13813.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13816.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13819.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13820.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13823.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 25.2028 | 126013.8134 | ACTION | 13824.8757 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 13825.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13825.8757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13831.3757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13836.8757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13838.8757 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13839.8757 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 13840.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13845.3757 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13847.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13850.8757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13851.8757 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 25.2028 | 126013.8134 | ACTION | 13877.0784 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13878.0784 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13883.5784 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13889.0784 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13891.0784 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13892.0784 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13897.5784 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13903.0784 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13904.0784 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13919.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 13919.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 19.8969 | 99484.5822 | ACTION | 13923.9753 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13924.9753 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13925.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13927.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13930.4753 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13935.9753 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13937.9753 | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 13938.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13938.9753 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13939.6069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 13940.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13943.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13944.4753 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13946.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13947.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13949.9753 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13950.9753 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13959.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13963.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13966.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13966.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13969.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13970.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 19.8969 | 99484.5822 | ACTION | 13970.8722 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13971.8722 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 13972.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13977.3722 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13982.8722 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13984.8722 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13985.8722 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 13987.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13991.3722 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13994.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13996.8722 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13997.8722 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 14.914 | 74569.9928 | ACTION | 14012.7862 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14013.7862 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14019.2862 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14024.7862 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14026.7862 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14027.7862 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14033.2862 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14038.7862 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14039.7862 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 14.914 | 74569.9928 | ACTION | 14054.7002 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14055.7002 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14061.2002 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14066.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 14066.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14066.7002 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14068.7002 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14069.7002 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14072.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14074.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14075.2002 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14080.7002 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14081.7002 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 14084.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14086.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 14086.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14090.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 11.0794 | 55397.2266 | ACTION | 14092.7797 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14092.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14093.7797 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14094.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14099.2797 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14104.7797 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14106.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14106.7797 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14107.7797 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14109.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14112.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14113.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14113.2797 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14116.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14118.7797 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 14118.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14119.7797 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 11.0794 | 55397.2266 | ACTION | 14130.8591 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14131.8591 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 14133.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14137.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14137.3591 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14140.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14142.8591 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 14150.6084 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 14158.3577 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14212.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 14212.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14218.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14220.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 14231.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14232.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 14233.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14236.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14239.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14240.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14252.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14256.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14259.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14259.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14263.1069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 14265.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 14280.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14287.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14305.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14359.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 14359.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14365.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14367.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 14377.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14379.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 14379.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14383.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14385.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14387.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14399.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14402.6069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14405.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 14408.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 14411.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14412.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14415.6069 | MooredSubInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 14426.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14439.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14473.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14511.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 377.9162 | 2519441.1111 | ACTION | 14511.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14517.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14519.6069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 14530.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14531.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 14532.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14535.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14538.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14539.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14551.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14555.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14558.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14558.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14562.1069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 14564.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 14579.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14586.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14641.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14658.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 377.9162 | 2519441.1111 | ACTION | 14658.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14664.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14666.1069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 14676.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14678.1069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 14678.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14682.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14684.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14686.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14698.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14701.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14704.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14705.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14708.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 14710.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 14725.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14732.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14804.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 377.9162 | 2519441.1111 | ACTION | 14804.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14809.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 4.5 | 0 | ACTION | 14809.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14810.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14817.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14829.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14833.1069 | MooredSubInstallation
| Towing Group 3 | Delay | 26 | 173333.3333 | ACTION | 14836.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14837.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14849.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 14849.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 14851.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14852.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14856.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14857.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14859.6069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14877.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 14883.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14883.6069 | MooredSubInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 14898.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14955.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 376.4162 | 2509441.1111 | ACTION | 14955.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14961.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 14974.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 14976.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14977.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 14977.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14982.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14985.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14997.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15001.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 15002.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15005.1069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 15008.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15017.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15020.6069 | MooredSubInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 15023.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15024.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15027.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15051.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15123.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 397.9162 | 2652774.4444 | ACTION | 15123.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15129.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 15142.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 15144.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15145.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 15145.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15150.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15153.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15165.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15169.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 15170.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15173.1069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 15176.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15185.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15188.6069 | MooredSubInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 15191.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15192.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15195.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15219.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15291.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 393.4162 | 2622774.4444 | ACTION | 15291.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15297.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 15310.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 15312.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15313.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 15313.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15318.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15321.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15333.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15337.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 15338.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15341.1069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 15344.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15353.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15356.6069 | MooredSubInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 15359.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15360.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15363.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15387.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15459.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 436.4162 | 2909441.1111 | ACTION | 15459.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 1 | 6666.6667 | ACTION | 15460.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15466.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 15479.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 15481.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15487.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 15507.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 4 | 26666.6667 | ACTION | 15511.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 26 | 173333.3333 | ACTION | 15537.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 2 | 13333.3333 | ACTION | 15539.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 15554.1908 | MooredSubInstallation | [5 empty] | 2 | 1