## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | location | phase_name | max_waveheight | max_windspeed | transit_speed | num_vessels | num_ahts_vessels
0.5 | Export Cable Installation Vessel | Mobilize | 72 | 180000 | ACTION | 0 | ExportCableInstallation
| Onshore Construction | Onshore Construction | 0 | 1665604.3526 | ACTION | 0 | ExportCableInstallation | Landfall
1 | Mooring System Installation Vessel | Mobilize | 168 | 700000 | ACTION | 0 | MooringSystemInstallation
| Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 6 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Delay | 185 | 770833.3333 | ACTION | 185 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 190 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 195 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 203.9117 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 205.9117 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 209.9117 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 212 | 1060000 | ACTION | 218 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Tow Plow | 0.4 | 2000 | ACTION | 218.4 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Pull Winch | 0.4 | 2000 | ACTION | 218.8 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 219.8 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 226.4767 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 84 | 350000 | ACTION | 310.4767 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 315.0417 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 317.0417 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 321.0417 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 61 | 254166.6667 | ACTION | 382.0417 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 173 | 865000 | ACTION | 392.8 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 398.3 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 398.6067 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 403.1717 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 403.8 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 404.8 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 405.1717 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 409.1717 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 5 | 25000 | ACTION | 409.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Delay | 47 | 195833.3333 | ACTION | 456.1717 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 472.7367 | MooringSystemInstallation |  | MooringSystemInstallation
| Substation Assembly Line 1 | Substation Substructure Assembly | 0 | 0 | ACTION | 518.5632 | FloatingSubstationInstallation
| Substation Assembly Line 1 | Attach Topside | 24 | 0 | ACTION | 542.5632 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay: Waiting on Completed Assembly | 24 | 100000 | ACTION | 542.5632 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 121 | 504166.6667 | ACTION | 593.7367 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 598.3017 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 600.3017 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 604.3017 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 217 | 904166.6667 | ACTION | 821.3017 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 279 | 1162500 | ACTION | 821.5632 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Tow Substation to Site | 14.8528 | 61886.8056 | ACTION | 836.416 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 837.8667 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 838.416 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 41 | 170833.3333 | ACTION | 878.8667 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 883.4317 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 5 | 20833.3333 | ACTION | 888.4317 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 890.4317 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 894.4317 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 59 | 245833.3333 | ACTION | 953.4317 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 969.9967 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 974.5617 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 976.5617 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 980.5617 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 153 | 637500 | ACTION | 991.416 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 997.1267 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 997.416 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1001.416 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1001.6917 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1010.6034 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1015.6034 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.565 | 64854.1667 | ACTION | 1016.981 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1020.6034 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1021.546 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay | 3 | 12500 | ACTION | 1024.546 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1029.5151 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1031.5151 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1035.5151 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 628 | 3140000 | ACTION | 1037.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1046.546 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1052.0801 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1056.6451 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 20 | 100000 | ACTION | 1057.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1058.546 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1058.6451 | MooringSystemInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1062.546 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1062.6451 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 31 | 129166.6667 | ACTION | 1093.546 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 31 | 129166.6667 | ACTION | 1093.6451 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.565 | 64854.1667 | ACTION | 1109.111 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1110.2101 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1113.676 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1114.7751 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1116.7751 | MooringSystemInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 4 | 16666.6667 | ACTION | 1117.676 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1120.7751 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1137.3401 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1141.9051 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1143.9051 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 29 | 120833.3333 | ACTION | 1146.676 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1147.9051 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1164.4701 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 18 | 75000 | ACTION | 1164.676 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 110 | 550000 | ACTION | 1167.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1169.0351 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1171.0351 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1175.0351 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1176.676 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1180.676 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1191.6001 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1196.1651 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.565 | 64854.1667 | ACTION | 1196.241 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1198.1651 | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1200.806 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1202.1651 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1218.7301 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 54 | 270000 | ACTION | 1221.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1222.806 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1223.2951 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1232.2068 | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1234.806 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1237.2068 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 20 | 100000 | ACTION | 1241.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1242.2068 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1243.7177 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1251.1185 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1253.1185 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1257.1185 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 17 | 85000 | ACTION | 1258.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1273.6835 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1278.2485 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1280.2485 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 39 | 162500 | ACTION | 1319.2485 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1323.2485 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 74 | 370000 | ACTION | 1332.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1339.8135 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1344.3785 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1346.3785 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 15 | 75000 | ACTION | 1347.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1350.3785 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1366.9435 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1371.5085 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1373.5085 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1377.5085 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1394.0735 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1398.6385 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1400.6385 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1404.6385 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 52 | 216666.6667 | ACTION | 1456.6385 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1473.2035 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1477.7685 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1479.7685 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1483.7685 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1500.3335 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 42 | 175000 | ACTION | 1542.3335 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1546.8985 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 7 | 29166.6667 | ACTION | 1553.8985 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 42 | 175000 | ACTION | 1595.8985 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 1.9117 | 7965.4167 | ACTION | 1597.8102 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1602.8102 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1607.8102 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1616.7219 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 270 | 1350000 | ACTION | 1617.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1618.7219 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1622.7219 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1639.2869 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1643.8519 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1645.8519 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1649.8519 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1666.4169 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1670.9819 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1672.9819 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1676.9819 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 66 | 330000 | ACTION | 1683.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1693.5469 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1698.1119 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1700.1119 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1704.1119 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1720.6769 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1725.2419 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1727.2419 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1731.2419 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 55 | 275000 | ACTION | 1738.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1747.8069 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1752.3719 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1754.3719 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1758.3719 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 20 | 100000 | ACTION | 1758.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1774.9369 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1779.5019 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 26 | 130000 | ACTION | 1784.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1788.4136 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1793.4136 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1798.4136 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1807.3253 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1809.3253 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1813.3253 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1829.8903 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1834.4553 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1836.4553 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 54.5723 | 272861.6352 | ACTION | 1839.3723 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1840.4553 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 1847.1216 | ExportCableInstallation
| Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 1853.1216 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1857.0203 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 1860.8709 | ExportCableInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1861.5853 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1862.8709 | ExportCableInstallation
| Export Cable Installation Vessel | Raise Cable | 0.5 | 2500 | ACTION | 1863.3709 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1863.5853 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1867.5853 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1884.1503 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1888.7153 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1890.7153 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1894.7153 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1911.2803 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Splice Cable | 48 | 240000 | ACTION | 1911.3709 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 1912.3709 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1915.8453 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1917.8453 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1921.8453 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1938.4103 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1942.9753 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1944.9753 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1948.9753 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 39 | 195000 | ACTION | 1951.3709 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1965.5403 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1970.1053 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1979.017 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1984.017 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1989.017 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4 | 16666.6667 | ACTION | 1993.017 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 2000.017 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.9117 | 20465.4167 | ACTION | 2004.9287 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2006.9287 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2010.9287 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2027.4937 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2032.0587 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2034.0587 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 85 | 425000 | ACTION | 2036.3709 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2038.0587 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 17.1326 | 85662.8041 | ACTION | 2053.5035 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2054.6237 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 2055.5035 | ExportCableInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2059.1887 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 2061.0035 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2061.1887 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2065.1887 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 2066.5035 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 2074.2528 | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2081.7537 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2086.3187 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2088.3187 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2092.3187 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2108.8837 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2113.4487 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2115.4487 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2119.4487 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2136.0137 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2140.5787 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2142.5787 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 34 | 141666.6667 | ACTION | 2176.5787 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2180.5787 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2197.1437 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2201.7087 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2210.6204 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2215.6204 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2220.6204 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2229.5321 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2231.5321 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2235.5321 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2252.0971 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2256.6621 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2258.6621 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2262.6621 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2279.2271 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2283.7921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2285.7921 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2289.7921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2306.3571 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2310.9221 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2312.9221 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2316.9221 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2333.4871 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2338.0521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2340.0521 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2344.0521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2360.6171 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2365.1821 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2367.1821 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2371.1821 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2387.7471 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2392.3121 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2401.2238 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2406.2238 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2411.2238 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2420.1355 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2422.1355 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2426.1355 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2442.7005 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2447.2655 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2449.2655 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2453.2655 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2469.8305 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2474.3955 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2476.3955 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2480.3955 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2496.9605 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2501.5255 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2503.5255 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2507.5255 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2524.0905 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2528.6555 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2530.6555 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2534.6555 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2551.2205 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2555.7855 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2557.7855 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2561.7855 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2578.3505 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2582.9155 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2591.8272 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2596.8272 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2601.8272 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2610.7389 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2612.7389 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2616.7389 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2633.3039 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2637.8689 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2639.8689 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2643.8689 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2660.4339 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2664.9989 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2666.9989 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2670.9989 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2687.5639 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2692.1289 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2694.1289 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2698.1289 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2714.6939 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2719.2589 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2721.2589 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2725.2589 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2741.8239 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2746.3889 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2748.3889 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2752.3889 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2768.9539 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2773.5189 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2782.4306 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2787.4306 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2792.4306 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2801.3423 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2803.3423 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2807.3423 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2823.9073 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2828.4723 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2830.4723 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2834.4723 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2851.0373 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2855.6023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2857.6023 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2861.6023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 20 | 83333.3333 | ACTION | 2881.6023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2898.1673 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2902.7323 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2904.7323 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2908.7323 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2925.2973 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2929.8623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2931.8623 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2935.8623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2952.4273 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2956.9923 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2958.9923 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2962.9923 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2979.5573 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2984.1223 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2993.034 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2998.034 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3003.034 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3011.9457 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3013.9457 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3017.9457 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3034.5107 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3039.0757 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3041.0757 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3045.0757 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3061.6407 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3066.2057 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3068.2057 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3072.2057 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3088.7707 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3093.3357 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3095.3357 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3099.3357 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3115.9007 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3120.4657 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3122.4657 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3126.4657 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3143.0307 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3147.5957 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3149.5957 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3153.5957 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3170.1607 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3174.7257 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3183.6374 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3188.6374 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3193.6374 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3202.5491 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3204.5491 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3208.5491 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3225.1141 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3229.6791 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3231.6791 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3235.6791 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3252.2441 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3256.8091 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3258.8091 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3262.8091 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3279.3741 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3283.9391 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3285.9391 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3289.9391 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3306.5041 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3311.0691 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3313.0691 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3317.0691 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3333.6341 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3338.1991 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3340.1991 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3344.1991 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3360.7641 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3365.3291 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3374.2408 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3379.2408 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3384.2408 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3393.1525 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3395.1525 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3399.1525 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3415.7175 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3420.2825 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3422.2825 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3426.2825 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3442.8475 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3447.4125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3449.4125 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3453.4125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3469.9775 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3474.5425 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3476.5425 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3480.5425 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3497.1075 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3501.6725 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3503.6725 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3507.6725 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3524.2375 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3528.8025 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3530.8025 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3534.8025 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3551.3675 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3555.9325 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3564.8442 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3569.8442 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3574.8442 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3583.7559 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3585.7559 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 3593.7559 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3597.7559 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3614.3209 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3618.8859 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3620.8859 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3624.8859 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3641.4509 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3646.0159 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3648.0159 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3652.0159 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3668.5809 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3673.1459 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3675.1459 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3679.1459 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3695.7109 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3700.2759 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3702.2759 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3706.2759 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3722.8409 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3727.4059 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3729.4059 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3733.4059 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3749.9709 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3754.5359 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3763.4476 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3768.4476 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3773.4476 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3782.3593 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3784.3593 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3788.3593 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3804.9243 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3809.4893 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3811.4893 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3815.4893 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3832.0543 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3836.6193 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3838.6193 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3842.6193 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 10 | 41666.6667 | ACTION | 3852.6193 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3869.1843 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3873.7493 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3875.7493 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3879.7493 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3896.3143 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3900.8793 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3902.8793 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3906.8793 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3923.4443 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3928.0093 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3930.0093 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3934.0093 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3950.5743 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3955.1393 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3964.051 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3969.051 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3974.051 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3982.9627 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3984.9627 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3988.9627 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4005.5277 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4010.0927 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4012.0927 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4016.0927 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4032.6577 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4037.2227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4039.2227 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4043.2227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4059.7877 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4064.3527 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4066.3527 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4070.3527 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4086.9177 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4091.4827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4093.4827 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4097.4827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4114.0477 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4118.6127 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4120.6127 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4124.6127 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4141.1777 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4145.7427 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4154.6544 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4159.6544 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4164.6544 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4173.5661 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4175.5661 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4179.5661 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4196.1311 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4200.6961 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4202.6961 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4206.6961 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4210.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 4210.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4218.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4223.2611 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4227.8261 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4229.8261 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4230.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4233.8261 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4234.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4238.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4250.3911 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4250.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4254.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4254.9561 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4256.9561 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4257.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4260.9561 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4261.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4277.5211 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4282.0861 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4284.0861 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4285.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4288.0861 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4304.6511 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4309.2161 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4311.2161 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4315.2161 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4331.7811 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4336.3461 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4345.2578 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4350.2578 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4355.2578 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4357.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 314.5 | 2096666.6667 | ACTION | 4357.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4363.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4364.1695 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4366.1695 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4370.1695 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4378.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 4378.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4386.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4386.7345 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4391.2995 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4393.2995 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4397.2995 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4398.6069 | MooredSubInstallation
| Towing Group 1 | Delay | 38 | 253333.3333 | ACTION | 4401.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4402.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4406.6069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 4413.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4413.8645 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 4415.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4418.4295 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4418.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4420.4295 | MooringSystemInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4421.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4422.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4424.4295 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4425.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4429.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4440.9945 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 4441.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4445.5595 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4447.5595 | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 4447.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4451.5595 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4453.1069 | MooredSubInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 4462.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4468.1245 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4472.6895 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4474.6895 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4478.6895 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4495.2545 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4499.8195 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4501.8195 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4505.8195 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4522.3845 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4525.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 482.5 | 3216666.6667 | ACTION | 4525.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4526.9495 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4531.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4535.8612 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4540.8612 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 4543.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 4545.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4545.8612 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4546.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 4546.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4551.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4554.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4554.7729 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4556.7729 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4560.7729 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4566.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4570.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 4571.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4574.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4577.3379 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 4577.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4581.9029 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4583.9029 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4586.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4587.9029 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4590.1069 | MooredSubInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 4592.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4593.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4597.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4604.4679 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4609.0329 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4611.0329 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4615.0329 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4621.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4631.5979 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4636.1629 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4638.1629 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4642.1629 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4658.7279 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4663.2929 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4665.2929 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4669.2929 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4685.8579 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4690.4229 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4692.4229 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4693.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 650.5 | 4336666.6667 | ACTION | 4693.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4696.4229 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4699.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 4711.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4712.9879 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 4713.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4714.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 4714.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4717.5529 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4719.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4722.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4726.4646 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4731.4646 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4734.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4736.4646 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4738.6069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 4739.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4742.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4745.3763 | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 4745.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4747.3763 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4751.3763 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4754.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4758.1069 | MooredSubInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 4760.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4761.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4765.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4767.9413 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4772.5063 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4774.5063 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4778.5063 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4789.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4795.0713 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4799.6363 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4801.6363 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4805.6363 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4822.2013 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4826.7663 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4828.7663 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4832.7663 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4849.3313 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4853.8963 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4855.8963 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4859.8963 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4861.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 398.4162 | 2656107.7778 | ACTION | 4861.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 4867.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4876.4613 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 4879.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4881.0263 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 4881.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4882.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 4882.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4883.0263 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4887.0263 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 4887.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4890.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4902.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4903.5913 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4906.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 4907.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4908.1563 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4910.6069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 4913.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4917.068 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4922.068 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4922.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4926.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4927.068 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 4928.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4929.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4933.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4935.9797 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4937.9797 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4941.9797 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4957.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4958.5447 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4963.1097 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4965.1097 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4969.1097 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4985.6747 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4990.2397 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4992.2397 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4996.2397 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5012.8047 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5017.3697 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5019.3697 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5023.3697 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5029.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 436.4162 | 2909441.1111 | ACTION | 5029.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5035.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5039.9347 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5044.4997 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5046.4997 | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 5047.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 5049.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5050.4997 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5050.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 5050.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5055.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5058.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5067.0647 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5070.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5071.6297 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5073.6297 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5074.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5075.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5077.6297 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5078.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 5081.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5090.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5094.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5094.1947 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 5096.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5097.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5098.7597 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5101.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5107.6714 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5112.6714 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5117.6714 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5125.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5126.5831 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5128.5831 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5132.5831 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5149.1481 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5153.7131 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5155.7131 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5159.7131 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5176.2781 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5180.8431 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5182.8431 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5186.8431 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5197.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 436.4162 | 2909441.1111 | ACTION | 5197.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5203.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5203.4081 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5207.9731 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5209.9731 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5213.9731 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 5215.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 5217.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5218.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 5218.6069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5223.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5226.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5230.5381 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5235.1031 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5237.1031 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5238.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5241.1031 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5242.6069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5243.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5246.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 5249.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5257.6681 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5258.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5262.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5262.2331 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5264.2331 | MooringSystemInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 5264.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5265.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5268.2331 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5269.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5284.7981 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5289.3631 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5293.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5298.2748 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5303.2748 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5308.2748 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5317.1865 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5319.1865 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5323.1865 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5339.7515 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5344.3165 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5346.3165 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5350.3165 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5365.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 436.4162 | 2909441.1111 | ACTION | 5365.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5366.8815 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5371.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5371.4465 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5373.4465 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5377.4465 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 5383.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 5385.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5386.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 5386.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5391.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5394.0115 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5394.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5398.5765 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5400.5765 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5404.5765 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5406.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5410.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5411.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5414.6069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 5417.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5421.1415 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5425.7065 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5426.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5427.7065 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5430.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5431.7065 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 5432.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5433.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5437.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5448.2715 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5452.8365 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5454.8365 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5458.8365 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5461.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5475.4015 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5479.9665 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5488.8782 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5493.8782 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5498.8782 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5507.7899 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5509.7899 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5513.7899 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5530.3549 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5533.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 436.4162 | 2909441.1111 | ACTION | 5533.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5534.9199 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5536.9199 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5539.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5540.9199 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 5551.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 5553.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5554.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 5554.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5557.4849 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5559.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5562.0499 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5562.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5564.0499 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5568.0499 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5574.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5578.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5579.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5582.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 4 | 26666.6667 | ACTION | 5583.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5584.6149 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5589.1799 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5591.1799 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5595.1799 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Delay | 12 | 80000 | ACTION | 5595.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 2 | 13333.3333 | ACTION | 5597.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 5609.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5611.7449 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 5612.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5616.3099 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5618.3099 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5621.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5622.3099 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5625.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5628.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5632.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5638.8749 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5643.4399 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5645.4399 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5649.4399 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5656.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5666.0049 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5670.5699 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5679.4816 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5684.4816 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5689.4816 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5698.3933 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5700.3933 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5704.3933 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5720.9583 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5722.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5725.5233 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5727.5233 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5728.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 463.4162 | 3089441.1111 | ACTION | 5728.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5731.5233 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5734.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5736.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 5746.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5748.0883 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5748.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 5748.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5752.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5752.6533 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5754.6533 | MooringSystemInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5754.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5756.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5758.6533 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5768.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5771.6069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5774.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5775.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5775.2183 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5778.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5779.7833 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 5780.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5781.7833 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5785.7833 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 5795.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5802.3483 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5802.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5806.9133 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5808.9133 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5812.9133 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5829.4783 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5834.0433 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5836.0433 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5840.0433 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5856.6083 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5861.1733 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5870.085 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5874.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 441.9162 | 2946107.7778 | ACTION | 5874.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5875.085 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5880.085 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 5880.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5888.9967 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5890.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 16 | 0 | ACTION | 5890.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5890.9967 | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 5893.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5894.9967 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 5895.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5898.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 5901.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5910.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5911.5617 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5914.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5916.1267 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5918.1267 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5918.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 5921.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5922.1267 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 5927.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5930.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 5933.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5937.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5938.6917 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5940.6069 | MooredSubInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 5942.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5943.2567 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5944.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5945.2567 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5949.2567 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5965.8217 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5968.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5970.3867 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5972.3867 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5976.3867 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5992.9517 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5997.5167 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5999.5167 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6003.5167 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6020.0817 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6024.6467 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6026.6467 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6030.6467 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6040.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 427.4162 | 2849441.1111 | ACTION | 6040.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6046.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6047.2117 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6051.7767 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6058.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 18.5 | 0 | ACTION | 6058.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 6058.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6060.6884 | MooringSystemInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 6060.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6065.6884 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6066.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6066.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6070.6884 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6078.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6079.6001 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6081.6001 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6082.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6085.6001 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6086.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6086.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 6092.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6098.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6102.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6102.1651 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6105.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6106.7301 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 6107.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6108.7301 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6109.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6112.7301 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6129.2951 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6133.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6133.8601 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6135.8601 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6139.8601 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6156.4251 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6160.9901 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6162.9901 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6166.9901 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6183.5551 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6188.1201 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6190.1201 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6194.1201 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6205.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 409.4162 | 2729441.1111 | ACTION | 6205.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6210.6851 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6211.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6215.2501 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6217.2501 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6221.2501 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 6223.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 6225.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6226.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 6226.6069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6231.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6234.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6237.8151 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6242.3801 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6246.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6250.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6251.2918 | MooringSystemInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6251.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6254.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6256.2918 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 6257.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6261.2918 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6266.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6270.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6270.2035 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6272.2035 | MooringSystemInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 6272.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6273.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6276.2035 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6277.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6292.7685 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6297.3335 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6299.3335 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6301.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6303.3335 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6319.8985 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6324.4635 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6326.4635 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6330.4635 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6347.0285 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6351.5935 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6353.5935 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6357.5935 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6373.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 430.9162 | 2872774.4444 | ACTION | 6373.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6374.1585 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6378.7235 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6379.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6380.7235 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6384.7235 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6394.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 6394.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6402.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6414.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6418.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6422.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6434.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 6446.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6450.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6453.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6457.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 78 | 325000 | ACTION | 6462.7235 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Delay | 92 | 613333.3333 | ACTION | 6471.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6479.2885 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6481.1069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 6483.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6483.8535 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 6485.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6485.8535 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6489.8535 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6491.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6506.4185 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6510.9835 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6511.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 6517.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6519.8952 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6524.8952 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 6532.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 19 | 79166.6667 | ACTION | 6543.8952 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6548.8952 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6553.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 445.4162 | 2969441.1111 | ACTION | 6553.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6557.8069 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6559.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6559.8069 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6562.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 9.5 | 0 | ACTION | 6562.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6563.8069 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6570.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 6571.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 6573.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6579.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6580.3719 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6582.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6584.9369 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6586.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6586.9369 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6590.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6590.9369 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6599.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6602.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 6605.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6606.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6607.5019 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6609.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6612.0669 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6613.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6614.0669 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6618.0669 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 6620.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6634.6319 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6637.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6639.1969 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6641.1969 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6645.1969 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6661.7619 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6666.3269 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6668.3269 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6672.3269 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6688.8919 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6693.4569 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6695.4569 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6699.4569 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6709.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 436.4162 | 2909441.1111 | ACTION | 6709.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6715.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6716.0219 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6720.5869 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 6727.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6729.4986 | MooringSystemInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 6729.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6730.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 6730.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6734.4986 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6735.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6738.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6739.4986 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6748.4103 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6750.4103 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6750.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6754.4103 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6754.6069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 6755.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6758.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 6761.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6770.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6770.9753 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6774.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6775.5403 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 6776.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6777.5403 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6777.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6781.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6781.5403 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6798.1053 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6802.6703 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6804.6703 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6805.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6808.6703 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6825.2353 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6829.8003 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6831.8003 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 27 | 112500 | ACTION | 6858.8003 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6862.8003 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 80 | 0 | ACTION | 6885.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6898.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 40 | 166666.6667 | ACTION | 6902.8003 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6919.3653 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6923.9303 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6925.9303 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6929.9303 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6946.4953 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6951.0603 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6953.0603 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6957.0603 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6957.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 424.4162 | 2829441.1111 | ACTION | 6957.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 6963.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6965.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6973.6253 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 6975.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6977.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 6977.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6978.1903 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6981.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 6983.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6985.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6987.102 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6992.102 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6997.102 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6997.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 7000.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7003.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7003.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 7006.0137 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7007.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7008.0137 | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 7009.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7010.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7012.0137 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 7024.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7028.5787 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7033.1437 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7034.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7035.1437 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7039.1437 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7055.7087 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7060.2737 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7062.2737 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7066.2737 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7066.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7082.8387 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7087.4037 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7089.4037 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7093.4037 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7106.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 485.9162 | 3239441.1111 | ACTION | 7106.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7109.9687 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7112.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7114.5337 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7114.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7116.5337 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7120.5337 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7126.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 7132.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7136.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 18 | 75000 | ACTION | 7138.5337 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7140.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 30 | 200000 | ACTION | 7142.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7152.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7155.0987 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 7155.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7156.1069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 7157.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7159.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7159.6637 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7161.6637 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7163.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7163.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7165.6637 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7182.2287 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7183.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7186.7937 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7187.1069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 7189.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 7195.7054 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7200.7054 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 7204.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7205.7054 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 7214.6171 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7216.6171 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7220.6171 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7234.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7237.1821 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7241.7471 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7243.7471 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7247.7471 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7259.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 482.4162 | 3216107.7778 | ACTION | 7259.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7264.3121 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7265.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7267.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7268.8771 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7270.8771 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7274.8771 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 7277.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7279.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 7279.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 7282.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7286.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7290.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 26 | 108333.3333 | ACTION | 7300.8771 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7302.1069 | MooredSubInstallation
| Towing Group 3 | Delay | 25 | 166666.6667 | ACTION | 7304.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7305.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7309.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7310.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7312.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7317.4421 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7322.0071 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7324.0071 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7328.0071 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7330.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7336.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 7336.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7344.5721 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7349.1371 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7351.1371 | MooringSystemInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 7351.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7355.1371 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7371.7021 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7376.2671 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 7389.2671 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7391.2671 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7395.2671 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7402.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7411.8321 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7416.3971 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 1 | 4166.6667 | ACTION | 7417.3971 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 92 | 383333.3333 | ACTION | 7509.3971 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 7.9117 | 32965.4167 | ACTION | 7517.3088 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7522.3088 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7527.3088 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 7536.2205 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7538.2205 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7542.2205 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 28 | 116666.6667 | ACTION | 7570.2205 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7570.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7586.7855 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7591.3505 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7593.3505 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7597.3505 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 386 | 0 | ACTION | 7722.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7738.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 146 | 608333.3333 | ACTION | 7743.3505 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7759.9155 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7764.4805 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7766.4805 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7770.4805 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7787.0455 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7791.6105 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7793.6105 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7794.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 769.9162 | 5132774.4444 | ACTION | 7794.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7797.6105 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7800.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7802.6069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 7813.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7814.1755 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7814.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 7815.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7818.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7818.7405 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7820.7405 | MooringSystemInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 7821.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7822.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7824.7405 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7834.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7838.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7841.3055 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 7841.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7841.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7845.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7845.8705 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 7847.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7847.8705 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7851.8705 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 7862.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7868.4355 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7869.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7873.0005 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 7881.9122 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7886.9122 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4 | 16666.6667 | ACTION | 7890.9122 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7906.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 49 | 204166.6667 | ACTION | 7939.9122 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7941.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 736.9162 | 4912774.4444 | ACTION | 7941.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 4.9117 | 20465.4167 | ACTION | 7944.8239 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7946.8239 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7949.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7950.8239 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7961.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7965.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7969.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 25 | 104166.6667 | ACTION | 7975.8239 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7981.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7984.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 46 | 306666.6667 | ACTION | 7987.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7988.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7991.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7992.3889 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 7993.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7996.9539 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7998.9539 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8002.9539 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 8005.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 8007.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8013.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8015.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 20000 | ACTION | 8016.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 8019.5189 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 8030.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 34 | 141666.6667 | ACTION | 8053.5189 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 8058.0839 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Delay | 43 | 286666.6667 | ACTION | 8059.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8060.0839 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8064.0839 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8074.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 113333.3333 | ACTION | 8076.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 8080.6489 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 8082.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 8085.2139 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 8097.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8102.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 750.9162 | 5006107.7778 | ACTION | 8102.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8110.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8122.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8126.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8130.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8142.6069 | MooredSubInstallation
| Towing Group 3 | Delay | 42 | 280000 | ACTION | 8144.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 8145.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8149.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8150.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 8163.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8166.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8170.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8194.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8242.6069 | MooredSubInstallation
| Towing Group 3 | Delay | 115 | 766666.6667 | ACTION | 8265.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8266.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 403.9162 | 2692774.4444 | ACTION | 8266.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8272.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8274.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 8278.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 8280.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8286.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8290.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8294.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8306.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8309.6069 | MooredSubInstallation
| Towing Group 1 | Delay | 38 | 253333.3333 | ACTION | 8310.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 30 | 200000 | ACTION | 8310.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8313.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8316.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8316.6069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 8322.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 8324.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 80000 | ACTION | 8328.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8340.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8410.6069 | MooredSubInstallation
| Towing Group 1 | Delay | 243 | 1620000 | ACTION | 8567.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 240 | 1600000 | ACTION | 8568.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 8573.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 53333.3333 | ACTION | 8576.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8578.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 8582.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 8593.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 8597.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 8599.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 8614.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 304 | 0 | ACTION | 8644.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8716.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 618.9162 | 4126107.7778 | ACTION | 8716.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 8722.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8724.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 8735.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8736.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8746.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 36 | 0 | ACTION | 8772.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8776.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8780.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 51 | 0 | ACTION | 8831.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8843.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 8849.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8853.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8856.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 8867.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8871.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 36 | 0 | ACTION | 8907.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8914.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8931.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 28 | 0 | ACTION | 8959.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9031.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 433.9162 | 2892774.4444 | ACTION | 9031.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9039.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9051.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 9059.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9063.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9067.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 9082.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9082.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9094.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9097.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9101.1069 | MooredSubInstallation
| Towing Group 2 | Delay | 382 | 2546666.6667 | ACTION | 9117.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 9119.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 25 | 0 | ACTION | 9126.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9129.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9153.6069 | MooredSubInstallation
| Towing Group 3 | Delay | 193 | 1286666.6667 | ACTION | 9224.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 105 | 700000 | ACTION | 9224.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9225.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 610.9162 | 4072774.4444 | ACTION | 9225.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9230.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9230.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9231.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9233.6069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 9242.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 9244.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 9244.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9245.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 9246.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9249.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9250.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9250.6069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9250.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9252.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9253.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 9256.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9265.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9269.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9270.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 9271.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 9272.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9272.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9276.1069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 9276.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 9278.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 9291.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 9293.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9300.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9372.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 100.9162 | 672774.4444 | ACTION | 9372.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9380.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9392.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9396.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 9412.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9416.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9418.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9428.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9431.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9435.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9438.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 79 | 526666.6667 | ACTION | 9451.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9457.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9462.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 9469.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 9471.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9477.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 46666.6667 | ACTION | 9484.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 49 | 0 | ACTION | 9511.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 79 | 526666.6667 | ACTION | 9563.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 10 | 66666.6667 | ACTION | 9573.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9583.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 291.9162 | 1946107.7778 | ACTION | 9583.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9586.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9591.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 23 | 153333.3333 | ACTION | 9596.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 14 | 93333.3333 | ACTION | 9597.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 20000 | ACTION | 9599.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9603.6069 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9603.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 9605.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9607.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9611.6069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 9616.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 9618.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 9620.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9623.6069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9624.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9627.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 46666.6667 | ACTION | 9631.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 9641.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9644.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9648.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9672.1069 | MooredSubInstallation
| Towing Group 3 | Delay | 79 | 526666.6667 | ACTION | 9710.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 86666.6667 | ACTION | 9723.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 9729.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9744.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 450.9162 | 3006107.7778 | ACTION | 9744.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 9744.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9750.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9752.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9754.6069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 9762.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9764.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 9764.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9768.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 9770.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9772.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9784.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 106666.6667 | ACTION | 9786.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 1 | 6666.6667 | ACTION | 9787.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 13333.3333 | ACTION | 9789.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 9 | 60000 | ACTION | 9798.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 13333.3333 | ACTION | 9800.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 9806.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 9821.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 50 | 0 | ACTION | 9834.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9837.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9841.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9844.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9868.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 20 | 0 | ACTION | 9888.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9922.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9960.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 339.9162 | 2266107.7778 | ACTION | 9960.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 9966.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9968.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9980.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9984.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9988.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10000.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10004.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10007.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10011.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10035.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10090.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10107.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 362.9162 | 2419441.1111 | ACTION | 10107.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10115.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10127.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 37 | 0 | ACTION | 10164.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10168.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10172.1069 | MooredSubInstallation
| Towing Group 3 | Delay | 72 | 480000 | ACTION | 10179.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 213 | 1420000 | ACTION | 10179.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10184.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10185.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10187.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10191.1069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 10192.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 10194.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10194.6069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 10197.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 10199.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10200.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10205.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10218.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10220.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10225.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 10226.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 10241.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 31 | 206666.6667 | ACTION | 10256.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10258.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 10262.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 10277.6908 | MooredSubInstallation | [5 empty] | 2 | 1
0.5 | Array Cable Installation Vessel | Mobilize | 72 | 180000 | ACTION | 10303.3989 | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 10309.3989 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 132 | 0 | ACTION | 10350.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 113 | 565000 | ACTION | 10422.3989 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10422.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 600.9162 | 4006107.7778 | ACTION | 10422.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10426.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10428.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 10430.1482 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10430.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10432.1482 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10433.1482 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10438.6482 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 10441.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10442.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 10443.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10444.1482 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10445.1482 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10446.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10449.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10450.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 10455.5666 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10456.5666 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10462.0666 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10462.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10466.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10467.5666 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10469.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10469.5666 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10469.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10470.5666 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10473.1069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 10475.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10476.0666 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10481.5666 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10482.5666 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 10490.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 10492.9851 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10493.9851 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10497.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10499.4851 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10504.9851 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10506.9851 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10507.9851 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 29 | 0 | ACTION | 10526.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 57 | 285000 | ACTION | 10564.9851 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10570.4851 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10575.9851 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10576.9851 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 10587.4035 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10588.4035 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10593.9035 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10594.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10598.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 356.9162 | 2379441.1111 | ACTION | 10598.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10599.4035 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10601.4035 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10602.4035 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10604.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10606.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10618.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 10624.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10628.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 28 | 0 | ACTION | 10656.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10660.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10672.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 10677.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10680.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 77 | 513333.3333 | ACTION | 10681.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10684.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 85 | 425000 | ACTION | 10687.4035 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10687.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10692.9035 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 10693.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 10695.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10698.4035 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10699.4035 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10701.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 20000 | ACTION | 10704.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 1 | 6666.6667 | ACTION | 10705.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10711.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 113333.3333 | ACTION | 10722.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 15 | 100000 | ACTION | 10737.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 10743.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 49 | 245000 | ACTION | 10748.4035 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 10758.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 10758.822 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10759.822 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10762.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10783.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 505.9162 | 3372774.4444 | ACTION | 10783.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10791.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10803.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10807.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10811.6069 | MooredSubInstallation
| Towing Group 3 | Delay | 36 | 240000 | ACTION | 10819.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10823.6069 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10825.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 66 | 330000 | ACTION | 10825.822 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10827.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10830.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10831.322 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10834.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10836.822 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 10838.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10838.822 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10839.822 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 10840.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10845.322 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10846.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10850.822 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10851.822 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10858.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 10862.2404 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10863.2404 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 113333.3333 | ACTION | 10863.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 23 | 0 | ACTION | 10881.1069 | MooredSubInstallation
| Towing Group 3 | Delay | 53 | 353333.3333 | ACTION | 10916.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 20000 | ACTION | 10919.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 59 | 295000 | ACTION | 10922.2404 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 10925.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10927.7404 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10930.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10933.2404 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10935.2404 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10936.2404 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 10940.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10941.7404 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10947.2404 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10948.2404 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10953.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 462.9162 | 3086107.7778 | ACTION | 10953.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 10958.6589 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 10959.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10959.6589 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10961.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10965.1589 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10970.6589 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 10971.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 10972.6589 | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10973.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10973.6589 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 10973.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10977.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 10979.1589 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 10979.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10981.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 10984.6589 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 10985.6589 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10993.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 10996.0774 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10996.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 10997.0774 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 10999.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11000.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11002.5774 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11003.6069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 11005.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 11020.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11027.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 53 | 265000 | ACTION | 11055.5774 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11061.0774 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11063.0774 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11064.0774 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11069.5774 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11075.0774 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11076.0774 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11086.4958 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11087.4958 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11092.9958 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11098.4958 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11098.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11099.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 340.9162 | 2272774.4444 | ACTION | 11099.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11100.4958 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11101.4958 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11105.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11106.9958 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11107.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11112.4958 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11113.4958 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | ACTION | 11116.4958 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 11118.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11119.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 11120.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11123.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11126.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11127.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 16 | 80000 | ACTION | 11132.4958 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11139.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 7.4185 | 37092.2749 | ACTION | 11139.9143 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11140.9143 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11143.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11146.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11146.4143 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11146.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11150.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11151.9143 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 11152.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11153.9143 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11154.9143 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 11167.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11174.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 62 | 310000 | ACTION | 11216.9143 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11222.4143 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11227.9143 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11228.9143 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11239.3327 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11240.3327 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11245.8327 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11246.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 305.9162 | 2039441.1111 | ACTION | 11246.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11251.3327 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11252.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11253.3327 | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11254.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11254.3327 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11259.8327 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 11264.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11265.3327 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11266.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11266.3327 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11266.6069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 11266.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11270.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11272.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11274.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11276.7512 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11277.7512 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11283.2512 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11286.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11288.7512 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11289.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11290.7512 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11291.7512 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11292.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11293.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11296.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11297.2512 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 11298.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11302.7512 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11303.7512 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 11313.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11314.1696 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11315.1696 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11320.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11320.6696 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11326.1696 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11328.1696 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11329.1696 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11334.6696 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11340.1696 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11341.1696 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11351.5881 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11352.5881 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11358.0881 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11363.5881 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11365.5881 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11366.5881 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11372.0881 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11377.5881 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11378.5881 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11389.0065 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11390.0065 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11392.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 11392.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11395.5065 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11398.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11400.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11401.0065 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11403.0065 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11404.0065 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11409.5065 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 11411.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11412.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 11413.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11416.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11419.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11420.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11432.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11434.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11436.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11439.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11439.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11443.1069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 11445.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 11460.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11467.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 61 | 305000 | ACTION | 11470.5065 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11476.0065 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11477.0065 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11487.425 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11488.425 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11493.925 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11499.425 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11501.425 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11502.425 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11507.925 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11513.425 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11514.425 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11524.8435 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11525.8435 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11531.3435 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11536.8435 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11538.8435 | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11539.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 11539.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11539.8435 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11545.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11545.3435 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11547.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11550.8435 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11551.8435 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 11557.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11559.1069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 11559.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11562.2619 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11563.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11563.2619 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11565.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11567.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11568.7619 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11574.2619 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11576.2619 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11577.2619 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11579.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11582.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11582.7619 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11585.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11586.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11588.2619 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11589.2619 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11589.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 11591.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11599.6804 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11600.6804 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11602.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11606.1804 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 11606.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11611.6804 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11613.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11613.6804 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11614.6804 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11620.1804 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11625.6804 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11626.6804 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11637.0988 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11638.0988 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11643.5988 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11649.0988 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11651.0988 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11652.0988 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 3 | 15000 | ACTION | 11655.0988 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11660.5988 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11666.0988 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11667.0988 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11677.5173 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11678.5173 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11684.0173 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11685.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 11685.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11689.5173 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11691.5173 | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11691.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11692.5173 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11693.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11698.0173 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 11704.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11705.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 8 | 40000 | ACTION | 11706.0173 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 11706.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11709.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11711.5173 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11712.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11712.5173 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11713.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11722.9357 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11723.9357 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11725.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11729.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11729.4357 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11732.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11732.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11734.9357 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11736.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11736.9357 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11737.9357 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 11738.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11743.4357 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11748.9357 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11749.9357 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 11753.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11760.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11760.3542 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11761.3542 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11766.8542 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11770.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11772.3542 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11774.3542 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11775.3542 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11780.8542 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11786.3542 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11787.3542 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11797.7726 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11798.7726 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11832.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 11832.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11838.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11840.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 44 | 220000 | ACTION | 11842.7726 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11848.2726 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 11850.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11852.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 11852.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11853.7726 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11855.7726 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11856.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11856.7726 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 11858.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11860.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11862.2726 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11867.7726 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11868.7726 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11872.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11875.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 11878.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11879.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11879.1911 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11880.1911 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11882.6069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 11884.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11885.6911 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11891.1911 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11893.1911 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11894.1911 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 11899.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11899.6911 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11905.1911 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11906.1911 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11906.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11916.6095 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11917.6095 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11923.1095 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11928.6095 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11930.6095 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11931.6095 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11937.1095 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11938.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11942.6095 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11943.6095 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11954.028 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11955.028 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11960.528 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11966.028 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11968.028 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11969.028 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11974.528 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11978.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 11978.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11980.028 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11981.028 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 11984.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11986.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 11991.4465 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11992.4465 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 11997.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11998.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 11999.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12002.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12005.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12006.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 26 | 130000 | ACTION | 12018.4465 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12018.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12022.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12023.9465 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12025.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12025.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12029.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12029.4465 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 12031.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12031.4465 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12032.4465 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12037.9465 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12043.4465 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12044.4465 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 12046.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12053.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12054.8649 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12055.8649 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12061.3649 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12066.8649 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12068.8649 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12069.8649 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 15 | 75000 | ACTION | 12084.8649 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12090.3649 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12095.8649 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12096.8649 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12106.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12107.2834 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12108.2834 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12113.7834 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12125.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 12125.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12131.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12133.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 23 | 115000 | ACTION | 12136.7834 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12142.2834 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 12143.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12144.2834 | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12145.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12145.2834 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 12145.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12149.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12150.7834 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12151.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12153.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12156.2834 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12157.2834 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12165.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12167.7018 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12168.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12168.7018 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12171.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12172.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12174.2018 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12175.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 12177.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12179.7018 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12181.7018 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12182.7018 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12188.2018 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 12192.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12193.7018 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12194.7018 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12199.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12205.1203 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12206.1203 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12211.6203 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12217.1203 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12219.1203 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12220.1203 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12225.6203 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12231.1203 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12232.1203 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12242.5387 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12243.5387 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12249.0387 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12254.5387 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12256.5387 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12257.5387 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12263.0387 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12268.5387 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12269.5387 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12271.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 12271.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12274.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12277.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12279.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12279.9572 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12280.9572 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12286.4572 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 12290.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12291.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 12292.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 12297.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12301.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 12307.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12311.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12323.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12327.1069 | MooredSubInstallation
| Towing Group 1 | Delay | 36 | 240000 | ACTION | 12328.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12330.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12334.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12334.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 48 | 240000 | ACTION | 12334.4572 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12339.9572 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12341.9572 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12342.9572 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12348.4572 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12353.9572 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12354.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12354.9572 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12358.1069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 12360.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 12375.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 36.1234 | 180617.0334 | ACTION | 12391.0806 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12392.0806 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12397.5806 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12403.0806 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 12410.8299 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 12418.5792 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 12424.5792 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12430.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 383.9162 | 2559441.1111 | ACTION | 12430.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 12432.3285 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12434.3285 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12435.3285 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12436.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12438.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12440.8285 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12442.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12446.3285 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12447.3285 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 12448.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12450.1069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 12450.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12454.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12456.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12458.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12470.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12473.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12476.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12477.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 32 | 160000 | ACTION | 12479.3285 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12480.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 3 | 15000 | ACTION | 12482.3285 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 12482.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 4.1234 | 20617.0334 | ACTION | 12486.4519 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12487.4519 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12492.9519 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 12497.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12498.4519 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12500.4519 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12501.4519 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12504.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12506.9519 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12576.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 383.9162 | 2559441.1111 | ACTION | 12576.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 70 | 350000 | ACTION | 12576.9519 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12582.4519 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12582.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12583.4519 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12584.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12593.8704 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12594.8704 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 12595.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12596.6069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 12597.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12600.3704 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12600.6069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12603.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12604.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12605.8704 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12607.8704 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12608.8704 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12610.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12614.3704 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12616.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12619.8704 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12620.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12620.8704 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12623.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12623.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12627.1069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 12629.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12631.2888 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12632.2888 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12637.7888 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12643.2888 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 12644.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12645.2888 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12646.2888 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12651.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12651.7888 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 41 | 205000 | ACTION | 12692.7888 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12698.2888 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12699.2888 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 12700.2888 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Delay | 52 | 0 | ACTION | 12703.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 17 | 85000 | ACTION | 12717.2888 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 9.4185 | 47092.2749 | ACTION | 12726.7073 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12727.7073 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12733.2073 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12738.7073 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12740.7073 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12741.7073 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12747.2073 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12752.7073 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12753.7073 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12764.1257 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12765.1257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12770.6257 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12775.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 399.9162 | 2666107.7778 | ACTION | 12775.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12776.1257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12778.1257 | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12778.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12779.1257 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12781.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12783.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12784.6257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12790.1257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12791.1257 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 12793.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12795.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 12795.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12799.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12801.5442 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12801.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12802.5442 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12803.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12808.0442 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12813.5442 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12815.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12815.5442 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12816.5442 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12818.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12821.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12822.0442 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12822.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12825.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12827.5442 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 12827.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12828.5442 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12838.9626 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12839.9626 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 12842.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 6 | 30000 | ACTION | 12845.9626 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12849.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12851.4626 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12856.9626 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12858.9626 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12859.9626 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12865.4626 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12870.9626 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12871.9626 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12882.3811 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12883.3811 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12888.8811 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12894.3811 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12896.3811 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12897.3811 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12902.8811 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12908.3811 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12909.3811 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 6 | 30000 | ACTION | 12915.3811 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12921.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 423.9162 | 2826107.7778 | ACTION | 12921.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 12927.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12929.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 16 | 80000 | ACTION | 12931.3811 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 4.4185 | 22092.2749 | ACTION | 12935.7996 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12936.7996 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 12940.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12941.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12942.2996 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 12942.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12945.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12946.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12947.7996 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 12948.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12949.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12949.7996 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12950.7996 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12956.2996 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12961.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12961.7996 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12962.7996 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12965.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 12968.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12968.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12972.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 12973.218 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12974.218 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 12974.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12979.718 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12985.218 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12987.218 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12988.218 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 12989.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12993.718 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12996.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12999.218 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13000.218 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13010.6365 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13011.6365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13017.1365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13022.6365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13024.6365 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13025.6365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13031.1365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13036.6365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13037.6365 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13048.0549 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13049.0549 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13054.5549 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13060.0549 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13062.0549 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13063.0549 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13068.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 423.9162 | 2826107.7778 | ACTION | 13068.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13068.5549 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13074.0549 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13074.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13075.0549 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13076.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13085.4734 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13086.4734 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 13086.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13088.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 13088.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13091.9734 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13092.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13094.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13096.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13097.4734 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13099.4734 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13100.4734 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13105.9734 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13108.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13111.4734 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13111.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13112.4734 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13114.6069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13114.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13115.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13118.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 13120.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13122.8918 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13123.8918 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 13135.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13142.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13214.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 13214.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 95 | 475000 | ACTION | 13218.8918 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13220.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13222.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13224.3918 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13229.8918 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13231.8918 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13232.8918 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 13233.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13234.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 13235.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13238.3918 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13238.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13241.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13242.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13243.8918 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13244.8918 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13254.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13255.3103 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13256.3103 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13258.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13261.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13261.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13261.8103 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13265.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13267.3103 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 13267.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13269.3103 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13270.3103 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13275.8103 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13281.3103 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 13282.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13282.3103 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13282.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13289.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13292.7287 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13293.7287 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13299.2287 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13304.7287 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13306.7287 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13307.7287 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13313.2287 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13318.7287 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13319.7287 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13330.1472 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13331.1472 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13336.6472 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13342.1472 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13344.1472 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13345.1472 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13350.6472 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13356.1472 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13357.1472 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13361.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 13361.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13367.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13367.5656 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13368.5656 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13369.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13374.0656 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13379.5656 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 13379.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13381.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13381.5656 | ArrayCableInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 13381.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13382.5656 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13385.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13387.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13388.0656 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13389.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13393.5656 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13394.5656 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13401.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13404.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13404.9841 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13405.9841 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13407.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13408.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13411.4841 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13411.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 13413.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 11 | 55000 | ACTION | 13422.4841 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13427.9841 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 13428.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13429.9841 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13430.9841 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13435.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13436.4841 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13441.9841 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13442.9841 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13450.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13453.4026 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13454.4026 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13459.9026 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13465.4026 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13467.4026 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13468.4026 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13473.9026 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13479.4026 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13480.4026 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13490.821 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13491.821 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13497.321 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13502.821 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13504.821 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13505.821 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13507.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 13507.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13511.321 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13513.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13515.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13516.821 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13517.821 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 13526.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13527.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13528.2395 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 13528.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13529.2395 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13531.6069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13534.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13534.7395 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13535.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13540.2395 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13542.2395 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13543.2395 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13547.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13548.7395 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13551.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13554.2395 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13554.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13554.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13555.2395 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13558.1069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 13560.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 10.4185 | 52092.2749 | ACTION | 13565.6579 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13566.6579 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13572.1579 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 13575.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13577.6579 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13579.6579 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13580.6579 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13582.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13586.1579 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13591.6579 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13592.6579 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13618.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 30.6332 | 153165.8973 | ACTION | 13623.2911 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13624.2911 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13629.7911 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13635.2911 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 13643.0404 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 13649.0404 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13654.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 13654.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 13656.7897 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13658.7897 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13659.7897 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13660.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13662.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13665.2897 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13670.7897 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13671.7897 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 13672.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13674.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 13674.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13678.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13680.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13682.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13694.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13697.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13700.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13701.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 30.6332 | 153165.8973 | ACTION | 13702.4229 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13703.4229 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13704.6069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 13706.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13708.9229 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13714.4229 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13716.4229 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13717.4229 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 13721.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13722.9229 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13728.4229 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13728.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13729.4229 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 25.2028 | 126013.8134 | ACTION | 13754.6257 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13755.6257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13761.1257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13766.6257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13768.6257 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13769.6257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13775.1257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13780.6257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13781.6257 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13786.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13800.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 13800.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13806.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 25.2028 | 126013.8134 | ACTION | 13806.8284 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13807.8284 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13808.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13813.3284 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13818.8284 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 13819.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13820.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13820.8284 | ArrayCableInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 13821.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13821.8284 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13824.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13827.3284 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13827.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13828.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13832.8284 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13833.8284 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13840.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13844.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13847.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13847.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13851.1069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 13853.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 19.8969 | 99484.5822 | ACTION | 13853.7253 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13854.7253 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13860.2253 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13865.7253 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13867.7253 | ArrayCableInstallation
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 13868.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13868.7253 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13874.2253 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13875.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13879.7253 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13880.7253 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 19.8969 | 99484.5822 | ACTION | 13900.6222 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13901.6222 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13907.1222 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13912.6222 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13914.6222 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13915.6222 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13921.1222 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 5 | 25000 | ACTION | 13926.1222 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13931.6222 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13932.6222 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13947.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 13947.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 14.914 | 74569.9928 | ACTION | 13947.5362 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13948.5362 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 13953.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13954.0362 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13954.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13955.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13959.5362 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13961.5362 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13962.5362 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 13965.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13967.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 13967.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13968.0362 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13971.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13973.5362 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 13973.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13974.5362 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13975.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13987.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 14.914 | 74569.9928 | ACTION | 13989.4502 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13990.4502 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13990.6069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 13993.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13994.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13995.9502 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13997.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 13999.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14001.4502 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14003.4502 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14004.4502 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14009.9502 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 14014.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14015.4502 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14016.4502 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14021.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 11.0794 | 55397.2266 | ACTION | 14027.5297 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14028.5297 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14034.0297 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14039.5297 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14041.5297 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14042.5297 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14048.0297 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14053.5297 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14054.5297 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 11.0794 | 55397.2266 | ACTION | 14065.6091 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14066.6091 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14072.1091 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14077.6091 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 14085.3584 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 7.7493 | 38746.5217 | ACTION | 14093.1077 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14093.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 14093.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14099.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14101.6069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 14112.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14113.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 14114.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14117.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14120.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14121.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14122.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14133.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14137.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14140.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14140.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14144.1069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 14146.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 14161.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14168.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14240.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 14240.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14246.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14248.1069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 14258.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14260.1069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 14260.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14264.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14268.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14280.1069 | MooredSubInstallation
| Towing Group 2 | Delay | 22 | 146666.6667 | ACTION | 14282.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14283.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14287.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14288.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14290.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14290.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 7 | 46666.6667 | ACTION | 14295.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 100000 | ACTION | 14310.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14314.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 34 | 226666.6667 | ACTION | 14344.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 33333.3333 | ACTION | 14349.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 14355.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 14370.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14386.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 14386.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14392.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14394.6069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 14405.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14406.6069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 14407.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14410.6069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14413.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14414.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14426.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14430.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14433.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14433.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14437.1069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 14439.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 14454.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14458.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14461.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14533.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 14533.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14539.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14541.1069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 14551.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14553.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 14553.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14557.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14559.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14561.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14573.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14576.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14579.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14580.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14583.6069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 14585.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 14600.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14607.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14626.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14679.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 308.9162 | 2059441.1111 | ACTION | 14679.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14685.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14687.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 14698.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14699.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 14700.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14703.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14706.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14707.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14719.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14723.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14726.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14726.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14730.1069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 14732.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 14747.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14754.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14794.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14826.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 14826.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14832.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14834.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 14844.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14846.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 14846.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14850.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14852.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14854.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14866.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14869.6069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 14872.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14873.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14876.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 14878.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 14893.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14900.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14962.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14972.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 371.9162 | 2479441.1111 | ACTION | 14972.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 14978.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14980.6069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 14991.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14992.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 14993.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14996.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 14999.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15000.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15012.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 93333.3333 | ACTION | 15013.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 22 | 0 | ACTION | 15034.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15038.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15041.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15045.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15069.1069 | MooredSubInstallation
| Towing Group 1 | Delay | 72 | 480000 | ACTION | 15085.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 40000 | ACTION | 15091.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 15097.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 15112.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15130.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15141.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 393.9162 | 2626107.7778 | ACTION | 15141.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15147.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15149.1069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 15159.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15161.1069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 15161.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15165.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15167.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15169.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15181.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15184.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 15187.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15188.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15191.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 40000 | ACTION | 15193.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 15208.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15215.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15298.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 99 | 0 | ACTION | 15314.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15386.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 492.9162 | 3286107.7778 | ACTION | 15386.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15394.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15406.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15410.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15414.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15426.6069 | MooredSubInstallation
| Towing Group 3 | Delay | 42 | 280000 | ACTION | 15428.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15430.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15433.6069 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15434.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15437.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 15445.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15469.1069 | MooredSubInstallation
| Towing Group 3 | Delay | 44 | 293333.3333 | ACTION | 15478.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 15491.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 15493.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15499.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 15519.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 40000 | ACTION | 15525.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 15540.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15541.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 428.9162 | 2859441.1111 | ACTION | 15541.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15547.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15549.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15561.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15565.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15569.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15581.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15584.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15588.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15591.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15615.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15687.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 478.9162 | 3192774.4444 | ACTION | 15687.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15695.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15707.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 15718.6069 | MooredSubInstallation
| Towing Group 1 | Delay | 175 | 1166666.6667 | ACTION | 15722.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 35 | 233333.3333 | ACTION | 15722.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15722.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15726.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 40000 | ACTION | 15728.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 15734.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 15736.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15738.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 15741.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15742.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15742.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 13333.3333 | ACTION | 15743.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15745.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 26666.6667 | ACTION | 15746.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15749.1069 | MooredSubInstallation
| Towing Group 1 | Delay | 9 | 60000 | ACTION | 15755.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 13 | 86666.6667 | ACTION | 15756.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 40000 | ACTION | 15762.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 106666.6667 | ACTION | 15771.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15773.1069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 15777.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 133333.3333 | ACTION | 15782.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 2 | 13333.3333 | ACTION | 15784.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 15792.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 221 | 0 | ACTION | 15994.1069 | MooredSubInstallation
| Towing Group 2 | Delay | 252 | 1680000 | ACTION | 16036.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 4 | 26666.6667 | ACTION | 16040.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 14.8528 | 99018.8889 | ACTION | 16055.1908 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16066.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 525.9162 | 3506107.7778 | ACTION | 16066.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 40000 | ACTION | 16072.1069 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16074.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 16084.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16086.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 13333.3333 | ACTION | 16086.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16090.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 10 | 0 | ACTION | 16100.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16104.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16116.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 71 | 0 | ACTION | 16187.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16190.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 16193.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16197.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16200.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16224.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 71 | 0 | ACTION | 16295.6069 | MooredSubInstallation
| Towing Group 3 | Delay | 243 | 1620000 | ACTION | 16329.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 40000 | ACTION | 16335.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 86666.6667 | ACTION | 16348.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 4 | 26666.6667 | ACTION | 16352.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 46666.6667 | ACTION | 16359.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 2 | 13333.3333 | ACTION | 16361.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16367.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 574.9162 | 3832774.4444 | ACTION | 16367.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 106 | 706666.6667 | ACTION | 16467.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 101 | 673333.3333 | ACTION | 16468.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 4 | 26666.6667 | ACTION | 16471.8379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 40000 | ACTION | 16474.6069 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 14.8528 | 99018.8889 | ACTION | 16486.6908 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 12.731 | 84873.3333 | ACTION | 16487.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 13333.3333 | ACTION | 16489.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 40000 | ACTION | 16495.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 93333.3333 | ACTION | 16509.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 28 | 186666.6667 | ACTION | 16537.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 40000 | ACTION | 16543.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 40000 | ACTION | 16549.3379 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 14.8528 | 99018.8889 | ACTION | 16564.1908 | MooredSubInstallation | [5 empty] | 2 | 1