## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | include_onshore_construction | max_waveheight | max_windspeed | transit_speed | num_vessels | num_ahts_vessels
0.5 | Export Cable Installation Vessel | Mobilize | 72 | 450000 | ACTION | 0 | ExportCableInstallation
1 | Mooring System Installation Vessel | Mobilize | 168 | 700000 | ACTION | 0 | MooringSystemInstallation
| Export Cable Installation Vessel | Load Cable | 6 | 75000 | ACTION | 6 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Delay | 43 | 179166.6667 | ACTION | 43 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 48 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 53 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 61.9117 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 57 | 712500 | ACTION | 63 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Tow Plow | 0.4 | 5000 | ACTION | 63.4 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Pull Winch | 0.4 | 5000 | ACTION | 63.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 63.9117 | MooringSystemInstallation
| Export Cable Installation Vessel | Prepare Cable | 1 | 12500 | ACTION | 64.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 67.9117 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 70.3 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 75.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Lower Cable | 1 | 12500 | ACTION | 76.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 84.4767 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 89.0417 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 91.0417 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 17 | 212500 | ACTION | 93.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 95.0417 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 111.6067 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 116.1717 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 118.1717 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 122.1717 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 138.7367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 143.3017 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 145.3017 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 149.3017 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 60 | 750000 | ACTION | 153.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 165.8667 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 170.4317 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 172.4317 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 20 | 83333.3333 | ACTION | 192.4317 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 196.4317 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 212.9967 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 217.5617 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 219.5617 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 223.5617 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 17 | 70833.3333 | ACTION | 240.5617 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 103 | 1287500 | ACTION | 256.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 257.1267 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 261.6917 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 270.6034 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 275.6034 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 19 | 237500 | ACTION | 275.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Delay | 1 | 12500 | ACTION | 276.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 280.6034 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 289.5151 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 291.5151 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 295.5151 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 312.0801 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 316.6451 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 318.6451 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 322.6451 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 339.2101 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 64 | 800000 | ACTION | 340.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 343.7751 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 345.7751 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 349.7751 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 9 | 112500 | ACTION | 349.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 1 | 12500 | ACTION | 350.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 366.3401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 370.9051 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 372.9051 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 376.9051 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 186 | 775000 | ACTION | 562.9051 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 228 | 2850000 | ACTION | 578.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 579.4701 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 584.0351 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 586.0351 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 590.0351 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 17 | 212500 | ACTION | 595.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Delay | 46 | 191666.6667 | ACTION | 636.0351 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 652.6001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 657.1651 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 659.1651 | MooringSystemInstallation
| Substation Assembly Line 1 | Substation Substructure Assembly | 0 | 0 | ACTION | 668.187 | FloatingSubstationInstallation
| Substation Assembly Line 1 | Attach Topside | 24 | 0 | ACTION | 692.187 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay: Waiting on Substation Assembly | 24 | 100000 | ACTION | 692.187 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 39 | 162500 | ACTION | 698.1651 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 6 | 25000 | ACTION | 698.187 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 702.1651 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Tow Substation to Site | 14.8528 | 61886.8056 | ACTION | 713.0399 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 715.0399 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 718.7301 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 721.0399 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 723.2951 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 725.0399 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 130 | 1625000 | ACTION | 725.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 732.2068 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 7 | 87500 | ACTION | 732.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 737.2068 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.565 | 64854.1667 | ACTION | 740.6049 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 8 | 100000 | ACTION | 740.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 742.2068 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 745.1699 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 751.1185 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 753.1185 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 14 | 175000 | ACTION | 754.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 757.1185 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 13 | 54166.6667 | ACTION | 758.1699 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 765.1699 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 766.1699 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 773.6835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 778.2485 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 789.2485 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 791.2485 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 16 | 66666.6667 | ACTION | 807.2485 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 811.2485 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 5 | 20833.3333 | ACTION | 816.2485 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 64 | 266666.6667 | ACTION | 830.1699 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 832.8135 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 837.3785 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 8 | 33333.3333 | ACTION | 838.1699 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 839.3785 | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 3 | 12500 | ACTION | 841.1699 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 843.3785 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 851.3785 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 17 | 70833.3333 | ACTION | 858.1699 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 9 | 37500 | ACTION | 867.1699 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 867.9435 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 871.1699 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 872.5085 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 874.5085 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 878.5085 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.565 | 64854.1667 | ACTION | 886.7349 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 891.2999 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 139 | 1737500 | ACTION | 893.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 895.0735 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 899.6385 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 901.6385 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 905.6385 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 913.2999 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 922.2035 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 925.2999 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 926.7685 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 33 | 412500 | ACTION | 926.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 928.7685 | MooringSystemInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 929.2999 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 932.7685 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 60 | 250000 | ACTION | 989.2999 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 58 | 241666.6667 | ACTION | 990.7685 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.565 | 64854.1667 | ACTION | 1004.8649 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1007.3335 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1009.4299 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1011.8985 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 9 | 37500 | ACTION | 1018.4299 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1020.8102 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1025.8102 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1030.8102 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 19 | 79166.6667 | ACTION | 1037.4299 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1039.7219 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1041.7219 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1045.7219 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 18 | 75000 | ACTION | 1055.4299 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 3 | 12500 | ACTION | 1058.4299 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1062.2869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1066.8519 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 142 | 1775000 | ACTION | 1068.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1068.8519 | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1070.4299 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 3 | 37500 | ACTION | 1071.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1072.8519 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1079.3416 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 70 | 291666.6667 | ACTION | 1142.8519 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1159.4169 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1163.9819 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1165.9819 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1169.9819 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 104 | 1300000 | ACTION | 1175.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1186.5469 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 12 | 150000 | ACTION | 1187.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1191.1119 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1193.1119 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1197.1119 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 23 | 95833.3333 | ACTION | 1220.1119 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1236.6769 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1241.2419 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1243.2419 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1247.2419 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1263.8069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1268.3719 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 82 | 1025000 | ACTION | 1269.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1270.3719 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1274.3719 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1290.9369 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1295.5019 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1304.4136 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1309.4136 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1314.4136 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 53 | 662500 | ACTION | 1322.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1323.3253 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1325.3253 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 6 | 75000 | ACTION | 1328.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1329.3253 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 17 | 212500 | ACTION | 1345.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1345.8903 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1350.4553 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1352.4553 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1356.4553 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 32 | 133333.3333 | ACTION | 1388.4553 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1405.0203 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1409.5853 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1411.5853 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1415.5853 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1432.1503 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1436.7153 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1438.7153 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1442.7153 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1459.2803 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1463.8453 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1465.8453 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1469.8453 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 28 | 116666.6667 | ACTION | 1497.8453 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1514.4103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 30 | 125000 | ACTION | 1544.4103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1548.9753 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1550.9753 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1554.9753 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 214 | 2675000 | ACTION | 1559.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 3 | 37500 | ACTION | 1562.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Delay | 5 | 62500 | ACTION | 1567.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 1 | 12500 | ACTION | 1568.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Delay | 1 | 12500 | ACTION | 1569.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1571.5403 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1576.1053 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 12 | 150000 | ACTION | 1581.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1585.017 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1590.017 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1595.017 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1603.9287 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1605.9287 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1609.9287 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 36 | 450000 | ACTION | 1617.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1626.4937 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 11 | 137500 | ACTION | 1628.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Delay | 1 | 12500 | ACTION | 1629.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1631.0587 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 2 | 25000 | ACTION | 1631.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1633.0587 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 1654.0587 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1658.0587 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 34 | 425000 | ACTION | 1665.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 6 | 75000 | ACTION | 1671.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1674.6237 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1679.1887 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1681.1887 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1685.1887 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1701.7537 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 32 | 400000 | ACTION | 1703.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1706.3187 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 3 | 37500 | ACTION | 1706.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1708.3187 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 2 | 25000 | ACTION | 1708.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 3 | 37500 | ACTION | 1711.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1712.3187 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1728.8837 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1733.4487 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1735.4487 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1739.4487 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 1746.4487 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1763.0137 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 55 | 687500 | ACTION | 1766.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1767.5787 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1769.5787 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1773.5787 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 9 | 112500 | ACTION | 1775.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1790.1437 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1794.7087 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1803.6204 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1808.6204 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1813.6204 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 1822.5321 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1824.5321 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1828.5321 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 15 | 62500 | ACTION | 1843.5321 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1860.0971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1864.6621 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1866.6621 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1870.6621 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 109 | 1362500 | ACTION | 1884.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 1 | 12500 | ACTION | 1885.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1887.2271 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 2 | 25000 | ACTION | 1887.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1891.7921 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1893.7921 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1897.7921 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 16 | 200000 | ACTION | 1903.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1914.3571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1918.9221 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1920.9221 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1924.9221 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 1941.4871 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 1946.0521 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1948.0521 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1952.0521 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 57 | 237500 | ACTION | 2009.0521 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2025.6171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2030.1821 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 2037.1821 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2039.1821 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2043.1821 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 79 | 329166.6667 | ACTION | 2122.1821 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2138.7471 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2143.3121 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 248 | 3100000 | ACTION | 2151.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2152.2238 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2157.2238 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2162.2238 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 17 | 212500 | ACTION | 2168.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2171.1355 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2173.1355 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 5 | 62500 | ACTION | 2173.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2177.1355 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 5 | 62500 | ACTION | 2178.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Delay | 51 | 212500 | ACTION | 2228.1355 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 61 | 762500 | ACTION | 2239.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2244.7005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2249.2655 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 10 | 125000 | ACTION | 2249.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2251.2655 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2255.2655 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 96 | 400000 | ACTION | 2351.2655 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2367.8305 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 44 | 183333.3333 | ACTION | 2411.8305 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2416.3955 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2418.3955 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2422.3955 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 178 | 2225000 | ACTION | 2427.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2438.9605 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 13 | 162500 | ACTION | 2440.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2443.5255 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2445.5255 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2449.5255 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2466.0905 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2470.6555 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2472.6555 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2476.6555 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2493.2205 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2497.7855 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2499.7855 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2503.7855 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 78 | 975000 | ACTION | 2518.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2520.3505 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2524.9155 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2533.8272 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2538.8272 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2543.8272 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2552.7389 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2554.7389 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2558.7389 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 40 | 500000 | ACTION | 2558.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2575.3039 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2579.8689 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 23 | 287500 | ACTION | 2581.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2581.8689 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2585.8689 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 6 | 75000 | ACTION | 2587.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Delay | 2 | 25000 | ACTION | 2589.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 6.1988 | 77485.5155 | ACTION | 2595.9988 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Position Onsite | 2 | 25000 | ACTION | 2597.9988 | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2602.4339 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 2609.4339 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2613.9989 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2615.9989 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2619.9989 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2636.5639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2641.1289 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2643.1289 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2647.1289 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 56 | 700000 | ACTION | 2653.9988 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 2659.4988 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2663.6939 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 2664.9988 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2668.2589 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2670.2589 | MooringSystemInstallation
| Export Cable Installation Vessel | Transit | 7.7493 | 96866.3043 | ACTION | 2672.7481 | ExportCableInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2674.2589 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2690.8239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2695.3889 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2697.3889 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2701.3889 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2717.9539 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2722.5189 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2731.4306 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2736.4306 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2741.4306 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2750.3423 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2752.3423 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2756.3423 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2772.9073 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2777.4723 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2779.4723 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2783.4723 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2800.0373 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2804.6023 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2806.6023 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2810.6023 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2827.1673 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2831.7323 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2833.7323 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2837.7323 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2854.2973 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2858.8623 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2860.8623 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2864.8623 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2881.4273 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2885.9923 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2887.9923 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2891.9923 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2908.5573 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2913.1223 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2922.034 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2927.034 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2932.034 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 2940.9457 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2942.9457 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2946.9457 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2963.5107 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2968.0757 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2970.0757 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2974.0757 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 2990.6407 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 2995.2057 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2997.2057 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3001.2057 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3017.7707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3022.3357 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3024.3357 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3028.3357 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3044.9007 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3049.4657 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3051.4657 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3055.4657 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3072.0307 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3076.5957 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3078.5957 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3082.5957 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3099.1607 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3103.7257 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3112.6374 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3117.6374 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3122.6374 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3131.5491 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3133.5491 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3137.5491 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3154.1141 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3158.6791 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3160.6791 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3164.6791 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3181.2441 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3185.8091 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3187.8091 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3191.8091 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3208.3741 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3212.9391 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3214.9391 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3218.9391 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3235.5041 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3240.0691 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3242.0691 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3246.0691 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 20 | 83333.3333 | ACTION | 3266.0691 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3282.6341 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3287.1991 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3289.1991 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3293.1991 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3309.7641 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3314.3291 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3323.2408 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3328.2408 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3333.2408 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3342.1525 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3344.1525 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3348.1525 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3364.7175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3369.2825 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3371.2825 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3375.2825 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3391.8475 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3396.4125 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3398.4125 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3402.4125 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3418.9775 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3423.5425 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3425.5425 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3429.5425 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 3442.5425 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3459.1075 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 3466.1075 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3470.6725 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3472.6725 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3476.6725 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3493.2375 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3497.8025 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3499.8025 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3503.8025 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3520.3675 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3524.9325 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3533.8442 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3538.8442 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3543.8442 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3552.7559 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3554.7559 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3558.7559 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3575.3209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3579.8859 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3581.8859 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3585.8859 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3602.4509 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3607.0159 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3609.0159 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3613.0159 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3629.5809 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3634.1459 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3636.1459 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3640.1459 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3656.7109 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3661.2759 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3663.2759 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3667.2759 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3683.8409 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3688.4059 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3690.4059 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3694.4059 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3710.9709 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3715.5359 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3724.4476 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3729.4476 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3734.4476 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3743.3593 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3745.3593 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3749.3593 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3765.9243 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3770.4893 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3772.4893 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3776.4893 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3793.0543 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3797.6193 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3799.6193 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3803.6193 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3820.1843 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3824.7493 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3826.7493 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3830.7493 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3847.3143 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3851.8793 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3853.8793 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3857.8793 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3874.4443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3879.0093 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3881.0093 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3885.0093 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3901.5743 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3906.1393 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3915.051 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3920.051 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3925.051 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 3933.9627 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3935.9627 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3939.9627 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 3956.5277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 3961.0927 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3963.0927 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3967.0927 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 18 | 75000 | ACTION | 3985.0927 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4001.6577 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4006.2227 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4008.2227 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4012.2227 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4028.7877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4033.3527 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4035.3527 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4039.3527 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4055.9177 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4060.4827 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4062.4827 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4066.4827 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4083.0477 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4087.6127 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4089.6127 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4093.6127 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4110.1777 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4114.7427 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4123.6544 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4128.6544 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4133.6544 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4142.5661 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4144.5661 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4148.5661 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4165.1311 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4169.6961 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4171.6961 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4175.6961 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4192.2611 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4196.8261 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4198.8261 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4202.8261 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4219.3911 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4223.9561 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4225.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 4225.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4225.9561 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4229.9561 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4233.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4245.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4246.5211 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4249.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4251.0861 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4253.0861 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4253.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4257.0861 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4257.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4261.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4273.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4273.6511 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4276.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4278.2161 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4280.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4280.2161 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4283.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4284.2161 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4300.7811 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4305.3461 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4307.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4314.2578 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4319.2578 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4324.2578 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4333.1695 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4335.1695 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4339.1695 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4355.7345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4360.2995 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4362.2995 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4366.2995 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4379.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 322.5 | 2553125 | ACTION | 4379.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4382.8645 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4385.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4387.4295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4389.4295 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4393.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 4393.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4393.4295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4401.1069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 4401.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 4403.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4409.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4409.9945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4413.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4414.5595 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4416.5595 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4417.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4420.5595 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4421.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4425.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4429.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 4429.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 4435.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4437.1245 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4441.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4441.6895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 4442.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4443.6895 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4444.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4447.6895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4448.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4451.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4464.2545 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4468.8195 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4470.8195 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4474.8195 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4475.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4491.3845 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4495.9495 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4504.8612 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4509.8612 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4514.8612 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4523.7729 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4525.7729 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4529.7729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4546.3379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4547.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 490.5 | 3883125 | ACTION | 4547.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4550.9029 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4552.9029 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4553.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4556.9029 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4561.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 4561.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4569.1069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 4569.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 4571.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4573.4679 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4577.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4578.0329 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4580.0329 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4581.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4584.0329 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4585.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4589.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4593.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4597.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 4597.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4600.5979 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 4603.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4605.1629 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4607.1629 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4609.1069 | MooredSubInstallation
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 4610.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4611.1629 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4612.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4616.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4619.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4627.7279 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4632.2929 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4634.2929 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4638.2929 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4643.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4654.8579 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4659.4229 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4661.4229 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4665.4229 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4681.9879 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4686.5529 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4695.4646 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4700.4646 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4705.4646 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4714.3763 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4715.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 658.5 | 5213125 | ACTION | 4715.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4716.3763 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4720.3763 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4721.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4729.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 4729.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4736.9413 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4737.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 4737.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 4739.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4741.5063 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4743.5063 | MooringSystemInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4745.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4747.5063 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4749.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4753.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4757.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4761.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4764.0713 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4765.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 4765.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4768.6363 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4770.6363 | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 4771.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4774.6363 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4777.1069 | MooredSubInstallation
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 4778.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4780.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4784.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4787.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4791.2013 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4795.7663 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4797.7663 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4801.7663 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4811.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4818.3313 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4822.8963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4824.8963 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4828.8963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4845.4613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4850.0263 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4852.0263 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4856.0263 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4872.5913 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4877.1563 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4883.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 441.4314 | 3494665.322 | ACTION | 4883.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4886.068 | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 4889.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4891.068 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4896.068 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4897.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 4897.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 4904.9797 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4905.1069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 4905.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4906.9797 | MooringSystemInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 4907.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4910.9797 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 4913.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4917.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4921.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4925.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4927.5447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4929.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4932.1097 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4933.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 4933.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4934.1097 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4938.1097 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 4939.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4945.1069 | MooredSubInstallation
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 4946.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 4949.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4952.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4954.6747 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4956.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4959.2397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4959.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4961.2397 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4965.2397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 4981.8047 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4983.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 4986.3697 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4988.3697 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4992.3697 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5008.9347 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5013.4997 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5015.4997 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5019.4997 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5036.0647 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5040.6297 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5042.6297 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5046.6297 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5055.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 445.4314 | 3526331.9886 | ACTION | 5055.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5061.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5063.1947 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5065.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 9.5 | 0 | ACTION | 5065.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5067.7597 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5073.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5076.6714 | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 5077.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 5079.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5081.6714 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5085.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5085.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5086.6714 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5089.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5093.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5095.5831 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5097.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5097.5831 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5101.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5101.5831 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5105.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 5111.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5113.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5118.1481 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 5118.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 5119.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5122.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5122.7131 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5124.7131 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5126.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5128.7131 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5129.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5145.2781 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5149.8431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5151.8431 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5153.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5155.8431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5172.4081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5176.9731 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5178.9731 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5182.9731 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5199.5381 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5204.1031 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5206.1031 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5210.1031 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5225.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 447.4314 | 3542165.322 | ACTION | 5225.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5226.6681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5231.2331 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5231.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5233.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 7.5 | 0 | ACTION | 5233.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5233.2331 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5237.2331 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5241.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 5247.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 5249.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5253.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5253.7981 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5255.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5257.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5258.3631 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5261.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5265.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5267.2748 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5269.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5272.2748 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5275.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5277.2748 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5281.1069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 5281.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5284.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5286.1865 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5288.1069 | MooredSubInstallation
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 5288.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5288.1865 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5291.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5292.1865 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5308.7515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5313.3165 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5315.3165 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5315.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5319.3165 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5335.8815 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5340.4465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5342.4465 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5346.4465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5363.0115 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5367.5765 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5369.5765 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5373.5765 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5387.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 441.4314 | 3494665.322 | ACTION | 5387.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5390.1415 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5393.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5394.7065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5396.7065 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5400.7065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5401.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 5401.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5409.1069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 5409.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 5411.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5417.2715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5417.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5421.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5421.8365 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5423.8365 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5425.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5427.8365 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5429.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5433.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5437.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5437.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 5443.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5444.4015 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5448.9665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5449.1069 | MooredSubInstallation
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 5450.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5452.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5456.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5457.8782 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5459.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5462.8782 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5467.8782 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5476.7899 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5478.7899 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5482.7899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5483.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5499.3549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5503.9199 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5505.9199 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5509.9199 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5526.4849 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5531.0499 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5533.0499 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5537.0499 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5553.6149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5555.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 437.4314 | 3462998.6553 | ACTION | 5555.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5558.1799 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5560.1799 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5561.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5564.1799 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5569.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 5569.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5577.1069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 5577.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 5579.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5580.7449 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5585.3099 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5585.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5587.3099 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5589.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5591.3099 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5593.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5597.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5601.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5605.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5605.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5607.8749 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 5611.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5612.4399 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5614.4399 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5617.1069 | MooredSubInstallation
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 5618.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5618.4399 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5620.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5624.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5627.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5635.0049 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5639.5699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5648.4816 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5651.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5653.4816 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5658.4816 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5667.3933 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5669.3933 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5673.3933 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5689.9583 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5694.5233 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5696.5233 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5700.5233 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5717.0883 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5721.6533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5723.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 435.4314 | 3447165.322 | ACTION | 5723.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5723.6533 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5727.6533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5729.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5737.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 5737.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5744.2183 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5745.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 5745.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 5747.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5748.7833 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5750.7833 | MooringSystemInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5753.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5754.7833 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5757.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5761.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5765.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5769.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5771.3483 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5773.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5773.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5775.9133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5777.9133 | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 5779.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5781.9133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5785.1069 | MooredSubInstallation
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 5786.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5788.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5792.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5795.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5798.4783 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5803.0433 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5805.0433 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5809.0433 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5819.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5825.6083 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5830.1733 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5839.085 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5844.085 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5849.085 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 5857.9967 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5859.9967 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5863.9967 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5880.5617 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5885.1267 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5887.1267 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5891.1267 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5891.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 441.4314 | 3494665.322 | ACTION | 5891.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 5897.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5905.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 5905.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5907.6917 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5912.2567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5913.1069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 5913.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5914.2567 | MooringSystemInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 5915.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5918.2567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 5921.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5925.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5929.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5933.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5934.8217 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5937.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5939.3867 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5941.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5941.3867 | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 5941.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5945.3867 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 5947.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5953.1069 | MooredSubInstallation
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 5954.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5956.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5960.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5961.9517 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5963.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5966.5167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5968.5167 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5972.5167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5987.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 5989.0817 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 5993.6467 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5995.6467 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5999.6467 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6016.2117 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6020.7767 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6029.6884 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6034.6884 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6039.6884 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6048.6001 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6050.6001 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6054.6001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6059.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 441.4314 | 3494665.322 | ACTION | 6059.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6065.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6071.1651 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6073.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 6073.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6075.7301 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6077.7301 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6081.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6081.7301 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 6081.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 6083.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6089.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6093.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6097.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6098.2951 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6101.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6102.8601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6104.8601 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6105.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6108.8601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6109.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6109.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 6115.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6121.1069 | MooredSubInstallation
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 6122.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6125.4251 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 6129.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6129.9901 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6131.9901 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6132.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6135.9901 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6136.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6139.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6152.5551 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6157.1201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6159.1201 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6163.1201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6163.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6179.6851 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6184.2501 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6186.2501 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6190.2501 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6206.8151 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6211.3801 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6220.2918 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6225.2918 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6230.2918 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6235.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 449.4314 | 3557998.6553 | ACTION | 6235.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6239.2035 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6241.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 5.5 | 0 | ACTION | 6241.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6241.2035 | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6241.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6245.2035 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6249.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 6257.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 6259.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6261.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6261.7685 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6265.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6269.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6273.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6277.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6289.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 29 | 120833.3333 | ACTION | 6290.7685 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6292.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6295.3335 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 36 | 285000 | ACTION | 6295.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6296.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6297.3335 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6299.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6301.3335 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6301.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 102916.6667 | ACTION | 6314.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 3 | 23750 | ACTION | 6317.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6317.8985 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6322.4635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6323.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6324.4635 | MooringSystemInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 55416.6667 | ACTION | 6324.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6328.4635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 6330.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 6337.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6345.0285 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6349.5935 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6351.5935 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6355.5935 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6372.1585 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6376.7235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6378.7235 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6382.7235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6395.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 441.4314 | 3494665.322 | ACTION | 6395.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6399.2885 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6401.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6403.8535 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6405.8535 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6409.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 6409.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6409.8535 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6417.1069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 6417.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 6419.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6425.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6426.4185 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6429.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6430.9835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6433.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6437.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6439.8952 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6441.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6444.8952 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6445.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6445.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6449.8952 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 6451.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6457.1069 | MooredSubInstallation
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 6458.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6458.8069 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6460.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6460.8069 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6464.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6464.8069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6467.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6481.3719 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6485.9369 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6487.9369 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6491.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6491.9369 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6508.5019 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6513.0669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6515.0669 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6519.0669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6535.6319 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6540.1969 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6542.1969 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6546.1969 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6562.7619 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6563.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 441.4314 | 3494665.322 | ACTION | 6563.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6567.3269 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6569.3269 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6569.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6573.3269 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6577.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 6577.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6585.1069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 6585.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 6587.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6589.8919 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6593.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6594.4569 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6596.4569 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6597.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6600.4569 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6601.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6605.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6609.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6613.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6613.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6617.0219 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 6619.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6621.5869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6625.1069 | MooredSubInstallation
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 6626.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6628.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6630.4986 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6632.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6635.4986 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6635.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6640.4986 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6649.4103 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6651.4103 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6655.4103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6659.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6671.9753 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6676.5403 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6678.5403 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6682.5403 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6699.1053 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6703.6703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6705.6703 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6709.6703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6731.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 394.4314 | 3122581.9886 | ACTION | 6731.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6745.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 6745.1069 | MooredSubInstallation
| Towing Group 3 | Delay | 20 | 158333.3333 | ACTION | 6751.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 43 | 179166.6667 | ACTION | 6752.6703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6753.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6757.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6765.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6769.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6769.2353 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6773.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6773.8003 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 6773.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6775.8003 | MooringSystemInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 6775.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6777.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6779.8003 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6781.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6781.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6793.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6796.3653 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6796.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6800.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6800.9303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6802.9303 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6803.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6806.9303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 41 | 324583.3333 | ACTION | 6822.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6823.4953 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6827.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6828.0603 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6830.0603 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6834.0603 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 126666.6667 | ACTION | 6838.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6850.6253 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6855.1903 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6864.102 | MooringSystemInstallation
| Towing Group 3 | Delay | 28 | 221666.6667 | ACTION | 6866.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6869.102 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 31666.6667 | ACTION | 6870.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6874.102 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 6876.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 6883.0137 | MooringSystemInstallation
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 6883.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6885.0137 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6889.0137 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6899.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 441.4314 | 3494665.322 | ACTION | 6899.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6905.5787 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6905.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6910.1437 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6912.1437 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6913.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 6913.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6916.1437 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6921.1069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 6921.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 6923.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6929.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6932.7087 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6933.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6937.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 6937.2737 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 63333.3333 | ACTION | 6937.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6939.2737 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6941.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6943.2737 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6945.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 6951.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6955.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 6956.2737 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 27 | 213750 | ACTION | 6964.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6967.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6970.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 55416.6667 | ACTION | 6971.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 6972.8387 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 33 | 0 | ACTION | 7003.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7007.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7010.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7034.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 28 | 0 | ACTION | 7062.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7081.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 139 | 579166.6667 | ACTION | 7111.8387 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7116.4037 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 146 | 1155833.3333 | ACTION | 7117.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7118.4037 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7122.4037 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 39583.3333 | ACTION | 7122.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 7128.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7134.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 508.4314 | 4025081.9886 | ACTION | 7134.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 7135.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7138.9687 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7140.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7142.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7143.5337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7145.5337 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7149.5337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7154.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 7156.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7158.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 7158.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7162.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7164.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7166.0987 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7166.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7170.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7170.6637 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7172.6637 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7176.6637 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7182.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7184.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7186.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7189.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 7190.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7193.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7193.2287 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 7197.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7197.7937 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 7206.7054 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7211.7054 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7216.7054 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7217.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 7225.6171 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7227.6171 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7231.6171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7248.1821 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7249.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7252.7471 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7254.7471 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7258.7471 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7275.3121 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7279.8771 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7281.8771 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7285.8771 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7289.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 405.9314 | 3213623.6553 | ACTION | 7289.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7295.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7297.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7302.4421 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7307.0071 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7309.0071 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7309.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 7311.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7313.0071 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7313.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7317.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7321.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7325.1069 | MooredSubInstallation
| Towing Group 3 | Delay | 14 | 110833.3333 | ACTION | 7325.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 7327.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7329.5721 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7333.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7334.1371 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7916.6667 | ACTION | 7334.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7336.1371 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7337.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 7344.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7347.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7351.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7354.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 7357.1371 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7361.1371 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 28 | 221666.6667 | ACTION | 7362.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7377.7021 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7378.6069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 19 | 150416.6667 | ACTION | 7381.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7382.2671 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7384.2671 | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 7387.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7388.2671 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 7393.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7404.8321 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7409.3971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7417.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 7418.3088 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7423.3088 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7428.3088 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 7437.2205 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7439.2205 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7443.2205 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7450.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 315.4314 | 2497165.322 | ACTION | 7450.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7456.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7458.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7459.7855 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7464.3505 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7466.3505 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7470.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 31 | 0 | ACTION | 7501.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7505.6069 | MooredSubInstallation
| Towing Group 1 | Delay | 51 | 403750 | ACTION | 7507.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 42 | 175000 | ACTION | 7508.3505 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7509.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7512.3505 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7513.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7517.6069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 7523.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 7525.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7528.9155 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7529.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7531.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7533.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7533.4805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7535.4805 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7536.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7539.4805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7540.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7551.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7556.0455 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 7557.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7560.6105 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7562.6105 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7564.1069 | MooredSubInstallation
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 7564.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7566.6105 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7583.1755 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7585.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 72 | 0 | ACTION | 7636.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 80 | 333333.3333 | ACTION | 7663.1755 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7667.7405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7669.7405 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7673.7405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7690.3055 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7694.8705 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7696.8705 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7700.8705 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7708.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 510.9314 | 4044873.6553 | ACTION | 7708.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7714.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7716.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7717.4355 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7722.0005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7728.1069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 7730.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 8.9117 | 37132.0833 | ACTION | 7730.9122 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7732.1069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 7732.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7735.9122 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 6 | 25000 | ACTION | 7741.9122 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7753.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 25 | 0 | ACTION | 7757.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7761.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7765.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7769.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 31 | 129166.6667 | ACTION | 7772.9122 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2.9117 | 12132.0833 | ACTION | 7775.8239 | MooringSystemInstallation
| Towing Group 2 | Delay | 44 | 348333.3333 | ACTION | 7776.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7777.8239 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7781.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7781.8239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7782.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 39583.3333 | ACTION | 7787.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 52 | 0 | ACTION | 7833.1069 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 54 | 225000 | ACTION | 7835.8239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7836.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7840.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7843.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7852.3889 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7856.9539 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7858.9539 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7862.9539 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 76 | 601666.6667 | ACTION | 7863.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 7866.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7867.6069 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 7879.5189 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 7884.0839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7886.0839 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7890.0839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7921.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 89 | 0 | ACTION | 7956.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8028.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 634.9314 | 5026540.322 | ACTION | 8028.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8036.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8048.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8052.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8056.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8060.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8064.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8076.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 8078.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8082.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8089.1069 | MooredSubInstallation
| Towing Group 3 | Delay | 64 | 506666.6667 | ACTION | 8092.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 203 | 845833.3333 | ACTION | 8093.0839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 8093.1069 | MooredSubInstallation
| Towing Group 2 | Delay | 230 | 1820833.3333 | ACTION | 8096.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8096.6069 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8098.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8100.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 95000 | ACTION | 8108.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.565 | 69020.8333 | ACTION | 8109.6489 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.565 | 19020.8333 | ACTION | 8114.2139 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 8114.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 8114.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 8116.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 8120.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8122.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8124.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 15833.3333 | ACTION | 8124.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 25 | 197916.6667 | ACTION | 8149.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 102916.6667 | ACTION | 8162.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 2 | 15833.3333 | ACTION | 8164.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 39583.3333 | ACTION | 8169.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 8175.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 8182.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8196.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 631.9314 | 5002790.322 | ACTION | 8196.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8202.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8204.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8216.1069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 8218.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8220.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 8220.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8224.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8226.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8228.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8232.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8244.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 8246.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8247.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8251.1069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 8252.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8254.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8257.1069 | MooredSubInstallation
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 8258.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8278.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8350.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 229.9314 | 1820290.322 | ACTION | 8350.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8356.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8358.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8370.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 8372.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8374.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8378.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8382.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8386.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 14 | 110833.3333 | ACTION | 8386.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 8388.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8394.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8398.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8402.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 8407.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8410.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8414.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 8414.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 8420.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8425.1069 | MooredSubInstallation
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 8427.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8438.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 24 | 0 | ACTION | 8462.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8534.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 351.9314 | 2786123.6553 | ACTION | 8534.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8540.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8542.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8554.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 8556.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8558.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 8558.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8562.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8564.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8566.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8570.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8582.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 8583.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 8584.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8586.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8590.1069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 8590.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8593.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 8593.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8596.6069 | MooredSubInstallation
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 8596.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8620.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8692.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 433.9314 | 3435290.322 | ACTION | 8692.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8698.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8700.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8712.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 8717.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8721.6069 | MooredSubInstallation
| Towing Group 1 | Delay | 25 | 197916.6667 | ACTION | 8723.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8725.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8729.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8733.6069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 8739.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 8741.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8745.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8747.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8749.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8752.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8756.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8761.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 8767.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 8773.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8780.1069 | MooredSubInstallation
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 8780.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8852.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 424.9314 | 3364040.322 | ACTION | 8852.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8858.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8860.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8872.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 8875.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8879.1069 | MooredSubInstallation
| Towing Group 2 | Delay | 26 | 205833.3333 | ACTION | 8884.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 8884.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8888.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8892.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8896.1069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 8900.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 2 | 15833.3333 | ACTION | 8902.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 8904.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8908.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8910.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8911.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 55416.6667 | ACTION | 8917.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8929.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 19 | 0 | ACTION | 8930.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8934.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8937.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8961.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 67 | 530416.6667 | ACTION | 8984.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 102916.6667 | ACTION | 8997.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 5 | 39583.3333 | ACTION | 9002.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 55 | 0 | ACTION | 9016.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 58 | 459166.6667 | ACTION | 9060.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 1 | 7916.6667 | ACTION | 9061.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 9067.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9088.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 491.9314 | 3894456.9886 | ACTION | 9088.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9094.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9096.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9097.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9108.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9112.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 9126.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9130.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9134.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9138.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9150.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 62 | 0 | ACTION | 9212.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9216.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9219.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9223.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 31 | 0 | ACTION | 9254.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9265.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9278.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 28 | 0 | ACTION | 9306.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9378.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 597.9314 | 4733623.6553 | ACTION | 9378.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9386.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9398.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 9401.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9405.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9409.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9413.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9417.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9433.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 32 | 0 | ACTION | 9449.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9461.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9464.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 9468.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9472.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9475.6069 | MooredSubInstallation
| Towing Group 3 | Delay | 401 | 3174583.3333 | ACTION | 9495.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 118 | 934166.6667 | ACTION | 9496.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9499.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9502.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 9511.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 9513.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 9518.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9519.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 9520.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9526.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9539.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 9545.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9546.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 9552.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 9552.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 9558.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9571.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 503.9314 | 3989456.9886 | ACTION | 9571.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9577.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9579.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9591.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 9593.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9595.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 9595.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9599.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9601.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9601.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9603.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9607.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9619.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9621.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9623.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9626.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 9627.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9630.1069 | MooredSubInstallation
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 9634.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9654.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9726.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 173.9314 | 1376956.9886 | ACTION | 9726.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9732.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9734.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9746.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 9748.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9750.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 9750.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9754.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9756.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9758.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9762.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9769.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9774.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9776.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9777.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9781.1069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 9782.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9784.6069 | MooredSubInstallation
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 9788.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9808.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9880.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 321.9314 | 2548623.6553 | ACTION | 9880.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9886.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9888.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9900.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 9927.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9931.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9935.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9937.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 9940.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9944.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9948.6069 | MooredSubInstallation
| Towing Group 1 | Delay | 67 | 530416.6667 | ACTION | 9953.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9960.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9964.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9967.6069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 9969.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9971.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 9971.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9977.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9995.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9997.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 10003.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 10010.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10067.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 432.9314 | 3427373.6553 | ACTION | 10067.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10075.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10087.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 10095.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10099.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10103.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10105.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10107.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10111.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10123.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10126.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10130.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10133.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 71 | 562083.3333 | ACTION | 10138.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 10144.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10157.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 10160.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 19 | 0 | ACTION | 10176.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 76 | 601666.6667 | ACTION | 10236.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 10238.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 10244.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10248.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 459.9314 | 3641123.6553 | ACTION | 10248.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 10254.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10256.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 10264.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10268.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 10270.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 10270.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10272.6069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 10272.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10273.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10276.6069 | MooredSubInstallation
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 10276.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 10278.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10280.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10284.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10296.6069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 10298.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10300.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10303.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 10304.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10307.1069 | MooredSubInstallation
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 10311.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10331.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 10358.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10430.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 419.9314 | 3324456.9886 | ACTION | 10430.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 10436.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10438.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10441.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10450.1069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 10452.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10454.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 10454.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10458.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 10460.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10462.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10466.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 118750 | ACTION | 10475.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10478.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 10491.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10494.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10498.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10501.6069 | MooredSubInstallation
| Towing Group 1 | Delay | 33 | 261250 | ACTION | 10508.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 39583.3333 | ACTION | 10513.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 10519.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10525.6069 | MooredSubInstallation
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 10525.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10597.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 320.9314 | 2540706.9886 | ACTION | 10597.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 10603.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10605.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10609.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10617.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 10619.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10621.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 10621.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10625.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 10627.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10629.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10633.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10645.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 10647.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10649.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10652.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 10653.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10656.1069 | MooredSubInstallation
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 10660.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10680.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10752.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 440.9314 | 3490706.9886 | ACTION | 10752.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 10758.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10760.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10772.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 10774.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10776.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 10776.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10777.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10780.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 10782.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10784.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10788.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10800.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 10802.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10803.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10807.1069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 10808.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 10812.1069 | MooredSubInstallation
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 10814.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10815.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10839.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10911.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 385.9314 | 3055290.322 | ACTION | 10911.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 10917.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10919.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10931.6069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 10933.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10935.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 10935.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10939.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 10941.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10943.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10945.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10947.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 63333.3333 | ACTION | 10949.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 10952.6069 | MooredSubInstallation
| Towing Group 1 | Delay | 13 | 102916.6667 | ACTION | 10962.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10964.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 15833.3333 | ACTION | 10964.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 1 | 7916.6667 | ACTION | 10965.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10968.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10971.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10975.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 10 | 79166.6667 | ACTION | 10975.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 10981.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 10988.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10999.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11071.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 410.9314 | 3253206.9886 | ACTION | 11071.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11079.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11091.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 11107.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11111.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11113.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11115.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11119.1069 | MooredSubInstallation
| Towing Group 2 | Delay | 50 | 395833.3333 | ACTION | 11121.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11123.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11127.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11135.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11138.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 11143.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 38 | 0 | ACTION | 11176.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11180.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11183.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11207.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11279.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 464.9314 | 3680706.9886 | ACTION | 11279.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11281.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11287.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11299.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 11306.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11310.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11314.6069 | MooredSubInstallation
| Towing Group 3 | Delay | 38 | 300833.3333 | ACTION | 11317.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11318.6069 | MooredSubInstallation
| Towing Group 2 | Delay | 179 | 1417083.3333 | ACTION | 11322.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11322.6069 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11323.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 11324.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11330.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11334.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11338.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 11339.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11341.6069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 11341.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11345.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11347.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11350.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 11356.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 11362.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11367.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11369.1069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 11373.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 11380.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11441.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 452.9314 | 3585706.9886 | ACTION | 11441.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11447.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11449.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11449.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11461.1069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 11463.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11465.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 11465.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11469.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11471.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11473.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11477.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 102916.6667 | ACTION | 11484.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11489.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11492.6069 | MooredSubInstallation
| Towing Group 1 | Delay | 9 | 71250 | ACTION | 11493.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11496.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 55416.6667 | ACTION | 11500.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 11503.1069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 11506.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11506.6069 | MooredSubInstallation
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 11512.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11530.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11602.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 239.9314 | 1899456.9886 | ACTION | 11602.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11608.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11610.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11617.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11622.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 11624.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11626.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 11626.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11630.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11632.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11634.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11638.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11650.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11652.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11654.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11657.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 11658.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11661.1069 | MooredSubInstallation
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 11665.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11685.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11757.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 376.9314 | 2984040.322 | ACTION | 11757.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11763.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11765.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11777.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 11779.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11781.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 11781.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11785.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11785.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11787.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11789.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11793.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11805.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11807.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11808.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11812.1069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 11813.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11815.6069 | MooredSubInstallation
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 11819.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11839.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11911.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 398.9314 | 3158206.9886 | ACTION | 11911.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11917.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11919.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11931.6069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 11933.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11935.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 11935.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11939.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11941.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11943.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11947.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11953.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11959.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11961.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11963.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11966.6069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 11967.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11970.1069 | MooredSubInstallation
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 11974.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11994.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12066.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 12066.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12072.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12074.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12086.1069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 12088.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12090.1069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 12090.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12094.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12096.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12098.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12102.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12114.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 12116.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12117.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12121.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12121.1069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 12122.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12124.6069 | MooredSubInstallation
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 12128.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12148.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12220.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 12220.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12226.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12228.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12240.6069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 12242.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12244.6069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 12244.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12248.6069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12250.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12252.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12256.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12268.6069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 12270.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12272.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12275.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 12276.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12279.1069 | MooredSubInstallation
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 12283.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12289.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12303.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12375.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 12375.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12381.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12383.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12395.1069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 12397.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12399.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 12399.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12403.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12405.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12407.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12411.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12423.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 12425.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12426.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12430.1069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 12431.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12433.6069 | MooredSubInstallation
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 12437.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12457.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12457.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12529.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 12529.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12535.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12537.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12549.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 12551.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12553.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 12553.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12557.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12559.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12561.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12565.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12577.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 12579.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12581.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12584.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 12585.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12588.1069 | MooredSubInstallation
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 12592.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12612.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12625.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12684.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 12684.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12690.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12692.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12704.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 12706.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12708.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 12708.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12712.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12714.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12716.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12720.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12732.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 12734.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12735.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12739.1069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 12740.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12742.6069 | MooredSubInstallation
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 12746.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12766.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12793.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12838.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 12838.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12844.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12846.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12858.6069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 12860.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12862.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 12862.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12866.6069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12868.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12870.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12874.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12886.6069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 12888.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12890.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12893.6069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 12894.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12897.1069 | MooredSubInstallation
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 12901.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12921.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12961.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12993.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 12993.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12999.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13001.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13013.1069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 13015.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13017.1069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 13017.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13021.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13023.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13025.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13029.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13041.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13043.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13044.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13048.1069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 13049.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13051.6069 | MooredSubInstallation
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 13055.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13075.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13129.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13147.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 13147.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13153.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13155.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13167.6069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 13169.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13171.6069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 13171.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13175.6069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13177.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13179.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13183.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13195.6069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13197.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13199.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13202.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 13203.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13206.1069 | MooredSubInstallation
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 13210.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13230.1069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13297.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13302.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 13302.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13308.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13310.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13322.1069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 13324.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13326.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 13326.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13330.1069 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13332.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13334.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13338.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13350.1069 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13352.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 13353.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13356.6069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 13358.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13360.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13363.6069 | MooredSubInstallation
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 13364.6755 | MooredSubInstallation | [5 empty] | 3 | 1
0.5 | Array Cable Installation Vessel | Mobilize | 72 | 337500 | ACTION | 13372.3618 | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 56250 | ACTION | 13378.3618 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13387.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 55 | 515625 | ACTION | 13433.3618 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 7.7493 | 72649.7283 | ACTION | 13441.1111 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13443.1111 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13444.1111 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13449.6111 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13455.1111 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13456.1111 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13459.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 403.9314 | 3197790.322 | ACTION | 13459.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13465.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13465.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13467.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 16.0719 | 150673.7741 | ACTION | 13472.183 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13473.183 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13478.683 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13479.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 13481.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13483.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 13483.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13484.183 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13486.183 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13487.183 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13487.6069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13489.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13491.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13492.683 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13495.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13498.183 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13499.183 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13507.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13509.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13511.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13514.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 16.0719 | 150673.7741 | ACTION | 13515.2549 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 13515.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13516.2549 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13518.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13521.7549 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 13522.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13527.2549 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13529.2549 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13530.2549 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13535.7549 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13541.2549 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13542.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13542.2549 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 13547.2385 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13548.2385 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13553.7385 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13559.2385 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13561.2385 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13562.2385 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13567.7385 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 3 | 28125 | ACTION | 13570.7385 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13576.2385 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13577.2385 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 13582.2221 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13583.2221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13588.7221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 10 | 93750 | ACTION | 13598.7221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13604.2221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13606.2221 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13607.2221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13612.7221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13614.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 403.9314 | 3197790.322 | ACTION | 13614.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13618.2221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13619.2221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13620.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13622.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 13624.2058 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13625.2058 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13630.7058 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13633.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13634.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13636.2058 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 13636.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13638.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13638.2058 | ArrayCableInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 13638.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13639.2058 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13642.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13644.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13644.7058 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13646.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13650.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13650.2058 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13651.2058 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 13656.1894 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13657.1894 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13662.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13662.6894 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13664.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13665.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13668.1894 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13669.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13670.1894 | ArrayCableInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 13670.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13671.1894 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13672.6069 | MooredSubInstallation
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 13676.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13676.6894 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13682.1894 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13683.1894 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 13688.1731 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13689.1731 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13694.6731 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13696.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13700.1731 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13702.1731 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13703.1731 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13708.6731 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13714.1731 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13715.1731 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 13720.1567 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13721.1567 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13726.6567 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13732.1567 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13734.1567 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13735.1567 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13740.6567 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13746.1567 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13747.1567 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 13752.1403 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13753.1403 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13758.6403 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13764.1403 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13766.1403 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13767.1403 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13768.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 403.9314 | 3197790.322 | ACTION | 13768.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13772.6403 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13774.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13776.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13778.1403 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13779.1403 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 13784.124 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13785.124 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13788.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13790.624 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 13790.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13792.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 13792.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13796.124 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13796.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13798.124 | ArrayCableInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13798.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13799.124 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13800.6069 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13801.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13804.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13804.624 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13810.124 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13811.124 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 13816.1076 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13816.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13817.1076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13818.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13820.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13822.6076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13823.6069 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 13824.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13827.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13828.1076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13830.1076 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13831.1076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 13831.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13836.6076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13842.1076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13843.1076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 13848.0913 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13849.0913 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13851.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13854.5913 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13860.0913 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13862.0913 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13863.0913 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13868.5913 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13874.0913 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13875.0913 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 13880.0749 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13881.0749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13886.5749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13892.0749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13894.0749 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13895.0749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13900.5749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13906.0749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13907.0749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 13912.0585 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13913.0585 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13918.5585 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13923.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 13923.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13924.0585 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13926.0585 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13927.0585 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13929.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13931.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13932.5585 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13938.0585 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13939.0585 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13943.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 13944.0422 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13945.0422 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 13945.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13947.1069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 13947.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13950.5422 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13951.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13953.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13955.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13956.0422 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13958.0422 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13959.0422 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13959.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13964.5422 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13969.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13970.0422 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13971.0422 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13971.1069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13973.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13974.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 13976.0258 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13977.0258 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13978.1069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 13979.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13981.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13982.5258 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 13985.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13988.0258 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13990.0258 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13991.0258 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13996.5258 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14002.0258 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14003.0258 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14005.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14008.0094 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14009.0094 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14014.5094 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14020.0094 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14022.0094 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14023.0094 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14028.5094 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14034.0094 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14035.0094 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14039.9931 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14040.9931 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14046.4931 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14051.9931 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14053.9931 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14054.9931 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14060.4931 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14065.9931 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14066.9931 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14071.9767 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14072.9767 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14077.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 14077.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14078.4767 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14083.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14083.9767 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14085.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14085.9767 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14086.9767 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14092.4767 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14097.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14097.9767 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14098.9767 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 14099.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14101.6069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 14101.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14103.9604 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14104.9604 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14105.6069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14107.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14109.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14110.4604 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14113.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14115.9604 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14117.9604 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14118.9604 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14124.4604 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14125.6069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14127.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14129.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14129.9604 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14130.9604 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14132.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 14133.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14135.944 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14136.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14136.944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14137.1069 | MooredSubInstallation
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 14140.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14142.444 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14147.944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14149.944 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14150.944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14156.444 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14160.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14161.944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14162.944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14167.9276 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14168.9276 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14174.4276 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14179.9276 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14181.9276 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14182.9276 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14188.4276 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 29 | 271875 | ACTION | 14217.4276 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14222.9276 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14223.9276 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14228.9113 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14229.9113 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14232.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 14232.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14235.4113 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14238.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14240.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14240.9113 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14242.9113 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14243.9113 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14249.4113 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14252.1069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 14254.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14254.9113 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14255.9113 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14256.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 14256.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14260.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14260.8949 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14261.8949 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14262.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14264.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14267.3949 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14268.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14272.8949 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14274.8949 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14275.8949 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14280.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14281.3949 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14282.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14283.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14286.8949 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14287.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14287.8949 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 14288.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14290.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14292.8786 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14293.8786 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 14294.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14299.3786 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14304.8786 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14305.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14306.8786 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14307.8786 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14313.3786 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14314.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14318.8786 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14319.8786 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14324.8622 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14325.8622 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14331.3622 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14336.8622 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14338.8622 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14339.8622 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14345.3622 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14350.8622 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14351.8622 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14356.8458 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14357.8458 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14363.3458 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14368.8458 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14370.8458 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14371.8458 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14377.3458 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14382.8458 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14383.8458 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14386.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 14386.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14388.8295 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14389.8295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14392.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14394.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14395.3295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14400.8295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14402.8295 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14403.8295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14406.6069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 14408.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14410.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 14410.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14414.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 12 | 112500 | ACTION | 14415.8295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14416.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14418.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14421.3295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14422.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14426.8295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14427.8295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14432.8131 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14433.8131 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14434.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14436.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14438.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14439.3131 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14441.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 14442.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14444.8131 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14445.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14446.8131 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14447.8131 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 14449.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14453.3131 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14458.8131 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14459.8131 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14464.7967 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14465.7967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14469.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14471.2967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14473.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 24 | 225000 | ACTION | 14495.2967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14500.7967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14502.7967 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14503.7967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14509.2967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14514.7967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14515.7967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14520.7804 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14521.7804 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14527.2804 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14532.7804 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14534.7804 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14535.7804 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14541.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 14541.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14541.2804 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14546.7804 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14547.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14547.7804 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14549.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14552.764 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14553.764 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14559.264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14561.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 14563.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14564.764 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14565.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 14565.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14566.764 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14567.764 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14569.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14571.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14573.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14573.264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14577.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14578.764 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14579.764 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14584.7477 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14585.7477 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14589.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14591.2477 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14591.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14592.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14596.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14596.7477 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 14597.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14598.7477 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14599.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14599.7477 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 14603.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14605.2477 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14610.7477 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14611.7477 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14616.7313 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14617.7313 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14623.2313 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14623.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14628.7313 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14630.7313 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14631.7313 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14637.2313 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14641.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14642.7313 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14643.7313 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14648.7149 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14649.7149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14655.2149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14660.7149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14662.7149 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14663.7149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14669.2149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14674.7149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14675.7149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14680.6986 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14681.6986 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14687.1986 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14692.6986 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14694.6986 | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14695.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 14695.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14695.6986 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14701.1986 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14701.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14703.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14706.6986 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14707.6986 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14712.6822 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14713.6822 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14715.6069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 14717.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14719.1822 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14719.6069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 14719.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14723.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14724.6822 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14725.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14726.6822 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14727.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14727.6822 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14731.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14733.1822 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14738.6822 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14739.6822 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14743.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14744.6659 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14745.6659 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14745.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14747.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14750.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14751.1659 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 14751.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14754.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14756.6659 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 14758.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14758.6659 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14759.6659 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14765.1659 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14770.6659 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14771.6659 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14776.6495 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14777.6495 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14778.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14783.1495 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14788.6495 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14790.6495 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14791.6495 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14797.1495 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14809.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 52 | 487500 | ACTION | 14849.1495 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14850.1069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 14850.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14854.6495 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14855.6495 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14856.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14858.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14860.6331 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14861.6331 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14867.1331 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14870.1069 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 14872.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14872.6331 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14874.1069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 14874.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14874.6331 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14875.6331 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14878.1069 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14880.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14881.1331 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14882.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14886.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14886.6331 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14887.6331 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14892.6168 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14893.6168 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14898.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14899.1168 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14900.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14901.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14904.6168 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14905.1069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 14906.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14906.6168 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14907.6168 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14908.6069 | MooredSubInstallation
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 14912.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14913.1168 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14918.6168 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14919.6168 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14924.6004 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14925.6004 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14931.1004 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14932.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14936.6004 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14938.6004 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14939.6004 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14945.1004 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14950.6004 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14951.6004 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14956.584 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14957.584 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14963.084 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14968.584 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14970.584 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14971.584 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14977.084 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14977.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14982.584 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14983.584 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 14988.5677 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14989.5677 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14995.0677 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15000.5677 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15002.5677 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15003.5677 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15004.6069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 15004.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15009.0677 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15010.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15012.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15014.5677 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15015.5677 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 15020.5513 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15021.5513 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15024.6069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 15026.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15027.0513 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15028.6069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 15028.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15032.5513 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15032.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15034.5513 | ArrayCableInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15034.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15035.5513 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15036.6069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15040.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15041.0513 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15046.5513 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15047.5513 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 15052.535 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15052.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15053.535 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 15054.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15056.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15059.035 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15059.6069 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 15060.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15063.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15064.535 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15066.535 | ArrayCableInstallation
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 15067.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15067.535 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15073.035 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15078.535 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15079.535 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 15084.5186 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15085.5186 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15087.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15091.0186 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 39 | 365625 | ACTION | 15130.0186 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15135.5186 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15137.5186 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15138.5186 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15144.0186 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15145.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15149.5186 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15150.5186 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 15155.5022 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15156.5022 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15159.1069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 15159.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15162.0022 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15165.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15167.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15167.5022 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15169.5022 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15170.5022 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15176.0022 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15179.1069 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 15181.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15181.5022 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15182.5022 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15183.1069 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 15183.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15187.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 15187.4859 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15188.4859 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15189.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15191.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15193.9859 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15195.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15199.4859 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15201.4859 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15202.4859 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15207.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15207.9859 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 15209.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15210.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15213.4859 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15214.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15214.4859 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 15215.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15217.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 15219.4695 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15220.4695 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 15221.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15225.9695 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15231.4695 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15233.4695 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15234.4695 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15239.9695 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15241.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15245.4695 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15246.4695 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 15251.4532 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15252.4532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15257.9532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15263.4532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15265.4532 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15266.4532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15271.9532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15277.4532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15278.4532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 15283.4368 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15284.4368 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15289.9368 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15295.4368 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15297.4368 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15298.4368 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15303.9368 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15309.4368 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15310.4368 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15313.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15313.6069 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 15313.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 6 | 56250 | ACTION | 15316.4368 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15319.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 15321.4204 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15321.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15322.4204 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15327.9204 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15333.4204 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15333.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15335.4204 | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 15335.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15336.4204 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15337.6069 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 15337.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15341.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15341.9204 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15343.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15345.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15347.4204 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15348.4204 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15349.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 15353.4041 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15354.4041 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15359.9041 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15361.6069 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 15363.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15365.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15365.4041 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15367.4041 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15368.4041 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15368.6069 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 15369.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15372.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15373.9041 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 6.3655 | 50393.5417 | ACTION | 15376.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15379.4041 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15380.4041 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 15385.3877 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15386.3877 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15391.8877 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15396.1069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15397.3877 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15399.3877 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15400.3877 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15405.8877 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15411.3877 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15412.3877 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 15417.3713 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15418.3713 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15468.1069 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 400.9314 | 3174040.322 | ACTION | 15468.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15474.1069 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15476.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15488.1069 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 15490.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15492.1069 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 15492.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15496.1069 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15498.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15500.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15504.1069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 102916.6667 | ACTION | 15511.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 15520.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15532.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15535.6069 | MooredSubInstallation
| Towing Group 3 | Delay | 26 | 205833.3333 | ACTION | 15537.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15539.1069 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15542.6069 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 55416.6667 | ACTION | 15544.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 128 | 1200000 | ACTION | 15546.3713 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 15550.31 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15551.8713 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 6.3655 | 50393.5417 | ACTION | 15556.6755 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15557.3713 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15559.3713 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15560.3713 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15565.8713 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15566.6069 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15571.3713 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15572.3713 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 15577.355 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15578.355 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15583.855 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15589.355 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15591.355 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15592.355 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15597.855 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15603.355 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15604.355 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 1 | 9375 | ACTION | 15605.355 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 9 | 84375 | ACTION | 15614.355 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 3.9836 | 37346.6107 | ACTION | 15618.3386 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15619.3386 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15624.8386 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15630.3386 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15632.3386 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15633.3386 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15638.6069 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 416.9314 | 3300706.9886 | ACTION | 15638.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15638.8386 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15644.3386 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15644.6069 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15645.3386 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 15650.3223 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15651.3223 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15656.8223 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Tow Substructure | 16.2031 | 128274.4697 | ACTION | 15660.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15662.3223 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 15662.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15664.3223 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15665.3223 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15668.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15670.8223 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15676.3223 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15677.3223 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 15682.3059 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15683.3059 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15688.8059 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 15688.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15694.3059 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 15694.81 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15696.3059 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15697.3059 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 6.3655 | 50393.5417 | ACTION | 15701.1755 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15702.8059 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15708.3059 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15709.3059 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9836 | 46721.6107 | ACTION | 15714.2895 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15715.2895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15720.7895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 29 | 271875 | ACTION | 15749.7895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15755.2895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15757.2895 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15758.2895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15763.7895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15769.2895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15770.2895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 12.0925 | 113367.0428 | ACTION | 15782.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15783.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15788.882 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15794.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15796.382 | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 20 | 187500 | ACTION | 15816.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15817.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15822.882 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15828.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15829.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 28125 | ACTION | 15832.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 383 | 3590625 | ACTION | 16215.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 9.0925 | 85242.0428 | ACTION | 16224.4745 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16225.4745 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16230.9745 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16236.4745 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16238.4745 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16239.4745 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16244.9745 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16250.4745 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16251.4745 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8.3553 | 78330.9014 | ACTION | 16259.8298 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16260.8298 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16266.3298 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16271.8298 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16273.8298 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16274.8298 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16280.3298 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 6 | 56250 | ACTION | 16286.3298 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16291.8298 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16292.8298 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8.3553 | 78330.9014 | ACTION | 16301.1851 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16302.1851 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16307.6851 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16313.1851 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16315.1851 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16316.1851 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16321.6851 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16327.1851 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16328.1851 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.4794 | 51369.199 | ACTION | 16333.6645 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16334.6645 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16340.1645 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16345.6645 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16347.6645 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16348.6645 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16354.1645 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16359.6645 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16360.6645 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.4794 | 51369.199 | ACTION | 16366.1439 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16367.1439 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 74 | 693750 | ACTION | 16441.1439 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16446.6439 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16452.1439 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 2 | 18750 | ACTION | 16454.1439 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 8 | 75000 | ACTION | 16462.1439 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 5.7493 | 53899.7283 | ACTION | 16467.8932 | ArrayCableInstallation | ArrayCableInstallation | FALSE