## Sheet1
agent | action | duration | cost | time | start_date | end_date | phase | days_to_start | days_to_end | phase_duration
Export Cable Installation Vessel | Mobilize | 72 | 180000 | 0 | 2010-01-01 | 2010-01-04 | ExportCableInstallation | 0 | 3 | 4
Onshore Construction | Onshore Construction | 0 | 1665604.3526 | 0 | 2010-01-01 | 2010-01-01 | ExportCableInstallation | 0 | 0 | 1
Mooring System Installation Vessel | Mobilize | 168 | 700000 | 0 | 2010-01-01 | 2010-01-08 | MooringSystemInstallation | 0 | 7 | 8
Export Cable Installation Vessel | Load Cable | 6 | 30000 | 6 | 2010-01-01 06:00 | 2010-01-01 12:00 | ExportCableInstallation | 0 | 0 | 1
Mooring System Installation Vessel | Delay | 52 | 216666.6667 | 52 | 2010-01-03 04:00 | 2010-01-05 08:00 | MooringSystemInstallation | 2 | 4 | 3
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 57 | 2010-01-03 09:00 | 2010-01-03 14:00 | MooringSystemInstallation | 2 | 2 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 62 | 2010-01-03 14:00 | 2010-01-03 19:00 | MooringSystemInstallation | 2 | 2 | 1
Export Cable Installation Vessel | Delay | 57 | 285000 | 63 | 2010-01-03 15:00 | 2010-01-06 | ExportCableInstallation | 2 | 5 | 4
Export Cable Installation Vessel | Tow Plow | 0.4 | 2000 | 63.4 | 2010-01-03 15:24 | 2010-01-03 15:48 | ExportCableInstallation | 2 | 2 | 1
Export Cable Installation Vessel | Pull Winch | 0.4 | 2000 | 63.8 | 2010-01-03 15:48 | 2010-01-03 16:12 | ExportCableInstallation | 2 | 2 | 1
Export Cable Installation Vessel | Prepare Cable | 1 | 5000 | 64.8 | 2010-01-03 16:48 | 2010-01-03 17:48 | ExportCableInstallation | 2 | 2 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 66.3349 | 2010-01-03 18:20 | 2010-01-03 22:40 | MooringSystemInstallation | 2 | 2 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 68.3349 | 2010-01-03 20:20 | 2010-01-03 22:20 | MooringSystemInstallation | 2 | 2 | 1
Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 70.3 | 2010-01-03 22:18 | 2010-01-04 03:48 | ExportCableInstallation | 2 | 3 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 72.3349 | 2010-01-04 00:20 | 2010-01-04 04:20 | MooringSystemInstallation | 3 | 3 | 1
Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 75.8 | 2010-01-04 03:48 | 2010-01-04 09:18 | ExportCableInstallation | 3 | 3 | 1
Export Cable Installation Vessel | Lower Cable | 1 | 5000 | 76.8 | 2010-01-04 04:48 | 2010-01-04 05:48 | ExportCableInstallation | 3 | 3 | 1
Export Cable Installation Vessel | Lay/Bury Cable | 11 | 55000 | 87.8 | 2010-01-04 15:48 | 2010-01-05 02:48 | ExportCableInstallation | 3 | 4 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 88.4949 | 2010-01-04 16:30 | 2010-01-05 08:39 | MooringSystemInstallation | 3 | 4 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 92.6549 | 2010-01-04 20:39 | 2010-01-05 00:49 | MooringSystemInstallation | 3 | 4 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 94.6549 | 2010-01-04 22:39 | 2010-01-05 00:39 | MooringSystemInstallation | 3 | 4 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 98.6549 | 2010-01-05 02:39 | 2010-01-05 06:39 | MooringSystemInstallation | 4 | 4 | 1
Export Cable Installation Vessel | Delay | 20 | 100000 | 107.8 | 2010-01-05 11:48 | 2010-01-06 07:48 | ExportCableInstallation | 4 | 5 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 114.8149 | 2010-01-05 18:49 | 2010-01-06 10:58 | MooringSystemInstallation | 4 | 5 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 118.9749 | 2010-01-05 22:58 | 2010-01-06 03:08 | MooringSystemInstallation | 4 | 5 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 120.9749 | 2010-01-06 00:58 | 2010-01-06 02:58 | MooringSystemInstallation | 5 | 5 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 124.9749 | 2010-01-06 04:58 | 2010-01-06 08:58 | MooringSystemInstallation | 5 | 5 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 141.1349 | 2010-01-06 21:08 | 2010-01-07 13:18 | MooringSystemInstallation | 5 | 6 | 2
Export Cable Installation Vessel | Lay/Bury Cable | 35 | 175000 | 142.8 | 2010-01-06 22:48 | 2010-01-08 09:48 | ExportCableInstallation | 5 | 7 | 3
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 145.2949 | 2010-01-07 01:18 | 2010-01-07 05:27 | MooringSystemInstallation | 6 | 6 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 147.2949 | 2010-01-07 03:18 | 2010-01-07 05:18 | MooringSystemInstallation | 6 | 6 | 1
Export Cable Installation Vessel | Delay | 5 | 25000 | 147.8 | 2010-01-07 03:48 | 2010-01-07 08:48 | ExportCableInstallation | 6 | 6 | 1
Export Cable Installation Vessel | Lay/Bury Cable | 2 | 10000 | 149.8 | 2010-01-07 05:48 | 2010-01-07 07:48 | ExportCableInstallation | 6 | 6 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 151.2949 | 2010-01-07 07:18 | 2010-01-07 11:18 | MooringSystemInstallation | 6 | 6 | 1
Export Cable Installation Vessel | Delay | 7 | 35000 | 156.8 | 2010-01-07 12:48 | 2010-01-07 19:48 | ExportCableInstallation | 6 | 6 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 167.4549 | 2010-01-07 23:27 | 2010-01-08 15:37 | MooringSystemInstallation | 6 | 7 | 2
Export Cable Installation Vessel | Lay/Bury Cable | 11 | 55000 | 167.8 | 2010-01-07 23:48 | 2010-01-08 10:48 | ExportCableInstallation | 6 | 7 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 171.6149 | 2010-01-08 03:37 | 2010-01-08 07:46 | MooringSystemInstallation | 7 | 7 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 173.6149 | 2010-01-08 05:37 | 2010-01-08 07:37 | MooringSystemInstallation | 7 | 7 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 177.6149 | 2010-01-08 09:37 | 2010-01-08 13:37 | MooringSystemInstallation | 7 | 7 | 1
Mooring System Installation Vessel | Delay | 153 | 637500 | 330.6149 | 2010-01-14 18:37 | 2010-01-21 03:37 | MooringSystemInstallation | 13 | 20 | 8
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 346.7749 | 2010-01-15 10:46 | 2010-01-16 02:56 | MooringSystemInstallation | 14 | 15 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 350.9349 | 2010-01-15 14:56 | 2010-01-15 19:06 | MooringSystemInstallation | 14 | 14 | 1
Mooring System Installation Vessel | Delay | 26 | 108333.3333 | 376.9349 | 2010-01-16 16:56 | 2010-01-17 18:56 | MooringSystemInstallation | 15 | 16 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 378.9349 | 2010-01-16 18:56 | 2010-01-16 20:56 | MooringSystemInstallation | 15 | 15 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 382.9349 | 2010-01-16 22:56 | 2010-01-17 02:56 | MooringSystemInstallation | 15 | 16 | 2
Export Cable Installation Vessel | Delay | 226 | 1130000 | 393.8 | 2010-01-17 09:48 | 2010-01-26 19:48 | ExportCableInstallation | 16 | 25 | 10
Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | 394.8 | 2010-01-17 10:48 | 2010-01-17 11:48 | ExportCableInstallation | 16 | 16 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 399.0949 | 2010-01-17 15:06 | 2010-01-18 07:15 | MooringSystemInstallation | 16 | 17 | 2
Substation Assembly Line 1 | Substation Substructure Assembly | 0 | 0 | 472.5654 | 2010-01-20 16:34 | 2010-01-20 16:34 | FloatingSubstationInstallation | 19 | 19 | 1
Substation Assembly Line 1 | Attach Topside | 24 | 0 | 496.5654 | 2010-01-21 16:34 | 2010-01-22 16:34 | FloatingSubstationInstallation | 20 | 21 | 2
Floating Substation Installation Vessel | Delay: Waiting on Completed Assembly | 24 | 100000 | 496.5654 | 2010-01-21 16:34 | 2010-01-22 16:34 | FloatingSubstationInstallation | 20 | 21 | 2
Mooring System Installation Vessel | Delay | 224 | 933333.3333 | 623.0949 | 2010-01-26 23:06 | 2010-02-05 07:06 | MooringSystemInstallation | 25 | 35 | 11
Floating Substation Installation Vessel | Delay | 127 | 529166.6667 | 623.5654 | 2010-01-26 23:34 | 2010-02-01 06:34 | FloatingSubstationInstallation | 25 | 31 | 7
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 627.2549 | 2010-01-27 03:15 | 2010-01-27 07:25 | MooringSystemInstallation | 26 | 26 | 1
Floating Substation Installation Vessel | Tow Substation to Site | 7.2248 | 30103.4722 | 630.7902 | 2010-01-27 06:47 | 2010-01-27 14:01 | FloatingSubstationInstallation | 26 | 26 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 631.5898 | 2010-01-27 07:35 | 2010-01-27 11:55 | MooringSystemInstallation | 26 | 26 | 1
Floating Substation Installation Vessel | Position Onsite | 2 | 8333.3333 | 632.7902 | 2010-01-27 08:47 | 2010-01-27 10:47 | FloatingSubstationInstallation | 26 | 26 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 636.5898 | 2010-01-27 12:35 | 2010-01-27 17:35 | MooringSystemInstallation | 26 | 26 | 1
Floating Substation Installation Vessel | Delay | 4 | 16666.6667 | 636.7902 | 2010-01-27 12:47 | 2010-01-27 16:47 | FloatingSubstationInstallation | 26 | 26 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 641.5898 | 2010-01-27 17:35 | 2010-01-27 22:35 | MooringSystemInstallation | 26 | 26 | 1
Floating Substation Installation Vessel | Ballast to Operational Draft | 6 | 25000 | 642.7902 | 2010-01-27 18:47 | 2010-01-28 00:47 | FloatingSubstationInstallation | 26 | 27 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 645.9247 | 2010-01-27 21:55 | 2010-01-28 02:16 | MooringSystemInstallation | 26 | 27 | 2
Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 646.7902 | 2010-01-27 22:47 | 2010-01-28 02:47 | FloatingSubstationInstallation | 26 | 27 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 647.9247 | 2010-01-27 23:55 | 2010-01-28 01:55 | MooringSystemInstallation | 26 | 27 | 2
Export Cable Installation Vessel | Delay | 255 | 1275000 | 649.8 | 2010-01-28 01:48 | 2010-02-07 16:48 | ExportCableInstallation | 27 | 37 | 11
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 651.9247 | 2010-01-28 03:55 | 2010-01-28 07:55 | MooringSystemInstallation | 27 | 27 | 1
Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | 661.9502 | 2010-01-28 13:57 | 2010-01-29 05:07 | FloatingSubstationInstallation | 27 | 28 | 2
Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 666.1102 | 2010-01-28 18:07 | 2010-01-28 22:16 | FloatingSubstationInstallation | 27 | 27 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 668.0847 | 2010-01-28 20:05 | 2010-01-29 12:15 | MooringSystemInstallation | 27 | 28 | 2
Export Cable Installation Vessel | Lay/Bury Cable | 20 | 100000 | 669.8 | 2010-01-28 21:48 | 2010-01-29 17:48 | ExportCableInstallation | 27 | 28 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 672.2447 | 2010-01-29 00:15 | 2010-01-29 04:24 | MooringSystemInstallation | 28 | 28 | 1
Floating Substation Installation Vessel | Connect Mooring Lines | 8 | 33333.3333 | 674.1102 | 2010-01-29 02:07 | 2010-01-29 10:07 | FloatingSubstationInstallation | 28 | 28 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 674.2447 | 2010-01-29 02:15 | 2010-01-29 04:15 | MooringSystemInstallation | 28 | 28 | 1
Mooring System Installation Vessel | Delay | 56 | 233333.3333 | 730.2447 | 2010-01-31 10:15 | 2010-02-02 18:15 | MooringSystemInstallation | 30 | 32 | 3
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 734.2447 | 2010-01-31 14:15 | 2010-01-31 18:15 | MooringSystemInstallation | 30 | 30 | 1
Floating Substation Installation Vessel | Delay | 63 | 262500 | 737.1102 | 2010-01-31 17:07 | 2010-02-03 08:07 | FloatingSubstationInstallation | 30 | 33 | 4
Export Cable Installation Vessel | Delay | 78 | 390000 | 747.8 | 2010-02-01 03:48 | 2010-02-04 09:48 | ExportCableInstallation | 31 | 34 | 4
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 750.4047 | 2010-02-01 06:24 | 2010-02-01 22:34 | MooringSystemInstallation | 31 | 31 | 1
Export Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | 750.8 | 2010-02-01 06:48 | 2010-02-01 09:48 | ExportCableInstallation | 31 | 31 | 1
Floating Substation Installation Vessel | Connect Mooring Lines | 14 | 58333.3333 | 751.1102 | 2010-02-01 07:07 | 2010-02-01 21:07 | FloatingSubstationInstallation | 31 | 31 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 754.5647 | 2010-02-01 10:34 | 2010-02-01 14:43 | MooringSystemInstallation | 31 | 31 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 756.5647 | 2010-02-01 12:34 | 2010-02-01 14:34 | MooringSystemInstallation | 31 | 31 | 1
Floating Substation Installation Vessel | Check Mooring Lines | 6 | 25000 | 757.1102 | 2010-02-01 13:07 | 2010-02-01 19:07 | FloatingSubstationInstallation | 31 | 31 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 760.5647 | 2010-02-01 16:34 | 2010-02-01 20:34 | MooringSystemInstallation | 31 | 31 | 1
Floating Substation Installation Vessel | Delay | 8 | 33333.3333 | 765.1102 | 2010-02-01 21:07 | 2010-02-02 05:07 | FloatingSubstationInstallation | 31 | 32 | 2
Floating Substation Installation Vessel | Check Mooring Lines | 6 | 25000 | 771.1102 | 2010-02-02 03:07 | 2010-02-02 09:07 | FloatingSubstationInstallation | 32 | 32 | 1
Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 775.1102 | 2010-02-02 07:07 | 2010-02-02 11:07 | FloatingSubstationInstallation | 32 | 32 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 776.7247 | 2010-02-02 08:43 | 2010-02-03 00:53 | MooringSystemInstallation | 32 | 33 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 780.8847 | 2010-02-02 12:53 | 2010-02-02 17:03 | MooringSystemInstallation | 32 | 32 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 782.8847 | 2010-02-02 14:53 | 2010-02-02 16:53 | MooringSystemInstallation | 32 | 32 | 1
Floating Substation Installation Vessel | Delay | 15 | 62500 | 790.1102 | 2010-02-02 22:07 | 2010-02-03 13:07 | FloatingSubstationInstallation | 32 | 33 | 2
Mooring System Installation Vessel | Delay | 8 | 33333.3333 | 790.8847 | 2010-02-02 22:53 | 2010-02-03 06:53 | MooringSystemInstallation | 32 | 33 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 794.8847 | 2010-02-03 02:53 | 2010-02-03 06:53 | MooringSystemInstallation | 33 | 33 | 1
Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | 805.2702 | 2010-02-03 13:16 | 2010-02-04 04:26 | FloatingSubstationInstallation | 33 | 34 | 2
Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 809.4302 | 2010-02-03 17:26 | 2010-02-03 21:35 | FloatingSubstationInstallation | 33 | 33 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 811.0447 | 2010-02-03 19:03 | 2010-02-04 11:12 | MooringSystemInstallation | 33 | 34 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 815.2047 | 2010-02-03 23:12 | 2010-02-04 03:22 | MooringSystemInstallation | 33 | 34 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 817.2047 | 2010-02-04 01:12 | 2010-02-04 03:12 | MooringSystemInstallation | 34 | 34 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 821.2047 | 2010-02-04 05:12 | 2010-02-04 09:12 | MooringSystemInstallation | 34 | 34 | 1
Floating Substation Installation Vessel | Connect Mooring Lines | 16 | 66666.6667 | 825.4302 | 2010-02-04 09:26 | 2010-02-05 01:26 | FloatingSubstationInstallation | 34 | 35 | 2
Mooring System Installation Vessel | Delay | 99 | 412500 | 920.2047 | 2010-02-08 08:12 | 2010-02-12 11:12 | MooringSystemInstallation | 38 | 42 | 5
Floating Substation Installation Vessel | Delay | 104 | 433333.3333 | 929.4302 | 2010-02-08 17:26 | 2010-02-13 01:26 | FloatingSubstationInstallation | 38 | 43 | 6
Floating Substation Installation Vessel | Connect Mooring Lines | 6 | 25000 | 935.4302 | 2010-02-08 23:26 | 2010-02-09 05:26 | FloatingSubstationInstallation | 38 | 39 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 936.3647 | 2010-02-09 00:22 | 2010-02-09 16:31 | MooringSystemInstallation | 39 | 39 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 940.5247 | 2010-02-09 04:31 | 2010-02-09 08:41 | MooringSystemInstallation | 39 | 39 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 942.5247 | 2010-02-09 06:31 | 2010-02-09 08:31 | MooringSystemInstallation | 39 | 39 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 946.5247 | 2010-02-09 10:31 | 2010-02-09 14:31 | MooringSystemInstallation | 39 | 39 | 1
Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | 947.4302 | 2010-02-09 11:26 | 2010-02-09 23:26 | FloatingSubstationInstallation | 39 | 39 | 1
Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 951.4302 | 2010-02-09 15:26 | 2010-02-09 19:26 | FloatingSubstationInstallation | 39 | 39 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 962.6847 | 2010-02-10 02:41 | 2010-02-10 18:51 | MooringSystemInstallation | 40 | 40 | 1
Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | 966.5902 | 2010-02-10 06:35 | 2010-02-10 21:45 | FloatingSubstationInstallation | 40 | 40 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 966.8447 | 2010-02-10 06:51 | 2010-02-10 11:00 | MooringSystemInstallation | 40 | 40 | 1
Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 970.7502 | 2010-02-10 10:45 | 2010-02-10 14:55 | FloatingSubstationInstallation | 40 | 40 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 971.1796 | 2010-02-10 11:11 | 2010-02-10 15:31 | MooringSystemInstallation | 40 | 40 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 976.1796 | 2010-02-10 16:11 | 2010-02-10 21:11 | MooringSystemInstallation | 40 | 40 | 1
Export Cable Installation Vessel | Delay | 226 | 1130000 | 976.8 | 2010-02-10 16:48 | 2010-02-20 02:48 | ExportCableInstallation | 40 | 50 | 11
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 981.1796 | 2010-02-10 21:11 | 2010-02-11 02:11 | MooringSystemInstallation | 40 | 41 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 985.5145 | 2010-02-11 01:31 | 2010-02-11 05:51 | MooringSystemInstallation | 41 | 41 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 987.5145 | 2010-02-11 03:31 | 2010-02-11 05:31 | MooringSystemInstallation | 41 | 41 | 1
Export Cable Installation Vessel | Lay/Bury Cable | 13 | 65000 | 989.8 | 2010-02-11 05:48 | 2010-02-11 18:48 | ExportCableInstallation | 41 | 41 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 991.5145 | 2010-02-11 07:31 | 2010-02-11 11:31 | MooringSystemInstallation | 41 | 41 | 1
Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | 992.7502 | 2010-02-11 08:45 | 2010-02-12 06:45 | FloatingSubstationInstallation | 41 | 42 | 2
Floating Substation Installation Vessel | Check Mooring Lines | 4 | 16666.6667 | 996.7502 | 2010-02-11 12:45 | 2010-02-11 16:45 | FloatingSubstationInstallation | 41 | 41 | 1
Mooring System Installation Vessel | Delay | 113 | 470833.3333 | 1104.5145 | 2010-02-16 00:31 | 2010-02-20 17:31 | MooringSystemInstallation | 46 | 50 | 5
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 1120.6745 | 2010-02-16 16:40 | 2010-02-17 08:50 | MooringSystemInstallation | 46 | 47 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 1124.8345 | 2010-02-16 20:50 | 2010-02-17 01:00 | MooringSystemInstallation | 46 | 47 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 1126.8345 | 2010-02-16 22:50 | 2010-02-17 00:50 | MooringSystemInstallation | 46 | 47 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 1130.8345 | 2010-02-17 02:50 | 2010-02-17 06:50 | MooringSystemInstallation | 47 | 47 | 1
Floating Substation Installation Vessel | Delay | 142 | 591666.6667 | 1138.7502 | 2010-02-17 10:45 | 2010-02-23 08:45 | FloatingSubstationInstallation | 47 | 53 | 7
Floating Substation Installation Vessel | Check Mooring Lines | 8 | 33333.3333 | 1146.7502 | 2010-02-17 18:45 | 2010-02-18 02:45 | FloatingSubstationInstallation | 47 | 48 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 1146.9945 | 2010-02-17 19:00 | 2010-02-18 11:09 | MooringSystemInstallation | 47 | 48 | 2
Floating Substation Installation Vessel | Transit | 4.3349 | 18062.0833 | 1151.0851 | 2010-02-17 23:05 | 2010-02-18 03:25 | FloatingSubstationInstallation | 47 | 48 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 1151.1545 | 2010-02-17 23:09 | 2010-02-18 03:19 | MooringSystemInstallation | 47 | 48 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 1153.1545 | 2010-02-18 01:09 | 2010-02-18 03:09 | MooringSystemInstallation | 48 | 48 | 1
Export Cable Installation Vessel | Delay | 165 | 825000 | 1154.8 | 2010-02-18 02:48 | 2010-02-24 23:48 | ExportCableInstallation | 48 | 54 | 7
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 1157.1545 | 2010-02-18 05:09 | 2010-02-18 09:09 | MooringSystemInstallation | 48 | 48 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 1173.3145 | 2010-02-18 21:19 | 2010-02-19 13:28 | MooringSystemInstallation | 48 | 49 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 1177.4745 | 2010-02-19 01:28 | 2010-02-19 05:38 | MooringSystemInstallation | 49 | 49 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 1179.4745 | 2010-02-19 03:28 | 2010-02-19 05:28 | MooringSystemInstallation | 49 | 49 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 1183.4745 | 2010-02-19 07:28 | 2010-02-19 11:28 | MooringSystemInstallation | 49 | 49 | 1
Export Cable Installation Vessel | Lay/Bury Cable | 30 | 150000 | 1184.8 | 2010-02-19 08:48 | 2010-02-20 14:48 | ExportCableInstallation | 49 | 50 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 1199.6345 | 2010-02-19 23:38 | 2010-02-20 15:48 | MooringSystemInstallation | 49 | 50 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 1203.7945 | 2010-02-20 03:48 | 2010-02-20 07:57 | MooringSystemInstallation | 50 | 50 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 1205.7945 | 2010-02-20 05:48 | 2010-02-20 07:48 | MooringSystemInstallation | 50 | 50 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 1209.7945 | 2010-02-20 09:48 | 2010-02-20 13:48 | MooringSystemInstallation | 50 | 50 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 1225.9545 | 2010-02-21 01:57 | 2010-02-21 18:07 | MooringSystemInstallation | 51 | 51 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 1230.1145 | 2010-02-21 06:07 | 2010-02-21 10:16 | MooringSystemInstallation | 51 | 51 | 1
Export Cable Installation Vessel | Delay | 46 | 230000 | 1230.8 | 2010-02-21 06:48 | 2010-02-23 04:48 | ExportCableInstallation | 51 | 53 | 3
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 1232.1145 | 2010-02-21 08:07 | 2010-02-21 10:07 | MooringSystemInstallation | 51 | 51 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 1236.1145 | 2010-02-21 12:07 | 2010-02-21 16:07 | MooringSystemInstallation | 51 | 51 | 1
Export Cable Installation Vessel | Lay/Bury Cable | 16 | 80000 | 1246.8 | 2010-02-21 22:48 | 2010-02-22 14:48 | ExportCableInstallation | 51 | 52 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 1252.2745 | 2010-02-22 04:16 | 2010-02-22 20:26 | MooringSystemInstallation | 52 | 52 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 1256.4345 | 2010-02-22 08:26 | 2010-02-22 12:36 | MooringSystemInstallation | 52 | 52 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 1260.7694 | 2010-02-22 12:46 | 2010-02-22 17:06 | MooringSystemInstallation | 52 | 52 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 1265.7694 | 2010-02-22 17:46 | 2010-02-22 22:46 | MooringSystemInstallation | 52 | 52 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 1270.7694 | 2010-02-22 22:46 | 2010-02-23 03:46 | MooringSystemInstallation | 52 | 53 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 1275.1043 | 2010-02-23 03:06 | 2010-02-23 07:26 | MooringSystemInstallation | 53 | 53 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 1277.1043 | 2010-02-23 05:06 | 2010-02-23 07:06 | MooringSystemInstallation | 53 | 53 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 1281.1043 | 2010-02-23 09:06 | 2010-02-23 13:06 | MooringSystemInstallation | 53 | 53 | 1
Mooring System Installation Vessel | Delay | 43 | 179166.6667 | 1324.1043 | 2010-02-25 04:06 | 2010-02-26 23:06 | MooringSystemInstallation | 55 | 56 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 1340.2643 | 2010-02-25 20:16 | 2010-02-26 12:25 | MooringSystemInstallation | 55 | 56 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 1344.4243 | 2010-02-26 00:25 | 2010-02-26 04:35 | MooringSystemInstallation | 56 | 56 | 1
Mooring System Installation Vessel | Delay | 69 | 287500 | 1413.4243 | 2010-02-28 21:25 | 2010-03-03 18:25 | MooringSystemInstallation | 58 | 61 | 4
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 1415.4243 | 2010-02-28 23:25 | 2010-03-01 01:25 | MooringSystemInstallation | 58 | 59 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 1419.4243 | 2010-03-01 03:25 | 2010-03-01 07:25 | MooringSystemInstallation | 59 | 59 | 1
Export Cable Installation Vessel | Delay | 180 | 900000 | 1426.8 | 2010-03-01 10:48 | 2010-03-08 22:48 | ExportCableInstallation | 59 | 66 | 8
Export Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | 1429.8 | 2010-03-01 13:48 | 2010-03-01 16:48 | ExportCableInstallation | 59 | 59 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 1435.5843 | 2010-03-01 19:35 | 2010-03-02 11:45 | MooringSystemInstallation | 59 | 60 | 2
Mooring System Installation Vessel | Delay | 68 | 283333.3333 | 1503.5843 | 2010-03-04 15:35 | 2010-03-07 11:35 | MooringSystemInstallation | 62 | 65 | 4
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 1507.7443 | 2010-03-04 19:45 | 2010-03-04 23:54 | MooringSystemInstallation | 62 | 62 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 1509.7443 | 2010-03-04 21:45 | 2010-03-04 23:45 | MooringSystemInstallation | 62 | 62 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 1513.7443 | 2010-03-05 01:45 | 2010-03-05 05:45 | MooringSystemInstallation | 63 | 63 | 1
Mooring System Installation Vessel | Delay | 39 | 162500 | 1552.7443 | 2010-03-06 16:45 | 2010-03-08 07:45 | MooringSystemInstallation | 64 | 66 | 3
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 1568.9043 | 2010-03-07 08:54 | 2010-03-08 01:04 | MooringSystemInstallation | 65 | 66 | 2
Mooring System Installation Vessel | Delay | 56 | 233333.3333 | 1624.9043 | 2010-03-09 16:54 | 2010-03-12 00:54 | MooringSystemInstallation | 67 | 70 | 4
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 1629.0643 | 2010-03-09 21:04 | 2010-03-10 01:13 | MooringSystemInstallation | 67 | 68 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 1631.0643 | 2010-03-09 23:04 | 2010-03-10 01:04 | MooringSystemInstallation | 67 | 68 | 2
Mooring System Installation Vessel | Delay | 106 | 441666.6667 | 1737.0643 | 2010-03-14 09:04 | 2010-03-18 19:04 | MooringSystemInstallation | 72 | 76 | 5
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 1741.0643 | 2010-03-14 13:04 | 2010-03-14 17:04 | MooringSystemInstallation | 72 | 72 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 1757.2243 | 2010-03-15 05:13 | 2010-03-15 21:23 | MooringSystemInstallation | 73 | 73 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 1761.3843 | 2010-03-15 09:23 | 2010-03-15 13:33 | MooringSystemInstallation | 73 | 73 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 1763.3843 | 2010-03-15 11:23 | 2010-03-15 13:23 | MooringSystemInstallation | 73 | 73 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 1767.3843 | 2010-03-15 15:23 | 2010-03-15 19:23 | MooringSystemInstallation | 73 | 73 | 1
Mooring System Installation Vessel | Delay | 82 | 341666.6667 | 1849.3843 | 2010-03-19 01:23 | 2010-03-22 11:23 | MooringSystemInstallation | 77 | 80 | 4
Export Cable Installation Vessel | Delay | 432 | 2160000 | 1861.8 | 2010-03-19 13:48 | 2010-04-06 13:48 | ExportCableInstallation | 77 | 95 | 19
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 1865.5443 | 2010-03-19 17:33 | 2010-03-20 09:42 | MooringSystemInstallation | 77 | 78 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 1869.7043 | 2010-03-19 21:42 | 2010-03-20 01:52 | MooringSystemInstallation | 77 | 78 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 1871.7043 | 2010-03-19 23:42 | 2010-03-20 01:42 | MooringSystemInstallation | 77 | 78 | 2
Export Cable Installation Vessel | Lay/Bury Cable | 11.6922 | 58460.7554 | 1873.4922 | 2010-03-20 01:30 | 2010-03-20 13:11 | ExportCableInstallation | 78 | 78 | 1
Export Cable Installation Vessel | Position Onsite | 2 | 10000 | 1875.4922 | 2010-03-20 03:30 | 2010-03-20 05:30 | ExportCableInstallation | 78 | 78 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 1875.7043 | 2010-03-20 03:42 | 2010-03-20 07:42 | MooringSystemInstallation | 78 | 78 | 1
Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 1880.9922 | 2010-03-20 09:00 | 2010-03-20 14:30 | ExportCableInstallation | 78 | 78 | 1
Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 1886.4922 | 2010-03-20 14:30 | 2010-03-20 20:00 | ExportCableInstallation | 78 | 78 | 1
Export Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | 1890.2616 | 2010-03-20 18:16 | 2010-03-20 22:02 | ExportCableInstallation | 78 | 78 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 1891.8643 | 2010-03-20 19:52 | 2010-03-21 12:01 | MooringSystemInstallation | 78 | 79 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 1896.0243 | 2010-03-21 00:01 | 2010-03-21 04:11 | MooringSystemInstallation | 79 | 79 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 1900.3592 | 2010-03-21 04:22 | 2010-03-21 08:42 | MooringSystemInstallation | 79 | 79 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 1905.3592 | 2010-03-21 09:22 | 2010-03-21 14:22 | MooringSystemInstallation | 79 | 79 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 1910.3592 | 2010-03-21 14:22 | 2010-03-21 19:22 | MooringSystemInstallation | 79 | 79 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 1914.6941 | 2010-03-21 18:42 | 2010-03-21 23:02 | MooringSystemInstallation | 79 | 79 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 1916.6941 | 2010-03-21 20:42 | 2010-03-21 22:42 | MooringSystemInstallation | 79 | 79 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 1920.6941 | 2010-03-22 00:42 | 2010-03-22 04:42 | MooringSystemInstallation | 80 | 80 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 1936.8541 | 2010-03-22 16:51 | 2010-03-23 09:01 | MooringSystemInstallation | 80 | 81 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 1941.0141 | 2010-03-22 21:01 | 2010-03-23 01:10 | MooringSystemInstallation | 80 | 81 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 1943.0141 | 2010-03-22 23:01 | 2010-03-23 01:01 | MooringSystemInstallation | 80 | 81 | 2
Mooring System Installation Vessel | Delay | 14 | 58333.3333 | 1957.0141 | 2010-03-23 13:01 | 2010-03-24 03:01 | MooringSystemInstallation | 81 | 82 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 1961.0141 | 2010-03-23 17:01 | 2010-03-23 21:01 | MooringSystemInstallation | 81 | 81 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 1977.1741 | 2010-03-24 09:10 | 2010-03-25 01:20 | MooringSystemInstallation | 82 | 83 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 1981.3341 | 2010-03-24 13:20 | 2010-03-24 17:30 | MooringSystemInstallation | 82 | 82 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 1983.3341 | 2010-03-24 15:20 | 2010-03-24 17:20 | MooringSystemInstallation | 82 | 82 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 1987.3341 | 2010-03-24 19:20 | 2010-03-24 23:20 | MooringSystemInstallation | 82 | 82 | 1
Mooring System Installation Vessel | Delay | 46 | 191666.6667 | 2033.3341 | 2010-03-26 17:20 | 2010-03-28 15:20 | MooringSystemInstallation | 84 | 86 | 3
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 2049.4941 | 2010-03-27 09:30 | 2010-03-28 01:39 | MooringSystemInstallation | 85 | 86 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 2053.6541 | 2010-03-27 13:39 | 2010-03-27 17:49 | MooringSystemInstallation | 85 | 85 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 2055.6541 | 2010-03-27 15:39 | 2010-03-27 17:39 | MooringSystemInstallation | 85 | 85 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 2059.6541 | 2010-03-27 19:39 | 2010-03-27 23:39 | MooringSystemInstallation | 85 | 85 | 1
Mooring System Installation Vessel | Delay | 332 | 1383333.3333 | 2391.6541 | 2010-04-10 15:39 | 2010-04-24 11:39 | MooringSystemInstallation | 99 | 113 | 15
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 2407.8141 | 2010-04-11 07:49 | 2010-04-11 23:58 | MooringSystemInstallation | 100 | 100 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 2411.9741 | 2010-04-11 11:58 | 2010-04-11 16:08 | MooringSystemInstallation | 100 | 100 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 2413.9741 | 2010-04-11 13:58 | 2010-04-11 15:58 | MooringSystemInstallation | 100 | 100 | 1
Mooring System Installation Vessel | Delay | 18 | 75000 | 2431.9741 | 2010-04-12 07:58 | 2010-04-13 01:58 | MooringSystemInstallation | 101 | 102 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 2435.9741 | 2010-04-12 11:58 | 2010-04-12 15:58 | MooringSystemInstallation | 101 | 101 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 2452.1341 | 2010-04-13 04:08 | 2010-04-13 20:18 | MooringSystemInstallation | 102 | 102 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 2456.2941 | 2010-04-13 08:18 | 2010-04-13 12:27 | MooringSystemInstallation | 102 | 102 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 2458.2941 | 2010-04-13 10:18 | 2010-04-13 12:18 | MooringSystemInstallation | 102 | 102 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 2462.2941 | 2010-04-13 14:18 | 2010-04-13 18:18 | MooringSystemInstallation | 102 | 102 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 2478.4541 | 2010-04-14 06:27 | 2010-04-14 22:37 | MooringSystemInstallation | 103 | 103 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 2482.6141 | 2010-04-14 10:37 | 2010-04-14 14:46 | MooringSystemInstallation | 103 | 103 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 2486.949 | 2010-04-14 14:57 | 2010-04-14 19:17 | MooringSystemInstallation | 103 | 103 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 2491.949 | 2010-04-14 19:57 | 2010-04-15 00:57 | MooringSystemInstallation | 103 | 104 | 2
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 2496.949 | 2010-04-15 00:57 | 2010-04-15 05:57 | MooringSystemInstallation | 104 | 104 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 2501.2839 | 2010-04-15 05:17 | 2010-04-15 09:37 | MooringSystemInstallation | 104 | 104 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 2503.2839 | 2010-04-15 07:17 | 2010-04-15 09:17 | MooringSystemInstallation | 104 | 104 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 2507.2839 | 2010-04-15 11:17 | 2010-04-15 15:17 | MooringSystemInstallation | 104 | 104 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 2523.4439 | 2010-04-16 03:27 | 2010-04-16 19:36 | MooringSystemInstallation | 105 | 105 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 2527.6039 | 2010-04-16 07:36 | 2010-04-16 11:46 | MooringSystemInstallation | 105 | 105 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 2529.6039 | 2010-04-16 09:36 | 2010-04-16 11:36 | MooringSystemInstallation | 105 | 105 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 2533.6039 | 2010-04-16 13:36 | 2010-04-16 17:36 | MooringSystemInstallation | 105 | 105 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 2549.7639 | 2010-04-17 05:46 | 2010-04-17 21:55 | MooringSystemInstallation | 106 | 106 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 2553.9239 | 2010-04-17 09:55 | 2010-04-17 14:05 | MooringSystemInstallation | 106 | 106 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 2555.9239 | 2010-04-17 11:55 | 2010-04-17 13:55 | MooringSystemInstallation | 106 | 106 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 2559.9239 | 2010-04-17 15:55 | 2010-04-17 19:55 | MooringSystemInstallation | 106 | 106 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 2576.0839 | 2010-04-18 08:05 | 2010-04-19 00:15 | MooringSystemInstallation | 107 | 108 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 2580.2439 | 2010-04-18 12:15 | 2010-04-18 16:24 | MooringSystemInstallation | 107 | 107 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 2582.2439 | 2010-04-18 14:15 | 2010-04-18 16:15 | MooringSystemInstallation | 107 | 107 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 2586.2439 | 2010-04-18 18:15 | 2010-04-18 22:15 | MooringSystemInstallation | 107 | 107 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 2602.4039 | 2010-04-19 10:24 | 2010-04-20 02:34 | MooringSystemInstallation | 108 | 109 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 2606.5639 | 2010-04-19 14:34 | 2010-04-19 18:43 | MooringSystemInstallation | 108 | 108 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 2608.5639 | 2010-04-19 16:34 | 2010-04-19 18:34 | MooringSystemInstallation | 108 | 108 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 2612.5639 | 2010-04-19 20:34 | 2010-04-20 00:34 | MooringSystemInstallation | 108 | 109 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 2628.7239 | 2010-04-20 12:43 | 2010-04-21 04:53 | MooringSystemInstallation | 109 | 110 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 2632.8839 | 2010-04-20 16:53 | 2010-04-20 21:03 | MooringSystemInstallation | 109 | 109 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 2634.8839 | 2010-04-20 18:53 | 2010-04-20 20:53 | MooringSystemInstallation | 109 | 109 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 2638.8839 | 2010-04-20 22:53 | 2010-04-21 02:53 | MooringSystemInstallation | 109 | 110 | 2
Mooring System Installation Vessel | Delay | 70 | 291666.6667 | 2708.8839 | 2010-04-23 20:53 | 2010-04-26 18:53 | MooringSystemInstallation | 112 | 115 | 4
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 2725.0439 | 2010-04-24 13:03 | 2010-04-25 05:12 | MooringSystemInstallation | 113 | 114 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 2729.2039 | 2010-04-24 17:12 | 2010-04-24 21:22 | MooringSystemInstallation | 113 | 113 | 1
Mooring System Installation Vessel | Transit | 3 | 12500 | 2732.2039 | 2010-04-24 20:12 | 2010-04-24 23:12 | MooringSystemInstallation | 113 | 113 | 1
Mooring System Installation Vessel | Delay | 22 | 91666.6667 | 2754.2039 | 2010-04-25 18:12 | 2010-04-26 16:12 | MooringSystemInstallation | 114 | 115 | 2
Mooring System Installation Vessel | Transit | 1.3349 | 5562.0833 | 2755.5388 | 2010-04-25 19:32 | 2010-04-25 20:52 | MooringSystemInstallation | 114 | 114 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 2760.5388 | 2010-04-26 00:32 | 2010-04-26 05:32 | MooringSystemInstallation | 115 | 115 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 2765.5388 | 2010-04-26 05:32 | 2010-04-26 10:32 | MooringSystemInstallation | 115 | 115 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 2769.8737 | 2010-04-26 09:52 | 2010-04-26 14:13 | MooringSystemInstallation | 115 | 115 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 2771.8737 | 2010-04-26 11:52 | 2010-04-26 13:52 | MooringSystemInstallation | 115 | 115 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 2775.8737 | 2010-04-26 15:52 | 2010-04-26 19:52 | MooringSystemInstallation | 115 | 115 | 1
Mooring System Installation Vessel | Delay | 99 | 412500 | 2874.8737 | 2010-04-30 18:52 | 2010-05-04 21:52 | MooringSystemInstallation | 119 | 123 | 5
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 2891.0337 | 2010-05-01 11:02 | 2010-05-02 03:12 | MooringSystemInstallation | 120 | 121 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 2895.1937 | 2010-05-01 15:12 | 2010-05-01 19:21 | MooringSystemInstallation | 120 | 120 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 2897.1937 | 2010-05-01 17:12 | 2010-05-01 19:12 | MooringSystemInstallation | 120 | 120 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 2901.1937 | 2010-05-01 21:12 | 2010-05-02 01:12 | MooringSystemInstallation | 120 | 121 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 2917.3537 | 2010-05-02 13:21 | 2010-05-03 05:31 | MooringSystemInstallation | 121 | 122 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 2921.5137 | 2010-05-02 17:31 | 2010-05-02 21:40 | MooringSystemInstallation | 121 | 121 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 2923.5137 | 2010-05-02 19:31 | 2010-05-02 21:31 | MooringSystemInstallation | 121 | 121 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 2927.5137 | 2010-05-02 23:31 | 2010-05-03 03:31 | MooringSystemInstallation | 121 | 122 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 2943.6737 | 2010-05-03 15:40 | 2010-05-04 07:50 | MooringSystemInstallation | 122 | 123 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 2947.8337 | 2010-05-03 19:50 | 2010-05-04 | MooringSystemInstallation | 122 | 122 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 2949.8337 | 2010-05-03 21:50 | 2010-05-03 23:50 | MooringSystemInstallation | 122 | 122 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 2953.8337 | 2010-05-04 01:50 | 2010-05-04 05:50 | MooringSystemInstallation | 123 | 123 | 1
Mooring System Installation Vessel | Delay | 13 | 54166.6667 | 2966.8337 | 2010-05-04 14:50 | 2010-05-05 03:50 | MooringSystemInstallation | 123 | 124 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 2982.9937 | 2010-05-05 07:00 | 2010-05-05 23:09 | MooringSystemInstallation | 124 | 124 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 2987.1537 | 2010-05-05 11:09 | 2010-05-05 15:19 | MooringSystemInstallation | 124 | 124 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 2989.1537 | 2010-05-05 13:09 | 2010-05-05 15:09 | MooringSystemInstallation | 124 | 124 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 2993.1537 | 2010-05-05 17:09 | 2010-05-05 21:09 | MooringSystemInstallation | 124 | 124 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3009.3137 | 2010-05-06 09:19 | 2010-05-07 01:28 | MooringSystemInstallation | 125 | 126 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3013.4737 | 2010-05-06 13:28 | 2010-05-06 17:38 | MooringSystemInstallation | 125 | 125 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3015.4737 | 2010-05-06 15:28 | 2010-05-06 17:28 | MooringSystemInstallation | 125 | 125 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3019.4737 | 2010-05-06 19:28 | 2010-05-06 23:28 | MooringSystemInstallation | 125 | 125 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3035.6337 | 2010-05-07 11:38 | 2010-05-08 03:48 | MooringSystemInstallation | 126 | 127 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3039.7937 | 2010-05-07 15:48 | 2010-05-07 19:57 | MooringSystemInstallation | 126 | 126 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 3044.1286 | 2010-05-07 20:08 | 2010-05-08 00:28 | MooringSystemInstallation | 126 | 127 | 2
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 3049.1286 | 2010-05-08 01:08 | 2010-05-08 06:08 | MooringSystemInstallation | 127 | 127 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 3054.1286 | 2010-05-08 06:08 | 2010-05-08 11:08 | MooringSystemInstallation | 127 | 127 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 3058.4635 | 2010-05-08 10:28 | 2010-05-08 14:48 | MooringSystemInstallation | 127 | 127 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3060.4635 | 2010-05-08 12:28 | 2010-05-08 14:28 | MooringSystemInstallation | 127 | 127 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3064.4635 | 2010-05-08 16:28 | 2010-05-08 20:28 | MooringSystemInstallation | 127 | 127 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3080.6235 | 2010-05-09 08:37 | 2010-05-10 00:47 | MooringSystemInstallation | 128 | 129 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3084.7835 | 2010-05-09 12:47 | 2010-05-09 16:57 | MooringSystemInstallation | 128 | 128 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3086.7835 | 2010-05-09 14:47 | 2010-05-09 16:47 | MooringSystemInstallation | 128 | 128 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3090.7835 | 2010-05-09 18:47 | 2010-05-09 22:47 | MooringSystemInstallation | 128 | 128 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3106.9435 | 2010-05-10 10:57 | 2010-05-11 03:06 | MooringSystemInstallation | 129 | 130 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3111.1035 | 2010-05-10 15:06 | 2010-05-10 19:16 | MooringSystemInstallation | 129 | 129 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3113.1035 | 2010-05-10 17:06 | 2010-05-10 19:06 | MooringSystemInstallation | 129 | 129 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3117.1035 | 2010-05-10 21:06 | 2010-05-11 01:06 | MooringSystemInstallation | 129 | 130 | 2
Mooring System Installation Vessel | Delay | 16 | 66666.6667 | 3133.1035 | 2010-05-11 13:06 | 2010-05-12 05:06 | MooringSystemInstallation | 130 | 131 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3149.2635 | 2010-05-12 05:16 | 2010-05-12 21:25 | MooringSystemInstallation | 131 | 131 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3153.4235 | 2010-05-12 09:25 | 2010-05-12 13:35 | MooringSystemInstallation | 131 | 131 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3155.4235 | 2010-05-12 11:25 | 2010-05-12 13:25 | MooringSystemInstallation | 131 | 131 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3159.4235 | 2010-05-12 15:25 | 2010-05-12 19:25 | MooringSystemInstallation | 131 | 131 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3175.5835 | 2010-05-13 07:35 | 2010-05-13 23:45 | MooringSystemInstallation | 132 | 132 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3179.7435 | 2010-05-13 11:45 | 2010-05-13 15:54 | MooringSystemInstallation | 132 | 132 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3181.7435 | 2010-05-13 13:45 | 2010-05-13 15:45 | MooringSystemInstallation | 132 | 132 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3185.7435 | 2010-05-13 17:45 | 2010-05-13 21:45 | MooringSystemInstallation | 132 | 132 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3201.9035 | 2010-05-14 09:54 | 2010-05-15 02:04 | MooringSystemInstallation | 133 | 134 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3206.0635 | 2010-05-14 14:04 | 2010-05-14 18:13 | MooringSystemInstallation | 133 | 133 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3208.0635 | 2010-05-14 16:04 | 2010-05-14 18:04 | MooringSystemInstallation | 133 | 133 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3212.0635 | 2010-05-14 20:04 | 2010-05-15 00:04 | MooringSystemInstallation | 133 | 134 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3228.2235 | 2010-05-15 12:13 | 2010-05-16 04:23 | MooringSystemInstallation | 134 | 135 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3232.3835 | 2010-05-15 16:23 | 2010-05-15 20:33 | MooringSystemInstallation | 134 | 134 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 3236.7184 | 2010-05-15 20:43 | 2010-05-16 01:03 | MooringSystemInstallation | 134 | 135 | 2
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 3241.7184 | 2010-05-16 01:43 | 2010-05-16 06:43 | MooringSystemInstallation | 135 | 135 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 3246.7184 | 2010-05-16 06:43 | 2010-05-16 11:43 | MooringSystemInstallation | 135 | 135 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 3251.0533 | 2010-05-16 11:03 | 2010-05-16 15:23 | MooringSystemInstallation | 135 | 135 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3253.0533 | 2010-05-16 13:03 | 2010-05-16 15:03 | MooringSystemInstallation | 135 | 135 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3257.0533 | 2010-05-16 17:03 | 2010-05-16 21:03 | MooringSystemInstallation | 135 | 135 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3273.2133 | 2010-05-17 09:13 | 2010-05-18 01:22 | MooringSystemInstallation | 136 | 137 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3277.3733 | 2010-05-17 13:22 | 2010-05-17 17:32 | MooringSystemInstallation | 136 | 136 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3279.3733 | 2010-05-17 15:22 | 2010-05-17 17:22 | MooringSystemInstallation | 136 | 136 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3283.3733 | 2010-05-17 19:22 | 2010-05-17 23:22 | MooringSystemInstallation | 136 | 136 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3299.5333 | 2010-05-18 11:32 | 2010-05-19 03:42 | MooringSystemInstallation | 137 | 138 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3303.6933 | 2010-05-18 15:42 | 2010-05-18 19:51 | MooringSystemInstallation | 137 | 137 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3305.6933 | 2010-05-18 17:42 | 2010-05-18 19:42 | MooringSystemInstallation | 137 | 137 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3309.6933 | 2010-05-18 21:42 | 2010-05-19 01:42 | MooringSystemInstallation | 137 | 138 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3325.8533 | 2010-05-19 13:51 | 2010-05-20 06:01 | MooringSystemInstallation | 138 | 139 | 2
Mooring System Installation Vessel | Delay | 3 | 12500 | 3328.8533 | 2010-05-19 16:51 | 2010-05-19 19:51 | MooringSystemInstallation | 138 | 138 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3333.0133 | 2010-05-19 21:01 | 2010-05-20 01:10 | MooringSystemInstallation | 138 | 139 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3335.0133 | 2010-05-19 23:01 | 2010-05-20 01:01 | MooringSystemInstallation | 138 | 139 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3339.0133 | 2010-05-20 03:01 | 2010-05-20 07:01 | MooringSystemInstallation | 139 | 139 | 1
Mooring System Installation Vessel | Delay | 17 | 70833.3333 | 3356.0133 | 2010-05-20 20:01 | 2010-05-21 13:01 | MooringSystemInstallation | 139 | 140 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3372.1733 | 2010-05-21 12:10 | 2010-05-22 04:20 | MooringSystemInstallation | 140 | 141 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3376.3333 | 2010-05-21 16:20 | 2010-05-21 20:30 | MooringSystemInstallation | 140 | 140 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3378.3333 | 2010-05-21 18:20 | 2010-05-21 20:20 | MooringSystemInstallation | 140 | 140 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3382.3333 | 2010-05-21 22:20 | 2010-05-22 02:20 | MooringSystemInstallation | 140 | 141 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3398.4933 | 2010-05-22 14:30 | 2010-05-23 06:39 | MooringSystemInstallation | 141 | 142 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3402.6533 | 2010-05-22 18:39 | 2010-05-22 22:49 | MooringSystemInstallation | 141 | 141 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3404.6533 | 2010-05-22 20:39 | 2010-05-22 22:39 | MooringSystemInstallation | 141 | 141 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3408.6533 | 2010-05-23 00:39 | 2010-05-23 04:39 | MooringSystemInstallation | 142 | 142 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3424.8133 | 2010-05-23 16:49 | 2010-05-24 08:58 | MooringSystemInstallation | 142 | 143 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3428.9733 | 2010-05-23 20:58 | 2010-05-24 01:08 | MooringSystemInstallation | 142 | 143 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 3433.3082 | 2010-05-24 01:18 | 2010-05-24 05:39 | MooringSystemInstallation | 143 | 143 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 3438.3082 | 2010-05-24 06:18 | 2010-05-24 11:18 | MooringSystemInstallation | 143 | 143 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 3443.3082 | 2010-05-24 11:18 | 2010-05-24 16:18 | MooringSystemInstallation | 143 | 143 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 3447.6431 | 2010-05-24 15:39 | 2010-05-24 19:59 | MooringSystemInstallation | 143 | 143 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3449.6431 | 2010-05-24 17:39 | 2010-05-24 19:39 | MooringSystemInstallation | 143 | 143 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3453.6431 | 2010-05-24 21:39 | 2010-05-25 01:39 | MooringSystemInstallation | 143 | 144 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3469.8031 | 2010-05-25 13:48 | 2010-05-26 05:58 | MooringSystemInstallation | 144 | 145 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3473.9631 | 2010-05-25 17:58 | 2010-05-25 22:07 | MooringSystemInstallation | 144 | 144 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3475.9631 | 2010-05-25 19:58 | 2010-05-25 21:58 | MooringSystemInstallation | 144 | 144 | 1
Mooring System Installation Vessel | Delay | 4 | 16666.6667 | 3479.9631 | 2010-05-25 23:58 | 2010-05-26 03:58 | MooringSystemInstallation | 144 | 145 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3483.9631 | 2010-05-26 03:58 | 2010-05-26 07:58 | MooringSystemInstallation | 145 | 145 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3500.1231 | 2010-05-26 20:07 | 2010-05-27 12:17 | MooringSystemInstallation | 145 | 146 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3504.2831 | 2010-05-27 00:17 | 2010-05-27 04:27 | MooringSystemInstallation | 146 | 146 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3506.2831 | 2010-05-27 02:17 | 2010-05-27 04:17 | MooringSystemInstallation | 146 | 146 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3510.2831 | 2010-05-27 06:17 | 2010-05-27 10:17 | MooringSystemInstallation | 146 | 146 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3526.4431 | 2010-05-27 22:27 | 2010-05-28 14:36 | MooringSystemInstallation | 146 | 147 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3530.6031 | 2010-05-28 02:36 | 2010-05-28 06:46 | MooringSystemInstallation | 147 | 147 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3532.6031 | 2010-05-28 04:36 | 2010-05-28 06:36 | MooringSystemInstallation | 147 | 147 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3536.6031 | 2010-05-28 08:36 | 2010-05-28 12:36 | MooringSystemInstallation | 147 | 147 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3552.7631 | 2010-05-29 00:46 | 2010-05-29 16:55 | MooringSystemInstallation | 148 | 148 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3556.9231 | 2010-05-29 04:55 | 2010-05-29 09:05 | MooringSystemInstallation | 148 | 148 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3558.9231 | 2010-05-29 06:55 | 2010-05-29 08:55 | MooringSystemInstallation | 148 | 148 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3562.9231 | 2010-05-29 10:55 | 2010-05-29 14:55 | MooringSystemInstallation | 148 | 148 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3579.0831 | 2010-05-30 03:05 | 2010-05-30 19:15 | MooringSystemInstallation | 149 | 149 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3583.2431 | 2010-05-30 07:15 | 2010-05-30 11:24 | MooringSystemInstallation | 149 | 149 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3585.2431 | 2010-05-30 09:15 | 2010-05-30 11:15 | MooringSystemInstallation | 149 | 149 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3589.2431 | 2010-05-30 13:15 | 2010-05-30 17:15 | MooringSystemInstallation | 149 | 149 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3605.4031 | 2010-05-31 05:24 | 2010-05-31 21:34 | MooringSystemInstallation | 150 | 150 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3609.5631 | 2010-05-31 09:34 | 2010-05-31 13:43 | MooringSystemInstallation | 150 | 150 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 3613.898 | 2010-05-31 13:54 | 2010-05-31 18:14 | MooringSystemInstallation | 150 | 150 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 3618.898 | 2010-05-31 18:54 | 2010-05-31 23:54 | MooringSystemInstallation | 150 | 150 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 3623.898 | 2010-05-31 23:54 | 2010-06-01 04:54 | MooringSystemInstallation | 150 | 151 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 3628.2329 | 2010-06-01 04:14 | 2010-06-01 08:34 | MooringSystemInstallation | 151 | 151 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3630.2329 | 2010-06-01 06:14 | 2010-06-01 08:14 | MooringSystemInstallation | 151 | 151 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3634.2329 | 2010-06-01 10:14 | 2010-06-01 14:14 | MooringSystemInstallation | 151 | 151 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3650.3929 | 2010-06-02 02:24 | 2010-06-02 18:33 | MooringSystemInstallation | 152 | 152 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3654.5529 | 2010-06-02 06:33 | 2010-06-02 10:43 | MooringSystemInstallation | 152 | 152 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3656.5529 | 2010-06-02 08:33 | 2010-06-02 10:33 | MooringSystemInstallation | 152 | 152 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3660.5529 | 2010-06-02 12:33 | 2010-06-02 16:33 | MooringSystemInstallation | 152 | 152 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3676.7129 | 2010-06-03 04:43 | 2010-06-03 20:52 | MooringSystemInstallation | 153 | 153 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3680.8729 | 2010-06-03 08:52 | 2010-06-03 13:02 | MooringSystemInstallation | 153 | 153 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3682.8729 | 2010-06-03 10:52 | 2010-06-03 12:52 | MooringSystemInstallation | 153 | 153 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3686.8729 | 2010-06-03 14:52 | 2010-06-03 18:52 | MooringSystemInstallation | 153 | 153 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3703.0329 | 2010-06-04 07:02 | 2010-06-04 23:12 | MooringSystemInstallation | 154 | 154 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3707.1929 | 2010-06-04 11:12 | 2010-06-04 15:21 | MooringSystemInstallation | 154 | 154 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3709.1929 | 2010-06-04 13:12 | 2010-06-04 15:12 | MooringSystemInstallation | 154 | 154 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3713.1929 | 2010-06-04 17:12 | 2010-06-04 21:12 | MooringSystemInstallation | 154 | 154 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3729.3529 | 2010-06-05 09:21 | 2010-06-06 01:31 | MooringSystemInstallation | 155 | 156 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3733.5129 | 2010-06-05 13:31 | 2010-06-05 17:40 | MooringSystemInstallation | 155 | 155 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3735.5129 | 2010-06-05 15:31 | 2010-06-05 17:31 | MooringSystemInstallation | 155 | 155 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3739.5129 | 2010-06-05 19:31 | 2010-06-05 23:31 | MooringSystemInstallation | 155 | 155 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3755.6729 | 2010-06-06 11:40 | 2010-06-07 03:50 | MooringSystemInstallation | 156 | 157 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3759.8329 | 2010-06-06 15:50 | 2010-06-06 20:00 | MooringSystemInstallation | 156 | 156 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3761.8329 | 2010-06-06 17:50 | 2010-06-06 19:50 | MooringSystemInstallation | 156 | 156 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3765.8329 | 2010-06-06 21:50 | 2010-06-07 01:50 | MooringSystemInstallation | 156 | 157 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3781.9929 | 2010-06-07 14:00 | 2010-06-08 06:09 | MooringSystemInstallation | 157 | 158 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3786.1529 | 2010-06-07 18:09 | 2010-06-07 22:19 | MooringSystemInstallation | 157 | 157 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 3790.4878 | 2010-06-07 22:29 | 2010-06-08 02:49 | MooringSystemInstallation | 157 | 158 | 2
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 3795.4878 | 2010-06-08 03:29 | 2010-06-08 08:29 | MooringSystemInstallation | 158 | 158 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 3800.4878 | 2010-06-08 08:29 | 2010-06-08 13:29 | MooringSystemInstallation | 158 | 158 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 3804.8227 | 2010-06-08 12:49 | 2010-06-08 17:09 | MooringSystemInstallation | 158 | 158 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3806.8227 | 2010-06-08 14:49 | 2010-06-08 16:49 | MooringSystemInstallation | 158 | 158 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3810.8227 | 2010-06-08 18:49 | 2010-06-08 22:49 | MooringSystemInstallation | 158 | 158 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3826.9827 | 2010-06-09 10:59 | 2010-06-10 03:09 | MooringSystemInstallation | 159 | 160 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3831.1427 | 2010-06-09 15:09 | 2010-06-09 19:18 | MooringSystemInstallation | 159 | 159 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3833.1427 | 2010-06-09 17:09 | 2010-06-09 19:09 | MooringSystemInstallation | 159 | 159 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3837.1427 | 2010-06-09 21:09 | 2010-06-10 01:09 | MooringSystemInstallation | 159 | 160 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 3853.3027 | 2010-06-10 13:18 | 2010-06-11 05:28 | MooringSystemInstallation | 160 | 161 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 3857.4627 | 2010-06-10 17:28 | 2010-06-10 21:37 | MooringSystemInstallation | 160 | 160 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 3859.4627 | 2010-06-10 19:28 | 2010-06-10 21:28 | MooringSystemInstallation | 160 | 160 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 3863.4627 | 2010-06-10 23:28 | 2010-06-11 03:28 | MooringSystemInstallation | 160 | 161 | 2
Mooring System Installation Vessel | Delay | 137 | 570833.3333 | 4000.4627 | 2010-06-16 16:28 | 2010-06-22 09:28 | MooringSystemInstallation | 166 | 172 | 7
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4016.6227 | 2010-06-17 08:37 | 2010-06-18 00:47 | MooringSystemInstallation | 167 | 168 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4020.7827 | 2010-06-17 12:47 | 2010-06-17 16:57 | MooringSystemInstallation | 167 | 167 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4022.7827 | 2010-06-17 14:47 | 2010-06-17 16:47 | MooringSystemInstallation | 167 | 167 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4026.7827 | 2010-06-17 18:47 | 2010-06-17 22:47 | MooringSystemInstallation | 167 | 167 | 1
Mooring System Installation Vessel | Delay | 19 | 79166.6667 | 4045.7827 | 2010-06-18 13:47 | 2010-06-19 08:47 | MooringSystemInstallation | 168 | 169 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4061.9427 | 2010-06-19 05:57 | 2010-06-19 22:06 | MooringSystemInstallation | 169 | 169 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4066.1027 | 2010-06-19 10:06 | 2010-06-19 14:16 | MooringSystemInstallation | 169 | 169 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4068.1027 | 2010-06-19 12:06 | 2010-06-19 14:06 | MooringSystemInstallation | 169 | 169 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4072.1027 | 2010-06-19 16:06 | 2010-06-19 20:06 | MooringSystemInstallation | 169 | 169 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4088.2627 | 2010-06-20 08:16 | 2010-06-21 00:25 | MooringSystemInstallation | 170 | 171 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4092.4227 | 2010-06-20 12:25 | 2010-06-20 16:35 | MooringSystemInstallation | 170 | 170 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4094.4227 | 2010-06-20 14:25 | 2010-06-20 16:25 | MooringSystemInstallation | 170 | 170 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4098.4227 | 2010-06-20 18:25 | 2010-06-20 22:25 | MooringSystemInstallation | 170 | 170 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4114.5827 | 2010-06-21 10:35 | 2010-06-22 02:45 | MooringSystemInstallation | 171 | 172 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4118.7427 | 2010-06-21 14:45 | 2010-06-21 18:54 | MooringSystemInstallation | 171 | 171 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 4123.0776 | 2010-06-21 19:05 | 2010-06-21 23:25 | MooringSystemInstallation | 171 | 171 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 4128.0776 | 2010-06-22 00:05 | 2010-06-22 05:05 | MooringSystemInstallation | 172 | 172 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 4133.0776 | 2010-06-22 05:05 | 2010-06-22 10:05 | MooringSystemInstallation | 172 | 172 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 4137.4125 | 2010-06-22 09:25 | 2010-06-22 13:45 | MooringSystemInstallation | 172 | 172 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4139.4125 | 2010-06-22 11:25 | 2010-06-22 13:25 | MooringSystemInstallation | 172 | 172 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4143.4125 | 2010-06-22 15:25 | 2010-06-22 19:25 | MooringSystemInstallation | 172 | 172 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4159.5725 | 2010-06-23 07:34 | 2010-06-23 23:44 | MooringSystemInstallation | 173 | 173 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4163.7325 | 2010-06-23 11:44 | 2010-06-23 15:54 | MooringSystemInstallation | 173 | 173 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4165.7325 | 2010-06-23 13:44 | 2010-06-23 15:44 | MooringSystemInstallation | 173 | 173 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4169.7325 | 2010-06-23 17:44 | 2010-06-23 21:44 | MooringSystemInstallation | 173 | 173 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4185.8925 | 2010-06-24 09:54 | 2010-06-25 02:03 | MooringSystemInstallation | 174 | 175 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4190.0525 | 2010-06-24 14:03 | 2010-06-24 18:13 | MooringSystemInstallation | 174 | 174 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4192.0525 | 2010-06-24 16:03 | 2010-06-24 18:03 | MooringSystemInstallation | 174 | 174 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4196.0525 | 2010-06-24 20:03 | 2010-06-25 00:03 | MooringSystemInstallation | 174 | 175 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4212.2125 | 2010-06-25 12:13 | 2010-06-26 04:22 | MooringSystemInstallation | 175 | 176 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4216.3725 | 2010-06-25 16:22 | 2010-06-25 20:32 | MooringSystemInstallation | 175 | 175 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4218.3725 | 2010-06-25 18:22 | 2010-06-25 20:22 | MooringSystemInstallation | 175 | 175 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4222.3725 | 2010-06-25 22:22 | 2010-06-26 02:22 | MooringSystemInstallation | 175 | 176 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4238.5325 | 2010-06-26 14:32 | 2010-06-27 06:42 | MooringSystemInstallation | 176 | 177 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4242.6925 | 2010-06-26 18:42 | 2010-06-26 22:51 | MooringSystemInstallation | 176 | 176 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4244.6925 | 2010-06-26 20:42 | 2010-06-26 22:42 | MooringSystemInstallation | 176 | 176 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4248.6925 | 2010-06-27 00:42 | 2010-06-27 04:42 | MooringSystemInstallation | 177 | 177 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4264.8525 | 2010-06-27 16:51 | 2010-06-28 09:01 | MooringSystemInstallation | 177 | 178 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4269.0125 | 2010-06-27 21:01 | 2010-06-28 01:10 | MooringSystemInstallation | 177 | 178 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4271.0125 | 2010-06-27 23:01 | 2010-06-28 01:01 | MooringSystemInstallation | 177 | 178 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4275.0125 | 2010-06-28 03:01 | 2010-06-28 07:01 | MooringSystemInstallation | 178 | 178 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4291.1725 | 2010-06-28 19:10 | 2010-06-29 11:20 | MooringSystemInstallation | 178 | 179 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4295.3325 | 2010-06-28 23:20 | 2010-06-29 03:30 | MooringSystemInstallation | 178 | 179 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 4299.6674 | 2010-06-29 03:40 | 2010-06-29 08:00 | MooringSystemInstallation | 179 | 179 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 4304.6674 | 2010-06-29 08:40 | 2010-06-29 13:40 | MooringSystemInstallation | 179 | 179 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 4309.6674 | 2010-06-29 13:40 | 2010-06-29 18:40 | MooringSystemInstallation | 179 | 179 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 4314.0023 | 2010-06-29 18:00 | 2010-06-29 22:20 | MooringSystemInstallation | 179 | 179 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4316.0023 | 2010-06-29 20:00 | 2010-06-29 22:00 | MooringSystemInstallation | 179 | 179 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4320.0023 | 2010-06-30 | 2010-06-30 04:00 | MooringSystemInstallation | 180 | 180 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4336.1623 | 2010-06-30 16:10 | 2010-07-01 08:19 | MooringSystemInstallation | 180 | 181 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4340.3223 | 2010-06-30 20:19 | 2010-07-01 00:29 | MooringSystemInstallation | 180 | 181 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4342.3223 | 2010-06-30 22:19 | 2010-07-01 00:19 | MooringSystemInstallation | 180 | 181 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4346.3223 | 2010-07-01 02:19 | 2010-07-01 06:19 | MooringSystemInstallation | 181 | 181 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4362.4823 | 2010-07-01 18:29 | 2010-07-02 10:39 | MooringSystemInstallation | 181 | 182 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4366.6423 | 2010-07-01 22:39 | 2010-07-02 02:48 | MooringSystemInstallation | 181 | 182 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4368.6423 | 2010-07-02 00:39 | 2010-07-02 02:39 | MooringSystemInstallation | 182 | 182 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4372.6423 | 2010-07-02 04:39 | 2010-07-02 08:39 | MooringSystemInstallation | 182 | 182 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4388.8023 | 2010-07-02 20:48 | 2010-07-03 12:58 | MooringSystemInstallation | 182 | 183 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4392.9623 | 2010-07-03 00:58 | 2010-07-03 05:07 | MooringSystemInstallation | 183 | 183 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4394.9623 | 2010-07-03 02:58 | 2010-07-03 04:58 | MooringSystemInstallation | 183 | 183 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4398.9623 | 2010-07-03 06:58 | 2010-07-03 10:58 | MooringSystemInstallation | 183 | 183 | 1
Mooring System Installation Vessel | Delay | 87 | 362500 | 4485.9623 | 2010-07-06 21:58 | 2010-07-10 12:58 | MooringSystemInstallation | 186 | 190 | 5
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4502.1223 | 2010-07-07 14:07 | 2010-07-08 06:17 | MooringSystemInstallation | 187 | 188 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4506.2823 | 2010-07-07 18:17 | 2010-07-07 22:27 | MooringSystemInstallation | 187 | 187 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4508.2823 | 2010-07-07 20:17 | 2010-07-07 22:17 | MooringSystemInstallation | 187 | 187 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4512.2823 | 2010-07-08 00:17 | 2010-07-08 04:17 | MooringSystemInstallation | 188 | 188 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4528.4423 | 2010-07-08 16:27 | 2010-07-09 08:36 | MooringSystemInstallation | 188 | 189 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4532.6023 | 2010-07-08 20:36 | 2010-07-09 00:46 | MooringSystemInstallation | 188 | 189 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4534.6023 | 2010-07-08 22:36 | 2010-07-09 00:36 | MooringSystemInstallation | 188 | 189 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4538.6023 | 2010-07-09 02:36 | 2010-07-09 06:36 | MooringSystemInstallation | 189 | 189 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4554.7623 | 2010-07-09 18:46 | 2010-07-10 10:55 | MooringSystemInstallation | 189 | 190 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4558.9223 | 2010-07-09 22:55 | 2010-07-10 03:05 | MooringSystemInstallation | 189 | 190 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 4563.2572 | 2010-07-10 03:15 | 2010-07-10 07:36 | MooringSystemInstallation | 190 | 190 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 4568.2572 | 2010-07-10 08:15 | 2010-07-10 13:15 | MooringSystemInstallation | 190 | 190 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 4573.2572 | 2010-07-10 13:15 | 2010-07-10 18:15 | MooringSystemInstallation | 190 | 190 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 4577.5921 | 2010-07-10 17:36 | 2010-07-10 21:56 | MooringSystemInstallation | 190 | 190 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4579.5921 | 2010-07-10 19:36 | 2010-07-10 21:36 | MooringSystemInstallation | 190 | 190 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4583.5921 | 2010-07-10 23:36 | 2010-07-11 03:36 | MooringSystemInstallation | 190 | 191 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4599.7521 | 2010-07-11 15:45 | 2010-07-12 07:55 | MooringSystemInstallation | 191 | 192 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4603.9121 | 2010-07-11 19:55 | 2010-07-12 00:04 | MooringSystemInstallation | 191 | 192 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4605.9121 | 2010-07-11 21:55 | 2010-07-11 23:55 | MooringSystemInstallation | 191 | 191 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4609.9121 | 2010-07-12 01:55 | 2010-07-12 05:55 | MooringSystemInstallation | 192 | 192 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4626.0721 | 2010-07-12 18:04 | 2010-07-13 10:14 | MooringSystemInstallation | 192 | 193 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4630.2321 | 2010-07-12 22:14 | 2010-07-13 02:24 | MooringSystemInstallation | 192 | 193 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4632.2321 | 2010-07-13 00:14 | 2010-07-13 02:14 | MooringSystemInstallation | 193 | 193 | 1
Mooring System Installation Vessel | Delay | 42 | 175000 | 4674.2321 | 2010-07-14 18:14 | 2010-07-16 12:14 | MooringSystemInstallation | 194 | 196 | 3
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4678.2321 | 2010-07-14 22:14 | 2010-07-15 02:14 | MooringSystemInstallation | 194 | 195 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4694.3921 | 2010-07-15 14:24 | 2010-07-16 06:33 | MooringSystemInstallation | 195 | 196 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4698.5521 | 2010-07-15 18:33 | 2010-07-15 22:43 | MooringSystemInstallation | 195 | 195 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4700.5521 | 2010-07-15 20:33 | 2010-07-15 22:33 | MooringSystemInstallation | 195 | 195 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4704.5521 | 2010-07-16 00:33 | 2010-07-16 04:33 | MooringSystemInstallation | 196 | 196 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4720.7121 | 2010-07-16 16:43 | 2010-07-17 08:52 | MooringSystemInstallation | 196 | 197 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4724.8721 | 2010-07-16 20:52 | 2010-07-17 01:02 | MooringSystemInstallation | 196 | 197 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4726.8721 | 2010-07-16 22:52 | 2010-07-17 00:52 | MooringSystemInstallation | 196 | 197 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4730.8721 | 2010-07-17 02:52 | 2010-07-17 06:52 | MooringSystemInstallation | 197 | 197 | 1
Mooring System Installation Vessel | Delay | 10 | 41666.6667 | 4740.8721 | 2010-07-17 12:52 | 2010-07-17 22:52 | MooringSystemInstallation | 197 | 197 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4757.0321 | 2010-07-18 05:02 | 2010-07-18 21:12 | MooringSystemInstallation | 198 | 198 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4761.1921 | 2010-07-18 09:12 | 2010-07-18 13:21 | MooringSystemInstallation | 198 | 198 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4763.1921 | 2010-07-18 11:12 | 2010-07-18 13:12 | MooringSystemInstallation | 198 | 198 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4767.1921 | 2010-07-18 15:12 | 2010-07-18 19:12 | MooringSystemInstallation | 198 | 198 | 1
Mooring System Installation Vessel | Delay | 123 | 512500 | 4890.1921 | 2010-07-23 18:12 | 2010-07-28 21:12 | MooringSystemInstallation | 203 | 208 | 6
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4906.3521 | 2010-07-24 10:21 | 2010-07-25 02:31 | MooringSystemInstallation | 204 | 205 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4910.5121 | 2010-07-24 14:31 | 2010-07-24 18:40 | MooringSystemInstallation | 204 | 204 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 4914.847 | 2010-07-24 18:51 | 2010-07-24 23:11 | MooringSystemInstallation | 204 | 204 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 4919.847 | 2010-07-24 23:51 | 2010-07-25 04:51 | MooringSystemInstallation | 204 | 205 | 2
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 4924.847 | 2010-07-25 04:51 | 2010-07-25 09:51 | MooringSystemInstallation | 205 | 205 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 4929.1819 | 2010-07-25 09:11 | 2010-07-25 13:31 | MooringSystemInstallation | 205 | 205 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4931.1819 | 2010-07-25 11:11 | 2010-07-25 13:11 | MooringSystemInstallation | 205 | 205 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4935.1819 | 2010-07-25 15:11 | 2010-07-25 19:11 | MooringSystemInstallation | 205 | 205 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4951.3419 | 2010-07-26 07:21 | 2010-07-26 23:30 | MooringSystemInstallation | 206 | 206 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4955.5019 | 2010-07-26 11:30 | 2010-07-26 15:40 | MooringSystemInstallation | 206 | 206 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4957.5019 | 2010-07-26 13:30 | 2010-07-26 15:30 | MooringSystemInstallation | 206 | 206 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4961.5019 | 2010-07-26 17:30 | 2010-07-26 21:30 | MooringSystemInstallation | 206 | 206 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 4977.6619 | 2010-07-27 09:40 | 2010-07-28 01:49 | MooringSystemInstallation | 207 | 208 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 4981.8219 | 2010-07-27 13:49 | 2010-07-27 17:59 | MooringSystemInstallation | 207 | 207 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 4983.8219 | 2010-07-27 15:49 | 2010-07-27 17:49 | MooringSystemInstallation | 207 | 207 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 4987.8219 | 2010-07-27 19:49 | 2010-07-27 23:49 | MooringSystemInstallation | 207 | 207 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5003.9819 | 2010-07-28 11:59 | 2010-07-29 04:09 | MooringSystemInstallation | 208 | 209 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5008.1419 | 2010-07-28 16:09 | 2010-07-28 20:18 | MooringSystemInstallation | 208 | 208 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5010.1419 | 2010-07-28 18:09 | 2010-07-28 20:09 | MooringSystemInstallation | 208 | 208 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5014.1419 | 2010-07-28 22:09 | 2010-07-29 02:09 | MooringSystemInstallation | 208 | 209 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5030.3019 | 2010-07-29 14:18 | 2010-07-30 06:28 | MooringSystemInstallation | 209 | 210 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5034.4619 | 2010-07-29 18:28 | 2010-07-29 22:37 | MooringSystemInstallation | 209 | 209 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5036.4619 | 2010-07-29 20:28 | 2010-07-29 22:28 | MooringSystemInstallation | 209 | 209 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5040.4619 | 2010-07-30 00:28 | 2010-07-30 04:28 | MooringSystemInstallation | 210 | 210 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5056.6219 | 2010-07-30 16:37 | 2010-07-31 08:47 | MooringSystemInstallation | 210 | 211 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5060.7819 | 2010-07-30 20:47 | 2010-07-31 00:57 | MooringSystemInstallation | 210 | 211 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5062.7819 | 2010-07-30 22:47 | 2010-07-31 00:47 | MooringSystemInstallation | 210 | 211 | 2
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 5066.3791 | 2010-07-31 02:23 | 2010-08-07 02:23 | MooredSubInstallation | 211 | 218 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | 5066.3791 | 2010-07-31 02:23 | 2010-08-07 02:23 | MooredSubInstallation | 211 | 218 | 8
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5066.7819 | 2010-07-31 02:47 | 2010-07-31 06:47 | MooringSystemInstallation | 211 | 211 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 5074.3791 | 2010-07-31 10:23 | 2010-07-31 18:23 | MooredSubInstallation | 211 | 211 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5082.9419 | 2010-07-31 18:57 | 2010-08-01 11:06 | MooringSystemInstallation | 211 | 212 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 5086.3791 | 2010-07-31 22:23 | 2010-08-01 10:23 | MooredSubInstallation | 211 | 212 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5087.1019 | 2010-07-31 23:06 | 2010-08-01 03:16 | MooringSystemInstallation | 211 | 212 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 5091.4368 | 2010-08-01 03:26 | 2010-08-01 07:46 | MooringSystemInstallation | 212 | 212 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 5096.4368 | 2010-08-01 08:26 | 2010-08-01 13:26 | MooringSystemInstallation | 212 | 212 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 5101.4368 | 2010-08-01 13:26 | 2010-08-01 18:26 | MooringSystemInstallation | 212 | 212 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 5105.7717 | 2010-08-01 17:46 | 2010-08-01 22:06 | MooringSystemInstallation | 212 | 212 | 1
Turbine Assembly Line 1 | Delay | 21 | 0 | 5107.3791 | 2010-08-01 19:23 | 2010-08-02 16:23 | MooredSubInstallation | 212 | 213 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5107.7717 | 2010-08-01 19:46 | 2010-08-01 21:46 | MooringSystemInstallation | 212 | 212 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5111.7717 | 2010-08-01 23:46 | 2010-08-02 03:46 | MooringSystemInstallation | 212 | 213 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 5119.3791 | 2010-08-02 07:23 | 2010-08-02 19:23 | MooredSubInstallation | 213 | 213 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5127.9317 | 2010-08-02 15:56 | 2010-08-03 08:06 | MooringSystemInstallation | 213 | 214 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 5131.3791 | 2010-08-02 19:23 | 2010-08-03 07:23 | MooredSubInstallation | 213 | 214 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5132.0917 | 2010-08-02 20:06 | 2010-08-03 00:15 | MooringSystemInstallation | 213 | 214 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5134.0917 | 2010-08-02 22:06 | 2010-08-03 00:06 | MooringSystemInstallation | 213 | 214 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5138.0917 | 2010-08-03 02:06 | 2010-08-03 06:06 | MooringSystemInstallation | 214 | 214 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 5138.3791 | 2010-08-03 02:23 | 2010-08-03 09:23 | MooredSubInstallation | 214 | 214 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5154.2517 | 2010-08-03 18:15 | 2010-08-04 10:25 | MooringSystemInstallation | 214 | 215 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5158.4117 | 2010-08-03 22:25 | 2010-08-04 02:34 | MooringSystemInstallation | 214 | 215 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5160.4117 | 2010-08-04 00:25 | 2010-08-04 02:25 | MooringSystemInstallation | 215 | 215 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5164.4117 | 2010-08-04 04:25 | 2010-08-04 08:25 | MooringSystemInstallation | 215 | 215 | 1
Turbine Assembly Line 1 | Delay | 40 | 0 | 5178.3791 | 2010-08-04 18:23 | 2010-08-06 10:23 | MooredSubInstallation | 215 | 217 | 3
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5180.5717 | 2010-08-04 20:34 | 2010-08-05 12:44 | MooringSystemInstallation | 215 | 216 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 5181.8791 | 2010-08-04 21:53 | 2010-08-05 01:23 | MooredSubInstallation | 215 | 216 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5184.7317 | 2010-08-05 00:44 | 2010-08-05 04:54 | MooringSystemInstallation | 216 | 216 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 5185.3791 | 2010-08-05 01:23 | 2010-08-05 04:53 | MooredSubInstallation | 216 | 216 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5186.7317 | 2010-08-05 02:44 | 2010-08-05 04:44 | MooringSystemInstallation | 216 | 216 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 5188.8791 | 2010-08-05 04:53 | 2010-08-05 08:23 | MooredSubInstallation | 216 | 216 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5190.7317 | 2010-08-05 06:44 | 2010-08-05 10:44 | MooringSystemInstallation | 216 | 216 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5206.8917 | 2010-08-05 22:54 | 2010-08-06 15:03 | MooringSystemInstallation | 216 | 217 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5211.0517 | 2010-08-06 03:03 | 2010-08-06 07:13 | MooringSystemInstallation | 217 | 217 | 1
Towing Group 1 | Delay: No Completed Assemblies Available | 314.5 | 393125 | 5212.8791 | 2010-08-06 04:53 | 2010-08-07 04:53 | MooredSubInstallation | 217 | 218 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 5212.8791 | 2010-08-06 04:53 | 2010-08-19 07:23 | MooredSubInstallation | 217 | 230 | 14
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5213.0517 | 2010-08-06 05:03 | 2010-08-06 07:03 | MooringSystemInstallation | 217 | 217 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5217.0517 | 2010-08-06 09:03 | 2010-08-06 13:03 | MooringSystemInstallation | 217 | 217 | 1
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 5218.8791 | 2010-08-06 10:53 | 2010-08-06 16:53 | MooredSubInstallation | 217 | 217 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 5225.0719 | 2010-08-06 17:04 | 2010-08-06 23:16 | MooredSubInstallation | 217 | 217 | 1
Multi-Purpose Support Vessel | Mobilize | 168 | 700000 | 5225.0719 | 2010-08-06 17:04 | 2010-08-13 17:04 | MooredSubInstallation | 217 | 224 | 8
Multi-Purpose Support Vessel | Transit | 4.3349 | 18062.0833 | 5229.4068 | 2010-08-06 21:24 | 2010-08-07 01:44 | MooredSubInstallation | 217 | 218 | 2
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 5231.4068 | 2010-08-06 23:24 | 2010-08-07 01:24 | MooredSubInstallation | 217 | 218 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5233.2117 | 2010-08-07 01:13 | 2010-08-07 17:22 | MooringSystemInstallation | 218 | 218 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 5234.3791 | 2010-08-07 02:23 | 2010-08-14 02:23 | MooredSubInstallation | 218 | 225 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | 5234.3791 | 2010-08-07 02:23 | 2010-08-07 23:53 | MooredSubInstallation | 218 | 218 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5237.3717 | 2010-08-07 05:22 | 2010-08-07 09:32 | MooringSystemInstallation | 218 | 218 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5239.3717 | 2010-08-07 07:22 | 2010-08-07 09:22 | MooringSystemInstallation | 218 | 218 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 5242.3791 | 2010-08-07 10:23 | 2010-08-07 18:23 | MooredSubInstallation | 218 | 218 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5243.3717 | 2010-08-07 11:22 | 2010-08-07 15:22 | MooringSystemInstallation | 218 | 218 | 1
Multi-Purpose Support Vessel | Delay | 20 | 83333.3333 | 5251.4068 | 2010-08-07 19:24 | 2010-08-08 15:24 | MooredSubInstallation | 218 | 219 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 5254.3791 | 2010-08-07 22:23 | 2010-08-08 10:23 | MooredSubInstallation | 218 | 219 | 2
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 5257.4068 | 2010-08-08 01:24 | 2010-08-08 07:24 | MooredSubInstallation | 219 | 219 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5259.5317 | 2010-08-08 03:32 | 2010-08-08 19:42 | MooringSystemInstallation | 219 | 219 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5263.6917 | 2010-08-08 07:42 | 2010-08-08 11:51 | MooringSystemInstallation | 219 | 219 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 5266.3791 | 2010-08-08 10:23 | 2010-08-08 22:23 | MooredSubInstallation | 219 | 219 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 5268.0266 | 2010-08-08 12:02 | 2010-08-08 16:22 | MooringSystemInstallation | 219 | 219 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 5273.0266 | 2010-08-08 17:02 | 2010-08-08 22:02 | MooringSystemInstallation | 219 | 219 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 5277.4068 | 2010-08-08 21:24 | 2010-08-09 17:24 | MooredSubInstallation | 219 | 220 | 2
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 5278.0266 | 2010-08-08 22:02 | 2010-08-09 03:02 | MooringSystemInstallation | 219 | 220 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 5278.3791 | 2010-08-08 22:23 | 2010-08-09 10:23 | MooredSubInstallation | 219 | 220 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 5282.3615 | 2010-08-09 02:22 | 2010-08-09 06:42 | MooringSystemInstallation | 220 | 220 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 5283.4068 | 2010-08-09 03:24 | 2010-08-09 09:24 | MooredSubInstallation | 220 | 220 | 1
Towing Group 1 | Positioning Support | 58.3349 | 72918.625 | 5283.4068 | 2010-08-09 03:24 | 2010-08-11 13:44 | MooredSubInstallation | 220 | 222 | 3
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5284.3615 | 2010-08-09 04:22 | 2010-08-09 06:22 | MooringSystemInstallation | 220 | 220 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 5285.3791 | 2010-08-09 05:23 | 2010-08-09 12:23 | MooredSubInstallation | 220 | 220 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5288.3615 | 2010-08-09 08:22 | 2010-08-09 12:22 | MooringSystemInstallation | 220 | 220 | 1
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 5290.6316 | 2010-08-09 10:38 | 2010-08-09 17:51 | MooredSubInstallation | 220 | 220 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5304.5215 | 2010-08-10 00:31 | 2010-08-10 16:41 | MooringSystemInstallation | 221 | 221 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5308.6815 | 2010-08-10 04:41 | 2010-08-10 08:50 | MooringSystemInstallation | 221 | 221 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5310.6815 | 2010-08-10 06:41 | 2010-08-10 08:41 | MooringSystemInstallation | 221 | 221 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5314.6815 | 2010-08-10 10:41 | 2010-08-10 14:41 | MooringSystemInstallation | 221 | 221 | 1
Turbine Assembly Line 1 | Delay | 42 | 0 | 5327.3791 | 2010-08-10 23:23 | 2010-08-12 17:23 | MooredSubInstallation | 221 | 223 | 3
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5330.8415 | 2010-08-11 02:50 | 2010-08-11 19:00 | MooringSystemInstallation | 222 | 222 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 5330.8791 | 2010-08-11 02:53 | 2010-08-11 06:23 | MooredSubInstallation | 222 | 222 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 5334.3791 | 2010-08-11 06:23 | 2010-08-11 09:53 | MooredSubInstallation | 222 | 222 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5335.0015 | 2010-08-11 07:00 | 2010-08-11 11:10 | MooringSystemInstallation | 222 | 222 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5337.0015 | 2010-08-11 09:00 | 2010-08-11 11:00 | MooringSystemInstallation | 222 | 222 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 5337.8791 | 2010-08-11 09:53 | 2010-08-11 13:23 | MooredSubInstallation | 222 | 222 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5341.0015 | 2010-08-11 13:00 | 2010-08-11 17:00 | MooringSystemInstallation | 222 | 222 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5357.1615 | 2010-08-12 05:10 | 2010-08-12 21:19 | MooringSystemInstallation | 223 | 223 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5361.3215 | 2010-08-12 09:19 | 2010-08-12 13:29 | MooringSystemInstallation | 223 | 223 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 5361.8791 | 2010-08-12 09:53 | 2010-08-13 09:53 | MooredSubInstallation | 223 | 224 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 463.5 | 579375 | 5361.8791 | 2010-08-12 09:53 | 2010-08-31 17:23 | MooredSubInstallation | 223 | 242 | 20
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5363.3215 | 2010-08-12 11:19 | 2010-08-12 13:19 | MooringSystemInstallation | 223 | 223 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5367.3215 | 2010-08-12 15:19 | 2010-08-12 19:19 | MooringSystemInstallation | 223 | 223 | 1
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 5367.8791 | 2010-08-12 15:53 | 2010-08-12 21:53 | MooredSubInstallation | 223 | 223 | 1
Multi-Purpose Support Vessel | Delay | 90.6651 | 377771.25 | 5374.0719 | 2010-08-12 22:04 | 2010-08-13 04:16 | MooredSubInstallation | 223 | 224 | 2
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 5374.0719 | 2010-08-12 22:04 | 2010-08-16 16:44 | MooredSubInstallation | 223 | 227 | 5
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 5376.0719 | 2010-08-13 00:04 | 2010-08-13 02:04 | MooredSubInstallation | 224 | 224 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 5382.0719 | 2010-08-13 06:04 | 2010-08-13 12:04 | MooredSubInstallation | 224 | 224 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5383.4815 | 2010-08-13 07:29 | 2010-08-13 23:38 | MooringSystemInstallation | 224 | 224 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5387.6415 | 2010-08-13 11:38 | 2010-08-13 15:48 | MooringSystemInstallation | 224 | 224 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5389.6415 | 2010-08-13 13:38 | 2010-08-13 15:38 | MooringSystemInstallation | 224 | 224 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5393.6415 | 2010-08-13 17:38 | 2010-08-13 21:38 | MooringSystemInstallation | 224 | 224 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 5402.0719 | 2010-08-14 02:04 | 2010-08-14 22:04 | MooredSubInstallation | 225 | 225 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 5402.3791 | 2010-08-14 02:23 | 2010-08-21 02:23 | MooredSubInstallation | 225 | 232 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 40.5 | 0 | 5402.3791 | 2010-08-14 02:23 | 2010-08-15 18:53 | MooredSubInstallation | 225 | 226 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 5408.0719 | 2010-08-14 08:04 | 2010-08-14 14:04 | MooredSubInstallation | 225 | 225 | 1
Towing Group 2 | Positioning Support | 34 | 42500 | 5408.0719 | 2010-08-14 08:04 | 2010-08-15 18:04 | MooredSubInstallation | 225 | 226 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5409.8015 | 2010-08-14 09:48 | 2010-08-15 01:58 | MooringSystemInstallation | 225 | 226 | 2
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 5410.3791 | 2010-08-14 10:23 | 2010-08-14 18:23 | MooredSubInstallation | 225 | 225 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5413.9615 | 2010-08-14 13:58 | 2010-08-14 18:07 | MooringSystemInstallation | 225 | 225 | 1
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 5415.2967 | 2010-08-14 15:18 | 2010-08-14 22:31 | MooredSubInstallation | 225 | 225 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5415.9615 | 2010-08-14 15:58 | 2010-08-14 17:58 | MooringSystemInstallation | 225 | 225 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5419.9615 | 2010-08-14 19:58 | 2010-08-14 23:58 | MooringSystemInstallation | 225 | 225 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 5422.3791 | 2010-08-14 22:23 | 2010-08-15 10:23 | MooredSubInstallation | 225 | 226 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 5434.3791 | 2010-08-15 10:23 | 2010-08-15 22:23 | MooredSubInstallation | 226 | 226 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5436.1215 | 2010-08-15 12:07 | 2010-08-16 04:17 | MooringSystemInstallation | 226 | 227 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5440.2815 | 2010-08-15 16:17 | 2010-08-15 20:26 | MooringSystemInstallation | 226 | 226 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 5444.6164 | 2010-08-15 20:37 | 2010-08-16 00:57 | MooringSystemInstallation | 226 | 227 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 5446.3791 | 2010-08-15 22:23 | 2010-08-16 10:23 | MooredSubInstallation | 226 | 227 | 2
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 5449.6164 | 2010-08-16 01:37 | 2010-08-16 06:37 | MooringSystemInstallation | 227 | 227 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 5453.3791 | 2010-08-16 05:23 | 2010-08-16 12:23 | MooredSubInstallation | 227 | 227 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 5454.6164 | 2010-08-16 06:37 | 2010-08-16 11:37 | MooringSystemInstallation | 227 | 227 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 5456.8791 | 2010-08-16 08:53 | 2010-08-16 12:23 | MooredSubInstallation | 227 | 227 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 5458.9513 | 2010-08-16 10:57 | 2010-08-16 15:17 | MooringSystemInstallation | 227 | 227 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 5460.3791 | 2010-08-16 12:23 | 2010-08-16 15:53 | MooredSubInstallation | 227 | 227 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5460.9513 | 2010-08-16 12:57 | 2010-08-16 14:57 | MooringSystemInstallation | 227 | 227 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 5463.8791 | 2010-08-16 15:53 | 2010-08-16 19:23 | MooredSubInstallation | 227 | 227 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5464.9513 | 2010-08-16 16:57 | 2010-08-16 20:57 | MooringSystemInstallation | 227 | 227 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5481.1113 | 2010-08-17 09:07 | 2010-08-18 01:16 | MooringSystemInstallation | 228 | 229 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5485.2713 | 2010-08-17 13:16 | 2010-08-17 17:26 | MooringSystemInstallation | 228 | 228 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5487.2713 | 2010-08-17 15:16 | 2010-08-17 17:16 | MooringSystemInstallation | 228 | 228 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 5487.8791 | 2010-08-17 15:53 | 2010-08-18 15:53 | MooredSubInstallation | 228 | 229 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 589.5 | 736875 | 5487.8791 | 2010-08-17 15:53 | 2010-09-11 05:23 | MooredSubInstallation | 228 | 253 | 26
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5491.2713 | 2010-08-17 19:16 | 2010-08-17 23:16 | MooringSystemInstallation | 228 | 228 | 1
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 5493.8791 | 2010-08-17 21:53 | 2010-08-18 03:53 | MooredSubInstallation | 228 | 229 | 2
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 5500.0719 | 2010-08-18 04:04 | 2010-08-18 10:16 | MooredSubInstallation | 229 | 229 | 1
Multi-Purpose Support Vessel | Delay | 92 | 383333.3333 | 5500.0719 | 2010-08-18 04:04 | 2010-08-22 00:04 | MooredSubInstallation | 229 | 233 | 5
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 5502.0719 | 2010-08-18 06:04 | 2010-08-18 08:04 | MooredSubInstallation | 229 | 229 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5507.4313 | 2010-08-18 11:26 | 2010-08-19 03:35 | MooringSystemInstallation | 229 | 230 | 2
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 5508.0719 | 2010-08-18 12:04 | 2010-08-18 18:04 | MooredSubInstallation | 229 | 229 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5511.5913 | 2010-08-18 15:35 | 2010-08-18 19:45 | MooringSystemInstallation | 229 | 229 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5513.5913 | 2010-08-18 17:35 | 2010-08-18 19:35 | MooringSystemInstallation | 229 | 229 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5517.5913 | 2010-08-18 21:35 | 2010-08-19 01:35 | MooringSystemInstallation | 229 | 230 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 5528.0719 | 2010-08-19 08:04 | 2010-08-20 04:04 | MooredSubInstallation | 230 | 231 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5533.7513 | 2010-08-19 13:45 | 2010-08-20 05:55 | MooringSystemInstallation | 230 | 231 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 5534.0719 | 2010-08-19 14:04 | 2010-08-19 20:04 | MooredSubInstallation | 230 | 230 | 1
Towing Group 3 | Positioning Support | 34 | 42500 | 5534.0719 | 2010-08-19 14:04 | 2010-08-21 00:04 | MooredSubInstallation | 230 | 232 | 3
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5537.9113 | 2010-08-19 17:55 | 2010-08-19 22:04 | MooringSystemInstallation | 230 | 230 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5539.9113 | 2010-08-19 19:55 | 2010-08-19 21:55 | MooringSystemInstallation | 230 | 230 | 1
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 5541.2967 | 2010-08-19 21:18 | 2010-08-20 04:31 | MooredSubInstallation | 230 | 231 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5543.9113 | 2010-08-19 23:55 | 2010-08-20 03:55 | MooringSystemInstallation | 230 | 231 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5560.0713 | 2010-08-20 16:04 | 2010-08-21 08:14 | MooringSystemInstallation | 231 | 232 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5564.2313 | 2010-08-20 20:14 | 2010-08-21 00:23 | MooringSystemInstallation | 231 | 232 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5566.2313 | 2010-08-20 22:14 | 2010-08-21 00:14 | MooringSystemInstallation | 231 | 232 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5570.2313 | 2010-08-21 02:14 | 2010-08-21 06:14 | MooringSystemInstallation | 232 | 232 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 5570.3791 | 2010-08-21 02:23 | 2010-08-28 02:23 | MooredSubInstallation | 232 | 239 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 5570.3791 | 2010-08-21 02:23 | 2010-08-24 12:53 | MooredSubInstallation | 232 | 235 | 4
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 5578.3791 | 2010-08-21 10:23 | 2010-08-21 18:23 | MooredSubInstallation | 232 | 232 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5586.3913 | 2010-08-21 18:23 | 2010-08-22 10:33 | MooringSystemInstallation | 232 | 233 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 5590.3791 | 2010-08-21 22:23 | 2010-08-22 10:23 | MooredSubInstallation | 232 | 233 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5590.5513 | 2010-08-21 22:33 | 2010-08-22 02:43 | MooringSystemInstallation | 232 | 233 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5592.5513 | 2010-08-22 00:33 | 2010-08-22 02:33 | MooringSystemInstallation | 233 | 233 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5596.5513 | 2010-08-22 04:33 | 2010-08-22 08:33 | MooringSystemInstallation | 233 | 233 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 5602.3791 | 2010-08-22 10:23 | 2010-08-22 22:23 | MooredSubInstallation | 233 | 233 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5612.7113 | 2010-08-22 20:43 | 2010-08-23 12:52 | MooringSystemInstallation | 233 | 234 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 5614.3791 | 2010-08-22 22:23 | 2010-08-23 10:23 | MooredSubInstallation | 233 | 234 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5616.8713 | 2010-08-23 00:52 | 2010-08-23 05:02 | MooringSystemInstallation | 234 | 234 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 5621.2062 | 2010-08-23 05:12 | 2010-08-23 09:32 | MooringSystemInstallation | 234 | 234 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 5626.2062 | 2010-08-23 10:12 | 2010-08-23 15:12 | MooringSystemInstallation | 234 | 234 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 5631.2062 | 2010-08-23 15:12 | 2010-08-23 20:12 | MooringSystemInstallation | 234 | 234 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 5635.5411 | 2010-08-23 19:32 | 2010-08-23 23:53 | MooringSystemInstallation | 234 | 234 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5637.5411 | 2010-08-23 21:32 | 2010-08-23 23:32 | MooringSystemInstallation | 234 | 234 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5641.5411 | 2010-08-24 01:32 | 2010-08-24 05:32 | MooringSystemInstallation | 235 | 235 | 1
Turbine Assembly Line 1 | Delay | 29 | 0 | 5643.3791 | 2010-08-24 03:23 | 2010-08-25 08:23 | MooredSubInstallation | 235 | 236 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 5650.3791 | 2010-08-24 10:23 | 2010-08-24 17:23 | MooredSubInstallation | 235 | 235 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 5653.8791 | 2010-08-24 13:53 | 2010-08-24 17:23 | MooredSubInstallation | 235 | 235 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 5657.3791 | 2010-08-24 17:23 | 2010-08-24 20:53 | MooredSubInstallation | 235 | 235 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5657.7011 | 2010-08-24 17:42 | 2010-08-25 09:52 | MooringSystemInstallation | 235 | 236 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 5660.8791 | 2010-08-24 20:53 | 2010-08-25 00:23 | MooredSubInstallation | 235 | 236 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5661.8611 | 2010-08-24 21:52 | 2010-08-25 02:01 | MooringSystemInstallation | 235 | 236 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5663.8611 | 2010-08-24 23:52 | 2010-08-25 01:52 | MooringSystemInstallation | 235 | 236 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5667.8611 | 2010-08-25 03:52 | 2010-08-25 07:52 | MooringSystemInstallation | 236 | 236 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5684.0211 | 2010-08-25 20:01 | 2010-08-26 12:11 | MooringSystemInstallation | 236 | 237 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 5684.8791 | 2010-08-25 20:53 | 2010-08-26 20:53 | MooredSubInstallation | 236 | 237 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 394.2476 | 492809.4405 | 5684.8791 | 2010-08-25 20:53 | 2010-09-11 07:08 | MooredSubInstallation | 236 | 253 | 18
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5688.1811 | 2010-08-26 00:11 | 2010-08-26 04:20 | MooringSystemInstallation | 237 | 237 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5690.1811 | 2010-08-26 02:11 | 2010-08-26 04:11 | MooringSystemInstallation | 237 | 237 | 1
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 5690.8791 | 2010-08-26 02:53 | 2010-08-26 08:53 | MooredSubInstallation | 237 | 237 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5694.1811 | 2010-08-26 06:11 | 2010-08-26 10:11 | MooringSystemInstallation | 237 | 237 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 5697.0719 | 2010-08-26 09:04 | 2010-08-26 15:16 | MooredSubInstallation | 237 | 237 | 1
Multi-Purpose Support Vessel | Delay | 163 | 679166.6667 | 5697.0719 | 2010-08-26 09:04 | 2010-09-02 04:04 | MooredSubInstallation | 237 | 244 | 8
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 5699.0719 | 2010-08-26 11:04 | 2010-08-26 13:04 | MooredSubInstallation | 237 | 237 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 5705.0719 | 2010-08-26 17:04 | 2010-08-26 23:04 | MooredSubInstallation | 237 | 237 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 8333.3333 | 5707.0719 | 2010-08-26 19:04 | 2010-08-26 21:04 | MooredSubInstallation | 237 | 237 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5710.3411 | 2010-08-26 22:20 | 2010-08-27 14:30 | MooringSystemInstallation | 237 | 238 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5714.5011 | 2010-08-27 02:30 | 2010-08-27 06:40 | MooringSystemInstallation | 238 | 238 | 1
Mooring System Installation Vessel | Delay | 18 | 75000 | 5732.5011 | 2010-08-27 20:30 | 2010-08-28 14:30 | MooringSystemInstallation | 238 | 239 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5734.5011 | 2010-08-27 22:30 | 2010-08-28 00:30 | MooringSystemInstallation | 238 | 239 | 2
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 5738.3791 | 2010-08-28 02:23 | 2010-09-04 02:23 | MooredSubInstallation | 239 | 246 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 53.5 | 0 | 5738.3791 | 2010-08-28 02:23 | 2010-08-30 07:53 | MooredSubInstallation | 239 | 241 | 3
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5738.5011 | 2010-08-28 02:30 | 2010-08-28 06:30 | MooringSystemInstallation | 239 | 239 | 1
Multi-Purpose Support Vessel | Delay | 32 | 133333.3333 | 5739.0719 | 2010-08-28 03:04 | 2010-08-29 11:04 | MooredSubInstallation | 239 | 240 | 2
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 5746.3791 | 2010-08-28 10:23 | 2010-08-28 18:23 | MooredSubInstallation | 239 | 239 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5754.6611 | 2010-08-28 18:40 | 2010-08-29 10:49 | MooringSystemInstallation | 239 | 240 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 75000 | 5757.0719 | 2010-08-28 21:04 | 2010-08-29 15:04 | MooredSubInstallation | 239 | 240 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 5758.3791 | 2010-08-28 22:23 | 2010-08-29 10:23 | MooredSubInstallation | 239 | 240 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5758.8211 | 2010-08-28 22:49 | 2010-08-29 02:59 | MooringSystemInstallation | 239 | 240 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5760.8211 | 2010-08-29 00:49 | 2010-08-29 02:49 | MooringSystemInstallation | 240 | 240 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 5763.0719 | 2010-08-29 03:04 | 2010-08-29 09:04 | MooredSubInstallation | 240 | 240 | 1
Towing Group 1 | Positioning Support | 66 | 82500 | 5763.0719 | 2010-08-29 03:04 | 2010-08-31 21:04 | MooredSubInstallation | 240 | 242 | 3
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5764.8211 | 2010-08-29 04:49 | 2010-08-29 08:49 | MooringSystemInstallation | 240 | 240 | 1
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 5770.2967 | 2010-08-29 10:18 | 2010-08-29 17:31 | MooredSubInstallation | 240 | 240 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 5770.3791 | 2010-08-29 10:23 | 2010-08-29 22:23 | MooredSubInstallation | 240 | 240 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5780.9811 | 2010-08-29 20:59 | 2010-08-30 13:08 | MooringSystemInstallation | 240 | 241 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 5782.3791 | 2010-08-29 22:23 | 2010-08-30 10:23 | MooredSubInstallation | 240 | 241 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5785.1411 | 2010-08-30 01:08 | 2010-08-30 05:18 | MooringSystemInstallation | 241 | 241 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5787.1411 | 2010-08-30 03:08 | 2010-08-30 05:08 | MooringSystemInstallation | 241 | 241 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 5789.3791 | 2010-08-30 05:23 | 2010-08-30 12:23 | MooredSubInstallation | 241 | 241 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5791.1411 | 2010-08-30 07:08 | 2010-08-30 11:08 | MooringSystemInstallation | 241 | 241 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 5792.8791 | 2010-08-30 08:53 | 2010-08-30 12:23 | MooredSubInstallation | 241 | 241 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 5796.3791 | 2010-08-30 12:23 | 2010-08-30 15:53 | MooredSubInstallation | 241 | 241 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 5799.8791 | 2010-08-30 15:53 | 2010-08-30 19:23 | MooredSubInstallation | 241 | 241 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5807.3011 | 2010-08-30 23:18 | 2010-08-31 15:28 | MooringSystemInstallation | 241 | 242 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5811.4611 | 2010-08-31 03:28 | 2010-08-31 07:37 | MooringSystemInstallation | 242 | 242 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 5815.796 | 2010-08-31 07:48 | 2010-08-31 12:08 | MooringSystemInstallation | 242 | 242 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 5820.796 | 2010-08-31 12:48 | 2010-08-31 17:48 | MooringSystemInstallation | 242 | 242 | 1
Towing Group 2 | Delay: No Completed Assemblies Available | 408.5825 | 510728.0655 | 5823.8791 | 2010-08-31 15:53 | 2010-09-01 15:53 | MooredSubInstallation | 242 | 243 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 5823.8791 | 2010-08-31 15:53 | 2010-09-17 16:28 | MooredSubInstallation | 242 | 259 | 18
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 5825.796 | 2010-08-31 17:48 | 2010-08-31 22:48 | MooringSystemInstallation | 242 | 242 | 1
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 5829.8791 | 2010-08-31 21:53 | 2010-09-01 03:53 | MooredSubInstallation | 242 | 243 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 5830.1309 | 2010-08-31 22:08 | 2010-09-01 02:28 | MooringSystemInstallation | 242 | 243 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5832.1309 | 2010-09-01 00:08 | 2010-09-01 02:08 | MooringSystemInstallation | 243 | 243 | 1
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 5836.0719 | 2010-09-01 04:04 | 2010-09-01 10:16 | MooredSubInstallation | 243 | 243 | 1
Multi-Purpose Support Vessel | Delay | 73 | 304166.6667 | 5836.0719 | 2010-09-01 04:04 | 2010-09-04 05:04 | MooredSubInstallation | 243 | 246 | 4
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5836.1309 | 2010-09-01 04:08 | 2010-09-01 08:08 | MooringSystemInstallation | 243 | 243 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 5838.0719 | 2010-09-01 06:04 | 2010-09-01 08:04 | MooredSubInstallation | 243 | 243 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 5844.0719 | 2010-09-01 12:04 | 2010-09-01 18:04 | MooredSubInstallation | 243 | 243 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 33333.3333 | 5852.0719 | 2010-09-01 20:04 | 2010-09-02 04:04 | MooredSubInstallation | 243 | 244 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5852.2909 | 2010-09-01 20:17 | 2010-09-02 12:27 | MooringSystemInstallation | 243 | 244 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5856.4509 | 2010-09-02 00:27 | 2010-09-02 04:37 | MooringSystemInstallation | 244 | 244 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5858.4509 | 2010-09-02 02:27 | 2010-09-02 04:27 | MooringSystemInstallation | 244 | 244 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5862.4509 | 2010-09-02 06:27 | 2010-09-02 10:27 | MooringSystemInstallation | 244 | 244 | 1
Multi-Purpose Support Vessel | Delay | 21 | 87500 | 5873.0719 | 2010-09-02 17:04 | 2010-09-03 14:04 | MooredSubInstallation | 244 | 245 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5878.6109 | 2010-09-02 22:37 | 2010-09-03 14:46 | MooringSystemInstallation | 244 | 245 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5882.7709 | 2010-09-03 02:46 | 2010-09-03 06:56 | MooringSystemInstallation | 245 | 245 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5884.7709 | 2010-09-03 04:46 | 2010-09-03 06:46 | MooringSystemInstallation | 245 | 245 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 50000 | 5885.0719 | 2010-09-03 05:04 | 2010-09-03 17:04 | MooredSubInstallation | 245 | 245 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5888.7709 | 2010-09-03 08:46 | 2010-09-03 12:46 | MooringSystemInstallation | 245 | 245 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 5891.0719 | 2010-09-03 11:04 | 2010-09-03 17:04 | MooredSubInstallation | 245 | 245 | 1
Towing Group 2 | Positioning Support | 55 | 68750 | 5891.0719 | 2010-09-03 11:04 | 2010-09-05 18:04 | MooredSubInstallation | 245 | 247 | 3
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 5898.2967 | 2010-09-03 18:18 | 2010-09-04 01:31 | MooredSubInstallation | 245 | 246 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5904.9309 | 2010-09-04 00:56 | 2010-09-04 17:05 | MooringSystemInstallation | 246 | 246 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 5906.3791 | 2010-09-04 02:23 | 2010-09-11 02:23 | MooredSubInstallation | 246 | 253 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 5906.3791 | 2010-09-04 02:23 | 2010-09-07 12:53 | MooredSubInstallation | 246 | 249 | 4
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 5909.0909 | 2010-09-04 05:05 | 2010-09-04 09:15 | MooringSystemInstallation | 246 | 246 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 5911.0909 | 2010-09-04 07:05 | 2010-09-04 09:05 | MooringSystemInstallation | 246 | 246 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 5914.3791 | 2010-09-04 10:23 | 2010-09-04 18:23 | MooredSubInstallation | 246 | 246 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 5915.0909 | 2010-09-04 11:05 | 2010-09-04 15:05 | MooringSystemInstallation | 246 | 246 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 5926.3791 | 2010-09-04 22:23 | 2010-09-05 10:23 | MooredSubInstallation | 246 | 247 | 2
Mooring System Installation Vessel | Delay | 65 | 270833.3333 | 5980.0909 | 2010-09-07 04:05 | 2010-09-09 21:05 | MooringSystemInstallation | 249 | 251 | 3
Turbine Assembly Line 1 | Delay | 59 | 0 | 5985.3791 | 2010-09-07 09:23 | 2010-09-09 20:23 | MooredSubInstallation | 249 | 251 | 3
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 5996.2509 | 2010-09-07 20:15 | 2010-09-08 12:25 | MooringSystemInstallation | 249 | 250 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 5997.3791 | 2010-09-07 21:23 | 2010-09-08 09:23 | MooredSubInstallation | 249 | 250 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6000.4109 | 2010-09-08 00:25 | 2010-09-08 04:34 | MooringSystemInstallation | 250 | 250 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6002.4109 | 2010-09-08 02:25 | 2010-09-08 04:25 | MooringSystemInstallation | 250 | 250 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6006.4109 | 2010-09-08 06:25 | 2010-09-08 10:25 | MooringSystemInstallation | 250 | 250 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 6009.3791 | 2010-09-08 09:23 | 2010-09-08 21:23 | MooredSubInstallation | 250 | 250 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 6016.3791 | 2010-09-08 16:23 | 2010-09-08 23:23 | MooredSubInstallation | 250 | 250 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6019.8791 | 2010-09-08 19:53 | 2010-09-08 23:23 | MooredSubInstallation | 250 | 250 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6022.5709 | 2010-09-08 22:34 | 2010-09-09 14:44 | MooringSystemInstallation | 250 | 251 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6023.3791 | 2010-09-08 23:23 | 2010-09-09 02:53 | MooredSubInstallation | 250 | 251 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6026.7309 | 2010-09-09 02:44 | 2010-09-09 06:53 | MooringSystemInstallation | 251 | 251 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6026.8791 | 2010-09-09 02:53 | 2010-09-09 06:23 | MooredSubInstallation | 251 | 251 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6028.7309 | 2010-09-09 04:44 | 2010-09-09 06:44 | MooringSystemInstallation | 251 | 251 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6032.7309 | 2010-09-09 08:44 | 2010-09-09 12:44 | MooringSystemInstallation | 251 | 251 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6048.8909 | 2010-09-10 00:53 | 2010-09-10 17:03 | MooringSystemInstallation | 252 | 252 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 6050.8791 | 2010-09-10 02:53 | 2010-09-11 02:53 | MooredSubInstallation | 252 | 253 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 509.5825 | 636978.0655 | 6050.8791 | 2010-09-10 02:53 | 2010-10-01 08:28 | MooredSubInstallation | 252 | 273 | 22
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6053.0509 | 2010-09-10 05:03 | 2010-09-10 09:13 | MooringSystemInstallation | 252 | 252 | 1
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 6056.8791 | 2010-09-10 08:53 | 2010-09-10 14:53 | MooredSubInstallation | 252 | 252 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 6057.3858 | 2010-09-10 09:23 | 2010-09-10 13:43 | MooringSystemInstallation | 252 | 252 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 6062.3858 | 2010-09-10 14:23 | 2010-09-10 19:23 | MooringSystemInstallation | 252 | 252 | 1
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 6063.0719 | 2010-09-10 15:04 | 2010-09-10 21:16 | MooredSubInstallation | 252 | 252 | 1
Multi-Purpose Support Vessel | Delay | 172 | 716666.6667 | 6063.0719 | 2010-09-10 15:04 | 2010-09-17 19:04 | MooredSubInstallation | 252 | 259 | 8
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 6065.0719 | 2010-09-10 17:04 | 2010-09-10 19:04 | MooredSubInstallation | 252 | 252 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 6067.3858 | 2010-09-10 19:23 | 2010-09-11 00:23 | MooringSystemInstallation | 252 | 253 | 2
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 6071.0719 | 2010-09-10 23:04 | 2010-09-11 05:04 | MooredSubInstallation | 252 | 253 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 6071.7207 | 2010-09-10 23:43 | 2010-09-11 04:03 | MooringSystemInstallation | 252 | 253 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6073.7207 | 2010-09-11 01:43 | 2010-09-11 03:43 | MooringSystemInstallation | 253 | 253 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 6074.3791 | 2010-09-11 02:23 | 2010-09-18 02:23 | MooredSubInstallation | 253 | 260 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 23.5 | 0 | 6074.3791 | 2010-09-11 02:23 | 2010-09-12 01:53 | MooredSubInstallation | 253 | 254 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6077.7207 | 2010-09-11 05:43 | 2010-09-11 09:43 | MooringSystemInstallation | 253 | 253 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 6082.3791 | 2010-09-11 10:23 | 2010-09-11 18:23 | MooredSubInstallation | 253 | 253 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 6091.0719 | 2010-09-11 19:04 | 2010-09-12 15:04 | MooredSubInstallation | 253 | 254 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6093.8807 | 2010-09-11 21:53 | 2010-09-12 14:02 | MooringSystemInstallation | 253 | 254 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 6094.3791 | 2010-09-11 22:23 | 2010-09-12 10:23 | MooredSubInstallation | 253 | 254 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 6097.0719 | 2010-09-12 01:04 | 2010-09-12 07:04 | MooredSubInstallation | 254 | 254 | 1
Towing Group 3 | Positioning Support | 34 | 42500 | 6097.0719 | 2010-09-12 01:04 | 2010-09-13 11:04 | MooredSubInstallation | 254 | 255 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6098.0407 | 2010-09-12 02:02 | 2010-09-12 06:12 | MooringSystemInstallation | 254 | 254 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6100.0407 | 2010-09-12 04:02 | 2010-09-12 06:02 | MooringSystemInstallation | 254 | 254 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6104.0407 | 2010-09-12 08:02 | 2010-09-12 12:02 | MooringSystemInstallation | 254 | 254 | 1
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 6104.2967 | 2010-09-12 08:18 | 2010-09-12 15:31 | MooredSubInstallation | 254 | 254 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 6106.3791 | 2010-09-12 10:23 | 2010-09-12 22:23 | MooredSubInstallation | 254 | 254 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 6118.3791 | 2010-09-12 22:23 | 2010-09-13 10:23 | MooredSubInstallation | 254 | 255 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6120.2007 | 2010-09-13 00:12 | 2010-09-13 16:22 | MooringSystemInstallation | 255 | 255 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6124.3607 | 2010-09-13 04:22 | 2010-09-13 08:31 | MooringSystemInstallation | 255 | 255 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 6125.3791 | 2010-09-13 05:23 | 2010-09-13 12:23 | MooredSubInstallation | 255 | 255 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6126.3607 | 2010-09-13 06:22 | 2010-09-13 08:22 | MooringSystemInstallation | 255 | 255 | 1
Turbine Assembly Line 1 | Delay | 4 | 0 | 6129.3791 | 2010-09-13 09:23 | 2010-09-13 13:23 | MooredSubInstallation | 255 | 255 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6130.3607 | 2010-09-13 10:22 | 2010-09-13 14:22 | MooringSystemInstallation | 255 | 255 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6132.8791 | 2010-09-13 12:53 | 2010-09-13 16:23 | MooredSubInstallation | 255 | 255 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6136.3791 | 2010-09-13 16:23 | 2010-09-13 19:53 | MooredSubInstallation | 255 | 255 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6139.8791 | 2010-09-13 19:53 | 2010-09-13 23:23 | MooredSubInstallation | 255 | 255 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6146.5207 | 2010-09-14 02:31 | 2010-09-14 18:41 | MooringSystemInstallation | 256 | 256 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6150.6807 | 2010-09-14 06:41 | 2010-09-14 10:50 | MooringSystemInstallation | 256 | 256 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6152.6807 | 2010-09-14 08:41 | 2010-09-14 10:41 | MooringSystemInstallation | 256 | 256 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6156.6807 | 2010-09-14 12:41 | 2010-09-14 16:41 | MooringSystemInstallation | 256 | 256 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 6163.8791 | 2010-09-14 19:53 | 2010-09-15 19:53 | MooredSubInstallation | 256 | 257 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 393.5825 | 491978.0655 | 6163.8791 | 2010-09-14 19:53 | 2010-10-01 05:28 | MooredSubInstallation | 256 | 273 | 18
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 6169.8791 | 2010-09-15 01:53 | 2010-09-15 07:53 | MooredSubInstallation | 257 | 257 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6172.8407 | 2010-09-15 04:50 | 2010-09-15 21:00 | MooringSystemInstallation | 257 | 257 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 6176.0719 | 2010-09-15 08:04 | 2010-09-15 14:16 | MooredSubInstallation | 257 | 257 | 1
Multi-Purpose Support Vessel | Delay | 79 | 329166.6667 | 6176.0719 | 2010-09-15 08:04 | 2010-09-18 15:04 | MooredSubInstallation | 257 | 260 | 4
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6177.0007 | 2010-09-15 09:00 | 2010-09-15 13:10 | MooringSystemInstallation | 257 | 257 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 6178.0719 | 2010-09-15 10:04 | 2010-09-15 12:04 | MooredSubInstallation | 257 | 257 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6179.0007 | 2010-09-15 11:00 | 2010-09-15 13:00 | MooringSystemInstallation | 257 | 257 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6183.0007 | 2010-09-15 15:00 | 2010-09-15 19:00 | MooringSystemInstallation | 257 | 257 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 6184.0719 | 2010-09-15 16:04 | 2010-09-15 22:04 | MooredSubInstallation | 257 | 257 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6199.1607 | 2010-09-16 07:10 | 2010-09-16 23:19 | MooringSystemInstallation | 258 | 258 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6203.3207 | 2010-09-16 11:19 | 2010-09-16 15:29 | MooringSystemInstallation | 258 | 258 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 6204.0719 | 2010-09-16 12:04 | 2010-09-17 08:04 | MooredSubInstallation | 258 | 259 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6205.3207 | 2010-09-16 13:19 | 2010-09-16 15:19 | MooringSystemInstallation | 258 | 258 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6209.3207 | 2010-09-16 17:19 | 2010-09-16 21:19 | MooringSystemInstallation | 258 | 258 | 1
Towing Group 1 | Positioning Support | 34 | 42500 | 6210.0719 | 2010-09-16 18:04 | 2010-09-17 00:04 | MooredSubInstallation | 258 | 259 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 6210.0719 | 2010-09-16 18:04 | 2010-09-18 04:04 | MooredSubInstallation | 258 | 260 | 3
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 6217.2967 | 2010-09-17 01:18 | 2010-09-17 08:31 | MooredSubInstallation | 259 | 259 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6225.4807 | 2010-09-17 09:29 | 2010-09-18 01:38 | MooringSystemInstallation | 259 | 260 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6229.6407 | 2010-09-17 13:38 | 2010-09-17 17:48 | MooringSystemInstallation | 259 | 259 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 6233.9756 | 2010-09-17 17:59 | 2010-09-17 22:19 | MooringSystemInstallation | 259 | 259 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 6238.9756 | 2010-09-17 22:59 | 2010-09-18 03:59 | MooringSystemInstallation | 259 | 260 | 2
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 6242.3791 | 2010-09-18 02:23 | 2010-09-25 02:23 | MooredSubInstallation | 260 | 267 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 78.5 | 0 | 6242.3791 | 2010-09-18 02:23 | 2010-09-21 08:53 | MooredSubInstallation | 260 | 263 | 4
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 6243.9756 | 2010-09-18 03:59 | 2010-09-18 08:59 | MooringSystemInstallation | 260 | 260 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 6248.3105 | 2010-09-18 08:19 | 2010-09-18 12:39 | MooringSystemInstallation | 260 | 260 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6250.3105 | 2010-09-18 10:19 | 2010-09-18 12:19 | MooringSystemInstallation | 260 | 260 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 6250.3791 | 2010-09-18 10:23 | 2010-09-18 18:23 | MooredSubInstallation | 260 | 260 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6254.3105 | 2010-09-18 14:19 | 2010-09-18 18:19 | MooringSystemInstallation | 260 | 260 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 6262.3791 | 2010-09-18 22:23 | 2010-09-19 10:23 | MooredSubInstallation | 260 | 261 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6270.4705 | 2010-09-19 06:28 | 2010-09-19 22:38 | MooringSystemInstallation | 261 | 261 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 6274.3791 | 2010-09-19 10:23 | 2010-09-19 22:23 | MooredSubInstallation | 261 | 261 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6274.6305 | 2010-09-19 10:38 | 2010-09-19 14:47 | MooringSystemInstallation | 261 | 261 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6276.6305 | 2010-09-19 12:38 | 2010-09-19 14:38 | MooringSystemInstallation | 261 | 261 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6280.6305 | 2010-09-19 16:38 | 2010-09-19 20:38 | MooringSystemInstallation | 261 | 261 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 6286.3791 | 2010-09-19 22:23 | 2010-09-20 10:23 | MooredSubInstallation | 261 | 262 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 6293.3791 | 2010-09-20 05:23 | 2010-09-20 12:23 | MooredSubInstallation | 262 | 262 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6296.7905 | 2010-09-20 08:47 | 2010-09-21 00:57 | MooringSystemInstallation | 262 | 263 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6296.8791 | 2010-09-20 08:53 | 2010-09-20 12:23 | MooredSubInstallation | 262 | 262 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6300.3791 | 2010-09-20 12:23 | 2010-09-20 15:53 | MooredSubInstallation | 262 | 262 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6300.9505 | 2010-09-20 12:57 | 2010-09-20 17:07 | MooringSystemInstallation | 262 | 262 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6302.9505 | 2010-09-20 14:57 | 2010-09-20 16:57 | MooringSystemInstallation | 262 | 262 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6303.8791 | 2010-09-20 15:53 | 2010-09-20 19:23 | MooredSubInstallation | 262 | 262 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6306.9505 | 2010-09-20 18:57 | 2010-09-20 22:57 | MooringSystemInstallation | 262 | 262 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6323.1105 | 2010-09-21 11:07 | 2010-09-22 03:16 | MooringSystemInstallation | 263 | 264 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6327.2705 | 2010-09-21 15:16 | 2010-09-21 19:26 | MooringSystemInstallation | 263 | 263 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 6327.8791 | 2010-09-21 15:53 | 2010-09-22 15:53 | MooredSubInstallation | 263 | 264 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 429.5825 | 536978.0655 | 6327.8791 | 2010-09-21 15:53 | 2010-10-09 13:28 | MooredSubInstallation | 263 | 281 | 19
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6329.2705 | 2010-09-21 17:16 | 2010-09-21 19:16 | MooringSystemInstallation | 263 | 263 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6333.2705 | 2010-09-21 21:16 | 2010-09-22 01:16 | MooringSystemInstallation | 263 | 264 | 2
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 6333.8791 | 2010-09-21 21:53 | 2010-09-22 03:53 | MooredSubInstallation | 263 | 264 | 2
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 6340.0719 | 2010-09-22 04:04 | 2010-09-22 10:16 | MooredSubInstallation | 264 | 264 | 1
Multi-Purpose Support Vessel | Delay | 130 | 541666.6667 | 6340.0719 | 2010-09-22 04:04 | 2010-09-27 14:04 | MooredSubInstallation | 264 | 269 | 6
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 6342.0719 | 2010-09-22 06:04 | 2010-09-22 08:04 | MooredSubInstallation | 264 | 264 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 6348.0719 | 2010-09-22 12:04 | 2010-09-22 18:04 | MooredSubInstallation | 264 | 264 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6349.4305 | 2010-09-22 13:26 | 2010-09-23 05:35 | MooringSystemInstallation | 264 | 265 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6353.5905 | 2010-09-22 17:35 | 2010-09-22 21:45 | MooringSystemInstallation | 264 | 264 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6355.5905 | 2010-09-22 19:35 | 2010-09-22 21:35 | MooringSystemInstallation | 264 | 264 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6359.5905 | 2010-09-22 23:35 | 2010-09-23 03:35 | MooringSystemInstallation | 264 | 265 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 6368.0719 | 2010-09-23 08:04 | 2010-09-24 04:04 | MooredSubInstallation | 265 | 266 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 6374.0719 | 2010-09-23 14:04 | 2010-09-23 20:04 | MooredSubInstallation | 265 | 265 | 1
Towing Group 2 | Positioning Support | 34 | 42500 | 6374.0719 | 2010-09-23 14:04 | 2010-09-25 00:04 | MooredSubInstallation | 265 | 267 | 3
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6375.7505 | 2010-09-23 15:45 | 2010-09-24 07:55 | MooringSystemInstallation | 265 | 266 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6379.9105 | 2010-09-23 19:55 | 2010-09-24 00:04 | MooringSystemInstallation | 265 | 266 | 2
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 6381.2967 | 2010-09-23 21:18 | 2010-09-24 04:31 | MooredSubInstallation | 265 | 266 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6381.9105 | 2010-09-23 21:55 | 2010-09-23 23:55 | MooringSystemInstallation | 265 | 265 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6385.9105 | 2010-09-24 01:55 | 2010-09-24 05:55 | MooringSystemInstallation | 266 | 266 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6402.0705 | 2010-09-24 18:04 | 2010-09-25 10:14 | MooringSystemInstallation | 266 | 267 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6406.2305 | 2010-09-24 22:14 | 2010-09-25 02:23 | MooringSystemInstallation | 266 | 267 | 2
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 6410.3791 | 2010-09-25 02:23 | 2010-10-02 02:23 | MooredSubInstallation | 267 | 274 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 6410.3791 | 2010-09-25 02:23 | 2010-09-28 12:53 | MooredSubInstallation | 267 | 270 | 4
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 6410.5654 | 2010-09-25 02:34 | 2010-09-25 06:54 | MooringSystemInstallation | 267 | 267 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 6415.5654 | 2010-09-25 07:34 | 2010-09-25 12:34 | MooringSystemInstallation | 267 | 267 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 6418.3791 | 2010-09-25 10:23 | 2010-09-25 18:23 | MooredSubInstallation | 267 | 267 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 6420.5654 | 2010-09-25 12:34 | 2010-09-25 17:34 | MooringSystemInstallation | 267 | 267 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 6424.9003 | 2010-09-25 16:54 | 2010-09-25 21:14 | MooringSystemInstallation | 267 | 267 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6426.9003 | 2010-09-25 18:54 | 2010-09-25 20:54 | MooringSystemInstallation | 267 | 267 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 6430.3791 | 2010-09-25 22:23 | 2010-09-26 10:23 | MooredSubInstallation | 267 | 268 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6430.9003 | 2010-09-25 22:54 | 2010-09-26 02:54 | MooringSystemInstallation | 267 | 268 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 6442.3791 | 2010-09-26 10:23 | 2010-09-26 22:23 | MooredSubInstallation | 268 | 268 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6447.0603 | 2010-09-26 15:04 | 2010-09-27 07:13 | MooringSystemInstallation | 268 | 269 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 6454.3791 | 2010-09-26 22:23 | 2010-09-27 10:23 | MooredSubInstallation | 268 | 269 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 6461.3791 | 2010-09-27 05:23 | 2010-09-27 12:23 | MooredSubInstallation | 269 | 269 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6464.8791 | 2010-09-27 08:53 | 2010-09-27 12:23 | MooredSubInstallation | 269 | 269 | 1
Mooring System Installation Vessel | Delay | 21 | 87500 | 6468.0603 | 2010-09-27 12:04 | 2010-09-28 09:04 | MooringSystemInstallation | 269 | 270 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6468.3791 | 2010-09-27 12:23 | 2010-09-27 15:53 | MooredSubInstallation | 269 | 269 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6471.8791 | 2010-09-27 15:53 | 2010-09-27 19:23 | MooredSubInstallation | 269 | 269 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6472.2203 | 2010-09-27 16:13 | 2010-09-27 20:23 | MooringSystemInstallation | 269 | 269 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6474.2203 | 2010-09-27 18:13 | 2010-09-27 20:13 | MooringSystemInstallation | 269 | 269 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6478.2203 | 2010-09-27 22:13 | 2010-09-28 02:13 | MooringSystemInstallation | 269 | 270 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 6495.8791 | 2010-09-28 15:53 | 2010-09-29 15:53 | MooredSubInstallation | 270 | 271 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 391.5825 | 489478.0655 | 6495.8791 | 2010-09-28 15:53 | 2010-10-14 23:28 | MooredSubInstallation | 270 | 286 | 17
Mooring System Installation Vessel | Delay | 46 | 191666.6667 | 6524.2203 | 2010-09-29 20:13 | 2010-10-01 18:13 | MooringSystemInstallation | 271 | 273 | 3
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6540.3803 | 2010-09-30 12:23 | 2010-10-01 04:32 | MooringSystemInstallation | 272 | 273 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6544.5403 | 2010-09-30 16:32 | 2010-09-30 20:42 | MooringSystemInstallation | 272 | 272 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6546.5403 | 2010-09-30 18:32 | 2010-09-30 20:32 | MooringSystemInstallation | 272 | 272 | 1
Towing Group 3 | Delay | 51 | 127500 | 6546.8791 | 2010-09-30 18:53 | 2010-10-02 21:53 | MooredSubInstallation | 272 | 274 | 3
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6550.5403 | 2010-09-30 22:32 | 2010-10-01 02:32 | MooringSystemInstallation | 272 | 273 | 2
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 6552.8791 | 2010-10-01 00:53 | 2010-10-01 06:53 | MooredSubInstallation | 273 | 273 | 1
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 6559.0719 | 2010-10-01 07:04 | 2010-10-01 13:16 | MooredSubInstallation | 273 | 273 | 1
Multi-Purpose Support Vessel | Delay | 185 | 770833.3333 | 6559.0719 | 2010-10-01 07:04 | 2010-10-09 00:04 | MooredSubInstallation | 273 | 281 | 9
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 6561.0719 | 2010-10-01 09:04 | 2010-10-01 11:04 | MooredSubInstallation | 273 | 273 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6566.7003 | 2010-10-01 14:42 | 2010-10-02 06:52 | MooringSystemInstallation | 273 | 274 | 2
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 6567.0719 | 2010-10-01 15:04 | 2010-10-01 21:04 | MooredSubInstallation | 273 | 273 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 12500 | 6570.0719 | 2010-10-01 18:04 | 2010-10-01 21:04 | MooredSubInstallation | 273 | 273 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6570.8603 | 2010-10-01 18:52 | 2010-10-01 23:01 | MooringSystemInstallation | 273 | 273 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6572.8603 | 2010-10-01 20:52 | 2010-10-01 22:52 | MooringSystemInstallation | 273 | 273 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6576.8603 | 2010-10-02 00:52 | 2010-10-02 04:52 | MooringSystemInstallation | 274 | 274 | 1
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 6578.3791 | 2010-10-02 02:23 | 2010-10-09 02:23 | MooredSubInstallation | 274 | 281 | 8
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 6578.3791 | 2010-10-02 02:23 | 2010-10-05 12:53 | MooredSubInstallation | 274 | 277 | 4
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 6586.3791 | 2010-10-02 10:23 | 2010-10-02 18:23 | MooredSubInstallation | 274 | 274 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6593.0203 | 2010-10-02 17:01 | 2010-10-03 09:11 | MooringSystemInstallation | 274 | 275 | 2
Multi-Purpose Support Vessel | Delay | 26 | 108333.3333 | 6596.0719 | 2010-10-02 20:04 | 2010-10-03 22:04 | MooredSubInstallation | 274 | 275 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6597.1803 | 2010-10-02 21:11 | 2010-10-03 01:20 | MooringSystemInstallation | 274 | 275 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 6598.3791 | 2010-10-02 22:23 | 2010-10-03 10:23 | MooredSubInstallation | 274 | 275 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 12500 | 6599.0719 | 2010-10-02 23:04 | 2010-10-03 02:04 | MooredSubInstallation | 274 | 275 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6599.1803 | 2010-10-02 23:11 | 2010-10-03 01:11 | MooringSystemInstallation | 274 | 275 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6603.1803 | 2010-10-03 03:11 | 2010-10-03 07:11 | MooringSystemInstallation | 275 | 275 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 6610.3791 | 2010-10-03 10:23 | 2010-10-03 22:23 | MooredSubInstallation | 275 | 275 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 6622.3791 | 2010-10-03 22:23 | 2010-10-04 10:23 | MooredSubInstallation | 275 | 276 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 6629.3791 | 2010-10-04 05:23 | 2010-10-04 12:23 | MooredSubInstallation | 276 | 276 | 1
Turbine Assembly Line 1 | Delay | 50 | 0 | 6679.3791 | 2010-10-06 07:23 | 2010-10-08 09:23 | MooredSubInstallation | 278 | 280 | 3
Mooring System Installation Vessel | Delay | 78 | 325000 | 6681.1803 | 2010-10-06 09:11 | 2010-10-09 15:11 | MooringSystemInstallation | 278 | 281 | 4
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6682.8791 | 2010-10-06 10:53 | 2010-10-06 14:23 | MooredSubInstallation | 278 | 278 | 1
Multi-Purpose Support Vessel | Delay | 85 | 354166.6667 | 6684.0719 | 2010-10-06 12:04 | 2010-10-10 01:04 | MooredSubInstallation | 278 | 282 | 5
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6686.3791 | 2010-10-06 14:23 | 2010-10-06 17:53 | MooredSubInstallation | 278 | 278 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6689.8791 | 2010-10-06 17:53 | 2010-10-06 21:23 | MooredSubInstallation | 278 | 278 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6697.3403 | 2010-10-07 01:20 | 2010-10-07 17:30 | MooringSystemInstallation | 279 | 279 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 58333.3333 | 6698.0719 | 2010-10-07 02:04 | 2010-10-07 16:04 | MooredSubInstallation | 279 | 279 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6701.5003 | 2010-10-07 05:30 | 2010-10-07 09:40 | MooringSystemInstallation | 279 | 279 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6703.5003 | 2010-10-07 07:30 | 2010-10-07 09:30 | MooringSystemInstallation | 279 | 279 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 6704.0719 | 2010-10-07 08:04 | 2010-10-07 14:04 | MooredSubInstallation | 279 | 279 | 1
Towing Group 3 | Positioning Support | 145 | 181250 | 6704.0719 | 2010-10-07 08:04 | 2010-10-13 09:04 | MooredSubInstallation | 279 | 285 | 7
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6707.5003 | 2010-10-07 11:30 | 2010-10-07 15:30 | MooringSystemInstallation | 279 | 279 | 1
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 6711.2967 | 2010-10-07 15:18 | 2010-10-07 22:31 | MooredSubInstallation | 279 | 279 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 6713.8791 | 2010-10-07 17:53 | 2010-10-08 17:53 | MooredSubInstallation | 279 | 280 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 496.5825 | 620728.0655 | 6713.8791 | 2010-10-07 17:53 | 2010-10-28 10:28 | MooredSubInstallation | 279 | 300 | 22
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 6719.8791 | 2010-10-07 23:53 | 2010-10-08 05:53 | MooredSubInstallation | 279 | 280 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6723.6603 | 2010-10-08 03:40 | 2010-10-08 19:49 | MooringSystemInstallation | 280 | 280 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 6726.0719 | 2010-10-08 06:04 | 2010-10-08 12:16 | MooredSubInstallation | 280 | 280 | 1
Multi-Purpose Support Vessel | Delay | 22 | 91666.6667 | 6726.0719 | 2010-10-08 06:04 | 2010-10-09 04:04 | MooredSubInstallation | 280 | 281 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6727.8203 | 2010-10-08 07:49 | 2010-10-08 11:59 | MooringSystemInstallation | 280 | 280 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 6728.0719 | 2010-10-08 08:04 | 2010-10-08 10:04 | MooredSubInstallation | 280 | 280 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 6732.1552 | 2010-10-08 12:09 | 2010-10-08 16:29 | MooringSystemInstallation | 280 | 280 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 6734.0719 | 2010-10-08 14:04 | 2010-10-08 20:04 | MooredSubInstallation | 280 | 280 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 6737.1552 | 2010-10-08 17:09 | 2010-10-08 22:09 | MooringSystemInstallation | 280 | 280 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 6742.1552 | 2010-10-08 22:09 | 2010-10-09 03:09 | MooringSystemInstallation | 280 | 281 | 2
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 32.5 | 0 | 6746.3791 | 2010-10-09 02:23 | 2010-10-16 02:23 | MooredSubInstallation | 281 | 288 | 8
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 6746.3791 | 2010-10-09 02:23 | 2010-10-10 10:53 | MooredSubInstallation | 281 | 282 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 6746.4901 | 2010-10-09 02:29 | 2010-10-09 06:50 | MooringSystemInstallation | 281 | 281 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6748.4901 | 2010-10-09 04:29 | 2010-10-09 06:29 | MooringSystemInstallation | 281 | 281 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6752.4901 | 2010-10-09 08:29 | 2010-10-09 12:29 | MooringSystemInstallation | 281 | 281 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 6754.0719 | 2010-10-09 10:04 | 2010-10-10 06:04 | MooredSubInstallation | 281 | 282 | 2
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 6754.3791 | 2010-10-09 10:23 | 2010-10-09 18:23 | MooredSubInstallation | 281 | 281 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 6760.0719 | 2010-10-09 16:04 | 2010-10-09 22:04 | MooredSubInstallation | 281 | 281 | 1
Towing Group 1 | Positioning Support | 34 | 42500 | 6760.0719 | 2010-10-09 16:04 | 2010-10-11 02:04 | MooredSubInstallation | 281 | 283 | 3
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 6766.3791 | 2010-10-09 22:23 | 2010-10-10 10:23 | MooredSubInstallation | 281 | 282 | 2
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 6767.2967 | 2010-10-09 23:18 | 2010-10-10 06:31 | MooredSubInstallation | 281 | 282 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6768.6501 | 2010-10-10 00:39 | 2010-10-10 16:49 | MooringSystemInstallation | 282 | 282 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6772.8101 | 2010-10-10 04:49 | 2010-10-10 08:58 | MooringSystemInstallation | 282 | 282 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6774.8101 | 2010-10-10 06:49 | 2010-10-10 08:49 | MooringSystemInstallation | 282 | 282 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 6778.3791 | 2010-10-10 10:23 | 2010-10-10 22:23 | MooredSubInstallation | 282 | 282 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6778.8101 | 2010-10-10 10:49 | 2010-10-10 14:49 | MooringSystemInstallation | 282 | 282 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 6790.3791 | 2010-10-10 22:23 | 2010-10-11 10:23 | MooredSubInstallation | 282 | 283 | 2
Turbine Assembly Line 1 | Delay | 41 | 0 | 6831.3791 | 2010-10-12 15:23 | 2010-10-14 08:23 | MooredSubInstallation | 284 | 286 | 3
Mooring System Installation Vessel | Delay | 53 | 220833.3333 | 6831.8101 | 2010-10-12 15:49 | 2010-10-14 20:49 | MooringSystemInstallation | 284 | 286 | 3
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 6838.3791 | 2010-10-12 22:23 | 2010-10-13 05:23 | MooredSubInstallation | 284 | 285 | 2
Turbine Assembly Line 1 | Delay | 4 | 0 | 6842.3791 | 2010-10-13 02:23 | 2010-10-13 06:23 | MooredSubInstallation | 285 | 285 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6845.8791 | 2010-10-13 05:53 | 2010-10-13 09:23 | MooredSubInstallation | 285 | 285 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6847.9701 | 2010-10-13 07:58 | 2010-10-14 00:08 | MooringSystemInstallation | 285 | 286 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6849.3791 | 2010-10-13 09:23 | 2010-10-13 12:53 | MooredSubInstallation | 285 | 285 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6852.1301 | 2010-10-13 12:08 | 2010-10-13 16:17 | MooringSystemInstallation | 285 | 285 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6852.8791 | 2010-10-13 12:53 | 2010-10-13 16:23 | MooredSubInstallation | 285 | 285 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6854.1301 | 2010-10-13 14:08 | 2010-10-13 16:08 | MooringSystemInstallation | 285 | 285 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6858.1301 | 2010-10-13 18:08 | 2010-10-13 22:08 | MooringSystemInstallation | 285 | 285 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6874.2901 | 2010-10-14 10:17 | 2010-10-15 02:27 | MooringSystemInstallation | 286 | 287 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 6876.8791 | 2010-10-14 12:53 | 2010-10-15 12:53 | MooredSubInstallation | 286 | 287 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 495.5825 | 619478.0655 | 6876.8791 | 2010-10-14 12:53 | 2010-11-04 04:28 | MooredSubInstallation | 286 | 307 | 22
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6878.4501 | 2010-10-14 14:27 | 2010-10-14 18:37 | MooringSystemInstallation | 286 | 286 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6880.4501 | 2010-10-14 16:27 | 2010-10-14 18:27 | MooringSystemInstallation | 286 | 286 | 1
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 6882.8791 | 2010-10-14 18:53 | 2010-10-15 00:53 | MooredSubInstallation | 286 | 287 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6884.4501 | 2010-10-14 20:27 | 2010-10-15 00:27 | MooringSystemInstallation | 286 | 287 | 2
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 6889.0719 | 2010-10-15 01:04 | 2010-10-15 07:16 | MooredSubInstallation | 287 | 287 | 1
Multi-Purpose Support Vessel | Delay | 129 | 537500 | 6889.0719 | 2010-10-15 01:04 | 2010-10-20 10:04 | MooredSubInstallation | 287 | 292 | 6
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 6891.0719 | 2010-10-15 03:04 | 2010-10-15 05:04 | MooredSubInstallation | 287 | 287 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6900.6101 | 2010-10-15 12:37 | 2010-10-16 04:46 | MooringSystemInstallation | 287 | 288 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6904.7701 | 2010-10-15 16:46 | 2010-10-15 20:56 | MooringSystemInstallation | 287 | 287 | 1
Mooring System Installation Vessel | Delay | 2 | 8333.3333 | 6906.7701 | 2010-10-15 18:46 | 2010-10-15 20:46 | MooringSystemInstallation | 287 | 287 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6908.7701 | 2010-10-15 20:46 | 2010-10-15 22:46 | MooringSystemInstallation | 287 | 287 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6912.7701 | 2010-10-16 00:46 | 2010-10-16 04:46 | MooringSystemInstallation | 288 | 288 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 6914.3791 | 2010-10-16 02:23 | 2010-10-23 02:23 | MooredSubInstallation | 288 | 295 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 37.5 | 0 | 6914.3791 | 2010-10-16 02:23 | 2010-10-17 15:53 | MooredSubInstallation | 288 | 289 | 2
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 6922.3791 | 2010-10-16 10:23 | 2010-10-16 18:23 | MooredSubInstallation | 288 | 288 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6928.9301 | 2010-10-16 16:56 | 2010-10-17 09:05 | MooringSystemInstallation | 288 | 289 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6933.0901 | 2010-10-16 21:05 | 2010-10-17 01:15 | MooringSystemInstallation | 288 | 289 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 6934.3791 | 2010-10-16 22:23 | 2010-10-17 10:23 | MooredSubInstallation | 288 | 289 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6935.0901 | 2010-10-16 23:05 | 2010-10-17 01:05 | MooringSystemInstallation | 288 | 289 | 2
Multi-Purpose Support Vessel | Delay | 48 | 200000 | 6939.0719 | 2010-10-17 03:04 | 2010-10-19 03:04 | MooredSubInstallation | 289 | 291 | 3
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6939.0901 | 2010-10-17 03:05 | 2010-10-17 07:05 | MooringSystemInstallation | 289 | 289 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 6945.0719 | 2010-10-17 09:04 | 2010-10-17 15:04 | MooredSubInstallation | 289 | 289 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 6946.3791 | 2010-10-17 10:23 | 2010-10-17 22:23 | MooredSubInstallation | 289 | 289 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 8333.3333 | 6947.0719 | 2010-10-17 11:04 | 2010-10-17 13:04 | MooredSubInstallation | 289 | 289 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 6955.2501 | 2010-10-17 19:15 | 2010-10-18 11:25 | MooringSystemInstallation | 289 | 290 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 6958.3791 | 2010-10-17 22:23 | 2010-10-18 10:23 | MooredSubInstallation | 289 | 290 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 6959.4101 | 2010-10-17 23:25 | 2010-10-18 03:34 | MooringSystemInstallation | 289 | 290 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 6963.745 | 2010-10-18 03:45 | 2010-10-18 08:05 | MooringSystemInstallation | 290 | 290 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 6965.3791 | 2010-10-18 05:23 | 2010-10-18 12:23 | MooredSubInstallation | 290 | 290 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 6968.745 | 2010-10-18 08:45 | 2010-10-18 13:45 | MooringSystemInstallation | 290 | 290 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 6973.745 | 2010-10-18 13:45 | 2010-10-18 18:45 | MooringSystemInstallation | 290 | 290 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 6978.0799 | 2010-10-18 18:05 | 2010-10-18 22:25 | MooringSystemInstallation | 290 | 290 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 6980.0799 | 2010-10-18 20:05 | 2010-10-18 22:05 | MooringSystemInstallation | 290 | 290 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 6984.0799 | 2010-10-19 00:05 | 2010-10-19 04:05 | MooringSystemInstallation | 291 | 291 | 1
Multi-Purpose Support Vessel | Delay | 43 | 179166.6667 | 6990.0719 | 2010-10-19 06:04 | 2010-10-21 01:04 | MooredSubInstallation | 291 | 293 | 3
Turbine Assembly Line 1 | Delay | 28 | 0 | 6993.3791 | 2010-10-19 09:23 | 2010-10-20 13:23 | MooredSubInstallation | 291 | 292 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 6996.8791 | 2010-10-19 12:53 | 2010-10-19 16:23 | MooredSubInstallation | 291 | 291 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7000.2399 | 2010-10-19 16:14 | 2010-10-20 08:24 | MooringSystemInstallation | 291 | 292 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7000.3791 | 2010-10-19 16:23 | 2010-10-19 19:53 | MooredSubInstallation | 291 | 291 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7003.8791 | 2010-10-19 19:53 | 2010-10-19 23:23 | MooredSubInstallation | 291 | 291 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7004.3999 | 2010-10-19 20:24 | 2010-10-20 00:34 | MooringSystemInstallation | 291 | 292 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 7006.3999 | 2010-10-19 22:24 | 2010-10-20 00:24 | MooringSystemInstallation | 291 | 292 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 75000 | 7008.0719 | 2010-10-20 00:04 | 2010-10-20 18:04 | MooredSubInstallation | 292 | 292 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 7010.3999 | 2010-10-20 02:24 | 2010-10-20 06:24 | MooringSystemInstallation | 292 | 292 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 7014.0719 | 2010-10-20 06:04 | 2010-10-20 12:04 | MooredSubInstallation | 292 | 292 | 1
Towing Group 2 | Positioning Support | 125 | 156250 | 7014.0719 | 2010-10-20 06:04 | 2010-10-25 11:04 | MooredSubInstallation | 292 | 297 | 6
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 7021.2967 | 2010-10-20 13:18 | 2010-10-20 20:31 | MooredSubInstallation | 292 | 292 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7026.5599 | 2010-10-20 18:34 | 2010-10-21 10:43 | MooringSystemInstallation | 292 | 293 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 316.5825 | 395728.0655 | 7027.8791 | 2010-10-20 19:53 | 2010-10-21 19:53 | MooredSubInstallation | 292 | 293 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 7027.8791 | 2010-10-20 19:53 | 2010-11-03 00:28 | MooredSubInstallation | 292 | 306 | 15
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7030.7199 | 2010-10-20 22:43 | 2010-10-21 02:53 | MooringSystemInstallation | 292 | 293 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 7032.7199 | 2010-10-21 00:43 | 2010-10-21 02:43 | MooringSystemInstallation | 293 | 293 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 7036.7199 | 2010-10-21 04:43 | 2010-10-21 08:43 | MooringSystemInstallation | 293 | 293 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7052.8799 | 2010-10-21 20:53 | 2010-10-22 13:02 | MooringSystemInstallation | 293 | 294 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7057.0399 | 2010-10-22 01:02 | 2010-10-22 05:12 | MooringSystemInstallation | 294 | 294 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 7059.0399 | 2010-10-22 03:02 | 2010-10-22 05:02 | MooringSystemInstallation | 294 | 294 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 7063.0399 | 2010-10-22 07:02 | 2010-10-22 11:02 | MooringSystemInstallation | 294 | 294 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 7082.3791 | 2010-10-23 02:23 | 2010-10-30 02:23 | MooredSubInstallation | 295 | 302 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 54.5 | 0 | 7082.3791 | 2010-10-23 02:23 | 2010-10-25 08:53 | MooredSubInstallation | 295 | 297 | 3
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 7090.3791 | 2010-10-23 10:23 | 2010-10-23 18:23 | MooredSubInstallation | 295 | 295 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 7102.3791 | 2010-10-23 22:23 | 2010-10-24 10:23 | MooredSubInstallation | 295 | 296 | 2
Turbine Assembly Line 1 | Delay | 12 | 0 | 7114.3791 | 2010-10-24 10:23 | 2010-10-24 22:23 | MooredSubInstallation | 296 | 296 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 7126.3791 | 2010-10-24 22:23 | 2010-10-25 10:23 | MooredSubInstallation | 296 | 297 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 7138.3791 | 2010-10-25 10:23 | 2010-10-25 22:23 | MooredSubInstallation | 297 | 297 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 7145.3791 | 2010-10-25 17:23 | 2010-10-26 00:23 | MooredSubInstallation | 297 | 298 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7148.8791 | 2010-10-25 20:53 | 2010-10-26 00:23 | MooredSubInstallation | 297 | 298 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7152.3791 | 2010-10-26 00:23 | 2010-10-26 03:53 | MooredSubInstallation | 298 | 298 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7155.8791 | 2010-10-26 03:53 | 2010-10-26 07:23 | MooredSubInstallation | 298 | 298 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 7179.8791 | 2010-10-27 03:53 | 2010-10-28 03:53 | MooredSubInstallation | 299 | 300 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 412.5825 | 515728.0655 | 7179.8791 | 2010-10-27 03:53 | 2010-11-13 08:28 | MooredSubInstallation | 299 | 316 | 18
Mooring System Installation Vessel | Delay | 179 | 745833.3333 | 7242.0399 | 2010-10-29 18:02 | 2010-11-06 05:02 | MooringSystemInstallation | 301 | 309 | 9
Towing Group 3 | Delay | 220 | 550000 | 7247.8791 | 2010-10-29 23:53 | 2010-11-08 03:53 | MooredSubInstallation | 301 | 311 | 11
Towing Group 1 | Delay | 68 | 170000 | 7247.8791 | 2010-10-29 23:53 | 2010-11-01 19:53 | MooredSubInstallation | 301 | 304 | 4
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 7250.3791 | 2010-10-30 02:23 | 2010-11-06 02:23 | MooredSubInstallation | 302 | 309 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 70.5 | 0 | 7250.3791 | 2010-10-30 02:23 | 2010-11-02 00:53 | MooredSubInstallation | 302 | 305 | 4
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 7253.8791 | 2010-10-30 05:53 | 2010-10-30 11:53 | MooredSubInstallation | 302 | 302 | 1
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 7253.8791 | 2010-10-30 05:53 | 2010-10-30 11:53 | MooredSubInstallation | 302 | 302 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7258.1999 | 2010-10-30 10:12 | 2010-10-31 02:22 | MooringSystemInstallation | 302 | 303 | 2
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 7258.3791 | 2010-10-30 10:23 | 2010-10-30 18:23 | MooredSubInstallation | 302 | 302 | 1
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 7260.0719 | 2010-10-30 12:04 | 2010-10-30 18:16 | MooredSubInstallation | 302 | 302 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 7260.0719 | 2010-10-30 12:04 | 2010-10-30 18:16 | MooredSubInstallation | 302 | 302 | 1
Multi-Purpose Support Vessel | Delay | 246 | 1025000 | 7260.0719 | 2010-10-30 12:04 | 2010-11-09 18:04 | MooredSubInstallation | 302 | 312 | 11
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 7262.0719 | 2010-10-30 14:04 | 2010-10-30 16:04 | MooredSubInstallation | 302 | 302 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7262.3599 | 2010-10-30 14:22 | 2010-10-30 18:31 | MooringSystemInstallation | 302 | 302 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 7264.3599 | 2010-10-30 16:22 | 2010-10-30 18:22 | MooringSystemInstallation | 302 | 302 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 7268.0719 | 2010-10-30 20:04 | 2010-10-31 02:04 | MooredSubInstallation | 302 | 303 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 7268.3599 | 2010-10-30 20:22 | 2010-10-31 00:22 | MooringSystemInstallation | 302 | 303 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 7270.3791 | 2010-10-30 22:23 | 2010-10-31 10:23 | MooredSubInstallation | 302 | 303 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 33333.3333 | 7276.0719 | 2010-10-31 04:04 | 2010-10-31 12:04 | MooredSubInstallation | 303 | 303 | 1
Multi-Purpose Support Vessel | Delay | 2 | 8333.3333 | 7278.0719 | 2010-10-31 06:04 | 2010-10-31 08:04 | MooredSubInstallation | 303 | 303 | 1
Turbine Assembly Line 1 | Delay | 8 | 0 | 7278.3791 | 2010-10-31 06:23 | 2010-10-31 14:23 | MooredSubInstallation | 303 | 303 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7284.5199 | 2010-10-31 12:31 | 2010-11-01 04:41 | MooringSystemInstallation | 303 | 304 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7288.6799 | 2010-10-31 16:41 | 2010-10-31 20:50 | MooringSystemInstallation | 303 | 303 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 50000 | 7290.0719 | 2010-10-31 18:04 | 2010-11-01 06:04 | MooredSubInstallation | 303 | 304 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 7290.3791 | 2010-10-31 18:23 | 2010-11-01 06:23 | MooredSubInstallation | 303 | 304 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 7290.6799 | 2010-10-31 18:41 | 2010-10-31 20:41 | MooringSystemInstallation | 303 | 303 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 7294.6799 | 2010-10-31 22:41 | 2010-11-01 02:41 | MooringSystemInstallation | 303 | 304 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 7296.0719 | 2010-11-01 00:04 | 2010-11-01 06:04 | MooredSubInstallation | 304 | 304 | 1
Towing Group 3 | Positioning Support | 36 | 45000 | 7296.0719 | 2010-11-01 00:04 | 2010-11-02 12:04 | MooredSubInstallation | 304 | 305 | 2
Towing Group 1 | Queue | 36 | 45000 | 7296.0719 | 2010-11-01 00:04 | 2010-11-02 12:04 | MooredSubInstallation | 304 | 305 | 2
Multi-Purpose Support Vessel | Delay | 0 | 0 | 7296.0719 | 2010-11-01 00:04 | 2010-11-01 00:04 | MooredSubInstallation | 304 | 304 | 1
Turbine Assembly Line 1 | Delay | 8 | 0 | 7298.3791 | 2010-11-01 02:23 | 2010-11-01 10:23 | MooredSubInstallation | 304 | 304 | 1
Multi-Purpose Support Vessel | Delay | 4 | 16666.6667 | 7300.0719 | 2010-11-01 04:04 | 2010-11-01 08:04 | MooredSubInstallation | 304 | 304 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 7302.0719 | 2010-11-01 06:04 | 2010-11-01 08:04 | MooredSubInstallation | 304 | 304 | 1
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 7303.2967 | 2010-11-01 07:18 | 2010-11-01 14:31 | MooredSubInstallation | 304 | 304 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 7308.0719 | 2010-11-01 12:04 | 2010-11-01 18:04 | MooredSubInstallation | 304 | 304 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 7310.3791 | 2010-11-01 14:23 | 2010-11-02 02:23 | MooredSubInstallation | 304 | 305 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7310.8399 | 2010-11-01 14:50 | 2010-11-02 07:00 | MooringSystemInstallation | 304 | 305 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7314.9999 | 2010-11-01 19:00 | 2010-11-01 23:10 | MooringSystemInstallation | 304 | 304 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 7317.3791 | 2010-11-01 21:23 | 2010-11-02 04:23 | MooredSubInstallation | 304 | 305 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 45833.3333 | 7319.0719 | 2010-11-01 23:04 | 2010-11-02 10:04 | MooredSubInstallation | 304 | 305 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 7319.3348 | 2010-11-01 23:20 | 2010-11-02 03:40 | MooringSystemInstallation | 304 | 305 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7320.8791 | 2010-11-02 00:53 | 2010-11-02 04:23 | MooredSubInstallation | 305 | 305 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7324.3791 | 2010-11-02 04:23 | 2010-11-02 07:53 | MooredSubInstallation | 305 | 305 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7327.8791 | 2010-11-02 07:53 | 2010-11-02 11:23 | MooredSubInstallation | 305 | 305 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 7351.8791 | 2010-11-03 07:53 | 2010-11-04 07:53 | MooredSubInstallation | 306 | 307 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 330.5825 | 413228.0655 | 7351.8791 | 2010-11-03 07:53 | 2010-11-17 02:28 | MooredSubInstallation | 306 | 320 | 15
Mooring System Installation Vessel | Delay | 49 | 204166.6667 | 7368.3348 | 2010-11-04 00:20 | 2010-11-06 01:20 | MooringSystemInstallation | 307 | 309 | 3
Towing Group 2 | Delay | 21 | 52500 | 7372.8791 | 2010-11-04 04:53 | 2010-11-05 01:53 | MooredSubInstallation | 307 | 308 | 2
Multi-Purpose Support Vessel | Delay | 54 | 225000 | 7373.0719 | 2010-11-04 05:04 | 2010-11-06 11:04 | MooredSubInstallation | 307 | 309 | 3
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 7373.3348 | 2010-11-04 05:20 | 2010-11-04 10:20 | MooringSystemInstallation | 307 | 307 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 7378.3348 | 2010-11-04 10:20 | 2010-11-04 15:20 | MooringSystemInstallation | 307 | 307 | 1
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 7378.8791 | 2010-11-04 10:53 | 2010-11-04 16:53 | MooredSubInstallation | 307 | 307 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 37500 | 7382.0719 | 2010-11-04 14:04 | 2010-11-04 23:04 | MooredSubInstallation | 307 | 307 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 7382.6697 | 2010-11-04 14:40 | 2010-11-04 19:00 | MooringSystemInstallation | 307 | 307 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 7384.6697 | 2010-11-04 16:40 | 2010-11-04 18:40 | MooringSystemInstallation | 307 | 307 | 1
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 7385.0719 | 2010-11-04 17:04 | 2010-11-04 23:16 | MooredSubInstallation | 307 | 307 | 1
Towing Group 2 | Queue | 3 | 3750 | 7388.0719 | 2010-11-04 20:04 | 2010-11-05 02:04 | MooredSubInstallation | 307 | 308 | 2
Multi-Purpose Support Vessel | Delay | 0 | 0 | 7388.0719 | 2010-11-04 20:04 | 2010-11-08 16:04 | MooredSubInstallation | 307 | 311 | 5
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 7388.0719 | 2010-11-04 20:04 | 2010-11-04 23:04 | MooredSubInstallation | 307 | 307 | 1
Towing Group 1 | Positioning Support | 92 | 115000 | 7388.0719 | 2010-11-04 20:04 | 2010-11-04 20:04 | MooredSubInstallation | 307 | 307 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 7388.6697 | 2010-11-04 20:40 | 2010-11-05 00:40 | MooringSystemInstallation | 307 | 308 | 2
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 7390.0719 | 2010-11-04 22:04 | 2010-11-05 00:04 | MooredSubInstallation | 307 | 308 | 2
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 7395.2967 | 2010-11-05 03:18 | 2010-11-05 10:31 | MooredSubInstallation | 308 | 308 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 7396.0719 | 2010-11-05 04:04 | 2010-11-05 10:04 | MooredSubInstallation | 308 | 308 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7404.8297 | 2010-11-05 12:50 | 2010-11-06 04:59 | MooringSystemInstallation | 308 | 309 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7408.9897 | 2010-11-05 16:59 | 2010-11-05 21:09 | MooringSystemInstallation | 308 | 308 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 54166.6667 | 7409.0719 | 2010-11-05 17:04 | 2010-11-06 06:04 | MooredSubInstallation | 308 | 309 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 7410.9897 | 2010-11-05 18:59 | 2010-11-05 20:59 | MooringSystemInstallation | 308 | 308 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 7414.9897 | 2010-11-05 22:59 | 2010-11-06 02:59 | MooringSystemInstallation | 308 | 309 | 2
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 7418.3791 | 2010-11-06 02:23 | 2010-11-13 02:23 | MooredSubInstallation | 309 | 316 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 66.5 | 0 | 7418.3791 | 2010-11-06 02:23 | 2010-11-08 20:53 | MooredSubInstallation | 309 | 311 | 3
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 7426.3791 | 2010-11-06 10:23 | 2010-11-06 18:23 | MooredSubInstallation | 309 | 309 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7431.1497 | 2010-11-06 15:09 | 2010-11-07 07:19 | MooringSystemInstallation | 309 | 310 | 2
Multi-Purpose Support Vessel | Delay | 23 | 95833.3333 | 7432.0719 | 2010-11-06 16:04 | 2010-11-07 15:04 | MooredSubInstallation | 309 | 310 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7435.3097 | 2010-11-06 19:19 | 2010-11-06 23:28 | MooringSystemInstallation | 309 | 309 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 7437.3097 | 2010-11-06 21:19 | 2010-11-06 23:19 | MooringSystemInstallation | 309 | 309 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 7438.3791 | 2010-11-06 22:23 | 2010-11-07 10:23 | MooredSubInstallation | 309 | 310 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 29166.6667 | 7439.0719 | 2010-11-06 23:04 | 2010-11-07 06:04 | MooredSubInstallation | 309 | 310 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 2 | 8333.3333 | 7441.0719 | 2010-11-07 01:04 | 2010-11-07 03:04 | MooredSubInstallation | 310 | 310 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 7441.3097 | 2010-11-07 01:19 | 2010-11-07 05:19 | MooringSystemInstallation | 310 | 310 | 1
Turbine Assembly Line 1 | Delay | 8 | 0 | 7446.3791 | 2010-11-07 06:23 | 2010-11-07 14:23 | MooredSubInstallation | 310 | 310 | 1
Multi-Purpose Support Vessel | Delay | 8 | 33333.3333 | 7449.0719 | 2010-11-07 09:04 | 2010-11-07 17:04 | MooredSubInstallation | 310 | 310 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 4 | 16666.6667 | 7453.0719 | 2010-11-07 13:04 | 2010-11-07 17:04 | MooredSubInstallation | 310 | 310 | 1
Towing Group 2 | Positioning Support | 65 | 81250 | 7453.0719 | 2010-11-07 13:04 | 2010-11-10 06:04 | MooredSubInstallation | 310 | 313 | 4
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7457.4697 | 2010-11-07 17:28 | 2010-11-08 09:38 | MooringSystemInstallation | 310 | 311 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 7458.3791 | 2010-11-07 18:23 | 2010-11-08 06:23 | MooredSubInstallation | 310 | 311 | 2
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 7460.2967 | 2010-11-07 20:18 | 2010-11-08 03:31 | MooredSubInstallation | 310 | 311 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7461.6297 | 2010-11-07 21:38 | 2010-11-08 01:47 | MooringSystemInstallation | 310 | 311 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 7463.6297 | 2010-11-07 23:38 | 2010-11-08 01:38 | MooringSystemInstallation | 310 | 311 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 7467.6297 | 2010-11-08 03:38 | 2010-11-08 07:38 | MooringSystemInstallation | 311 | 311 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 7470.3791 | 2010-11-08 06:23 | 2010-11-08 18:23 | MooredSubInstallation | 311 | 311 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 7477.3791 | 2010-11-08 13:23 | 2010-11-08 20:23 | MooredSubInstallation | 311 | 311 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7480.8791 | 2010-11-08 16:53 | 2010-11-08 20:23 | MooredSubInstallation | 311 | 311 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7483.7897 | 2010-11-08 19:47 | 2010-11-09 11:57 | MooringSystemInstallation | 311 | 312 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7484.3791 | 2010-11-08 20:23 | 2010-11-08 23:53 | MooredSubInstallation | 311 | 311 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7487.8791 | 2010-11-08 23:53 | 2010-11-09 03:23 | MooredSubInstallation | 311 | 312 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7487.9497 | 2010-11-08 23:57 | 2010-11-09 04:07 | MooringSystemInstallation | 311 | 312 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 7489.9497 | 2010-11-09 01:57 | 2010-11-09 03:57 | MooringSystemInstallation | 312 | 312 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 7493.9497 | 2010-11-09 05:57 | 2010-11-09 09:57 | MooringSystemInstallation | 312 | 312 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 7511.8791 | 2010-11-09 23:53 | 2010-11-10 23:53 | MooredSubInstallation | 312 | 313 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 208.5825 | 260728.0655 | 7511.8791 | 2010-11-09 23:53 | 2010-11-18 16:28 | MooredSubInstallation | 312 | 321 | 10
Mooring System Installation Vessel | Delay | 61 | 254166.6667 | 7554.9497 | 2010-11-11 18:57 | 2010-11-14 07:57 | MooringSystemInstallation | 314 | 317 | 4
Towing Group 3 | Delay | 47 | 117500 | 7558.8791 | 2010-11-11 22:53 | 2010-11-13 21:53 | MooredSubInstallation | 314 | 316 | 3
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 7564.8791 | 2010-11-12 04:53 | 2010-11-12 10:53 | MooredSubInstallation | 315 | 315 | 1
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 7571.0719 | 2010-11-12 11:04 | 2010-11-12 17:16 | MooredSubInstallation | 315 | 315 | 1
Multi-Purpose Support Vessel | Delay | 118 | 491666.6667 | 7571.0719 | 2010-11-12 11:04 | 2010-11-17 09:04 | MooredSubInstallation | 315 | 320 | 6
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7571.1097 | 2010-11-12 11:07 | 2010-11-13 03:16 | MooringSystemInstallation | 315 | 316 | 2
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 7573.0719 | 2010-11-12 13:04 | 2010-11-12 15:04 | MooredSubInstallation | 315 | 315 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7575.2697 | 2010-11-12 15:16 | 2010-11-12 19:26 | MooringSystemInstallation | 315 | 315 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 7577.2697 | 2010-11-12 17:16 | 2010-11-12 19:16 | MooringSystemInstallation | 315 | 315 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 7581.2697 | 2010-11-12 21:16 | 2010-11-13 01:16 | MooringSystemInstallation | 315 | 316 | 2
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 74.5 | 0 | 7586.3791 | 2010-11-13 02:23 | 2010-11-20 02:23 | MooredSubInstallation | 316 | 323 | 8
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 7586.3791 | 2010-11-13 02:23 | 2010-11-16 04:53 | MooredSubInstallation | 316 | 319 | 4
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 7594.3791 | 2010-11-13 10:23 | 2010-11-13 18:23 | MooredSubInstallation | 316 | 316 | 1
Mooring System Installation Vessel | Delay | 24 | 100000 | 7605.2697 | 2010-11-13 21:16 | 2010-11-14 21:16 | MooringSystemInstallation | 316 | 317 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 7606.3791 | 2010-11-13 22:23 | 2010-11-14 10:23 | MooredSubInstallation | 316 | 317 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7621.4297 | 2010-11-14 13:26 | 2010-11-15 05:35 | MooringSystemInstallation | 317 | 318 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7625.5897 | 2010-11-14 17:35 | 2010-11-14 21:45 | MooringSystemInstallation | 317 | 317 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 7629.9246 | 2010-11-14 21:55 | 2010-11-15 02:16 | MooringSystemInstallation | 317 | 318 | 2
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 7634.9246 | 2010-11-15 02:55 | 2010-11-15 07:55 | MooringSystemInstallation | 318 | 318 | 1
Mooring System Installation Vessel | Delay | 18 | 75000 | 7652.9246 | 2010-11-15 20:55 | 2010-11-16 14:55 | MooringSystemInstallation | 318 | 319 | 2
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 7657.9246 | 2010-11-16 01:55 | 2010-11-16 06:55 | MooringSystemInstallation | 319 | 319 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 7662.2595 | 2010-11-16 06:16 | 2010-11-16 10:36 | MooringSystemInstallation | 319 | 319 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 7664.2595 | 2010-11-16 08:16 | 2010-11-16 10:16 | MooringSystemInstallation | 319 | 319 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 7668.2595 | 2010-11-16 12:16 | 2010-11-16 16:16 | MooringSystemInstallation | 319 | 319 | 1
Turbine Assembly Line 1 | Delay | 71 | 0 | 7677.3791 | 2010-11-16 21:23 | 2010-11-19 20:23 | MooredSubInstallation | 319 | 322 | 4
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 7689.3791 | 2010-11-17 09:23 | 2010-11-17 21:23 | MooredSubInstallation | 320 | 320 | 1
Mooring System Installation Vessel | Delay | 25 | 104166.6667 | 7693.2595 | 2010-11-17 13:16 | 2010-11-18 14:16 | MooringSystemInstallation | 320 | 321 | 2
Multi-Purpose Support Vessel | Delay | 128 | 533333.3333 | 7701.0719 | 2010-11-17 21:04 | 2010-11-23 05:04 | MooredSubInstallation | 320 | 326 | 7
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 7701.3791 | 2010-11-17 21:23 | 2010-11-18 09:23 | MooredSubInstallation | 320 | 321 | 2
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 7707.0719 | 2010-11-18 03:04 | 2010-11-18 09:04 | MooredSubInstallation | 321 | 321 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 7708.3791 | 2010-11-18 04:23 | 2010-11-18 11:23 | MooredSubInstallation | 321 | 321 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7709.4195 | 2010-11-18 05:25 | 2010-11-18 21:35 | MooringSystemInstallation | 321 | 321 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7711.8791 | 2010-11-18 07:53 | 2010-11-18 11:23 | MooredSubInstallation | 321 | 321 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7713.5795 | 2010-11-18 09:35 | 2010-11-18 13:44 | MooringSystemInstallation | 321 | 321 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 29166.6667 | 7714.0719 | 2010-11-18 10:04 | 2010-11-18 17:04 | MooredSubInstallation | 321 | 321 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7715.3791 | 2010-11-18 11:23 | 2010-11-18 14:53 | MooredSubInstallation | 321 | 321 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 7715.5795 | 2010-11-18 11:35 | 2010-11-18 13:35 | MooringSystemInstallation | 321 | 321 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7718.8791 | 2010-11-18 14:53 | 2010-11-18 18:23 | MooredSubInstallation | 321 | 321 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 7719.5795 | 2010-11-18 15:35 | 2010-11-18 19:35 | MooringSystemInstallation | 321 | 321 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 7742.8791 | 2010-11-19 14:53 | 2010-11-20 14:53 | MooredSubInstallation | 322 | 323 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 347.5825 | 434478.0655 | 7742.8791 | 2010-11-19 14:53 | 2010-12-04 02:28 | MooredSubInstallation | 322 | 337 | 16
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 7754.3791 | 2010-11-20 02:23 | 2010-11-27 02:23 | MooredSubInstallation | 323 | 330 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 11.5 | 0 | 7754.3791 | 2010-11-20 02:23 | 2010-11-20 13:53 | MooredSubInstallation | 323 | 323 | 1
Mooring System Installation Vessel | Delay | 41 | 170833.3333 | 7760.5795 | 2010-11-20 08:35 | 2010-11-22 01:35 | MooringSystemInstallation | 323 | 325 | 3
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 7762.3791 | 2010-11-20 10:23 | 2010-11-20 18:23 | MooredSubInstallation | 323 | 323 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 7774.3791 | 2010-11-20 22:23 | 2010-11-21 10:23 | MooredSubInstallation | 323 | 324 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7776.7395 | 2010-11-21 00:44 | 2010-11-21 16:54 | MooringSystemInstallation | 324 | 324 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 7786.3791 | 2010-11-21 10:23 | 2010-11-21 22:23 | MooredSubInstallation | 324 | 324 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 7798.3791 | 2010-11-21 22:23 | 2010-11-22 10:23 | MooredSubInstallation | 324 | 325 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 7805.3791 | 2010-11-22 05:23 | 2010-11-22 12:23 | MooredSubInstallation | 325 | 325 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7808.8791 | 2010-11-22 08:53 | 2010-11-22 12:23 | MooredSubInstallation | 325 | 325 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7812.3791 | 2010-11-22 12:23 | 2010-11-22 15:53 | MooredSubInstallation | 325 | 325 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7815.8791 | 2010-11-22 15:53 | 2010-11-22 19:23 | MooredSubInstallation | 325 | 325 | 1
Mooring System Installation Vessel | Delay | 44 | 183333.3333 | 7820.7395 | 2010-11-22 20:44 | 2010-11-24 16:44 | MooringSystemInstallation | 325 | 327 | 3
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7824.8995 | 2010-11-23 00:54 | 2010-11-23 05:04 | MooringSystemInstallation | 326 | 326 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 7826.8995 | 2010-11-23 02:54 | 2010-11-23 04:54 | MooringSystemInstallation | 326 | 326 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 7830.8995 | 2010-11-23 06:54 | 2010-11-23 10:54 | MooringSystemInstallation | 326 | 326 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 7839.8791 | 2010-11-23 15:53 | 2010-11-24 15:53 | MooredSubInstallation | 326 | 327 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 379.5825 | 474478.0655 | 7839.8791 | 2010-11-23 15:53 | 2010-12-09 11:28 | MooredSubInstallation | 326 | 342 | 17
Mooring System Installation Vessel | Delay | 28 | 116666.6667 | 7858.8995 | 2010-11-24 10:54 | 2010-11-25 14:54 | MooringSystemInstallation | 327 | 328 | 2
Towing Group 1 | Delay | 120 | 300000 | 7862.8791 | 2010-11-24 14:53 | 2010-11-29 14:53 | MooredSubInstallation | 327 | 332 | 6
Towing Group 2 | Delay | 23 | 57500 | 7862.8791 | 2010-11-24 14:53 | 2010-11-25 13:53 | MooredSubInstallation | 327 | 328 | 2
Multi-Purpose Support Vessel | Delay | 149 | 620833.3333 | 7863.0719 | 2010-11-24 15:04 | 2010-11-30 20:04 | MooredSubInstallation | 327 | 333 | 7
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 7868.8791 | 2010-11-24 20:53 | 2010-11-25 02:53 | MooredSubInstallation | 327 | 328 | 2
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 7868.8791 | 2010-11-24 20:53 | 2010-11-25 02:53 | MooredSubInstallation | 327 | 328 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7875.0595 | 2010-11-25 03:04 | 2010-11-25 19:13 | MooringSystemInstallation | 328 | 328 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 7875.0719 | 2010-11-25 03:04 | 2010-11-25 09:16 | MooredSubInstallation | 328 | 328 | 1
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 7875.0719 | 2010-11-25 03:04 | 2010-11-25 09:16 | MooredSubInstallation | 328 | 328 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 54166.6667 | 7876.0719 | 2010-11-25 04:04 | 2010-11-25 17:04 | MooredSubInstallation | 328 | 328 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7879.2195 | 2010-11-25 07:13 | 2010-11-25 11:23 | MooringSystemInstallation | 328 | 328 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 7881.2195 | 2010-11-25 09:13 | 2010-11-25 11:13 | MooringSystemInstallation | 328 | 328 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 7882.0719 | 2010-11-25 10:04 | 2010-11-25 16:04 | MooredSubInstallation | 328 | 328 | 1
Towing Group 3 | Positioning Support | 311 | 388750 | 7882.0719 | 2010-11-25 10:04 | 2010-12-08 09:04 | MooredSubInstallation | 328 | 341 | 14
Towing Group 1 | Queue | 7 | 8750 | 7882.0719 | 2010-11-25 10:04 | 2010-11-25 17:04 | MooredSubInstallation | 328 | 328 | 1
Multi-Purpose Support Vessel | Delay | 0 | 0 | 7882.0719 | 2010-11-25 10:04 | 2010-11-25 10:04 | MooredSubInstallation | 328 | 328 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 7884.0719 | 2010-11-25 12:04 | 2010-11-25 14:04 | MooredSubInstallation | 328 | 328 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 7885.2195 | 2010-11-25 13:13 | 2010-11-25 17:13 | MooringSystemInstallation | 328 | 328 | 1
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 7889.2967 | 2010-11-25 17:18 | 2010-11-26 00:31 | MooredSubInstallation | 328 | 329 | 2
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 7890.0719 | 2010-11-25 18:04 | 2010-11-26 00:04 | MooredSubInstallation | 328 | 329 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7901.3795 | 2010-11-26 05:23 | 2010-11-26 21:32 | MooringSystemInstallation | 329 | 329 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7905.5395 | 2010-11-26 09:32 | 2010-11-26 13:42 | MooringSystemInstallation | 329 | 329 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 7907.5395 | 2010-11-26 11:32 | 2010-11-26 13:32 | MooringSystemInstallation | 329 | 329 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 7910.0719 | 2010-11-26 14:04 | 2010-11-27 10:04 | MooredSubInstallation | 329 | 330 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 7911.5395 | 2010-11-26 15:32 | 2010-11-26 19:32 | MooringSystemInstallation | 329 | 329 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 7916.0719 | 2010-11-26 20:04 | 2010-11-27 02:04 | MooredSubInstallation | 329 | 330 | 2
Towing Group 1 | Positioning Support | 34 | 42500 | 7916.0719 | 2010-11-26 20:04 | 2010-11-28 06:04 | MooredSubInstallation | 329 | 331 | 3
Towing Group 2 | Queue | 41 | 51250 | 7916.0719 | 2010-11-26 20:04 | 2010-11-28 13:04 | MooredSubInstallation | 329 | 331 | 3
Multi-Purpose Support Vessel | Delay | 0 | 0 | 7916.0719 | 2010-11-26 20:04 | 2010-11-26 20:04 | MooredSubInstallation | 329 | 329 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 7918.0719 | 2010-11-26 22:04 | 2010-11-27 00:04 | MooredSubInstallation | 329 | 330 | 2
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 7922.3791 | 2010-11-27 02:23 | 2010-12-04 02:23 | MooredSubInstallation | 330 | 337 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 7922.3791 | 2010-11-27 02:23 | 2010-11-30 12:53 | MooredSubInstallation | 330 | 333 | 4
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 7923.2967 | 2010-11-27 03:18 | 2010-11-27 10:31 | MooredSubInstallation | 330 | 330 | 1
Multi-Purpose Support Vessel | Delay | 8 | 33333.3333 | 7926.0719 | 2010-11-27 06:04 | 2010-11-27 14:04 | MooredSubInstallation | 330 | 330 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7927.6995 | 2010-11-27 07:42 | 2010-11-27 23:52 | MooringSystemInstallation | 330 | 330 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 7930.3791 | 2010-11-27 10:23 | 2010-11-27 18:23 | MooredSubInstallation | 330 | 330 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7931.8595 | 2010-11-27 11:52 | 2010-11-27 16:01 | MooringSystemInstallation | 330 | 330 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 7932.0719 | 2010-11-27 12:04 | 2010-11-27 18:04 | MooredSubInstallation | 330 | 330 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 7933.8595 | 2010-11-27 13:52 | 2010-11-27 15:52 | MooringSystemInstallation | 330 | 330 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 8333.3333 | 7934.0719 | 2010-11-27 14:04 | 2010-11-27 16:04 | MooredSubInstallation | 330 | 330 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 7937.8595 | 2010-11-27 17:52 | 2010-11-27 21:52 | MooringSystemInstallation | 330 | 330 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 7942.3791 | 2010-11-27 22:23 | 2010-11-28 10:23 | MooredSubInstallation | 330 | 331 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 7954.3791 | 2010-11-28 10:23 | 2010-11-28 22:23 | MooredSubInstallation | 331 | 331 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 7966.3791 | 2010-11-28 22:23 | 2010-11-29 10:23 | MooredSubInstallation | 331 | 332 | 2
Mooring System Installation Vessel | Delay | 30 | 125000 | 7967.8595 | 2010-11-28 23:52 | 2010-11-30 05:52 | MooringSystemInstallation | 331 | 333 | 3
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 7973.3791 | 2010-11-29 05:23 | 2010-11-29 12:23 | MooredSubInstallation | 332 | 332 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7976.8791 | 2010-11-29 08:53 | 2010-11-29 12:23 | MooredSubInstallation | 332 | 332 | 1
Multi-Purpose Support Vessel | Delay | 43 | 179166.6667 | 7977.0719 | 2010-11-29 09:04 | 2010-12-01 04:04 | MooredSubInstallation | 332 | 334 | 3
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7980.3791 | 2010-11-29 12:23 | 2010-11-29 15:53 | MooredSubInstallation | 332 | 332 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 7983.8791 | 2010-11-29 15:53 | 2010-11-29 19:23 | MooredSubInstallation | 332 | 332 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 7984.0195 | 2010-11-29 16:01 | 2010-11-30 08:11 | MooringSystemInstallation | 332 | 333 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 7988.1795 | 2010-11-29 20:11 | 2010-11-30 00:20 | MooringSystemInstallation | 332 | 333 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 7992.5144 | 2010-11-30 00:31 | 2010-11-30 04:51 | MooringSystemInstallation | 333 | 333 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 75000 | 7995.0719 | 2010-11-30 03:04 | 2010-11-30 21:04 | MooredSubInstallation | 333 | 333 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 7997.5144 | 2010-11-30 05:31 | 2010-11-30 10:31 | MooringSystemInstallation | 333 | 333 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 8001.0719 | 2010-11-30 09:04 | 2010-11-30 15:04 | MooredSubInstallation | 333 | 333 | 1
Towing Group 2 | Positioning Support | 85 | 106250 | 8001.0719 | 2010-11-30 09:04 | 2010-12-03 22:04 | MooredSubInstallation | 333 | 336 | 4
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 8002.5144 | 2010-11-30 10:31 | 2010-11-30 15:31 | MooringSystemInstallation | 333 | 333 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 8006.8493 | 2010-11-30 14:51 | 2010-11-30 19:11 | MooringSystemInstallation | 333 | 333 | 1
Towing Group 3 | Delay: No Completed Assemblies Available | 118.5825 | 148228.0655 | 8007.8791 | 2010-11-30 15:53 | 2010-12-01 15:53 | MooredSubInstallation | 333 | 334 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 8007.8791 | 2010-11-30 15:53 | 2010-12-05 14:28 | MooredSubInstallation | 333 | 338 | 6
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 8008.2967 | 2010-11-30 16:18 | 2010-11-30 23:31 | MooredSubInstallation | 333 | 333 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 8008.8493 | 2010-11-30 16:51 | 2010-11-30 18:51 | MooringSystemInstallation | 333 | 333 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 8012.8493 | 2010-11-30 20:51 | 2010-12-01 00:51 | MooringSystemInstallation | 333 | 334 | 2
Mooring System Installation Vessel | Delay | 27 | 112500 | 8039.8493 | 2010-12-01 23:51 | 2010-12-03 02:51 | MooringSystemInstallation | 334 | 336 | 3
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 8056.0093 | 2010-12-02 16:01 | 2010-12-03 08:10 | MooringSystemInstallation | 335 | 336 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 8060.1693 | 2010-12-02 20:10 | 2010-12-03 00:20 | MooringSystemInstallation | 335 | 336 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 8062.1693 | 2010-12-02 22:10 | 2010-12-03 00:10 | MooringSystemInstallation | 335 | 336 | 2
Mooring System Installation Vessel | Delay | 2 | 8333.3333 | 8064.1693 | 2010-12-03 00:10 | 2010-12-03 02:10 | MooringSystemInstallation | 336 | 336 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 8068.1693 | 2010-12-03 04:10 | 2010-12-03 08:10 | MooringSystemInstallation | 336 | 336 | 1
Towing Group 3 | Delay | 71 | 177500 | 8078.8791 | 2010-12-03 14:53 | 2010-12-06 13:53 | MooredSubInstallation | 336 | 339 | 4
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 8084.3293 | 2010-12-03 20:20 | 2010-12-04 12:29 | MooringSystemInstallation | 336 | 337 | 2
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 8084.8791 | 2010-12-03 20:53 | 2010-12-04 02:53 | MooredSubInstallation | 336 | 337 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 8088.4893 | 2010-12-04 00:29 | 2010-12-04 04:39 | MooringSystemInstallation | 337 | 337 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 8090.3791 | 2010-12-04 02:23 | 2010-12-11 02:23 | MooredSubInstallation | 337 | 344 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 8090.3791 | 2010-12-04 02:23 | 2010-12-07 12:53 | MooredSubInstallation | 337 | 340 | 4
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 8090.4893 | 2010-12-04 02:29 | 2010-12-04 04:29 | MooringSystemInstallation | 337 | 337 | 1
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 8091.0719 | 2010-12-04 03:04 | 2010-12-04 09:16 | MooredSubInstallation | 337 | 337 | 1
Multi-Purpose Support Vessel | Delay | 90 | 375000 | 8091.0719 | 2010-12-04 03:04 | 2010-12-07 21:04 | MooredSubInstallation | 337 | 340 | 4
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 8093.0719 | 2010-12-04 05:04 | 2010-12-04 07:04 | MooredSubInstallation | 337 | 337 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 8094.4893 | 2010-12-04 06:29 | 2010-12-04 10:29 | MooringSystemInstallation | 337 | 337 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 8098.3791 | 2010-12-04 10:23 | 2010-12-04 18:23 | MooredSubInstallation | 337 | 337 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 8099.0719 | 2010-12-04 11:04 | 2010-12-04 17:04 | MooredSubInstallation | 337 | 337 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 29166.6667 | 8106.0719 | 2010-12-04 18:04 | 2010-12-05 01:04 | MooredSubInstallation | 337 | 338 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 8110.3791 | 2010-12-04 22:23 | 2010-12-05 10:23 | MooredSubInstallation | 337 | 338 | 2
Turbine Assembly Line 1 | Delay | 6 | 0 | 8116.3791 | 2010-12-05 04:23 | 2010-12-05 10:23 | MooredSubInstallation | 338 | 338 | 1
Mooring System Installation Vessel | Delay | 24 | 100000 | 8118.4893 | 2010-12-05 06:29 | 2010-12-06 06:29 | MooringSystemInstallation | 338 | 339 | 2
Multi-Purpose Support Vessel | Delay | 18 | 75000 | 8124.0719 | 2010-12-05 12:04 | 2010-12-06 06:04 | MooredSubInstallation | 338 | 339 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 8128.3791 | 2010-12-05 16:23 | 2010-12-06 04:23 | MooredSubInstallation | 338 | 339 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 8134.6493 | 2010-12-05 22:39 | 2010-12-06 14:49 | MooringSystemInstallation | 338 | 339 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 54166.6667 | 8137.0719 | 2010-12-06 01:04 | 2010-12-06 14:04 | MooredSubInstallation | 339 | 339 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 8138.8093 | 2010-12-06 02:49 | 2010-12-06 06:58 | MooringSystemInstallation | 339 | 339 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 3 | 12500 | 8140.0719 | 2010-12-06 04:04 | 2010-12-06 07:04 | MooredSubInstallation | 339 | 339 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 8140.3791 | 2010-12-06 04:23 | 2010-12-06 16:23 | MooredSubInstallation | 339 | 339 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 8140.8093 | 2010-12-06 04:49 | 2010-12-06 06:49 | MooringSystemInstallation | 339 | 339 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 8144.8093 | 2010-12-06 08:49 | 2010-12-06 12:49 | MooringSystemInstallation | 339 | 339 | 1
Turbine Assembly Line 1 | Delay | 6 | 0 | 8146.3791 | 2010-12-06 10:23 | 2010-12-06 16:23 | MooredSubInstallation | 339 | 339 | 1
Multi-Purpose Support Vessel | Delay | 9 | 37500 | 8149.0719 | 2010-12-06 13:04 | 2010-12-06 22:04 | MooredSubInstallation | 339 | 339 | 1
Towing Group 3 | Positioning Support | 61 | 76250 | 8152.0719 | 2010-12-06 16:04 | 2010-12-06 19:04 | MooredSubInstallation | 339 | 339 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 3 | 12500 | 8152.0719 | 2010-12-06 16:04 | 2010-12-09 05:04 | MooredSubInstallation | 339 | 342 | 4
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 8153.3791 | 2010-12-06 17:23 | 2010-12-07 00:23 | MooredSubInstallation | 339 | 340 | 2
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 8159.2967 | 2010-12-06 23:18 | 2010-12-07 06:31 | MooredSubInstallation | 339 | 340 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 8160.9693 | 2010-12-07 00:58 | 2010-12-07 17:08 | MooringSystemInstallation | 340 | 340 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 8165.1293 | 2010-12-07 05:08 | 2010-12-07 09:17 | MooringSystemInstallation | 340 | 340 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 8167.1293 | 2010-12-07 07:08 | 2010-12-07 09:08 | MooringSystemInstallation | 340 | 340 | 1
Turbine Assembly Line 1 | Delay | 42 | 0 | 8195.3791 | 2010-12-08 11:23 | 2010-12-10 05:23 | MooredSubInstallation | 341 | 343 | 3
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8198.8791 | 2010-12-08 14:53 | 2010-12-08 18:23 | MooredSubInstallation | 341 | 341 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8202.3791 | 2010-12-08 18:23 | 2010-12-08 21:53 | MooredSubInstallation | 341 | 341 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8205.8791 | 2010-12-08 21:53 | 2010-12-09 01:23 | MooredSubInstallation | 341 | 342 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 8229.8791 | 2010-12-09 21:53 | 2010-12-10 21:53 | MooredSubInstallation | 342 | 343 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 306.5825 | 383228.0655 | 8229.8791 | 2010-12-09 21:53 | 2010-12-22 16:28 | MooredSubInstallation | 342 | 355 | 14
Mooring System Installation Vessel | Delay | 68 | 283333.3333 | 8235.1293 | 2010-12-10 03:08 | 2010-12-12 23:08 | MooringSystemInstallation | 343 | 345 | 3
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 8239.1293 | 2010-12-10 07:08 | 2010-12-10 11:08 | MooringSystemInstallation | 343 | 343 | 1
Towing Group 1 | Delay | 11 | 27500 | 8240.8791 | 2010-12-10 08:53 | 2010-12-10 19:53 | MooredSubInstallation | 343 | 343 | 1
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 8246.8791 | 2010-12-10 14:53 | 2010-12-10 20:53 | MooredSubInstallation | 343 | 343 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 8253.0719 | 2010-12-10 21:04 | 2010-12-11 03:16 | MooredSubInstallation | 343 | 344 | 2
Multi-Purpose Support Vessel | Delay | 101 | 420833.3333 | 8253.0719 | 2010-12-10 21:04 | 2010-12-15 02:04 | MooredSubInstallation | 343 | 348 | 6
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 8255.0719 | 2010-12-10 23:04 | 2010-12-11 01:04 | MooredSubInstallation | 343 | 344 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 8255.2893 | 2010-12-10 23:17 | 2010-12-11 15:27 | MooringSystemInstallation | 343 | 344 | 2
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 8258.3791 | 2010-12-11 02:23 | 2010-12-18 02:23 | MooredSubInstallation | 344 | 351 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 28.5 | 0 | 8258.3791 | 2010-12-11 02:23 | 2010-12-12 06:53 | MooredSubInstallation | 344 | 345 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 8259.4493 | 2010-12-11 03:27 | 2010-12-11 07:37 | MooringSystemInstallation | 344 | 344 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 8261.0719 | 2010-12-11 05:04 | 2010-12-11 11:04 | MooredSubInstallation | 344 | 344 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 8261.4493 | 2010-12-11 05:27 | 2010-12-11 07:27 | MooringSystemInstallation | 344 | 344 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 8265.4493 | 2010-12-11 09:27 | 2010-12-11 13:27 | MooringSystemInstallation | 344 | 344 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 8266.3791 | 2010-12-11 10:23 | 2010-12-11 18:23 | MooredSubInstallation | 344 | 344 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 8278.3791 | 2010-12-11 22:23 | 2010-12-12 10:23 | MooredSubInstallation | 344 | 345 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 8281.0719 | 2010-12-12 01:04 | 2010-12-12 21:04 | MooredSubInstallation | 345 | 345 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 8281.6093 | 2010-12-12 01:37 | 2010-12-12 17:46 | MooringSystemInstallation | 345 | 345 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 8285.7693 | 2010-12-12 05:46 | 2010-12-12 09:56 | MooringSystemInstallation | 345 | 345 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 8287.0719 | 2010-12-12 07:04 | 2010-12-12 13:04 | MooredSubInstallation | 345 | 345 | 1
Towing Group 1 | Positioning Support | 34 | 42500 | 8287.0719 | 2010-12-12 07:04 | 2010-12-13 17:04 | MooredSubInstallation | 345 | 346 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 8290.1042 | 2010-12-12 10:06 | 2010-12-12 14:26 | MooringSystemInstallation | 345 | 345 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 8290.3791 | 2010-12-12 10:23 | 2010-12-12 22:23 | MooredSubInstallation | 345 | 345 | 1
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 8294.2967 | 2010-12-12 14:18 | 2010-12-12 21:31 | MooredSubInstallation | 345 | 345 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 8295.1042 | 2010-12-12 15:06 | 2010-12-12 20:06 | MooringSystemInstallation | 345 | 345 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 8300.1042 | 2010-12-12 20:06 | 2010-12-13 01:06 | MooringSystemInstallation | 345 | 346 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 8302.3791 | 2010-12-12 22:23 | 2010-12-13 10:23 | MooredSubInstallation | 345 | 346 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 8304.4391 | 2010-12-13 00:26 | 2010-12-13 04:46 | MooringSystemInstallation | 346 | 346 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 8306.4391 | 2010-12-13 02:26 | 2010-12-13 04:26 | MooringSystemInstallation | 346 | 346 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 8309.3791 | 2010-12-13 05:23 | 2010-12-13 12:23 | MooredSubInstallation | 346 | 346 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 8310.4391 | 2010-12-13 06:26 | 2010-12-13 10:26 | MooringSystemInstallation | 346 | 346 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8312.8791 | 2010-12-13 08:53 | 2010-12-13 12:23 | MooredSubInstallation | 346 | 346 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8316.3791 | 2010-12-13 12:23 | 2010-12-13 15:53 | MooredSubInstallation | 346 | 346 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8319.8791 | 2010-12-13 15:53 | 2010-12-13 19:23 | MooredSubInstallation | 346 | 346 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 8326.5991 | 2010-12-13 22:36 | 2010-12-14 14:46 | MooringSystemInstallation | 346 | 347 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 8330.7591 | 2010-12-14 02:46 | 2010-12-14 06:55 | MooringSystemInstallation | 347 | 347 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 8332.7591 | 2010-12-14 04:46 | 2010-12-14 06:46 | MooringSystemInstallation | 347 | 347 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 8336.7591 | 2010-12-14 08:46 | 2010-12-14 12:46 | MooringSystemInstallation | 347 | 347 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 8343.8791 | 2010-12-14 15:53 | 2010-12-15 15:53 | MooredSubInstallation | 347 | 348 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 335.5825 | 419478.0655 | 8343.8791 | 2010-12-14 15:53 | 2010-12-28 15:28 | MooredSubInstallation | 347 | 361 | 15
Mooring System Installation Vessel | Delay | 35 | 145833.3333 | 8371.7591 | 2010-12-15 19:46 | 2010-12-17 06:46 | MooringSystemInstallation | 348 | 350 | 3
Towing Group 2 | Delay | 42 | 105000 | 8385.8791 | 2010-12-16 09:53 | 2010-12-18 03:53 | MooredSubInstallation | 349 | 351 | 3
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 8387.9191 | 2010-12-16 11:55 | 2010-12-17 04:05 | MooringSystemInstallation | 349 | 350 | 2
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 8391.8791 | 2010-12-16 15:53 | 2010-12-16 21:53 | MooredSubInstallation | 349 | 349 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 8392.0791 | 2010-12-16 16:05 | 2010-12-16 20:14 | MooringSystemInstallation | 349 | 349 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 8394.0791 | 2010-12-16 18:05 | 2010-12-16 20:05 | MooringSystemInstallation | 349 | 349 | 1
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 8398.0719 | 2010-12-16 22:04 | 2010-12-17 04:16 | MooredSubInstallation | 349 | 350 | 2
Multi-Purpose Support Vessel | Delay | 111 | 462500 | 8398.0719 | 2010-12-16 22:04 | 2010-12-21 13:04 | MooredSubInstallation | 349 | 354 | 6
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 8398.0791 | 2010-12-16 22:05 | 2010-12-17 02:05 | MooringSystemInstallation | 349 | 350 | 2
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 8400.0719 | 2010-12-17 00:04 | 2010-12-17 02:04 | MooredSubInstallation | 350 | 350 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 8406.0719 | 2010-12-17 06:04 | 2010-12-17 12:04 | MooredSubInstallation | 350 | 350 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 8414.2391 | 2010-12-17 14:14 | 2010-12-18 06:24 | MooringSystemInstallation | 350 | 351 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 50000 | 8418.0719 | 2010-12-17 18:04 | 2010-12-18 06:04 | MooredSubInstallation | 350 | 351 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 8418.3991 | 2010-12-17 18:24 | 2010-12-17 22:34 | MooringSystemInstallation | 350 | 350 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 8420.3991 | 2010-12-17 20:24 | 2010-12-17 22:24 | MooringSystemInstallation | 350 | 350 | 1
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 8426.3791 | 2010-12-18 02:23 | 2010-12-25 02:23 | MooredSubInstallation | 351 | 358 | 8
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 8426.3791 | 2010-12-18 02:23 | 2010-12-21 12:53 | MooredSubInstallation | 351 | 354 | 4
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 8434.3791 | 2010-12-18 10:23 | 2010-12-18 18:23 | MooredSubInstallation | 351 | 351 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 8446.3791 | 2010-12-18 22:23 | 2010-12-19 10:23 | MooredSubInstallation | 351 | 352 | 2
Mooring System Installation Vessel | Delay | 31 | 129166.6667 | 8451.3991 | 2010-12-19 03:24 | 2010-12-20 10:24 | MooringSystemInstallation | 352 | 353 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 8455.3991 | 2010-12-19 07:24 | 2010-12-19 11:24 | MooringSystemInstallation | 352 | 352 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 8458.3791 | 2010-12-19 10:23 | 2010-12-19 22:23 | MooredSubInstallation | 352 | 352 | 1
Turbine Assembly Line 1 | Delay | 21 | 0 | 8479.3791 | 2010-12-20 07:23 | 2010-12-21 04:23 | MooredSubInstallation | 353 | 354 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 8491.3791 | 2010-12-20 19:23 | 2010-12-21 07:23 | MooredSubInstallation | 353 | 354 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 8498.3791 | 2010-12-21 02:23 | 2010-12-21 09:23 | MooredSubInstallation | 354 | 354 | 1
Turbine Assembly Line 1 | Delay | 21 | 0 | 8519.3791 | 2010-12-21 23:23 | 2010-12-22 20:23 | MooredSubInstallation | 354 | 355 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8522.8791 | 2010-12-22 02:53 | 2010-12-22 06:23 | MooredSubInstallation | 355 | 355 | 1
Mooring System Installation Vessel | Delay | 68 | 283333.3333 | 8523.3991 | 2010-12-22 03:24 | 2010-12-24 23:24 | MooringSystemInstallation | 355 | 357 | 3
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8526.3791 | 2010-12-22 06:23 | 2010-12-22 09:53 | MooredSubInstallation | 355 | 355 | 1
Multi-Purpose Support Vessel | Delay | 110 | 458333.3333 | 8528.0719 | 2010-12-22 08:04 | 2010-12-26 22:04 | MooredSubInstallation | 355 | 359 | 5
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8529.8791 | 2010-12-22 09:53 | 2010-12-22 13:23 | MooredSubInstallation | 355 | 355 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 33333.3333 | 8536.0719 | 2010-12-22 16:04 | 2010-12-23 00:04 | MooredSubInstallation | 355 | 356 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 8539.5591 | 2010-12-22 19:34 | 2010-12-23 11:43 | MooringSystemInstallation | 355 | 356 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 8542.0719 | 2010-12-22 22:04 | 2010-12-23 04:04 | MooredSubInstallation | 355 | 356 | 2
Towing Group 2 | Positioning Support | 144 | 180000 | 8542.0719 | 2010-12-22 22:04 | 2010-12-28 22:04 | MooredSubInstallation | 355 | 361 | 7
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 8543.7191 | 2010-12-22 23:43 | 2010-12-23 03:53 | MooringSystemInstallation | 355 | 356 | 2
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 8545.7191 | 2010-12-23 01:43 | 2010-12-23 03:43 | MooringSystemInstallation | 356 | 356 | 1
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 8549.2967 | 2010-12-23 05:18 | 2010-12-23 12:31 | MooredSubInstallation | 356 | 356 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 8549.7191 | 2010-12-23 05:43 | 2010-12-23 09:43 | MooringSystemInstallation | 356 | 356 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 8553.8791 | 2010-12-23 09:53 | 2010-12-24 09:53 | MooredSubInstallation | 356 | 357 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 394.5825 | 493228.0655 | 8553.8791 | 2010-12-23 09:53 | 2011-01-08 20:28 | MooredSubInstallation | 356 | 372 | 17
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 8559.8791 | 2010-12-23 15:53 | 2010-12-23 21:53 | MooredSubInstallation | 356 | 356 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 8565.8791 | 2010-12-23 21:53 | 2010-12-24 14:02 | MooringSystemInstallation | 356 | 357 | 2
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 8594.3791 | 2010-12-25 02:23 | 2011-01-01 02:23 | MooredSubInstallation | 358 | 365 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 40.5 | 0 | 8594.3791 | 2010-12-25 02:23 | 2010-12-26 18:53 | MooredSubInstallation | 358 | 359 | 2
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 8602.3791 | 2010-12-25 10:23 | 2010-12-25 18:23 | MooredSubInstallation | 358 | 358 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 8614.3791 | 2010-12-25 22:23 | 2010-12-26 10:23 | MooredSubInstallation | 358 | 359 | 2
Turbine Assembly Line 1 | Delay | 16 | 0 | 8630.3791 | 2010-12-26 14:23 | 2010-12-27 06:23 | MooredSubInstallation | 359 | 360 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 8642.3791 | 2010-12-27 02:23 | 2010-12-27 14:23 | MooredSubInstallation | 360 | 360 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 8654.3791 | 2010-12-27 14:23 | 2010-12-28 02:23 | MooredSubInstallation | 360 | 361 | 2
Mooring System Installation Vessel | Delay | 94 | 391666.6667 | 8659.8791 | 2010-12-27 19:53 | 2010-12-31 17:53 | MooringSystemInstallation | 360 | 364 | 5
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 8661.3791 | 2010-12-27 21:23 | 2010-12-28 04:23 | MooredSubInstallation | 360 | 361 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 8664.0391 | 2010-12-28 00:02 | 2010-12-28 04:12 | MooringSystemInstallation | 361 | 361 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8664.8791 | 2010-12-28 00:53 | 2010-12-28 04:23 | MooredSubInstallation | 361 | 361 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 8666.0391 | 2010-12-28 02:02 | 2010-12-28 04:02 | MooringSystemInstallation | 361 | 361 | 1
Towing Group 3 | Delay | 108 | 270000 | 8667.8791 | 2010-12-28 03:53 | 2011-01-01 15:53 | MooredSubInstallation | 361 | 365 | 5
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 8670.0391 | 2010-12-28 06:02 | 2010-12-28 10:02 | MooringSystemInstallation | 361 | 361 | 1
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 8674.0719 | 2010-12-28 10:04 | 2010-12-28 16:16 | MooredSubInstallation | 361 | 361 | 1
Multi-Purpose Support Vessel | Delay | 132 | 550000 | 8674.0719 | 2010-12-28 10:04 | 2011-01-02 22:04 | MooredSubInstallation | 361 | 366 | 6
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 8676.0719 | 2010-12-28 12:04 | 2010-12-28 14:04 | MooredSubInstallation | 361 | 361 | 1
Turbine Assembly Line 1 | Delay | 61 | 0 | 8725.8791 | 2010-12-30 13:53 | 2011-01-02 02:53 | MooredSubInstallation | 363 | 366 | 4
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8729.3791 | 2010-12-30 17:23 | 2010-12-30 20:53 | MooredSubInstallation | 363 | 363 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8732.8791 | 2010-12-30 20:53 | 2010-12-31 00:23 | MooredSubInstallation | 363 | 364 | 2
Mooring System Installation Vessel | Delay | 64 | 266666.6667 | 8734.0391 | 2010-12-30 22:02 | 2011-01-02 14:02 | MooringSystemInstallation | 363 | 366 | 4
Multi-Purpose Support Vessel | Delay | 73 | 304166.6667 | 8749.0719 | 2010-12-31 13:04 | 2011-01-03 14:04 | MooredSubInstallation | 364 | 367 | 4
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 8750.1991 | 2010-12-31 14:12 | 2011-01-01 06:22 | MooringSystemInstallation | 364 | 365 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 8754.3591 | 2010-12-31 18:22 | 2010-12-31 22:31 | MooringSystemInstallation | 364 | 364 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 8755.0719 | 2010-12-31 19:04 | 2011-01-01 01:04 | MooredSubInstallation | 364 | 365 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 462.5825 | 578228.0655 | 8756.8791 | 2010-12-31 20:53 | 2011-01-01 20:53 | MooredSubInstallation | 364 | 365 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 8756.8791 | 2010-12-31 20:53 | 2011-01-20 03:28 | MooredSubInstallation | 364 | 384 | 21
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 12500 | 8758.0719 | 2010-12-31 22:04 | 2011-01-01 01:04 | MooredSubInstallation | 364 | 365 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 8758.694 | 2010-12-31 22:42 | 2011-01-01 03:02 | MooringSystemInstallation | 364 | 365 | 2
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 8762.3791 | 2011-01-01 02:23 | 2011-01-08 02:23 | MooredSubInstallation | 365 | 372 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 5.5 | 0 | 8762.3791 | 2011-01-01 02:23 | 2011-01-01 07:53 | MooredSubInstallation | 365 | 365 | 1
Mooring System Installation Vessel | Delay | 10 | 41666.6667 | 8768.694 | 2011-01-01 08:42 | 2011-01-01 18:42 | MooringSystemInstallation | 365 | 365 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 8770.3791 | 2011-01-01 10:23 | 2011-01-01 18:23 | MooredSubInstallation | 365 | 365 | 1
Multi-Purpose Support Vessel | Delay | 13 | 54166.6667 | 8771.0719 | 2011-01-01 11:04 | 2011-01-02 00:04 | MooredSubInstallation | 365 | 366 | 2
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 8773.694 | 2011-01-01 13:42 | 2011-01-01 18:42 | MooringSystemInstallation | 365 | 365 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 12500 | 8774.0719 | 2011-01-01 14:04 | 2011-01-01 17:04 | MooredSubInstallation | 365 | 365 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 8782.3791 | 2011-01-01 22:23 | 2011-01-02 10:23 | MooredSubInstallation | 365 | 366 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 8794.3791 | 2011-01-02 10:23 | 2011-01-02 22:23 | MooredSubInstallation | 366 | 366 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 8806.3791 | 2011-01-02 22:23 | 2011-01-03 10:23 | MooredSubInstallation | 366 | 367 | 2
Mooring System Installation Vessel | Delay | 37 | 154166.6667 | 8810.694 | 2011-01-03 02:42 | 2011-01-04 15:42 | MooringSystemInstallation | 367 | 368 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 8813.3791 | 2011-01-03 05:23 | 2011-01-03 12:23 | MooredSubInstallation | 367 | 367 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 8815.694 | 2011-01-03 07:42 | 2011-01-03 12:42 | MooringSystemInstallation | 367 | 367 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8816.8791 | 2011-01-03 08:53 | 2011-01-03 12:23 | MooredSubInstallation | 367 | 367 | 1
Towing Group 1 | Delay | 62 | 155000 | 8818.8791 | 2011-01-03 10:53 | 2011-01-06 00:53 | MooredSubInstallation | 367 | 370 | 4
Multi-Purpose Support Vessel | Delay | 45 | 187500 | 8819.0719 | 2011-01-03 11:04 | 2011-01-05 08:04 | MooredSubInstallation | 367 | 369 | 3
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 8820.0289 | 2011-01-03 12:02 | 2011-01-03 16:22 | MooringSystemInstallation | 367 | 367 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8820.3791 | 2011-01-03 12:23 | 2011-01-03 15:53 | MooredSubInstallation | 367 | 367 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 8822.0289 | 2011-01-03 14:02 | 2011-01-03 16:02 | MooringSystemInstallation | 367 | 367 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8823.8791 | 2011-01-03 15:53 | 2011-01-03 19:23 | MooredSubInstallation | 367 | 367 | 1
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 8824.8791 | 2011-01-03 16:53 | 2011-01-03 22:53 | MooredSubInstallation | 367 | 367 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 8826.0289 | 2011-01-03 18:02 | 2011-01-03 22:02 | MooringSystemInstallation | 367 | 367 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 8831.0719 | 2011-01-03 23:04 | 2011-01-04 05:16 | MooredSubInstallation | 367 | 368 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 58333.3333 | 8833.0719 | 2011-01-04 01:04 | 2011-01-04 15:04 | MooredSubInstallation | 368 | 368 | 1
Towing Group 2 | Delay: No Completed Assemblies Available | 298.5825 | 373228.0655 | 8847.8791 | 2011-01-04 15:53 | 2011-01-05 15:53 | MooredSubInstallation | 368 | 369 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 8847.8791 | 2011-01-04 15:53 | 2011-01-17 02:28 | MooredSubInstallation | 368 | 381 | 14
Mooring System Installation Vessel | Delay | 25 | 104166.6667 | 8851.0289 | 2011-01-04 19:02 | 2011-01-05 20:02 | MooringSystemInstallation | 368 | 369 | 2
Multi-Purpose Support Vessel | Delay | 31 | 129166.6667 | 8864.0719 | 2011-01-05 08:04 | 2011-01-06 15:04 | MooredSubInstallation | 369 | 370 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 2 | 8333.3333 | 8866.0719 | 2011-01-05 10:04 | 2011-01-05 12:04 | MooredSubInstallation | 369 | 369 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 8867.1889 | 2011-01-05 11:11 | 2011-01-06 03:21 | MooringSystemInstallation | 369 | 370 | 2
Towing Group 2 | Delay | 20 | 50000 | 8867.8791 | 2011-01-05 11:53 | 2011-01-06 07:53 | MooredSubInstallation | 369 | 370 | 2
Multi-Purpose Support Vessel | Delay | 2 | 8333.3333 | 8868.0719 | 2011-01-05 12:04 | 2011-01-05 14:04 | MooredSubInstallation | 369 | 369 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 8871.3489 | 2011-01-05 15:21 | 2011-01-05 19:31 | MooringSystemInstallation | 369 | 369 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 4 | 16666.6667 | 8872.0719 | 2011-01-05 16:04 | 2011-01-05 20:04 | MooredSubInstallation | 369 | 369 | 1
Towing Group 3 | Positioning Support | 198 | 247500 | 8872.0719 | 2011-01-05 16:04 | 2011-01-13 22:04 | MooredSubInstallation | 369 | 377 | 9
Towing Group 1 | Queue | 41 | 51250 | 8872.0719 | 2011-01-05 16:04 | 2011-01-07 09:04 | MooredSubInstallation | 369 | 371 | 3
Multi-Purpose Support Vessel | Delay | 0 | 0 | 8872.0719 | 2011-01-05 16:04 | 2011-01-05 16:04 | MooredSubInstallation | 369 | 369 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 8873.3489 | 2011-01-05 17:21 | 2011-01-05 19:21 | MooringSystemInstallation | 369 | 369 | 1
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 8873.8791 | 2011-01-05 17:53 | 2011-01-05 23:53 | MooredSubInstallation | 369 | 369 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 8874.0719 | 2011-01-05 18:04 | 2011-01-05 20:04 | MooredSubInstallation | 369 | 369 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 8877.3489 | 2011-01-05 21:21 | 2011-01-06 01:21 | MooringSystemInstallation | 369 | 370 | 2
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 8879.2967 | 2011-01-05 23:18 | 2011-01-06 06:31 | MooredSubInstallation | 369 | 370 | 2
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 8880.0719 | 2011-01-06 00:04 | 2011-01-06 06:16 | MooredSubInstallation | 370 | 370 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 8880.0719 | 2011-01-06 00:04 | 2011-01-06 06:04 | MooredSubInstallation | 370 | 370 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 54166.6667 | 8893.0719 | 2011-01-06 13:04 | 2011-01-07 02:04 | MooredSubInstallation | 370 | 371 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 8893.5089 | 2011-01-06 13:31 | 2011-01-07 05:40 | MooringSystemInstallation | 370 | 371 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 8897.6689 | 2011-01-06 17:40 | 2011-01-06 21:50 | MooringSystemInstallation | 370 | 370 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 8899.6689 | 2011-01-06 19:40 | 2011-01-06 21:40 | MooringSystemInstallation | 370 | 370 | 1
Mooring System Installation Vessel | Delay | 26 | 108333.3333 | 8925.6689 | 2011-01-07 21:40 | 2011-01-08 23:40 | MooringSystemInstallation | 371 | 372 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 8929.6689 | 2011-01-08 01:40 | 2011-01-08 05:40 | MooringSystemInstallation | 372 | 372 | 1
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 8930.3791 | 2011-01-08 02:23 | 2011-01-15 02:23 | MooredSubInstallation | 372 | 379 | 8
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 8930.3791 | 2011-01-08 02:23 | 2011-01-11 12:53 | MooredSubInstallation | 372 | 375 | 4
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 8938.3791 | 2011-01-08 10:23 | 2011-01-08 18:23 | MooredSubInstallation | 372 | 372 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 8950.3791 | 2011-01-08 22:23 | 2011-01-09 10:23 | MooredSubInstallation | 372 | 373 | 2
Turbine Assembly Line 1 | Delay | 2 | 0 | 8952.3791 | 2011-01-09 00:23 | 2011-01-09 02:23 | MooredSubInstallation | 373 | 373 | 1
Mooring System Installation Vessel | Delay | 28 | 116666.6667 | 8957.6689 | 2011-01-09 05:40 | 2011-01-10 09:40 | MooringSystemInstallation | 373 | 374 | 2
Multi-Purpose Support Vessel | Delay | 70 | 291666.6667 | 8963.0719 | 2011-01-09 11:04 | 2011-01-12 09:04 | MooredSubInstallation | 373 | 376 | 4
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 8964.3791 | 2011-01-09 12:23 | 2011-01-10 00:23 | MooredSubInstallation | 373 | 374 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 29166.6667 | 8970.0719 | 2011-01-09 18:04 | 2011-01-10 01:04 | MooredSubInstallation | 373 | 374 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 8973.8289 | 2011-01-09 21:50 | 2011-01-10 13:59 | MooringSystemInstallation | 373 | 374 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 8976.0719 | 2011-01-10 00:04 | 2011-01-10 06:04 | MooredSubInstallation | 374 | 374 | 1
Towing Group 1 | Positioning Support | 104 | 130000 | 8976.0719 | 2011-01-10 00:04 | 2011-01-14 08:04 | MooredSubInstallation | 374 | 378 | 5
Towing Group 2 | Queue | 96 | 120000 | 8976.0719 | 2011-01-10 00:04 | 2011-01-14 00:04 | MooredSubInstallation | 374 | 378 | 5
Multi-Purpose Support Vessel | Delay | 0 | 0 | 8976.0719 | 2011-01-10 00:04 | 2011-01-10 00:04 | MooredSubInstallation | 374 | 374 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 8976.3791 | 2011-01-10 00:23 | 2011-01-10 12:23 | MooredSubInstallation | 374 | 374 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 8977.9889 | 2011-01-10 01:59 | 2011-01-10 06:09 | MooringSystemInstallation | 374 | 374 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 8978.0719 | 2011-01-10 02:04 | 2011-01-10 04:04 | MooredSubInstallation | 374 | 374 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 8979.9889 | 2011-01-10 03:59 | 2011-01-10 05:59 | MooringSystemInstallation | 374 | 374 | 1
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 8983.2967 | 2011-01-10 07:18 | 2011-01-10 14:31 | MooredSubInstallation | 374 | 374 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 8983.3791 | 2011-01-10 07:23 | 2011-01-10 14:23 | MooredSubInstallation | 374 | 374 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 8983.9889 | 2011-01-10 07:59 | 2011-01-10 11:59 | MooringSystemInstallation | 374 | 374 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 8984.0719 | 2011-01-10 08:04 | 2011-01-10 14:04 | MooredSubInstallation | 374 | 374 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8986.8791 | 2011-01-10 10:53 | 2011-01-10 14:23 | MooredSubInstallation | 374 | 374 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8990.3791 | 2011-01-10 14:23 | 2011-01-10 17:53 | MooredSubInstallation | 374 | 374 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 8993.8791 | 2011-01-10 17:53 | 2011-01-10 21:23 | MooredSubInstallation | 374 | 374 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9000.1489 | 2011-01-11 00:09 | 2011-01-11 16:19 | MooringSystemInstallation | 375 | 375 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 9004.0719 | 2011-01-11 04:04 | 2011-01-12 00:04 | MooredSubInstallation | 375 | 376 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9004.3089 | 2011-01-11 04:19 | 2011-01-11 08:28 | MooringSystemInstallation | 375 | 375 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 9006.3089 | 2011-01-11 06:19 | 2011-01-11 08:19 | MooringSystemInstallation | 375 | 375 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 9010.0719 | 2011-01-11 10:04 | 2011-01-11 16:04 | MooredSubInstallation | 375 | 375 | 1
Towing Group 2 | Positioning Support | 34 | 42500 | 9010.0719 | 2011-01-11 10:04 | 2011-01-12 20:04 | MooredSubInstallation | 375 | 376 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 9010.3089 | 2011-01-11 10:19 | 2011-01-11 14:19 | MooringSystemInstallation | 375 | 375 | 1
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 9017.2967 | 2011-01-11 17:18 | 2011-01-12 00:31 | MooredSubInstallation | 375 | 376 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 9017.8791 | 2011-01-11 17:53 | 2011-01-12 17:53 | MooredSubInstallation | 375 | 376 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 138.5825 | 173228.0655 | 9017.8791 | 2011-01-11 17:53 | 2011-01-17 12:28 | MooredSubInstallation | 375 | 381 | 7
Mooring System Installation Vessel | Delay | 26 | 108333.3333 | 9036.3089 | 2011-01-12 12:19 | 2011-01-13 14:19 | MooringSystemInstallation | 376 | 377 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9052.4689 | 2011-01-13 04:28 | 2011-01-13 20:38 | MooringSystemInstallation | 377 | 377 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9056.6289 | 2011-01-13 08:38 | 2011-01-13 12:47 | MooringSystemInstallation | 377 | 377 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 9058.6289 | 2011-01-13 10:38 | 2011-01-13 12:38 | MooringSystemInstallation | 377 | 377 | 1
Towing Group 3 | Delay | 42 | 105000 | 9059.8791 | 2011-01-13 11:53 | 2011-01-15 05:53 | MooredSubInstallation | 377 | 379 | 3
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 9062.6289 | 2011-01-13 14:38 | 2011-01-13 18:38 | MooringSystemInstallation | 377 | 377 | 1
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 9065.8791 | 2011-01-13 17:53 | 2011-01-13 23:53 | MooredSubInstallation | 377 | 377 | 1
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 9072.0719 | 2011-01-14 00:04 | 2011-01-14 06:16 | MooredSubInstallation | 378 | 378 | 1
Multi-Purpose Support Vessel | Delay | 62 | 258333.3333 | 9072.0719 | 2011-01-14 00:04 | 2011-01-16 14:04 | MooredSubInstallation | 378 | 380 | 3
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 9074.0719 | 2011-01-14 02:04 | 2011-01-14 04:04 | MooredSubInstallation | 378 | 378 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9078.7889 | 2011-01-14 06:47 | 2011-01-14 22:57 | MooringSystemInstallation | 378 | 378 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 9080.0719 | 2011-01-14 08:04 | 2011-01-14 14:04 | MooredSubInstallation | 378 | 378 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9082.9489 | 2011-01-14 10:57 | 2011-01-14 15:07 | MooringSystemInstallation | 378 | 378 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 9087.2838 | 2011-01-14 15:17 | 2011-01-14 19:37 | MooringSystemInstallation | 378 | 378 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 9092.2838 | 2011-01-14 20:17 | 2011-01-15 01:17 | MooringSystemInstallation | 378 | 379 | 2
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 9097.2838 | 2011-01-15 01:17 | 2011-01-15 06:17 | MooringSystemInstallation | 379 | 379 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 9098.3791 | 2011-01-15 02:23 | 2011-01-22 02:23 | MooredSubInstallation | 379 | 386 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 80.5 | 0 | 9098.3791 | 2011-01-15 02:23 | 2011-01-18 10:53 | MooredSubInstallation | 379 | 382 | 4
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 9100.0719 | 2011-01-15 04:04 | 2011-01-16 00:04 | MooredSubInstallation | 379 | 380 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 9101.6187 | 2011-01-15 05:37 | 2011-01-15 09:57 | MooringSystemInstallation | 379 | 379 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 9103.6187 | 2011-01-15 07:37 | 2011-01-15 09:37 | MooringSystemInstallation | 379 | 379 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 9106.0719 | 2011-01-15 10:04 | 2011-01-15 16:04 | MooredSubInstallation | 379 | 379 | 1
Towing Group 3 | Positioning Support | 34 | 42500 | 9106.0719 | 2011-01-15 10:04 | 2011-01-16 20:04 | MooredSubInstallation | 379 | 380 | 2
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 9106.3791 | 2011-01-15 10:23 | 2011-01-15 18:23 | MooredSubInstallation | 379 | 379 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 9107.6187 | 2011-01-15 11:37 | 2011-01-15 15:37 | MooringSystemInstallation | 379 | 379 | 1
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 9113.2967 | 2011-01-15 17:18 | 2011-01-16 00:31 | MooredSubInstallation | 379 | 380 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 9118.3791 | 2011-01-15 22:23 | 2011-01-16 10:23 | MooredSubInstallation | 379 | 380 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9123.7787 | 2011-01-16 03:47 | 2011-01-16 19:56 | MooringSystemInstallation | 380 | 380 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9127.9387 | 2011-01-16 07:56 | 2011-01-16 12:06 | MooringSystemInstallation | 380 | 380 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 9129.9387 | 2011-01-16 09:56 | 2011-01-16 11:56 | MooringSystemInstallation | 380 | 380 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 9130.3791 | 2011-01-16 10:23 | 2011-01-16 22:23 | MooredSubInstallation | 380 | 380 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 9133.9387 | 2011-01-16 13:56 | 2011-01-16 17:56 | MooringSystemInstallation | 380 | 380 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 9142.3791 | 2011-01-16 22:23 | 2011-01-17 10:23 | MooredSubInstallation | 380 | 381 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 9149.3791 | 2011-01-17 05:23 | 2011-01-17 12:23 | MooredSubInstallation | 381 | 381 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9150.0987 | 2011-01-17 06:06 | 2011-01-17 22:16 | MooringSystemInstallation | 381 | 381 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 9152.8791 | 2011-01-17 08:53 | 2011-01-17 12:23 | MooredSubInstallation | 381 | 381 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9154.2587 | 2011-01-17 10:16 | 2011-01-17 14:25 | MooringSystemInstallation | 381 | 381 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 9156.2587 | 2011-01-17 12:16 | 2011-01-17 14:16 | MooringSystemInstallation | 381 | 381 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 9156.3791 | 2011-01-17 12:23 | 2011-01-17 15:53 | MooredSubInstallation | 381 | 381 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 9159.8791 | 2011-01-17 15:53 | 2011-01-17 19:23 | MooredSubInstallation | 381 | 381 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 9160.2587 | 2011-01-17 16:16 | 2011-01-17 20:16 | MooringSystemInstallation | 381 | 381 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 9183.8791 | 2011-01-18 15:53 | 2011-01-19 15:53 | MooredSubInstallation | 382 | 383 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 200.5825 | 250728.0655 | 9183.8791 | 2011-01-18 15:53 | 2011-01-27 00:28 | MooredSubInstallation | 382 | 391 | 10
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 9266.3791 | 2011-01-22 02:23 | 2011-01-29 02:23 | MooredSubInstallation | 386 | 393 | 8
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 9266.3791 | 2011-01-22 02:23 | 2011-01-25 12:53 | MooredSubInstallation | 386 | 389 | 4
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 9274.3791 | 2011-01-22 10:23 | 2011-01-22 18:23 | MooredSubInstallation | 386 | 386 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 9286.3791 | 2011-01-22 22:23 | 2011-01-23 10:23 | MooredSubInstallation | 386 | 387 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 9298.3791 | 2011-01-23 10:23 | 2011-01-23 22:23 | MooredSubInstallation | 387 | 387 | 1
Mooring System Installation Vessel | Delay | 143 | 595833.3333 | 9303.2587 | 2011-01-23 15:16 | 2011-01-29 14:16 | MooringSystemInstallation | 387 | 393 | 7
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 9310.3791 | 2011-01-23 22:23 | 2011-01-24 10:23 | MooredSubInstallation | 387 | 388 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 9317.3791 | 2011-01-24 05:23 | 2011-01-24 12:23 | MooredSubInstallation | 388 | 388 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9319.4187 | 2011-01-24 07:25 | 2011-01-24 23:35 | MooringSystemInstallation | 388 | 388 | 1
Towing Group 1 | Delay | 136 | 340000 | 9319.8791 | 2011-01-24 07:53 | 2011-01-29 23:53 | MooredSubInstallation | 388 | 393 | 6
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 9320.8791 | 2011-01-24 08:53 | 2011-01-24 12:23 | MooredSubInstallation | 388 | 388 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9323.5787 | 2011-01-24 11:35 | 2011-01-24 15:44 | MooringSystemInstallation | 388 | 388 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 9324.3791 | 2011-01-24 12:23 | 2011-01-24 15:53 | MooredSubInstallation | 388 | 388 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 9325.5787 | 2011-01-24 13:35 | 2011-01-24 15:35 | MooringSystemInstallation | 388 | 388 | 1
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 9325.8791 | 2011-01-24 13:53 | 2011-01-24 19:53 | MooredSubInstallation | 388 | 388 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 9327.8791 | 2011-01-24 15:53 | 2011-01-24 19:23 | MooredSubInstallation | 388 | 388 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 9329.5787 | 2011-01-24 17:35 | 2011-01-24 21:35 | MooringSystemInstallation | 388 | 388 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 9332.0719 | 2011-01-24 20:04 | 2011-01-25 02:16 | MooredSubInstallation | 388 | 389 | 2
Multi-Purpose Support Vessel | Delay | 226 | 941666.6667 | 9332.0719 | 2011-01-24 20:04 | 2011-02-03 06:04 | MooredSubInstallation | 388 | 398 | 11
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 9334.0719 | 2011-01-24 22:04 | 2011-01-25 00:04 | MooredSubInstallation | 388 | 389 | 2
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 9340.0719 | 2011-01-25 04:04 | 2011-01-25 10:04 | MooredSubInstallation | 389 | 389 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9345.7387 | 2011-01-25 09:44 | 2011-01-26 01:54 | MooringSystemInstallation | 389 | 390 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9349.8987 | 2011-01-25 13:54 | 2011-01-25 18:04 | MooringSystemInstallation | 389 | 389 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 9351.8791 | 2011-01-25 15:53 | 2011-01-26 15:53 | MooredSubInstallation | 389 | 390 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 334.5825 | 418228.0655 | 9351.8791 | 2011-01-25 15:53 | 2011-02-08 14:28 | MooredSubInstallation | 389 | 403 | 15
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 9351.8987 | 2011-01-25 15:54 | 2011-01-25 17:54 | MooringSystemInstallation | 389 | 389 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 54166.6667 | 9353.0719 | 2011-01-25 17:04 | 2011-01-26 06:04 | MooredSubInstallation | 389 | 390 | 2
Towing Group 2 | Delay | 3 | 7500 | 9354.8791 | 2011-01-25 18:53 | 2011-01-25 21:53 | MooredSubInstallation | 389 | 389 | 1
Multi-Purpose Support Vessel | Delay | 2 | 8333.3333 | 9355.0719 | 2011-01-25 19:04 | 2011-01-25 21:04 | MooredSubInstallation | 389 | 389 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 9355.8987 | 2011-01-25 19:54 | 2011-01-25 23:54 | MooringSystemInstallation | 389 | 389 | 1
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 9360.8791 | 2011-01-26 00:53 | 2011-01-26 06:53 | MooredSubInstallation | 390 | 390 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 29166.6667 | 9362.0719 | 2011-01-26 02:04 | 2011-01-26 09:04 | MooredSubInstallation | 390 | 390 | 1
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 9367.0719 | 2011-01-26 07:04 | 2011-01-26 13:16 | MooredSubInstallation | 390 | 390 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 9368.0719 | 2011-01-26 08:04 | 2011-01-26 14:04 | MooredSubInstallation | 390 | 390 | 1
Towing Group 1 | Positioning Support | 36 | 45000 | 9368.0719 | 2011-01-26 08:04 | 2011-01-27 20:04 | MooredSubInstallation | 390 | 391 | 2
Towing Group 2 | Queue | 1 | 1250 | 9368.0719 | 2011-01-26 08:04 | 2011-01-26 09:04 | MooredSubInstallation | 390 | 390 | 1
Multi-Purpose Support Vessel | Delay | 0 | 0 | 9368.0719 | 2011-01-26 08:04 | 2011-01-26 08:04 | MooredSubInstallation | 390 | 390 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 9370.0719 | 2011-01-26 10:04 | 2011-01-26 12:04 | MooredSubInstallation | 390 | 390 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9372.0587 | 2011-01-26 12:04 | 2011-01-27 04:13 | MooringSystemInstallation | 390 | 391 | 2
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 9375.2967 | 2011-01-26 15:18 | 2011-01-26 22:31 | MooredSubInstallation | 390 | 390 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 9376.0719 | 2011-01-26 16:04 | 2011-01-26 22:04 | MooredSubInstallation | 390 | 390 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9376.2187 | 2011-01-26 16:13 | 2011-01-26 20:23 | MooringSystemInstallation | 390 | 390 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 8333.3333 | 9378.0719 | 2011-01-26 18:04 | 2011-01-26 20:04 | MooredSubInstallation | 390 | 390 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 9378.2187 | 2011-01-26 18:13 | 2011-01-26 20:13 | MooringSystemInstallation | 390 | 390 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 9382.2187 | 2011-01-26 22:13 | 2011-01-27 02:13 | MooringSystemInstallation | 390 | 391 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9398.3787 | 2011-01-27 14:23 | 2011-01-28 06:32 | MooringSystemInstallation | 391 | 392 | 2
Multi-Purpose Support Vessel | Delay | 21 | 87500 | 9399.0719 | 2011-01-27 15:04 | 2011-01-28 12:04 | MooredSubInstallation | 391 | 392 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9402.5387 | 2011-01-27 18:32 | 2011-01-27 22:42 | MooringSystemInstallation | 391 | 391 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 9406.8736 | 2011-01-27 22:52 | 2011-01-28 03:13 | MooringSystemInstallation | 391 | 392 | 2
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 9411.8736 | 2011-01-28 03:52 | 2011-01-28 08:52 | MooringSystemInstallation | 392 | 392 | 1
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 9416.8736 | 2011-01-28 08:52 | 2011-01-28 13:52 | MooringSystemInstallation | 392 | 392 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 75000 | 9417.0719 | 2011-01-28 09:04 | 2011-01-29 03:04 | MooredSubInstallation | 392 | 393 | 2
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 9421.2085 | 2011-01-28 13:13 | 2011-01-28 17:33 | MooringSystemInstallation | 392 | 392 | 1
Towing Group 2 | Positioning Support | 55 | 68750 | 9423.0719 | 2011-01-28 15:04 | 2011-01-28 21:04 | MooredSubInstallation | 392 | 392 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 9423.0719 | 2011-01-28 15:04 | 2011-01-30 22:04 | MooredSubInstallation | 392 | 394 | 3
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 9423.2085 | 2011-01-28 15:13 | 2011-01-28 17:13 | MooringSystemInstallation | 392 | 392 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 9427.2085 | 2011-01-28 19:13 | 2011-01-28 23:13 | MooringSystemInstallation | 392 | 392 | 1
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 9430.2967 | 2011-01-28 22:18 | 2011-01-29 05:31 | MooredSubInstallation | 392 | 393 | 2
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 9434.3791 | 2011-01-29 02:23 | 2011-02-05 02:23 | MooredSubInstallation | 393 | 400 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 9434.3791 | 2011-01-29 02:23 | 2011-02-01 12:53 | MooredSubInstallation | 393 | 396 | 4
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 9442.3791 | 2011-01-29 10:23 | 2011-01-29 18:23 | MooredSubInstallation | 393 | 393 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9443.3685 | 2011-01-29 11:22 | 2011-01-30 03:32 | MooringSystemInstallation | 393 | 394 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9447.5285 | 2011-01-29 15:32 | 2011-01-29 19:41 | MooringSystemInstallation | 393 | 393 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 9449.5285 | 2011-01-29 17:32 | 2011-01-29 19:32 | MooringSystemInstallation | 393 | 393 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 9453.5285 | 2011-01-29 21:32 | 2011-01-30 01:32 | MooringSystemInstallation | 393 | 394 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 9454.3791 | 2011-01-29 22:23 | 2011-01-30 10:23 | MooredSubInstallation | 393 | 394 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 9466.3791 | 2011-01-30 10:23 | 2011-01-30 22:23 | MooredSubInstallation | 394 | 394 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 9478.3791 | 2011-01-30 22:23 | 2011-01-31 10:23 | MooredSubInstallation | 394 | 395 | 2
Mooring System Installation Vessel | Delay | 31 | 129166.6667 | 9484.5285 | 2011-01-31 04:32 | 2011-02-01 11:32 | MooringSystemInstallation | 395 | 396 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 9485.3791 | 2011-01-31 05:23 | 2011-01-31 12:23 | MooredSubInstallation | 395 | 395 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 9488.8791 | 2011-01-31 08:53 | 2011-01-31 12:23 | MooredSubInstallation | 395 | 395 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 9492.3791 | 2011-01-31 12:23 | 2011-01-31 15:53 | MooredSubInstallation | 395 | 395 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 9495.8791 | 2011-01-31 15:53 | 2011-01-31 19:23 | MooredSubInstallation | 395 | 395 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9500.6885 | 2011-01-31 20:41 | 2011-02-01 12:51 | MooringSystemInstallation | 395 | 396 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9504.8485 | 2011-02-01 00:51 | 2011-02-01 05:01 | MooringSystemInstallation | 396 | 396 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 9506.8485 | 2011-02-01 02:51 | 2011-02-01 04:51 | MooringSystemInstallation | 396 | 396 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 9510.8485 | 2011-02-01 06:51 | 2011-02-01 10:51 | MooringSystemInstallation | 396 | 396 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 9519.8791 | 2011-02-01 15:53 | 2011-02-02 15:53 | MooredSubInstallation | 396 | 397 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 406.5825 | 508228.0655 | 9519.8791 | 2011-02-01 15:53 | 2011-02-18 14:28 | MooredSubInstallation | 396 | 413 | 18
Towing Group 3 | Delay | 2 | 5000 | 9521.8791 | 2011-02-01 17:53 | 2011-02-01 19:53 | MooredSubInstallation | 396 | 396 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9527.0085 | 2011-02-01 23:01 | 2011-02-02 15:10 | MooringSystemInstallation | 396 | 397 | 2
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 9527.8791 | 2011-02-01 23:53 | 2011-02-02 05:53 | MooredSubInstallation | 396 | 397 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9531.1685 | 2011-02-02 03:10 | 2011-02-02 07:20 | MooringSystemInstallation | 397 | 397 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 9533.1685 | 2011-02-02 05:10 | 2011-02-02 07:10 | MooringSystemInstallation | 397 | 397 | 1
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 9534.0719 | 2011-02-02 06:04 | 2011-02-02 12:16 | MooredSubInstallation | 397 | 397 | 1
Multi-Purpose Support Vessel | Delay | 111 | 462500 | 9534.0719 | 2011-02-02 06:04 | 2011-02-06 21:04 | MooredSubInstallation | 397 | 401 | 5
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 9536.0719 | 2011-02-02 08:04 | 2011-02-02 10:04 | MooredSubInstallation | 397 | 397 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 9537.1685 | 2011-02-02 09:10 | 2011-02-02 13:10 | MooringSystemInstallation | 397 | 397 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 9542.0719 | 2011-02-02 14:04 | 2011-02-02 20:04 | MooredSubInstallation | 397 | 397 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9553.3285 | 2011-02-03 01:20 | 2011-02-03 17:29 | MooringSystemInstallation | 398 | 398 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9557.4885 | 2011-02-03 05:29 | 2011-02-03 09:39 | MooringSystemInstallation | 398 | 398 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 9559.4885 | 2011-02-03 07:29 | 2011-02-03 09:29 | MooringSystemInstallation | 398 | 398 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 9562.0719 | 2011-02-03 10:04 | 2011-02-04 06:04 | MooredSubInstallation | 398 | 399 | 2
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 9563.4885 | 2011-02-03 11:29 | 2011-02-03 15:29 | MooringSystemInstallation | 398 | 398 | 1
Towing Group 3 | Positioning Support | 34 | 42500 | 9568.0719 | 2011-02-03 16:04 | 2011-02-03 22:04 | MooredSubInstallation | 398 | 398 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 9568.0719 | 2011-02-03 16:04 | 2011-02-05 02:04 | MooredSubInstallation | 398 | 400 | 3
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 9575.2967 | 2011-02-03 23:18 | 2011-02-04 06:31 | MooredSubInstallation | 398 | 399 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9579.6485 | 2011-02-04 03:39 | 2011-02-04 19:49 | MooringSystemInstallation | 399 | 399 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 9602.3791 | 2011-02-05 02:23 | 2011-02-12 02:23 | MooredSubInstallation | 400 | 407 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 9602.3791 | 2011-02-05 02:23 | 2011-02-08 12:53 | MooredSubInstallation | 400 | 403 | 4
Mooring System Installation Vessel | Delay | 29 | 120833.3333 | 9608.6485 | 2011-02-05 08:39 | 2011-02-06 13:39 | MooringSystemInstallation | 400 | 401 | 2
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 9610.3791 | 2011-02-05 10:23 | 2011-02-05 18:23 | MooredSubInstallation | 400 | 400 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9612.8085 | 2011-02-05 12:49 | 2011-02-05 16:58 | MooringSystemInstallation | 400 | 400 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 9614.8085 | 2011-02-05 14:49 | 2011-02-05 16:49 | MooringSystemInstallation | 400 | 400 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 9618.8085 | 2011-02-05 18:49 | 2011-02-05 22:49 | MooringSystemInstallation | 400 | 400 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 9622.3791 | 2011-02-05 22:23 | 2011-02-06 10:23 | MooredSubInstallation | 400 | 401 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 9634.3791 | 2011-02-06 10:23 | 2011-02-06 22:23 | MooredSubInstallation | 401 | 401 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9634.9685 | 2011-02-06 10:58 | 2011-02-07 03:08 | MooringSystemInstallation | 401 | 402 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9639.1285 | 2011-02-06 15:08 | 2011-02-06 19:17 | MooringSystemInstallation | 401 | 401 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 9643.4634 | 2011-02-06 19:28 | 2011-02-06 23:48 | MooringSystemInstallation | 401 | 401 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 9646.3791 | 2011-02-06 22:23 | 2011-02-07 10:23 | MooredSubInstallation | 401 | 402 | 2
Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | 9648.4634 | 2011-02-07 00:28 | 2011-02-07 05:28 | MooringSystemInstallation | 402 | 402 | 1
Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | 9652.7983 | 2011-02-07 04:48 | 2011-02-07 09:08 | MooringSystemInstallation | 402 | 402 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 9653.3791 | 2011-02-07 05:23 | 2011-02-07 12:23 | MooredSubInstallation | 402 | 402 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 9654.7983 | 2011-02-07 06:48 | 2011-02-07 08:48 | MooringSystemInstallation | 402 | 402 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 9658.7983 | 2011-02-07 10:48 | 2011-02-07 14:48 | MooringSystemInstallation | 402 | 402 | 1
Mooring System Installation Vessel | Delay | 65 | 270833.3333 | 9723.7983 | 2011-02-10 03:48 | 2011-02-12 20:48 | MooringSystemInstallation | 405 | 407 | 3
Turbine Assembly Line 1 | Delay | 75 | 0 | 9728.3791 | 2011-02-10 08:23 | 2011-02-13 11:23 | MooredSubInstallation | 405 | 408 | 4
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 9731.8791 | 2011-02-10 11:53 | 2011-02-10 15:23 | MooredSubInstallation | 405 | 405 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 9735.3791 | 2011-02-10 15:23 | 2011-02-10 18:53 | MooredSubInstallation | 405 | 405 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 9738.8791 | 2011-02-10 18:53 | 2011-02-10 22:23 | MooredSubInstallation | 405 | 405 | 1
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9739.9583 | 2011-02-10 19:57 | 2011-02-11 12:07 | MooringSystemInstallation | 405 | 406 | 2
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9744.1183 | 2011-02-11 00:07 | 2011-02-11 04:17 | MooringSystemInstallation | 406 | 406 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 9746.1183 | 2011-02-11 02:07 | 2011-02-11 04:07 | MooringSystemInstallation | 406 | 406 | 1
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 9750.1183 | 2011-02-11 06:07 | 2011-02-11 10:07 | MooringSystemInstallation | 406 | 406 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 9762.8791 | 2011-02-11 18:53 | 2011-02-12 18:53 | MooredSubInstallation | 406 | 407 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 387.5825 | 484478.0655 | 9762.8791 | 2011-02-11 18:53 | 2011-02-27 22:28 | MooredSubInstallation | 406 | 422 | 17
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9766.2783 | 2011-02-11 22:17 | 2011-02-12 14:26 | MooringSystemInstallation | 406 | 407 | 2
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 9768.8791 | 2011-02-12 00:53 | 2011-02-12 06:53 | MooredSubInstallation | 407 | 407 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 9770.3791 | 2011-02-12 02:23 | 2011-02-19 02:23 | MooredSubInstallation | 407 | 414 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 7.5 | 0 | 9770.3791 | 2011-02-12 02:23 | 2011-02-12 09:53 | MooredSubInstallation | 407 | 407 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9770.4383 | 2011-02-12 02:26 | 2011-02-12 06:36 | MooringSystemInstallation | 407 | 407 | 1
Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | 9772.4383 | 2011-02-12 04:26 | 2011-02-12 06:26 | MooringSystemInstallation | 407 | 407 | 1
Multi-Purpose Support Vessel | Delay | 207 | 862500 | 9775.0719 | 2011-02-12 07:04 | 2011-02-12 13:16 | MooredSubInstallation | 407 | 407 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 9775.0719 | 2011-02-12 07:04 | 2011-02-20 22:04 | MooredSubInstallation | 407 | 415 | 9
Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | 9776.4383 | 2011-02-12 08:26 | 2011-02-12 12:26 | MooringSystemInstallation | 407 | 407 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 9777.0719 | 2011-02-12 09:04 | 2011-02-12 11:04 | MooredSubInstallation | 407 | 407 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 9778.3791 | 2011-02-12 10:23 | 2011-02-12 18:23 | MooredSubInstallation | 407 | 407 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 9783.0719 | 2011-02-12 15:04 | 2011-02-12 21:04 | MooredSubInstallation | 407 | 407 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 9790.3791 | 2011-02-12 22:23 | 2011-02-13 10:23 | MooredSubInstallation | 407 | 408 | 2
Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | 9792.5983 | 2011-02-13 00:36 | 2011-02-13 16:45 | MooringSystemInstallation | 408 | 408 | 1
Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | 9796.7583 | 2011-02-13 04:45 | 2011-02-13 08:55 | MooringSystemInstallation | 408 | 408 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 9802.3791 | 2011-02-13 10:23 | 2011-02-13 22:23 | MooredSubInstallation | 408 | 408 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 9803.0719 | 2011-02-13 11:04 | 2011-02-14 07:04 | MooredSubInstallation | 408 | 409 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 9809.0719 | 2011-02-13 17:04 | 2011-02-13 23:04 | MooredSubInstallation | 408 | 408 | 1
Towing Group 1 | Positioning Support | 34 | 42500 | 9809.0719 | 2011-02-13 17:04 | 2011-02-15 03:04 | MooredSubInstallation | 408 | 410 | 3
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 9814.3791 | 2011-02-13 22:23 | 2011-02-14 10:23 | MooredSubInstallation | 408 | 409 | 2
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 9816.2967 | 2011-02-14 00:18 | 2011-02-14 07:31 | MooredSubInstallation | 409 | 409 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 9821.3791 | 2011-02-14 05:23 | 2011-02-14 12:23 | MooredSubInstallation | 409 | 409 | 1
Turbine Assembly Line 1 | Delay | 40 | 0 | 9861.3791 | 2011-02-15 21:23 | 2011-02-17 13:23 | MooredSubInstallation | 410 | 412 | 3
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 9864.8791 | 2011-02-16 00:53 | 2011-02-16 04:23 | MooredSubInstallation | 411 | 411 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 9868.3791 | 2011-02-16 04:23 | 2011-02-16 07:53 | MooredSubInstallation | 411 | 411 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 9871.8791 | 2011-02-16 07:53 | 2011-02-16 11:23 | MooredSubInstallation | 411 | 411 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 9895.8791 | 2011-02-17 07:53 | 2011-02-18 07:53 | MooredSubInstallation | 412 | 413 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 465.5825 | 581978.0655 | 9895.8791 | 2011-02-17 07:53 | 2011-03-08 17:28 | MooredSubInstallation | 412 | 431 | 20
Towing Group 2 | Delay | 28 | 70000 | 9923.8791 | 2011-02-18 11:53 | 2011-02-19 15:53 | MooredSubInstallation | 413 | 414 | 2
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 9929.8791 | 2011-02-18 17:53 | 2011-02-18 23:53 | MooredSubInstallation | 413 | 413 | 1
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 9936.0719 | 2011-02-19 00:04 | 2011-02-19 06:16 | MooredSubInstallation | 414 | 414 | 1
Multi-Purpose Support Vessel | Delay | 127 | 529166.6667 | 9936.0719 | 2011-02-19 00:04 | 2011-02-24 07:04 | MooredSubInstallation | 414 | 419 | 6
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 9938.0719 | 2011-02-19 02:04 | 2011-02-19 04:04 | MooredSubInstallation | 414 | 414 | 1
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 42.5 | 0 | 9938.3791 | 2011-02-19 02:23 | 2011-02-26 02:23 | MooredSubInstallation | 414 | 421 | 8
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 9938.3791 | 2011-02-19 02:23 | 2011-02-20 20:53 | MooredSubInstallation | 414 | 415 | 2
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 9946.3791 | 2011-02-19 10:23 | 2011-02-19 18:23 | MooredSubInstallation | 414 | 414 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 9958.3791 | 2011-02-19 22:23 | 2011-02-20 10:23 | MooredSubInstallation | 414 | 415 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 9970.3791 | 2011-02-20 10:23 | 2011-02-20 22:23 | MooredSubInstallation | 415 | 415 | 1
Multi-Purpose Support Vessel | Delay | 40 | 166666.6667 | 9978.0719 | 2011-02-20 18:04 | 2011-02-22 10:04 | MooredSubInstallation | 415 | 417 | 3
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 9982.3791 | 2011-02-20 22:23 | 2011-02-21 10:23 | MooredSubInstallation | 415 | 416 | 2
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 9984.0719 | 2011-02-21 00:04 | 2011-02-21 06:04 | MooredSubInstallation | 416 | 416 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 9989.3791 | 2011-02-21 05:23 | 2011-02-21 12:23 | MooredSubInstallation | 416 | 416 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 9992.8791 | 2011-02-21 08:53 | 2011-02-21 12:23 | MooredSubInstallation | 416 | 416 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 9996.3791 | 2011-02-21 12:23 | 2011-02-21 15:53 | MooredSubInstallation | 416 | 416 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 62500 | 9999.0719 | 2011-02-21 15:04 | 2011-02-22 06:04 | MooredSubInstallation | 416 | 417 | 2
Multi-Purpose Support Vessel | Delay | 6 | 25000 | 10005.0719 | 2011-02-21 21:04 | 2011-02-22 03:04 | MooredSubInstallation | 416 | 417 | 2
Turbine Assembly Line 1 | Delay | 9 | 0 | 10005.3791 | 2011-02-21 21:23 | 2011-02-22 06:23 | MooredSubInstallation | 416 | 417 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 10008.8791 | 2011-02-22 00:53 | 2011-02-22 04:23 | MooredSubInstallation | 417 | 417 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 20833.3333 | 10010.0719 | 2011-02-22 02:04 | 2011-02-22 07:04 | MooredSubInstallation | 417 | 417 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 5 | 20833.3333 | 10015.0719 | 2011-02-22 07:04 | 2011-02-22 12:04 | MooredSubInstallation | 417 | 417 | 1
Multi-Purpose Support Vessel | Delay | 3 | 12500 | 10018.0719 | 2011-02-22 10:04 | 2011-02-22 13:04 | MooredSubInstallation | 417 | 417 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 1 | 4166.6667 | 10019.0719 | 2011-02-22 11:04 | 2011-02-22 12:04 | MooredSubInstallation | 417 | 417 | 1
Towing Group 2 | Positioning Support | 83 | 103750 | 10019.0719 | 2011-02-22 11:04 | 2011-02-25 22:04 | MooredSubInstallation | 417 | 420 | 4
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 10026.2967 | 2011-02-22 18:18 | 2011-02-23 01:31 | MooredSubInstallation | 417 | 418 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 10032.8791 | 2011-02-23 00:53 | 2011-02-24 00:53 | MooredSubInstallation | 418 | 419 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 457.5825 | 571978.0655 | 10032.8791 | 2011-02-23 00:53 | 2011-03-14 02:28 | MooredSubInstallation | 418 | 437 | 20
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 10106.3791 | 2011-02-26 02:23 | 2011-03-05 02:23 | MooredSubInstallation | 421 | 428 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 73.5 | 0 | 10106.3791 | 2011-02-26 02:23 | 2011-03-01 03:53 | MooredSubInstallation | 421 | 424 | 4
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 10114.3791 | 2011-02-26 10:23 | 2011-02-26 18:23 | MooredSubInstallation | 421 | 421 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 10126.3791 | 2011-02-26 22:23 | 2011-02-27 10:23 | MooredSubInstallation | 421 | 422 | 2
Towing Group 3 | Delay | 103 | 257500 | 10135.8791 | 2011-02-27 07:53 | 2011-03-03 14:53 | MooredSubInstallation | 422 | 426 | 5
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 10138.3791 | 2011-02-27 10:23 | 2011-02-27 22:23 | MooredSubInstallation | 422 | 422 | 1
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 10141.8791 | 2011-02-27 13:53 | 2011-02-27 19:53 | MooredSubInstallation | 422 | 422 | 1
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 10148.0719 | 2011-02-27 20:04 | 2011-02-28 02:16 | MooredSubInstallation | 422 | 423 | 2
Multi-Purpose Support Vessel | Delay | 129 | 537500 | 10148.0719 | 2011-02-27 20:04 | 2011-03-05 05:04 | MooredSubInstallation | 422 | 428 | 7
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 10150.0719 | 2011-02-27 22:04 | 2011-02-28 00:04 | MooredSubInstallation | 422 | 423 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 10150.3791 | 2011-02-27 22:23 | 2011-02-28 10:23 | MooredSubInstallation | 422 | 423 | 2
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 10156.0719 | 2011-02-28 04:04 | 2011-02-28 10:04 | MooredSubInstallation | 423 | 423 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 10157.3791 | 2011-02-28 05:23 | 2011-02-28 12:23 | MooredSubInstallation | 423 | 423 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 12500 | 10159.0719 | 2011-02-28 07:04 | 2011-02-28 10:04 | MooredSubInstallation | 423 | 423 | 1
Turbine Assembly Line 1 | Delay | 54 | 0 | 10211.3791 | 2011-03-02 11:23 | 2011-03-04 17:23 | MooredSubInstallation | 425 | 427 | 3
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 10214.8791 | 2011-03-02 14:53 | 2011-03-02 18:23 | MooredSubInstallation | 425 | 425 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 10218.3791 | 2011-03-02 18:23 | 2011-03-02 21:53 | MooredSubInstallation | 425 | 425 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 10221.8791 | 2011-03-02 21:53 | 2011-03-03 01:23 | MooredSubInstallation | 425 | 426 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 10245.8791 | 2011-03-03 21:53 | 2011-03-04 21:53 | MooredSubInstallation | 426 | 427 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 429.5825 | 536978.0655 | 10245.8791 | 2011-03-03 21:53 | 2011-03-21 19:28 | MooredSubInstallation | 426 | 444 | 19
Towing Group 1 | Delay | 4 | 10000 | 10249.8791 | 2011-03-04 01:53 | 2011-03-04 05:53 | MooredSubInstallation | 427 | 427 | 1
Multi-Purpose Support Vessel | Delay | 91 | 379166.6667 | 10250.0719 | 2011-03-04 02:04 | 2011-03-07 21:04 | MooredSubInstallation | 427 | 430 | 4
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 10255.8791 | 2011-03-04 07:53 | 2011-03-04 13:53 | MooredSubInstallation | 427 | 427 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 10262.0719 | 2011-03-04 14:04 | 2011-03-04 20:16 | MooredSubInstallation | 427 | 427 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 70833.3333 | 10267.0719 | 2011-03-04 19:04 | 2011-03-05 12:04 | MooredSubInstallation | 427 | 428 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 10273.0719 | 2011-03-05 01:04 | 2011-03-05 07:04 | MooredSubInstallation | 428 | 428 | 1
Towing Group 3 | Positioning Support | 125 | 156250 | 10273.0719 | 2011-03-05 01:04 | 2011-03-10 06:04 | MooredSubInstallation | 428 | 433 | 6
Towing Group 1 | Queue | 11 | 13750 | 10273.0719 | 2011-03-05 01:04 | 2011-03-05 12:04 | MooredSubInstallation | 428 | 428 | 1
Multi-Purpose Support Vessel | Delay | 0 | 0 | 10273.0719 | 2011-03-05 01:04 | 2011-03-05 01:04 | MooredSubInstallation | 428 | 428 | 1
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 28.5 | 0 | 10274.3791 | 2011-03-05 02:23 | 2011-03-12 02:23 | MooredSubInstallation | 428 | 435 | 8
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 10274.3791 | 2011-03-05 02:23 | 2011-03-06 06:53 | MooredSubInstallation | 428 | 429 | 2
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 10275.0719 | 2011-03-05 03:04 | 2011-03-05 05:04 | MooredSubInstallation | 428 | 428 | 1
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 10280.2967 | 2011-03-05 08:18 | 2011-03-05 15:31 | MooredSubInstallation | 428 | 428 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 10281.0719 | 2011-03-05 09:04 | 2011-03-05 15:04 | MooredSubInstallation | 428 | 428 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 10282.3791 | 2011-03-05 10:23 | 2011-03-05 18:23 | MooredSubInstallation | 428 | 428 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 10294.3791 | 2011-03-05 22:23 | 2011-03-06 10:23 | MooredSubInstallation | 428 | 429 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 10301.0719 | 2011-03-06 05:04 | 2011-03-07 01:04 | MooredSubInstallation | 429 | 430 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 10306.3791 | 2011-03-06 10:23 | 2011-03-06 22:23 | MooredSubInstallation | 429 | 429 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 10307.0719 | 2011-03-06 11:04 | 2011-03-06 17:04 | MooredSubInstallation | 429 | 429 | 1
Towing Group 1 | Positioning Support | 34 | 42500 | 10307.0719 | 2011-03-06 11:04 | 2011-03-07 21:04 | MooredSubInstallation | 429 | 430 | 2
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 10314.2967 | 2011-03-06 18:18 | 2011-03-07 01:31 | MooredSubInstallation | 429 | 430 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 10318.3791 | 2011-03-06 22:23 | 2011-03-07 10:23 | MooredSubInstallation | 429 | 430 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 10325.3791 | 2011-03-07 05:23 | 2011-03-07 12:23 | MooredSubInstallation | 430 | 430 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 10328.8791 | 2011-03-07 08:53 | 2011-03-07 12:23 | MooredSubInstallation | 430 | 430 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 10332.3791 | 2011-03-07 12:23 | 2011-03-07 15:53 | MooredSubInstallation | 430 | 430 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 10335.8791 | 2011-03-07 15:53 | 2011-03-07 19:23 | MooredSubInstallation | 430 | 430 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 10359.8791 | 2011-03-08 15:53 | 2011-03-09 15:53 | MooredSubInstallation | 431 | 432 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 333.5825 | 416978.0655 | 10359.8791 | 2011-03-08 15:53 | 2011-03-22 13:28 | MooredSubInstallation | 431 | 445 | 15
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 10365.8791 | 2011-03-08 21:53 | 2011-03-09 03:53 | MooredSubInstallation | 431 | 432 | 2
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 10372.0719 | 2011-03-09 04:04 | 2011-03-09 10:16 | MooredSubInstallation | 432 | 432 | 1
Multi-Purpose Support Vessel | Delay | 65 | 270833.3333 | 10372.0719 | 2011-03-09 04:04 | 2011-03-11 21:04 | MooredSubInstallation | 432 | 434 | 3
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 10374.0719 | 2011-03-09 06:04 | 2011-03-09 08:04 | MooredSubInstallation | 432 | 432 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 10380.0719 | 2011-03-09 12:04 | 2011-03-09 18:04 | MooredSubInstallation | 432 | 432 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 37500 | 10389.0719 | 2011-03-09 21:04 | 2011-03-10 06:04 | MooredSubInstallation | 432 | 433 | 2
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 10442.3791 | 2011-03-12 02:23 | 2011-03-19 02:23 | MooredSubInstallation | 435 | 442 | 8
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 10442.3791 | 2011-03-12 02:23 | 2011-03-15 12:53 | MooredSubInstallation | 435 | 438 | 4
Multi-Purpose Support Vessel | Delay | 55 | 229166.6667 | 10444.0719 | 2011-03-12 04:04 | 2011-03-14 11:04 | MooredSubInstallation | 435 | 437 | 3
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 10450.3791 | 2011-03-12 10:23 | 2011-03-12 18:23 | MooredSubInstallation | 435 | 435 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 37500 | 10453.0719 | 2011-03-12 13:04 | 2011-03-12 22:04 | MooredSubInstallation | 435 | 435 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 10462.3791 | 2011-03-12 22:23 | 2011-03-13 10:23 | MooredSubInstallation | 435 | 436 | 2
Turbine Assembly Line 1 | Delay | 24 | 0 | 10486.3791 | 2011-03-13 22:23 | 2011-03-14 22:23 | MooredSubInstallation | 436 | 437 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 10498.3791 | 2011-03-14 10:23 | 2011-03-14 22:23 | MooredSubInstallation | 437 | 437 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 10510.3791 | 2011-03-14 22:23 | 2011-03-15 10:23 | MooredSubInstallation | 437 | 438 | 2
Turbine Assembly Line 1 | Delay | 14 | 0 | 10524.3791 | 2011-03-15 12:23 | 2011-03-16 02:23 | MooredSubInstallation | 438 | 439 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 10531.3791 | 2011-03-15 19:23 | 2011-03-16 02:23 | MooredSubInstallation | 438 | 439 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 10534.8791 | 2011-03-15 22:53 | 2011-03-16 02:23 | MooredSubInstallation | 438 | 439 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 10538.3791 | 2011-03-16 02:23 | 2011-03-16 05:53 | MooredSubInstallation | 439 | 439 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 10541.8791 | 2011-03-16 05:53 | 2011-03-16 09:23 | MooredSubInstallation | 439 | 439 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 10565.8791 | 2011-03-17 05:53 | 2011-03-18 05:53 | MooredSubInstallation | 440 | 441 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 285.5825 | 356978.0655 | 10565.8791 | 2011-03-17 05:53 | 2011-03-29 03:28 | MooredSubInstallation | 440 | 452 | 13
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 44.5 | 0 | 10610.3791 | 2011-03-19 02:23 | 2011-03-26 02:23 | MooredSubInstallation | 442 | 449 | 8
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 10610.3791 | 2011-03-19 02:23 | 2011-03-20 22:53 | MooredSubInstallation | 442 | 443 | 2
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 10618.3791 | 2011-03-19 10:23 | 2011-03-19 18:23 | MooredSubInstallation | 442 | 442 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 10630.3791 | 2011-03-19 22:23 | 2011-03-20 10:23 | MooredSubInstallation | 442 | 443 | 2
Turbine Assembly Line 1 | Delay | 11 | 0 | 10641.3791 | 2011-03-20 09:23 | 2011-03-20 20:23 | MooredSubInstallation | 443 | 443 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 10653.3791 | 2011-03-20 21:23 | 2011-03-21 09:23 | MooredSubInstallation | 443 | 444 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 10665.3791 | 2011-03-21 09:23 | 2011-03-21 21:23 | MooredSubInstallation | 444 | 444 | 1
Array Cable Installation Vessel | Mobilize | 72 | 180000 | 10669.0879 | 2011-03-21 13:05 | 2011-03-24 13:05 | ArrayCableInstallation | 444 | 447 | 4
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 10672.3791 | 2011-03-21 16:23 | 2011-03-21 23:23 | MooredSubInstallation | 444 | 444 | 1
Array Cable Installation Vessel | Load Cable | 6 | 30000 | 10675.0879 | 2011-03-21 19:05 | 2011-03-22 01:05 | ArrayCableInstallation | 444 | 445 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 10675.8791 | 2011-03-21 19:53 | 2011-03-21 23:23 | MooredSubInstallation | 444 | 444 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 10679.3791 | 2011-03-21 23:23 | 2011-03-22 02:53 | MooredSubInstallation | 444 | 445 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 10682.8791 | 2011-03-22 02:53 | 2011-03-22 06:23 | MooredSubInstallation | 445 | 445 | 1
Towing Group 1 | Delay: No Completed Assemblies Available | 392.5825 | 490728.0655 | 10706.8791 | 2011-03-23 02:53 | 2011-03-24 02:53 | MooredSubInstallation | 446 | 447 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 10706.8791 | 2011-03-23 02:53 | 2011-04-08 11:28 | MooredSubInstallation | 446 | 462 | 17
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 10778.3791 | 2011-03-26 02:23 | 2011-04-02 02:23 | MooredSubInstallation | 449 | 456 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 71.5 | 0 | 10778.3791 | 2011-03-26 02:23 | 2011-03-29 01:53 | MooredSubInstallation | 449 | 452 | 4
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 10786.3791 | 2011-03-26 10:23 | 2011-03-26 18:23 | MooredSubInstallation | 449 | 449 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 10798.3791 | 2011-03-26 22:23 | 2011-03-27 10:23 | MooredSubInstallation | 449 | 450 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 10810.3791 | 2011-03-27 10:23 | 2011-03-27 22:23 | MooredSubInstallation | 450 | 450 | 1
Turbine Assembly Line 1 | Delay | 6 | 0 | 10816.3791 | 2011-03-27 16:23 | 2011-03-27 22:23 | MooredSubInstallation | 450 | 450 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 10828.3791 | 2011-03-28 04:23 | 2011-03-28 16:23 | MooredSubInstallation | 451 | 451 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 10835.3791 | 2011-03-28 11:23 | 2011-03-28 18:23 | MooredSubInstallation | 451 | 451 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 10838.8791 | 2011-03-28 14:53 | 2011-03-28 18:23 | MooredSubInstallation | 451 | 451 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 10842.3791 | 2011-03-28 18:23 | 2011-03-28 21:53 | MooredSubInstallation | 451 | 451 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 10845.8791 | 2011-03-28 21:53 | 2011-03-29 01:23 | MooredSubInstallation | 451 | 452 | 2
Towing Group 1 | Delay | 153 | 382500 | 10859.8791 | 2011-03-29 11:53 | 2011-04-10 17:53 | MooredSubInstallation | 452 | 464 | 13
Towing Group 3 | Delay | 294 | 735000 | 10859.8791 | 2011-03-29 11:53 | 2011-04-04 20:53 | MooredSubInstallation | 452 | 458 | 7
Multi-Purpose Support Vessel | Delay | 407 | 1695833.3333 | 10860.0719 | 2011-03-29 12:04 | 2011-04-15 11:04 | MooredSubInstallation | 452 | 469 | 18
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 8333.3333 | 10862.0719 | 2011-03-29 14:04 | 2011-03-29 16:04 | MooredSubInstallation | 452 | 452 | 1
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 10865.8791 | 2011-03-29 17:53 | 2011-03-29 23:53 | MooredSubInstallation | 452 | 452 | 1
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 10865.8791 | 2011-03-29 17:53 | 2011-03-29 23:53 | MooredSubInstallation | 452 | 452 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 10868.0719 | 2011-03-29 20:04 | 2011-03-30 02:04 | MooredSubInstallation | 452 | 453 | 2
Towing Group 2 | Positioning Support | 496 | 620000 | 10868.0719 | 2011-03-29 20:04 | 2011-04-19 12:04 | MooredSubInstallation | 452 | 473 | 22
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 10869.8791 | 2011-03-29 21:53 | 2011-03-30 21:53 | MooredSubInstallation | 452 | 453 | 2
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 10872.0719 | 2011-03-30 00:04 | 2011-03-30 06:16 | MooredSubInstallation | 453 | 453 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 10872.0719 | 2011-03-30 00:04 | 2011-03-30 06:16 | MooredSubInstallation | 453 | 453 | 1
Multi-Purpose Support Vessel | Delay | 4 | 16666.6667 | 10872.0719 | 2011-03-30 00:04 | 2011-03-30 04:04 | MooredSubInstallation | 453 | 453 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 10874.0719 | 2011-03-30 02:04 | 2011-03-30 04:04 | MooredSubInstallation | 453 | 453 | 1
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 10875.2967 | 2011-03-30 03:18 | 2011-03-30 10:31 | MooredSubInstallation | 453 | 453 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 10880.0719 | 2011-03-30 08:04 | 2011-03-30 14:04 | MooredSubInstallation | 453 | 453 | 1
Array Cable Installation Vessel | Delay | 205 | 1025000 | 10880.0879 | 2011-03-30 08:05 | 2011-04-07 21:05 | ArrayCableInstallation | 453 | 461 | 9
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 10881.2967 | 2011-03-30 09:18 | 2011-03-30 15:18 | MooredSubInstallation | 453 | 453 | 1
Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | 10883.8574 | 2011-03-30 11:51 | 2011-03-30 15:38 | ArrayCableInstallation | 453 | 453 | 1
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 10887.4894 | 2011-03-30 15:29 | 2011-03-30 21:41 | MooredSubInstallation | 453 | 453 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 58333.3333 | 10894.0719 | 2011-03-30 22:04 | 2011-03-31 12:04 | MooredSubInstallation | 453 | 454 | 2
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 10946.3791 | 2011-04-02 02:23 | 2011-04-09 02:23 | MooredSubInstallation | 456 | 463 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 76.5 | 0 | 10946.3791 | 2011-04-02 02:23 | 2011-04-05 06:53 | MooredSubInstallation | 456 | 459 | 4
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 10954.3791 | 2011-04-02 10:23 | 2011-04-02 18:23 | MooredSubInstallation | 456 | 456 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 10966.3791 | 2011-04-02 22:23 | 2011-04-03 10:23 | MooredSubInstallation | 456 | 457 | 2
Turbine Assembly Line 1 | Delay | 21 | 0 | 10987.3791 | 2011-04-03 19:23 | 2011-04-04 16:23 | MooredSubInstallation | 457 | 458 | 2
Multi-Purpose Support Vessel | Delay | 102 | 425000 | 10996.0719 | 2011-04-04 04:04 | 2011-04-08 10:04 | MooredSubInstallation | 458 | 462 | 5
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 10999.3791 | 2011-04-04 07:23 | 2011-04-04 19:23 | MooredSubInstallation | 458 | 458 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 25000 | 11002.0719 | 2011-04-04 10:04 | 2011-04-04 16:04 | MooredSubInstallation | 458 | 458 | 1
Array Cable Installation Vessel | Delay | 120 | 600000 | 11003.8574 | 2011-04-04 11:51 | 2011-04-09 11:51 | ArrayCableInstallation | 458 | 463 | 6
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 11005.8574 | 2011-04-04 13:51 | 2011-04-04 15:51 | ArrayCableInstallation | 458 | 458 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11006.8574 | 2011-04-04 14:51 | 2011-04-04 15:51 | ArrayCableInstallation | 458 | 458 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 11008.0719 | 2011-04-04 16:04 | 2011-04-04 22:04 | MooredSubInstallation | 458 | 458 | 1
Towing Group 3 | Positioning Support | 136 | 170000 | 11008.0719 | 2011-04-04 16:04 | 2011-04-10 08:04 | MooredSubInstallation | 458 | 464 | 7
Towing Group 1 | Queue | 136 | 170000 | 11008.0719 | 2011-04-04 16:04 | 2011-04-10 08:04 | MooredSubInstallation | 458 | 464 | 7
Multi-Purpose Support Vessel | Delay | 0 | 0 | 11008.0719 | 2011-04-04 16:04 | 2011-04-04 16:04 | MooredSubInstallation | 458 | 458 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 11010.0719 | 2011-04-04 18:04 | 2011-04-04 20:04 | MooredSubInstallation | 458 | 458 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 11011.3791 | 2011-04-04 19:23 | 2011-04-05 07:23 | MooredSubInstallation | 458 | 459 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11012.3574 | 2011-04-04 20:21 | 2011-04-05 01:51 | ArrayCableInstallation | 458 | 459 | 2
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 11015.2967 | 2011-04-04 23:18 | 2011-04-05 06:31 | MooredSubInstallation | 458 | 459 | 2
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 11016.0719 | 2011-04-05 00:04 | 2011-04-05 06:04 | MooredSubInstallation | 459 | 459 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11017.8574 | 2011-04-05 01:51 | 2011-04-05 07:21 | ArrayCableInstallation | 459 | 459 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 11018.3791 | 2011-04-05 02:23 | 2011-04-05 09:23 | MooredSubInstallation | 459 | 459 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 11018.8574 | 2011-04-05 02:51 | 2011-04-05 03:51 | ArrayCableInstallation | 459 | 459 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11021.8791 | 2011-04-05 05:53 | 2011-04-05 09:23 | MooredSubInstallation | 459 | 459 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 7 | 35000 | 11025.8574 | 2011-04-05 09:51 | 2011-04-05 16:51 | ArrayCableInstallation | 459 | 459 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 54166.6667 | 11029.0719 | 2011-04-05 13:04 | 2011-04-06 02:04 | MooredSubInstallation | 459 | 460 | 2
Turbine Assembly Line 1 | Delay | 25 | 0 | 11046.8791 | 2011-04-06 06:53 | 2011-04-07 07:53 | MooredSubInstallation | 460 | 461 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11050.3791 | 2011-04-06 10:23 | 2011-04-06 13:53 | MooredSubInstallation | 460 | 460 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11053.8791 | 2011-04-06 13:53 | 2011-04-06 17:23 | MooredSubInstallation | 460 | 460 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 11077.8791 | 2011-04-07 13:53 | 2011-04-08 13:53 | MooredSubInstallation | 461 | 462 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 62.5825 | 78228.0655 | 11077.8791 | 2011-04-07 13:53 | 2011-04-10 04:28 | MooredSubInstallation | 461 | 464 | 4
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 11114.3791 | 2011-04-09 02:23 | 2011-04-16 02:23 | MooredSubInstallation | 463 | 470 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 36.5 | 0 | 11114.3791 | 2011-04-09 02:23 | 2011-04-10 14:53 | MooredSubInstallation | 463 | 464 | 2
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 11122.3791 | 2011-04-09 10:23 | 2011-04-09 18:23 | MooredSubInstallation | 463 | 463 | 1
Towing Group 3 | Delay | 54 | 135000 | 11131.8791 | 2011-04-09 19:53 | 2011-04-12 01:53 | MooredSubInstallation | 463 | 466 | 4
Multi-Purpose Support Vessel | Delay | 103 | 429166.6667 | 11132.0719 | 2011-04-09 20:04 | 2011-04-14 03:04 | MooredSubInstallation | 463 | 468 | 6
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 11134.3791 | 2011-04-09 22:23 | 2011-04-10 10:23 | MooredSubInstallation | 463 | 464 | 2
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 11137.8791 | 2011-04-10 01:53 | 2011-04-10 07:53 | MooredSubInstallation | 464 | 464 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 29166.6667 | 11139.0719 | 2011-04-10 03:04 | 2011-04-10 10:04 | MooredSubInstallation | 464 | 464 | 1
Array Cable Installation Vessel | Delay | 115 | 575000 | 11140.8574 | 2011-04-10 04:51 | 2011-04-14 23:51 | ArrayCableInstallation | 464 | 468 | 5
Array Cable Installation Vessel | Lay/Bury Cable | 2.991 | 14954.8442 | 11143.8484 | 2011-04-10 07:51 | 2011-04-10 10:50 | ArrayCableInstallation | 464 | 464 | 1
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 11144.0719 | 2011-04-10 08:04 | 2011-04-10 14:16 | MooredSubInstallation | 464 | 464 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11144.8484 | 2011-04-10 08:51 | 2011-04-10 09:51 | ArrayCableInstallation | 464 | 464 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 11145.0719 | 2011-04-10 09:04 | 2011-04-10 15:04 | MooredSubInstallation | 464 | 464 | 1
Towing Group 1 | Positioning Support | 137 | 171250 | 11145.0719 | 2011-04-10 09:04 | 2011-04-16 02:04 | MooredSubInstallation | 464 | 470 | 7
Towing Group 2 | Queue | 257.5825 | 321978.0655 | 11145.0719 | 2011-04-10 09:04 | 2011-04-21 02:39 | MooredSubInstallation | 464 | 475 | 12
Multi-Purpose Support Vessel | Delay | 0 | 0 | 11145.0719 | 2011-04-10 09:04 | 2011-04-10 09:04 | MooredSubInstallation | 464 | 464 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 11146.3791 | 2011-04-10 10:23 | 2011-04-10 22:23 | MooredSubInstallation | 464 | 464 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 11147.0719 | 2011-04-10 11:04 | 2011-04-10 13:04 | MooredSubInstallation | 464 | 464 | 1
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 11152.2967 | 2011-04-10 16:18 | 2011-04-10 23:31 | MooredSubInstallation | 464 | 464 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 11153.0719 | 2011-04-10 17:04 | 2011-04-10 23:04 | MooredSubInstallation | 464 | 464 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 11158.3791 | 2011-04-10 22:23 | 2011-04-11 10:23 | MooredSubInstallation | 464 | 465 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 11165.3791 | 2011-04-11 05:23 | 2011-04-11 12:23 | MooredSubInstallation | 465 | 465 | 1
Turbine Assembly Line 1 | Delay | 1 | 0 | 11166.3791 | 2011-04-11 06:23 | 2011-04-11 07:23 | MooredSubInstallation | 465 | 465 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11169.8791 | 2011-04-11 09:53 | 2011-04-11 13:23 | MooredSubInstallation | 465 | 465 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 70833.3333 | 11170.0719 | 2011-04-11 10:04 | 2011-04-12 03:04 | MooredSubInstallation | 465 | 466 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11173.3791 | 2011-04-11 13:23 | 2011-04-11 16:53 | MooredSubInstallation | 465 | 465 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11176.8791 | 2011-04-11 16:53 | 2011-04-11 20:23 | MooredSubInstallation | 465 | 465 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 11200.8791 | 2011-04-12 16:53 | 2011-04-13 16:53 | MooredSubInstallation | 466 | 467 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 48.5825 | 60728.0655 | 11200.8791 | 2011-04-12 16:53 | 2011-04-14 17:28 | MooredSubInstallation | 466 | 468 | 3
Towing Group 1 | Delay | 6 | 15000 | 11206.8791 | 2011-04-12 22:53 | 2011-04-13 04:53 | MooredSubInstallation | 466 | 467 | 2
Multi-Purpose Support Vessel | Delay | 37 | 154166.6667 | 11207.0719 | 2011-04-12 23:04 | 2011-04-14 12:04 | MooredSubInstallation | 466 | 468 | 3
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 12500 | 11210.0719 | 2011-04-13 02:04 | 2011-04-13 05:04 | MooredSubInstallation | 467 | 467 | 1
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 11212.8791 | 2011-04-13 04:53 | 2011-04-13 10:53 | MooredSubInstallation | 467 | 467 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 11216.0719 | 2011-04-13 08:04 | 2011-04-13 14:04 | MooredSubInstallation | 467 | 467 | 1
Towing Group 2 | Positioning Support | 71 | 88750 | 11216.0719 | 2011-04-13 08:04 | 2011-04-16 07:04 | MooredSubInstallation | 467 | 470 | 4
Towing Group 3 | Queue | 72 | 90000 | 11216.0719 | 2011-04-13 08:04 | 2011-04-16 08:04 | MooredSubInstallation | 467 | 470 | 4
Multi-Purpose Support Vessel | Delay | 0 | 0 | 11216.0719 | 2011-04-13 08:04 | 2011-04-13 08:04 | MooredSubInstallation | 467 | 467 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 11218.0719 | 2011-04-13 10:04 | 2011-04-13 12:04 | MooredSubInstallation | 467 | 467 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 11219.0719 | 2011-04-13 11:04 | 2011-04-13 17:16 | MooredSubInstallation | 467 | 467 | 1
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 11223.2967 | 2011-04-13 15:18 | 2011-04-13 22:31 | MooredSubInstallation | 467 | 467 | 1
Multi-Purpose Support Vessel | Delay | 7 | 29166.6667 | 11225.0719 | 2011-04-13 17:04 | 2011-04-14 00:04 | MooredSubInstallation | 467 | 468 | 2
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 11231.0719 | 2011-04-13 23:04 | 2011-04-14 05:04 | MooredSubInstallation | 467 | 468 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 11251.0719 | 2011-04-14 19:04 | 2011-04-15 15:04 | MooredSubInstallation | 468 | 469 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 11257.0719 | 2011-04-15 01:04 | 2011-04-15 07:04 | MooredSubInstallation | 469 | 469 | 1
Towing Group 3 | Positioning Support | 41 | 51250 | 11257.0719 | 2011-04-15 01:04 | 2011-04-16 18:04 | MooredSubInstallation | 469 | 470 | 2
Towing Group 1 | Queue | 38 | 47500 | 11257.0719 | 2011-04-15 01:04 | 2011-04-16 15:04 | MooredSubInstallation | 469 | 470 | 2
Multi-Purpose Support Vessel | Delay | 0 | 0 | 11257.0719 | 2011-04-15 01:04 | 2011-04-15 01:04 | MooredSubInstallation | 469 | 469 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 11259.0719 | 2011-04-15 03:04 | 2011-04-15 05:04 | MooredSubInstallation | 469 | 469 | 1
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 11264.2967 | 2011-04-15 08:18 | 2011-04-15 15:31 | MooredSubInstallation | 469 | 469 | 1
Multi-Purpose Support Vessel | Delay | 17 | 70833.3333 | 11276.0719 | 2011-04-15 20:04 | 2011-04-16 13:04 | MooredSubInstallation | 469 | 470 | 2
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 11282.0719 | 2011-04-16 02:04 | 2011-04-16 08:04 | MooredSubInstallation | 470 | 470 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 11282.3791 | 2011-04-16 02:23 | 2011-04-23 02:23 | MooredSubInstallation | 470 | 477 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 81.5 | 0 | 11282.3791 | 2011-04-16 02:23 | 2011-04-19 11:53 | MooredSubInstallation | 470 | 473 | 4
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 11290.3791 | 2011-04-16 10:23 | 2011-04-16 18:23 | MooredSubInstallation | 470 | 470 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 11302.0719 | 2011-04-16 22:04 | 2011-04-17 18:04 | MooredSubInstallation | 470 | 471 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 11302.3791 | 2011-04-16 22:23 | 2011-04-17 10:23 | MooredSubInstallation | 470 | 471 | 2
Array Cable Installation Vessel | Delay | 161 | 805000 | 11305.8484 | 2011-04-17 01:51 | 2011-04-23 18:51 | ArrayCableInstallation | 471 | 477 | 7
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 11308.0719 | 2011-04-17 04:04 | 2011-04-17 10:04 | MooredSubInstallation | 471 | 471 | 1
Towing Group 1 | Positioning Support | 51 | 63750 | 11308.0719 | 2011-04-17 04:04 | 2011-04-19 07:04 | MooredSubInstallation | 471 | 473 | 3
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11311.3484 | 2011-04-17 07:21 | 2011-04-17 12:51 | ArrayCableInstallation | 471 | 471 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 11314.3791 | 2011-04-17 10:23 | 2011-04-17 22:23 | MooredSubInstallation | 471 | 471 | 1
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 11315.2967 | 2011-04-17 11:18 | 2011-04-17 18:31 | MooredSubInstallation | 471 | 471 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11316.8484 | 2011-04-17 12:51 | 2011-04-17 18:21 | ArrayCableInstallation | 471 | 471 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 11318.8484 | 2011-04-17 14:51 | 2011-04-17 16:51 | ArrayCableInstallation | 471 | 471 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11319.8484 | 2011-04-17 15:51 | 2011-04-17 16:51 | ArrayCableInstallation | 471 | 471 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11325.3484 | 2011-04-17 21:21 | 2011-04-18 02:51 | ArrayCableInstallation | 471 | 472 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 11326.3791 | 2011-04-17 22:23 | 2011-04-18 10:23 | MooredSubInstallation | 471 | 472 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11330.8484 | 2011-04-18 02:51 | 2011-04-18 08:21 | ArrayCableInstallation | 472 | 472 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 11331.8484 | 2011-04-18 03:51 | 2011-04-18 04:51 | ArrayCableInstallation | 472 | 472 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 11333.3791 | 2011-04-18 05:23 | 2011-04-18 12:23 | MooredSubInstallation | 472 | 472 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11336.8791 | 2011-04-18 08:53 | 2011-04-18 12:23 | MooredSubInstallation | 472 | 472 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11340.3791 | 2011-04-18 12:23 | 2011-04-18 15:53 | MooredSubInstallation | 472 | 472 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 11341.8393 | 2011-04-18 13:50 | 2011-04-18 23:50 | ArrayCableInstallation | 472 | 472 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11342.8393 | 2011-04-18 14:50 | 2011-04-18 15:50 | ArrayCableInstallation | 472 | 472 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11343.8791 | 2011-04-18 15:53 | 2011-04-18 19:23 | MooredSubInstallation | 472 | 472 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 11367.8791 | 2011-04-19 15:53 | 2011-04-20 15:53 | MooredSubInstallation | 473 | 474 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 144.5825 | 180728.0655 | 11367.8791 | 2011-04-19 15:53 | 2011-04-25 16:28 | MooredSubInstallation | 473 | 479 | 7
Towing Group 2 | Delay | 2 | 5000 | 11369.8791 | 2011-04-19 17:53 | 2011-04-19 19:53 | MooredSubInstallation | 473 | 473 | 1
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 11375.8791 | 2011-04-19 23:53 | 2011-04-20 05:53 | MooredSubInstallation | 473 | 474 | 2
Array Cable Installation Vessel | Delay | 37 | 185000 | 11379.8393 | 2011-04-20 03:50 | 2011-04-21 16:50 | ArrayCableInstallation | 474 | 475 | 2
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 11382.0719 | 2011-04-20 06:04 | 2011-04-20 12:16 | MooredSubInstallation | 474 | 474 | 1
Multi-Purpose Support Vessel | Delay | 74 | 308333.3333 | 11382.0719 | 2011-04-20 06:04 | 2011-04-23 08:04 | MooredSubInstallation | 474 | 477 | 4
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 11384.0719 | 2011-04-20 08:04 | 2011-04-20 10:04 | MooredSubInstallation | 474 | 474 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11385.3393 | 2011-04-20 09:20 | 2011-04-20 14:50 | ArrayCableInstallation | 474 | 474 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 11390.0719 | 2011-04-20 14:04 | 2011-04-20 20:04 | MooredSubInstallation | 474 | 474 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11390.8393 | 2011-04-20 14:50 | 2011-04-20 20:20 | ArrayCableInstallation | 474 | 474 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 11392.8393 | 2011-04-20 16:50 | 2011-04-20 18:50 | ArrayCableInstallation | 474 | 474 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11393.8393 | 2011-04-20 17:50 | 2011-04-20 18:50 | ArrayCableInstallation | 474 | 474 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11399.3393 | 2011-04-20 23:20 | 2011-04-21 04:50 | ArrayCableInstallation | 474 | 475 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11404.8393 | 2011-04-21 04:50 | 2011-04-21 10:20 | ArrayCableInstallation | 475 | 475 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 11405.8393 | 2011-04-21 05:50 | 2011-04-21 06:50 | ArrayCableInstallation | 475 | 475 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 11410.0719 | 2011-04-21 10:04 | 2011-04-22 06:04 | MooredSubInstallation | 475 | 476 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 6 | 30000 | 11411.8393 | 2011-04-21 11:50 | 2011-04-21 17:50 | ArrayCableInstallation | 475 | 475 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 11416.0719 | 2011-04-21 16:04 | 2011-04-21 22:04 | MooredSubInstallation | 475 | 475 | 1
Towing Group 2 | Positioning Support | 34 | 42500 | 11416.0719 | 2011-04-21 16:04 | 2011-04-23 02:04 | MooredSubInstallation | 475 | 477 | 3
Array Cable Installation Vessel | Delay | 8 | 40000 | 11419.8393 | 2011-04-21 19:50 | 2011-04-22 03:50 | ArrayCableInstallation | 475 | 476 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | 11422.8393 | 2011-04-21 22:50 | 2011-04-22 01:50 | ArrayCableInstallation | 475 | 476 | 2
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 11423.2967 | 2011-04-21 23:18 | 2011-04-22 06:31 | MooredSubInstallation | 475 | 476 | 2
Array Cable Installation Vessel | Delay | 21 | 105000 | 11443.8393 | 2011-04-22 19:50 | 2011-04-23 16:50 | ArrayCableInstallation | 476 | 477 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 0.99097 | 4954.8442 | 11444.8303 | 2011-04-22 20:50 | 2011-04-22 21:49 | ArrayCableInstallation | 476 | 476 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11445.8303 | 2011-04-22 21:50 | 2011-04-22 22:50 | ArrayCableInstallation | 476 | 476 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 11450.3791 | 2011-04-23 02:23 | 2011-04-30 02:23 | MooredSubInstallation | 477 | 484 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 11450.3791 | 2011-04-23 02:23 | 2011-04-26 12:53 | MooredSubInstallation | 477 | 480 | 4
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11451.3303 | 2011-04-23 03:20 | 2011-04-23 08:50 | ArrayCableInstallation | 477 | 477 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11456.8303 | 2011-04-23 08:50 | 2011-04-23 14:20 | ArrayCableInstallation | 477 | 477 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 11458.3791 | 2011-04-23 10:23 | 2011-04-23 18:23 | MooredSubInstallation | 477 | 477 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 11458.8303 | 2011-04-23 10:50 | 2011-04-23 12:50 | ArrayCableInstallation | 477 | 477 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11459.8303 | 2011-04-23 11:50 | 2011-04-23 12:50 | ArrayCableInstallation | 477 | 477 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11465.3303 | 2011-04-23 17:20 | 2011-04-23 22:50 | ArrayCableInstallation | 477 | 477 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 11470.3791 | 2011-04-23 22:23 | 2011-04-24 10:23 | MooredSubInstallation | 477 | 478 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11470.8303 | 2011-04-23 22:50 | 2011-04-24 04:20 | ArrayCableInstallation | 477 | 478 | 2
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 11471.8303 | 2011-04-23 23:50 | 2011-04-24 00:50 | ArrayCableInstallation | 477 | 478 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 11481.8213 | 2011-04-24 09:49 | 2011-04-24 19:49 | ArrayCableInstallation | 478 | 478 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 11482.3791 | 2011-04-24 10:23 | 2011-04-24 22:23 | MooredSubInstallation | 478 | 478 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11482.8213 | 2011-04-24 10:49 | 2011-04-24 11:49 | ArrayCableInstallation | 478 | 478 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11488.3213 | 2011-04-24 16:19 | 2011-04-24 21:49 | ArrayCableInstallation | 478 | 478 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11493.8213 | 2011-04-24 21:49 | 2011-04-25 03:19 | ArrayCableInstallation | 478 | 479 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 11494.3791 | 2011-04-24 22:23 | 2011-04-25 10:23 | MooredSubInstallation | 478 | 479 | 2
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 11495.8213 | 2011-04-24 23:49 | 2011-04-25 01:49 | ArrayCableInstallation | 478 | 479 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11496.8213 | 2011-04-25 00:49 | 2011-04-25 01:49 | ArrayCableInstallation | 479 | 479 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 11501.3791 | 2011-04-25 05:23 | 2011-04-25 12:23 | MooredSubInstallation | 479 | 479 | 1
Turbine Assembly Line 1 | Delay | 8 | 0 | 11509.3791 | 2011-04-25 13:23 | 2011-04-25 21:23 | MooredSubInstallation | 479 | 479 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11512.8791 | 2011-04-25 16:53 | 2011-04-25 20:23 | MooredSubInstallation | 479 | 479 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11516.3791 | 2011-04-25 20:23 | 2011-04-25 23:53 | MooredSubInstallation | 479 | 479 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11519.8791 | 2011-04-25 23:53 | 2011-04-26 03:23 | MooredSubInstallation | 479 | 480 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 11543.8791 | 2011-04-26 23:53 | 2011-04-27 23:53 | MooredSubInstallation | 480 | 481 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 279.5825 | 349478.0655 | 11543.8791 | 2011-04-26 23:53 | 2011-05-08 15:28 | MooredSubInstallation | 480 | 492 | 13
Towing Group 3 | Delay | 5 | 12500 | 11548.8791 | 2011-04-27 04:53 | 2011-04-27 09:53 | MooredSubInstallation | 481 | 481 | 1
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 11554.8791 | 2011-04-27 10:53 | 2011-04-27 16:53 | MooredSubInstallation | 481 | 481 | 1
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 11561.0719 | 2011-04-27 17:04 | 2011-04-27 23:16 | MooredSubInstallation | 481 | 481 | 1
Multi-Purpose Support Vessel | Delay | 145 | 604166.6667 | 11561.0719 | 2011-04-27 17:04 | 2011-05-03 18:04 | MooredSubInstallation | 481 | 487 | 7
Array Cable Installation Vessel | Delay | 66 | 330000 | 11562.8213 | 2011-04-27 18:49 | 2011-04-30 12:49 | ArrayCableInstallation | 481 | 484 | 4
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 11563.0719 | 2011-04-27 19:04 | 2011-04-27 21:04 | MooredSubInstallation | 481 | 481 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11568.3213 | 2011-04-28 00:19 | 2011-04-28 05:49 | ArrayCableInstallation | 482 | 482 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 11569.0719 | 2011-04-28 01:04 | 2011-04-28 07:04 | MooredSubInstallation | 482 | 482 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11573.8213 | 2011-04-28 05:49 | 2011-04-28 11:19 | ArrayCableInstallation | 482 | 482 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 11574.8213 | 2011-04-28 06:49 | 2011-04-28 07:49 | ArrayCableInstallation | 482 | 482 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9 | 45000 | 11583.8213 | 2011-04-28 15:49 | 2011-04-29 00:49 | ArrayCableInstallation | 482 | 483 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 11589.0719 | 2011-04-28 21:04 | 2011-04-29 17:04 | MooredSubInstallation | 482 | 483 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 2 | 8333.3333 | 11591.0719 | 2011-04-28 23:04 | 2011-04-29 01:04 | MooredSubInstallation | 482 | 483 | 2
Multi-Purpose Support Vessel | Delay | 20 | 83333.3333 | 11611.0719 | 2011-04-29 19:04 | 2011-04-30 15:04 | MooredSubInstallation | 483 | 484 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 4 | 16666.6667 | 11615.0719 | 2011-04-29 23:04 | 2011-04-30 03:04 | MooredSubInstallation | 483 | 484 | 2
Towing Group 3 | Positioning Support | 54 | 67500 | 11615.0719 | 2011-04-29 23:04 | 2011-05-02 05:04 | MooredSubInstallation | 483 | 486 | 4
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 11618.3791 | 2011-04-30 02:23 | 2011-05-07 02:23 | MooredSubInstallation | 484 | 491 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 74.5 | 0 | 11618.3791 | 2011-04-30 02:23 | 2011-05-03 04:53 | MooredSubInstallation | 484 | 487 | 4
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 11622.2967 | 2011-04-30 06:18 | 2011-04-30 13:31 | MooredSubInstallation | 484 | 484 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 11626.3791 | 2011-04-30 10:23 | 2011-04-30 18:23 | MooredSubInstallation | 484 | 484 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 11638.3791 | 2011-04-30 22:23 | 2011-05-01 10:23 | MooredSubInstallation | 484 | 485 | 2
Turbine Assembly Line 1 | Delay | 8 | 0 | 11646.3791 | 2011-05-01 06:23 | 2011-05-01 14:23 | MooredSubInstallation | 485 | 485 | 1
Array Cable Installation Vessel | Delay | 74 | 370000 | 11657.8213 | 2011-05-01 17:49 | 2011-05-04 19:49 | ArrayCableInstallation | 485 | 488 | 4
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 11658.3791 | 2011-05-01 18:23 | 2011-05-02 06:23 | MooredSubInstallation | 485 | 486 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 0.99097 | 4954.8442 | 11658.8122 | 2011-05-01 18:49 | 2011-05-01 19:48 | ArrayCableInstallation | 485 | 485 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11659.8122 | 2011-05-01 19:49 | 2011-05-01 20:49 | ArrayCableInstallation | 485 | 485 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11665.3122 | 2011-05-02 01:19 | 2011-05-02 06:49 | ArrayCableInstallation | 486 | 486 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 11670.3791 | 2011-05-02 06:23 | 2011-05-02 18:23 | MooredSubInstallation | 486 | 486 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11670.8122 | 2011-05-02 06:49 | 2011-05-02 12:19 | ArrayCableInstallation | 486 | 486 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 11672.8122 | 2011-05-02 08:49 | 2011-05-02 10:49 | ArrayCableInstallation | 486 | 486 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11673.8122 | 2011-05-02 09:49 | 2011-05-02 10:49 | ArrayCableInstallation | 486 | 486 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 11677.3791 | 2011-05-02 13:23 | 2011-05-02 20:23 | MooredSubInstallation | 486 | 486 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11679.3122 | 2011-05-02 15:19 | 2011-05-02 20:49 | ArrayCableInstallation | 486 | 486 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11680.8791 | 2011-05-02 16:53 | 2011-05-02 20:23 | MooredSubInstallation | 486 | 486 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11684.3791 | 2011-05-02 20:23 | 2011-05-02 23:53 | MooredSubInstallation | 486 | 486 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11684.8122 | 2011-05-02 20:49 | 2011-05-03 02:19 | ArrayCableInstallation | 486 | 487 | 2
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 11685.8122 | 2011-05-02 21:49 | 2011-05-02 22:49 | ArrayCableInstallation | 486 | 486 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11687.8791 | 2011-05-02 23:53 | 2011-05-03 03:23 | MooredSubInstallation | 486 | 487 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 5 | 25000 | 11690.8122 | 2011-05-03 02:49 | 2011-05-03 07:49 | ArrayCableInstallation | 487 | 487 | 1
Turbine Assembly Line 1 | Delay | 30 | 0 | 11717.8791 | 2011-05-04 05:53 | 2011-05-05 11:53 | MooredSubInstallation | 488 | 489 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 11741.8791 | 2011-05-05 05:53 | 2011-05-06 05:53 | MooredSubInstallation | 489 | 490 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 426.5825 | 533228.0655 | 11741.8791 | 2011-05-05 05:53 | 2011-05-23 00:28 | MooredSubInstallation | 489 | 507 | 19
Towing Group 1 | Delay | 1 | 2500 | 11742.8791 | 2011-05-05 06:53 | 2011-05-05 07:53 | MooredSubInstallation | 489 | 489 | 1
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 11748.8791 | 2011-05-05 12:53 | 2011-05-05 18:53 | MooredSubInstallation | 489 | 489 | 1
Array Cable Installation Vessel | Delay | 64 | 320000 | 11754.8122 | 2011-05-05 18:49 | 2011-05-08 10:49 | ArrayCableInstallation | 489 | 492 | 4
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 11755.0719 | 2011-05-05 19:04 | 2011-05-06 01:16 | MooredSubInstallation | 489 | 490 | 2
Multi-Purpose Support Vessel | Delay | 140 | 583333.3333 | 11755.0719 | 2011-05-05 19:04 | 2011-05-11 15:04 | MooredSubInstallation | 489 | 495 | 7
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 11757.0719 | 2011-05-05 21:04 | 2011-05-05 23:04 | MooredSubInstallation | 489 | 489 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 4.991 | 24954.8442 | 11759.8032 | 2011-05-05 23:48 | 2011-05-06 04:48 | ArrayCableInstallation | 489 | 490 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11760.8032 | 2011-05-06 00:48 | 2011-05-06 01:48 | ArrayCableInstallation | 490 | 490 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 11763.0719 | 2011-05-06 03:04 | 2011-05-06 09:04 | MooredSubInstallation | 490 | 490 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11766.3032 | 2011-05-06 06:18 | 2011-05-06 11:48 | ArrayCableInstallation | 490 | 490 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11771.8032 | 2011-05-06 11:48 | 2011-05-06 17:18 | ArrayCableInstallation | 490 | 490 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 11773.8032 | 2011-05-06 13:48 | 2011-05-06 15:48 | ArrayCableInstallation | 490 | 490 | 1
Array Cable Installation Vessel | Delay | 5 | 25000 | 11778.8032 | 2011-05-06 18:48 | 2011-05-06 23:48 | ArrayCableInstallation | 490 | 490 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11779.8032 | 2011-05-06 19:48 | 2011-05-06 20:48 | ArrayCableInstallation | 490 | 490 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 11783.0719 | 2011-05-06 23:04 | 2011-05-07 19:04 | MooredSubInstallation | 490 | 491 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11785.3032 | 2011-05-07 01:18 | 2011-05-07 06:48 | ArrayCableInstallation | 491 | 491 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 11786.3791 | 2011-05-07 02:23 | 2011-05-14 02:23 | MooredSubInstallation | 491 | 498 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 44.5 | 0 | 11786.3791 | 2011-05-07 02:23 | 2011-05-08 22:53 | MooredSubInstallation | 491 | 492 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 11789.0719 | 2011-05-07 05:04 | 2011-05-07 11:04 | MooredSubInstallation | 491 | 491 | 1
Towing Group 1 | Positioning Support | 34 | 42500 | 11789.0719 | 2011-05-07 05:04 | 2011-05-08 15:04 | MooredSubInstallation | 491 | 492 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11790.8032 | 2011-05-07 06:48 | 2011-05-07 12:18 | ArrayCableInstallation | 491 | 491 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 11791.8032 | 2011-05-07 07:48 | 2011-05-07 08:48 | ArrayCableInstallation | 491 | 491 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 11794.3791 | 2011-05-07 10:23 | 2011-05-07 18:23 | MooredSubInstallation | 491 | 491 | 1
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 11796.2967 | 2011-05-07 12:18 | 2011-05-07 19:31 | MooredSubInstallation | 491 | 491 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 11801.7942 | 2011-05-07 17:48 | 2011-05-08 03:47 | ArrayCableInstallation | 491 | 492 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11802.7942 | 2011-05-07 18:48 | 2011-05-07 19:48 | ArrayCableInstallation | 491 | 491 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 11806.3791 | 2011-05-07 22:23 | 2011-05-08 10:23 | MooredSubInstallation | 491 | 492 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11808.2942 | 2011-05-08 00:18 | 2011-05-08 05:48 | ArrayCableInstallation | 492 | 492 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11813.7942 | 2011-05-08 05:48 | 2011-05-08 11:18 | ArrayCableInstallation | 492 | 492 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 11815.7942 | 2011-05-08 07:48 | 2011-05-08 09:48 | ArrayCableInstallation | 492 | 492 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11816.7942 | 2011-05-08 08:48 | 2011-05-08 09:48 | ArrayCableInstallation | 492 | 492 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 11818.3791 | 2011-05-08 10:23 | 2011-05-08 22:23 | MooredSubInstallation | 492 | 492 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11822.2942 | 2011-05-08 14:18 | 2011-05-08 19:48 | ArrayCableInstallation | 492 | 492 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11827.7942 | 2011-05-08 19:48 | 2011-05-09 01:18 | ArrayCableInstallation | 492 | 493 | 2
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 11828.7942 | 2011-05-08 20:48 | 2011-05-08 21:48 | ArrayCableInstallation | 492 | 492 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 11830.3791 | 2011-05-08 22:23 | 2011-05-09 10:23 | MooredSubInstallation | 492 | 493 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 5 | 25000 | 11833.7942 | 2011-05-09 01:48 | 2011-05-09 06:48 | ArrayCableInstallation | 493 | 493 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 11837.3791 | 2011-05-09 05:23 | 2011-05-09 12:23 | MooredSubInstallation | 493 | 493 | 1
Turbine Assembly Line 1 | Delay | 43 | 0 | 11880.3791 | 2011-05-11 00:23 | 2011-05-12 19:23 | MooredSubInstallation | 495 | 496 | 2
Array Cable Installation Vessel | Delay | 49 | 245000 | 11882.7942 | 2011-05-11 02:48 | 2011-05-13 03:48 | ArrayCableInstallation | 495 | 497 | 3
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11883.8791 | 2011-05-11 03:53 | 2011-05-11 07:23 | MooredSubInstallation | 495 | 495 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11887.3791 | 2011-05-11 07:23 | 2011-05-11 10:53 | MooredSubInstallation | 495 | 495 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 4.991 | 24954.8442 | 11887.7852 | 2011-05-11 07:47 | 2011-05-11 12:47 | ArrayCableInstallation | 495 | 495 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11888.7852 | 2011-05-11 08:47 | 2011-05-11 09:47 | ArrayCableInstallation | 495 | 495 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 11890.8791 | 2011-05-11 10:53 | 2011-05-11 14:23 | MooredSubInstallation | 495 | 495 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11894.2852 | 2011-05-11 14:17 | 2011-05-11 19:47 | ArrayCableInstallation | 495 | 495 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11899.7852 | 2011-05-11 19:47 | 2011-05-12 01:17 | ArrayCableInstallation | 495 | 496 | 2
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 11901.7852 | 2011-05-11 21:47 | 2011-05-11 23:47 | ArrayCableInstallation | 495 | 495 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11902.7852 | 2011-05-11 22:47 | 2011-05-11 23:47 | ArrayCableInstallation | 495 | 495 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11908.2852 | 2011-05-12 04:17 | 2011-05-12 09:47 | ArrayCableInstallation | 496 | 496 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11913.7852 | 2011-05-12 09:47 | 2011-05-12 15:17 | ArrayCableInstallation | 496 | 496 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 11914.7852 | 2011-05-12 10:47 | 2011-05-12 11:47 | ArrayCableInstallation | 496 | 496 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 11914.8791 | 2011-05-12 10:53 | 2011-05-13 10:53 | MooredSubInstallation | 496 | 497 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 491.5825 | 614478.0655 | 11914.8791 | 2011-05-12 10:53 | 2011-06-01 22:28 | MooredSubInstallation | 496 | 516 | 21
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 11920.8791 | 2011-05-12 16:53 | 2011-05-12 22:53 | MooredSubInstallation | 496 | 496 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 11924.7761 | 2011-05-12 20:47 | 2011-05-13 06:46 | ArrayCableInstallation | 496 | 497 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11925.7761 | 2011-05-12 21:47 | 2011-05-12 22:47 | ArrayCableInstallation | 496 | 496 | 1
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 11927.0719 | 2011-05-12 23:04 | 2011-05-13 05:16 | MooredSubInstallation | 496 | 497 | 2
Multi-Purpose Support Vessel | Delay | 138 | 575000 | 11927.0719 | 2011-05-12 23:04 | 2011-05-18 17:04 | MooredSubInstallation | 496 | 502 | 7
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 11929.0719 | 2011-05-13 01:04 | 2011-05-13 03:04 | MooredSubInstallation | 497 | 497 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11931.2761 | 2011-05-13 03:17 | 2011-05-13 08:47 | ArrayCableInstallation | 497 | 497 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 11935.0719 | 2011-05-13 07:04 | 2011-05-13 13:04 | MooredSubInstallation | 497 | 497 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 16666.6667 | 11939.0719 | 2011-05-13 11:04 | 2011-05-13 15:04 | MooredSubInstallation | 497 | 497 | 1
Multi-Purpose Support Vessel | Delay | 14 | 58333.3333 | 11953.0719 | 2011-05-14 01:04 | 2011-05-14 15:04 | MooredSubInstallation | 498 | 498 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 11954.3791 | 2011-05-14 02:23 | 2011-05-21 02:23 | MooredSubInstallation | 498 | 505 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 39.5 | 0 | 11954.3791 | 2011-05-14 02:23 | 2011-05-15 17:53 | MooredSubInstallation | 498 | 499 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 25000 | 11959.0719 | 2011-05-14 07:04 | 2011-05-14 13:04 | MooredSubInstallation | 498 | 498 | 1
Multi-Purpose Support Vessel | Delay | 1 | 4166.6667 | 11960.0719 | 2011-05-14 08:04 | 2011-05-14 09:04 | MooredSubInstallation | 498 | 498 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 11962.3791 | 2011-05-14 10:23 | 2011-05-14 18:23 | MooredSubInstallation | 498 | 498 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 10 | 41666.6667 | 11970.0719 | 2011-05-14 18:04 | 2011-05-15 04:04 | MooredSubInstallation | 498 | 499 | 2
Array Cable Installation Vessel | Delay | 42 | 210000 | 11973.2761 | 2011-05-14 21:17 | 2011-05-16 15:17 | ArrayCableInstallation | 498 | 500 | 3
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 11974.3791 | 2011-05-14 22:23 | 2011-05-15 10:23 | MooredSubInstallation | 498 | 499 | 2
Towing Group 2 | Positioning Support | 49 | 61250 | 11976.0719 | 2011-05-15 00:04 | 2011-05-15 06:04 | MooredSubInstallation | 499 | 499 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 11976.0719 | 2011-05-15 00:04 | 2011-05-17 01:04 | MooredSubInstallation | 499 | 501 | 3
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11978.7761 | 2011-05-15 02:47 | 2011-05-15 08:17 | ArrayCableInstallation | 499 | 499 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 11980.7761 | 2011-05-15 04:47 | 2011-05-15 06:47 | ArrayCableInstallation | 499 | 499 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 11981.7761 | 2011-05-15 05:47 | 2011-05-15 06:47 | ArrayCableInstallation | 499 | 499 | 1
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 11983.2967 | 2011-05-15 07:18 | 2011-05-15 14:31 | MooredSubInstallation | 499 | 499 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 11986.3791 | 2011-05-15 10:23 | 2011-05-15 22:23 | MooredSubInstallation | 499 | 499 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 11987.2761 | 2011-05-15 11:17 | 2011-05-15 16:47 | ArrayCableInstallation | 499 | 499 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 11992.7761 | 2011-05-15 16:47 | 2011-05-15 22:17 | ArrayCableInstallation | 499 | 499 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 11993.7761 | 2011-05-15 17:47 | 2011-05-15 18:47 | ArrayCableInstallation | 499 | 499 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 11998.3791 | 2011-05-15 22:23 | 2011-05-16 10:23 | MooredSubInstallation | 499 | 500 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 12003.7671 | 2011-05-16 03:46 | 2011-05-16 13:45 | ArrayCableInstallation | 500 | 500 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12004.7671 | 2011-05-16 04:46 | 2011-05-16 05:46 | ArrayCableInstallation | 500 | 500 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 12005.3791 | 2011-05-16 05:23 | 2011-05-16 12:23 | MooredSubInstallation | 500 | 500 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 12008.8791 | 2011-05-16 08:53 | 2011-05-16 12:23 | MooredSubInstallation | 500 | 500 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12010.2671 | 2011-05-16 10:16 | 2011-05-16 15:46 | ArrayCableInstallation | 500 | 500 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 12012.3791 | 2011-05-16 12:23 | 2011-05-16 15:53 | MooredSubInstallation | 500 | 500 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12015.7671 | 2011-05-16 15:46 | 2011-05-16 21:16 | ArrayCableInstallation | 500 | 500 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 12015.8791 | 2011-05-16 15:53 | 2011-05-16 19:23 | MooredSubInstallation | 500 | 500 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 12017.7671 | 2011-05-16 17:46 | 2011-05-16 19:46 | ArrayCableInstallation | 500 | 500 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12018.7671 | 2011-05-16 18:46 | 2011-05-16 19:46 | ArrayCableInstallation | 500 | 500 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12024.2671 | 2011-05-17 00:16 | 2011-05-17 05:46 | ArrayCableInstallation | 501 | 501 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12029.7671 | 2011-05-17 05:46 | 2011-05-17 11:16 | ArrayCableInstallation | 501 | 501 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 12030.7671 | 2011-05-17 06:46 | 2011-05-17 07:46 | ArrayCableInstallation | 501 | 501 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 12039.8791 | 2011-05-17 15:53 | 2011-05-18 15:53 | MooredSubInstallation | 501 | 502 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 417.5825 | 521978.0655 | 12039.8791 | 2011-05-17 15:53 | 2011-06-04 01:28 | MooredSubInstallation | 501 | 519 | 19
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 12040.7581 | 2011-05-17 16:45 | 2011-05-18 02:45 | ArrayCableInstallation | 501 | 502 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12041.7581 | 2011-05-17 17:45 | 2011-05-17 18:45 | ArrayCableInstallation | 501 | 501 | 1
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 12045.8791 | 2011-05-17 21:53 | 2011-05-18 03:53 | MooredSubInstallation | 501 | 502 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12047.2581 | 2011-05-17 23:15 | 2011-05-18 04:45 | ArrayCableInstallation | 501 | 502 | 2
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 12052.0719 | 2011-05-18 04:04 | 2011-05-18 10:16 | MooredSubInstallation | 502 | 502 | 1
Multi-Purpose Support Vessel | Delay | 76 | 316666.6667 | 12052.0719 | 2011-05-18 04:04 | 2011-05-21 08:04 | MooredSubInstallation | 502 | 505 | 4
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12052.7581 | 2011-05-18 04:45 | 2011-05-18 10:15 | ArrayCableInstallation | 502 | 502 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 12054.0719 | 2011-05-18 06:04 | 2011-05-18 08:04 | MooredSubInstallation | 502 | 502 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 12054.7581 | 2011-05-18 06:45 | 2011-05-18 08:45 | ArrayCableInstallation | 502 | 502 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12055.7581 | 2011-05-18 07:45 | 2011-05-18 08:45 | ArrayCableInstallation | 502 | 502 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 12060.0719 | 2011-05-18 12:04 | 2011-05-18 18:04 | MooredSubInstallation | 502 | 502 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 45833.3333 | 12071.0719 | 2011-05-18 23:04 | 2011-05-19 10:04 | MooredSubInstallation | 502 | 503 | 2
Multi-Purpose Support Vessel | Delay | 37 | 154166.6667 | 12108.0719 | 2011-05-20 12:04 | 2011-05-22 01:04 | MooredSubInstallation | 504 | 506 | 3
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 37500 | 12117.0719 | 2011-05-20 21:04 | 2011-05-21 06:04 | MooredSubInstallation | 504 | 505 | 2
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 12122.3791 | 2011-05-21 02:23 | 2011-05-28 02:23 | MooredSubInstallation | 505 | 512 | 8
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 12122.3791 | 2011-05-21 02:23 | 2011-05-24 12:53 | MooredSubInstallation | 505 | 508 | 4
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 12123.0719 | 2011-05-21 03:04 | 2011-05-21 09:04 | MooredSubInstallation | 505 | 505 | 1
Towing Group 3 | Positioning Support | 71 | 88750 | 12123.0719 | 2011-05-21 03:04 | 2011-05-24 02:04 | MooredSubInstallation | 505 | 508 | 4
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 12130.2967 | 2011-05-21 10:18 | 2011-05-21 17:31 | MooredSubInstallation | 505 | 505 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 12130.3791 | 2011-05-21 10:23 | 2011-05-21 18:23 | MooredSubInstallation | 505 | 505 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 12142.3791 | 2011-05-21 22:23 | 2011-05-22 10:23 | MooredSubInstallation | 505 | 506 | 2
Turbine Assembly Line 1 | Delay | 2 | 0 | 12144.3791 | 2011-05-22 00:23 | 2011-05-22 02:23 | MooredSubInstallation | 506 | 506 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 12156.3791 | 2011-05-22 12:23 | 2011-05-23 00:23 | MooredSubInstallation | 506 | 507 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 12168.3791 | 2011-05-23 00:23 | 2011-05-23 12:23 | MooredSubInstallation | 507 | 507 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 12175.3791 | 2011-05-23 07:23 | 2011-05-23 14:23 | MooredSubInstallation | 507 | 507 | 1
Turbine Assembly Line 1 | Delay | 14 | 0 | 12189.3791 | 2011-05-23 21:23 | 2011-05-24 11:23 | MooredSubInstallation | 507 | 508 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 12192.8791 | 2011-05-24 00:53 | 2011-05-24 04:23 | MooredSubInstallation | 508 | 508 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 12196.3791 | 2011-05-24 04:23 | 2011-05-24 07:53 | MooredSubInstallation | 508 | 508 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 12199.8791 | 2011-05-24 07:53 | 2011-05-24 11:23 | MooredSubInstallation | 508 | 508 | 1
Array Cable Installation Vessel | Delay | 157 | 785000 | 12212.7581 | 2011-05-24 20:45 | 2011-05-31 09:45 | ArrayCableInstallation | 508 | 515 | 8
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12218.2581 | 2011-05-25 02:15 | 2011-05-25 07:45 | ArrayCableInstallation | 509 | 509 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 12223.8791 | 2011-05-25 07:53 | 2011-05-26 07:53 | MooredSubInstallation | 509 | 510 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 427.5825 | 534478.0655 | 12223.8791 | 2011-05-25 07:53 | 2011-06-12 03:28 | MooredSubInstallation | 509 | 527 | 19
Towing Group 1 | Delay | 2 | 5000 | 12225.8791 | 2011-05-25 09:53 | 2011-05-25 11:53 | MooredSubInstallation | 509 | 509 | 1
Array Cable Installation Vessel | Delay | 11 | 55000 | 12229.2581 | 2011-05-25 13:15 | 2011-05-26 00:15 | ArrayCableInstallation | 509 | 510 | 2
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 12231.8791 | 2011-05-25 15:53 | 2011-05-25 21:53 | MooredSubInstallation | 509 | 509 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12234.7581 | 2011-05-25 18:45 | 2011-05-26 00:15 | ArrayCableInstallation | 509 | 510 | 2
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 12235.7581 | 2011-05-25 19:45 | 2011-05-25 20:45 | ArrayCableInstallation | 509 | 509 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 12238.0719 | 2011-05-25 22:04 | 2011-05-26 04:16 | MooredSubInstallation | 509 | 510 | 2
Multi-Purpose Support Vessel | Delay | 115 | 479166.6667 | 12238.0719 | 2011-05-25 22:04 | 2011-05-30 17:04 | MooredSubInstallation | 509 | 514 | 6
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 12240.0719 | 2011-05-26 00:04 | 2011-05-26 02:04 | MooredSubInstallation | 510 | 510 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9 | 45000 | 12244.7581 | 2011-05-26 04:45 | 2011-05-26 13:45 | ArrayCableInstallation | 510 | 510 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 12246.0719 | 2011-05-26 06:04 | 2011-05-26 12:04 | MooredSubInstallation | 510 | 510 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 25000 | 12252.0719 | 2011-05-26 12:04 | 2011-05-26 18:04 | MooredSubInstallation | 510 | 510 | 1
Multi-Purpose Support Vessel | Delay | 20 | 83333.3333 | 12272.0719 | 2011-05-27 08:04 | 2011-05-28 04:04 | MooredSubInstallation | 511 | 512 | 2
Array Cable Installation Vessel | Delay | 36 | 180000 | 12280.7581 | 2011-05-27 16:45 | 2011-05-29 04:45 | ArrayCableInstallation | 511 | 513 | 3
Array Cable Installation Vessel | Lay/Bury Cable | 0.99097 | 4954.8442 | 12281.749 | 2011-05-27 17:45 | 2011-05-27 18:44 | ArrayCableInstallation | 511 | 511 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12282.749 | 2011-05-27 18:45 | 2011-05-27 19:45 | ArrayCableInstallation | 511 | 511 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 58333.3333 | 12286.0719 | 2011-05-27 22:04 | 2011-05-28 12:04 | MooredSubInstallation | 511 | 512 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12288.249 | 2011-05-28 00:15 | 2011-05-28 05:45 | ArrayCableInstallation | 512 | 512 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 12290.3791 | 2011-05-28 02:23 | 2011-06-04 02:23 | MooredSubInstallation | 512 | 519 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 66.5 | 0 | 12290.3791 | 2011-05-28 02:23 | 2011-05-30 20:53 | MooredSubInstallation | 512 | 514 | 3
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 12292.0719 | 2011-05-28 04:04 | 2011-05-28 10:04 | MooredSubInstallation | 512 | 512 | 1
Towing Group 1 | Positioning Support | 54 | 67500 | 12292.0719 | 2011-05-28 04:04 | 2011-05-30 10:04 | MooredSubInstallation | 512 | 514 | 3
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12293.749 | 2011-05-28 05:45 | 2011-05-28 11:15 | ArrayCableInstallation | 512 | 512 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 12295.749 | 2011-05-28 07:45 | 2011-05-28 09:45 | ArrayCableInstallation | 512 | 512 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12296.749 | 2011-05-28 08:45 | 2011-05-28 09:45 | ArrayCableInstallation | 512 | 512 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 12298.3791 | 2011-05-28 10:23 | 2011-05-28 18:23 | MooredSubInstallation | 512 | 512 | 1
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 12299.2967 | 2011-05-28 11:18 | 2011-05-28 18:31 | MooredSubInstallation | 512 | 512 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 12310.3791 | 2011-05-28 22:23 | 2011-05-29 10:23 | MooredSubInstallation | 512 | 513 | 2
Turbine Assembly Line 1 | Delay | 18 | 0 | 12328.3791 | 2011-05-29 16:23 | 2011-05-30 10:23 | MooredSubInstallation | 513 | 514 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 12340.3791 | 2011-05-30 04:23 | 2011-05-30 16:23 | MooredSubInstallation | 514 | 514 | 1
Array Cable Installation Vessel | Delay | 51 | 255000 | 12347.749 | 2011-05-30 11:45 | 2011-06-01 14:45 | ArrayCableInstallation | 514 | 516 | 3
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 12352.3791 | 2011-05-30 16:23 | 2011-05-31 04:23 | MooredSubInstallation | 514 | 515 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12353.249 | 2011-05-30 17:15 | 2011-05-30 22:45 | ArrayCableInstallation | 514 | 514 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 12359.3791 | 2011-05-30 23:23 | 2011-05-31 06:23 | MooredSubInstallation | 514 | 515 | 2
Array Cable Installation Vessel | Delay | 7 | 35000 | 12360.249 | 2011-05-31 00:15 | 2011-05-31 07:15 | ArrayCableInstallation | 515 | 515 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 12362.8791 | 2011-05-31 02:53 | 2011-05-31 06:23 | MooredSubInstallation | 515 | 515 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12365.749 | 2011-05-31 05:45 | 2011-05-31 11:15 | ArrayCableInstallation | 515 | 515 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 12366.3791 | 2011-05-31 06:23 | 2011-05-31 09:53 | MooredSubInstallation | 515 | 515 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 12366.749 | 2011-05-31 06:45 | 2011-05-31 07:45 | ArrayCableInstallation | 515 | 515 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 12369.8791 | 2011-05-31 09:53 | 2011-05-31 13:23 | MooredSubInstallation | 515 | 515 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 12393.8791 | 2011-06-01 09:53 | 2011-06-02 09:53 | MooredSubInstallation | 516 | 517 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 410.5825 | 513228.0655 | 12393.8791 | 2011-06-01 09:53 | 2011-06-18 12:28 | MooredSubInstallation | 516 | 533 | 18
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 12399.8791 | 2011-06-01 15:53 | 2011-06-01 21:53 | MooredSubInstallation | 516 | 516 | 1
Array Cable Installation Vessel | Delay | 38 | 190000 | 12404.749 | 2011-06-01 20:45 | 2011-06-03 10:45 | ArrayCableInstallation | 516 | 518 | 3
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 12406.0719 | 2011-06-01 22:04 | 2011-06-02 04:16 | MooredSubInstallation | 516 | 517 | 2
Multi-Purpose Support Vessel | Delay | 114 | 475000 | 12406.0719 | 2011-06-01 22:04 | 2011-06-06 16:04 | MooredSubInstallation | 516 | 521 | 6
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 12408.0719 | 2011-06-02 00:04 | 2011-06-02 02:04 | MooredSubInstallation | 517 | 517 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 12414.0719 | 2011-06-02 06:04 | 2011-06-02 12:04 | MooredSubInstallation | 517 | 517 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 12414.74 | 2011-06-02 06:44 | 2011-06-02 16:44 | ArrayCableInstallation | 517 | 517 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12415.74 | 2011-06-02 07:44 | 2011-06-02 08:44 | ArrayCableInstallation | 517 | 517 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12421.24 | 2011-06-02 13:14 | 2011-06-02 18:44 | ArrayCableInstallation | 517 | 517 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12426.74 | 2011-06-02 18:44 | 2011-06-03 00:14 | ArrayCableInstallation | 517 | 518 | 2
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 12428.74 | 2011-06-02 20:44 | 2011-06-02 22:44 | ArrayCableInstallation | 517 | 517 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12429.74 | 2011-06-02 21:44 | 2011-06-02 22:44 | ArrayCableInstallation | 517 | 517 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 12434.0719 | 2011-06-03 02:04 | 2011-06-03 22:04 | MooredSubInstallation | 518 | 518 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12435.24 | 2011-06-03 03:14 | 2011-06-03 08:44 | ArrayCableInstallation | 518 | 518 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 12440.0719 | 2011-06-03 08:04 | 2011-06-03 14:04 | MooredSubInstallation | 518 | 518 | 1
Towing Group 2 | Positioning Support | 34 | 42500 | 12440.0719 | 2011-06-03 08:04 | 2011-06-04 18:04 | MooredSubInstallation | 518 | 519 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12440.74 | 2011-06-03 08:44 | 2011-06-03 14:14 | ArrayCableInstallation | 518 | 518 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 12441.74 | 2011-06-03 09:44 | 2011-06-03 10:44 | ArrayCableInstallation | 518 | 518 | 1
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 12447.2967 | 2011-06-03 15:18 | 2011-06-03 22:31 | MooredSubInstallation | 518 | 518 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 12451.731 | 2011-06-03 19:44 | 2011-06-04 05:43 | ArrayCableInstallation | 518 | 519 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12452.731 | 2011-06-03 20:44 | 2011-06-03 21:44 | ArrayCableInstallation | 518 | 518 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12458.231 | 2011-06-04 02:14 | 2011-06-04 07:44 | ArrayCableInstallation | 519 | 519 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 12458.3791 | 2011-06-04 02:23 | 2011-06-11 02:23 | MooredSubInstallation | 519 | 526 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 64.5 | 0 | 12458.3791 | 2011-06-04 02:23 | 2011-06-06 18:53 | MooredSubInstallation | 519 | 521 | 3
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12463.731 | 2011-06-04 07:44 | 2011-06-04 13:14 | ArrayCableInstallation | 519 | 519 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 12465.731 | 2011-06-04 09:44 | 2011-06-04 11:44 | ArrayCableInstallation | 519 | 519 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 12466.3791 | 2011-06-04 10:23 | 2011-06-04 18:23 | MooredSubInstallation | 519 | 519 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12466.731 | 2011-06-04 10:44 | 2011-06-04 11:44 | ArrayCableInstallation | 519 | 519 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12472.231 | 2011-06-04 16:14 | 2011-06-04 21:44 | ArrayCableInstallation | 519 | 519 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12477.731 | 2011-06-04 21:44 | 2011-06-05 03:14 | ArrayCableInstallation | 519 | 520 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 12478.3791 | 2011-06-04 22:23 | 2011-06-05 10:23 | MooredSubInstallation | 519 | 520 | 2
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 12478.731 | 2011-06-04 22:44 | 2011-06-04 23:44 | ArrayCableInstallation | 519 | 519 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 12488.7219 | 2011-06-05 08:43 | 2011-06-05 18:43 | ArrayCableInstallation | 520 | 520 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12489.7219 | 2011-06-05 09:43 | 2011-06-05 10:43 | ArrayCableInstallation | 520 | 520 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 12490.3791 | 2011-06-05 10:23 | 2011-06-05 22:23 | MooredSubInstallation | 520 | 520 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12495.2219 | 2011-06-05 15:13 | 2011-06-05 20:43 | ArrayCableInstallation | 520 | 520 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12500.7219 | 2011-06-05 20:43 | 2011-06-06 02:13 | ArrayCableInstallation | 520 | 521 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 12502.3791 | 2011-06-05 22:23 | 2011-06-06 10:23 | MooredSubInstallation | 520 | 521 | 2
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 12502.7219 | 2011-06-05 22:43 | 2011-06-06 00:43 | ArrayCableInstallation | 520 | 521 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12503.7219 | 2011-06-05 23:43 | 2011-06-06 00:43 | ArrayCableInstallation | 520 | 521 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12509.2219 | 2011-06-06 05:13 | 2011-06-06 10:43 | ArrayCableInstallation | 521 | 521 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 12509.3791 | 2011-06-06 05:23 | 2011-06-06 12:23 | MooredSubInstallation | 521 | 521 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 12512.8791 | 2011-06-06 08:53 | 2011-06-06 12:23 | MooredSubInstallation | 521 | 521 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12514.7219 | 2011-06-06 10:43 | 2011-06-06 16:13 | ArrayCableInstallation | 521 | 521 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 12515.7219 | 2011-06-06 11:43 | 2011-06-06 12:43 | ArrayCableInstallation | 521 | 521 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 12516.3791 | 2011-06-06 12:23 | 2011-06-06 15:53 | MooredSubInstallation | 521 | 521 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 12519.8791 | 2011-06-06 15:53 | 2011-06-06 19:23 | MooredSubInstallation | 521 | 521 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 12525.7129 | 2011-06-06 21:43 | 2011-06-07 07:42 | ArrayCableInstallation | 521 | 522 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12526.7129 | 2011-06-06 22:43 | 2011-06-06 23:43 | ArrayCableInstallation | 521 | 521 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12532.2129 | 2011-06-07 04:13 | 2011-06-07 09:43 | ArrayCableInstallation | 522 | 522 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12537.7129 | 2011-06-07 09:43 | 2011-06-07 15:13 | ArrayCableInstallation | 522 | 522 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 12539.7129 | 2011-06-07 11:43 | 2011-06-07 13:43 | ArrayCableInstallation | 522 | 522 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12540.7129 | 2011-06-07 12:43 | 2011-06-07 13:43 | ArrayCableInstallation | 522 | 522 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 12543.8791 | 2011-06-07 15:53 | 2011-06-08 15:53 | MooredSubInstallation | 522 | 523 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 413.5825 | 516978.0655 | 12543.8791 | 2011-06-07 15:53 | 2011-06-24 21:28 | MooredSubInstallation | 522 | 539 | 18
Towing Group 3 | Delay | 73 | 182500 | 12616.8791 | 2011-06-10 16:53 | 2011-06-13 17:53 | MooredSubInstallation | 525 | 528 | 4
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 12622.8791 | 2011-06-10 22:53 | 2011-06-11 04:53 | MooredSubInstallation | 525 | 526 | 2
Array Cable Installation Vessel | Delay | 84 | 420000 | 12624.7129 | 2011-06-11 00:43 | 2011-06-14 12:43 | ArrayCableInstallation | 526 | 529 | 4
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 12626.3791 | 2011-06-11 02:23 | 2011-06-18 02:23 | MooredSubInstallation | 526 | 533 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 12626.3791 | 2011-06-11 02:23 | 2011-06-14 12:53 | MooredSubInstallation | 526 | 529 | 4
Multi-Purpose Support Vessel | Delay | 189 | 787500 | 12629.0719 | 2011-06-11 05:04 | 2011-06-11 11:16 | MooredSubInstallation | 526 | 526 | 1
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 12629.0719 | 2011-06-11 05:04 | 2011-06-19 02:04 | MooredSubInstallation | 526 | 534 | 9
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12630.2129 | 2011-06-11 06:13 | 2011-06-11 11:43 | ArrayCableInstallation | 526 | 526 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 12631.0719 | 2011-06-11 07:04 | 2011-06-11 09:04 | MooredSubInstallation | 526 | 526 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 12634.3791 | 2011-06-11 10:23 | 2011-06-11 18:23 | MooredSubInstallation | 526 | 526 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12635.7129 | 2011-06-11 11:43 | 2011-06-11 17:13 | ArrayCableInstallation | 526 | 526 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 12636.7129 | 2011-06-11 12:43 | 2011-06-11 13:43 | ArrayCableInstallation | 526 | 526 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 12637.0719 | 2011-06-11 13:04 | 2011-06-11 19:04 | MooredSubInstallation | 526 | 526 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 12646.3791 | 2011-06-11 22:23 | 2011-06-12 10:23 | MooredSubInstallation | 526 | 527 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 12646.7039 | 2011-06-11 22:42 | 2011-06-12 08:42 | ArrayCableInstallation | 526 | 527 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12647.7039 | 2011-06-11 23:42 | 2011-06-12 00:42 | ArrayCableInstallation | 526 | 527 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12653.2039 | 2011-06-12 05:12 | 2011-06-12 10:42 | ArrayCableInstallation | 527 | 527 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 12657.0719 | 2011-06-12 09:04 | 2011-06-13 05:04 | MooredSubInstallation | 527 | 528 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 12658.3791 | 2011-06-12 10:23 | 2011-06-12 22:23 | MooredSubInstallation | 527 | 527 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12658.7039 | 2011-06-12 10:42 | 2011-06-12 16:12 | ArrayCableInstallation | 527 | 527 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 12660.7039 | 2011-06-12 12:42 | 2011-06-12 14:42 | ArrayCableInstallation | 527 | 527 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12661.7039 | 2011-06-12 13:42 | 2011-06-12 14:42 | ArrayCableInstallation | 527 | 527 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 12663.0719 | 2011-06-12 15:04 | 2011-06-12 21:04 | MooredSubInstallation | 527 | 527 | 1
Towing Group 3 | Positioning Support | 34 | 42500 | 12663.0719 | 2011-06-12 15:04 | 2011-06-14 01:04 | MooredSubInstallation | 527 | 529 | 3
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12667.2039 | 2011-06-12 19:12 | 2011-06-13 00:42 | ArrayCableInstallation | 527 | 528 | 2
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 12670.2967 | 2011-06-12 22:18 | 2011-06-13 05:31 | MooredSubInstallation | 527 | 528 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 12670.3791 | 2011-06-12 22:23 | 2011-06-13 10:23 | MooredSubInstallation | 527 | 528 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12672.7039 | 2011-06-13 00:42 | 2011-06-13 06:12 | ArrayCableInstallation | 528 | 528 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 12673.7039 | 2011-06-13 01:42 | 2011-06-13 02:42 | ArrayCableInstallation | 528 | 528 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 12677.3791 | 2011-06-13 05:23 | 2011-06-13 12:23 | MooredSubInstallation | 528 | 528 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 12680.8791 | 2011-06-13 08:53 | 2011-06-13 12:23 | MooredSubInstallation | 528 | 528 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 12683.6948 | 2011-06-13 11:42 | 2011-06-13 21:41 | ArrayCableInstallation | 528 | 528 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 12684.3791 | 2011-06-13 12:23 | 2011-06-13 15:53 | MooredSubInstallation | 528 | 528 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12684.6948 | 2011-06-13 12:42 | 2011-06-13 13:42 | ArrayCableInstallation | 528 | 528 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 12687.8791 | 2011-06-13 15:53 | 2011-06-13 19:23 | MooredSubInstallation | 528 | 528 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12690.1948 | 2011-06-13 18:12 | 2011-06-13 23:42 | ArrayCableInstallation | 528 | 528 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12695.6948 | 2011-06-13 23:42 | 2011-06-14 05:12 | ArrayCableInstallation | 528 | 529 | 2
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 12697.6948 | 2011-06-14 01:42 | 2011-06-14 03:42 | ArrayCableInstallation | 529 | 529 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12698.6948 | 2011-06-14 02:42 | 2011-06-14 03:42 | ArrayCableInstallation | 529 | 529 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 12711.8791 | 2011-06-14 15:53 | 2011-06-15 15:53 | MooredSubInstallation | 529 | 530 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 412.5825 | 515728.0655 | 12711.8791 | 2011-06-14 15:53 | 2011-07-01 20:28 | MooredSubInstallation | 529 | 546 | 18
Towing Group 1 | Delay | 67 | 167500 | 12778.8791 | 2011-06-17 10:53 | 2011-06-20 05:53 | MooredSubInstallation | 532 | 535 | 4
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 12784.8791 | 2011-06-17 16:53 | 2011-06-17 22:53 | MooredSubInstallation | 532 | 532 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 12791.0719 | 2011-06-17 23:04 | 2011-06-18 05:16 | MooredSubInstallation | 532 | 533 | 2
Multi-Purpose Support Vessel | Delay | 128 | 533333.3333 | 12791.0719 | 2011-06-17 23:04 | 2011-06-23 07:04 | MooredSubInstallation | 532 | 538 | 7
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 12793.0719 | 2011-06-18 01:04 | 2011-06-18 03:04 | MooredSubInstallation | 533 | 533 | 1
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 12794.3791 | 2011-06-18 02:23 | 2011-06-25 02:23 | MooredSubInstallation | 533 | 540 | 8
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 12794.3791 | 2011-06-18 02:23 | 2011-06-21 12:53 | MooredSubInstallation | 533 | 536 | 4
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 12799.0719 | 2011-06-18 07:04 | 2011-06-18 13:04 | MooredSubInstallation | 533 | 533 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 12802.3791 | 2011-06-18 10:23 | 2011-06-18 18:23 | MooredSubInstallation | 533 | 533 | 1
Array Cable Installation Vessel | Delay | 107 | 535000 | 12805.6948 | 2011-06-18 13:42 | 2011-06-23 00:42 | ArrayCableInstallation | 533 | 538 | 6
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12811.1948 | 2011-06-18 19:12 | 2011-06-19 00:42 | ArrayCableInstallation | 533 | 534 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 12814.3791 | 2011-06-18 22:23 | 2011-06-19 10:23 | MooredSubInstallation | 533 | 534 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12816.6948 | 2011-06-19 00:42 | 2011-06-19 06:12 | ArrayCableInstallation | 534 | 534 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 12817.6948 | 2011-06-19 01:42 | 2011-06-19 02:42 | ArrayCableInstallation | 534 | 534 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 12819.0719 | 2011-06-19 03:04 | 2011-06-19 23:04 | MooredSubInstallation | 534 | 534 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | 12821.6948 | 2011-06-19 05:42 | 2011-06-19 09:42 | ArrayCableInstallation | 534 | 534 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 3 | 12500 | 12822.0719 | 2011-06-19 06:04 | 2011-06-19 09:04 | MooredSubInstallation | 534 | 534 | 1
Multi-Purpose Support Vessel | Delay | 18 | 75000 | 12840.0719 | 2011-06-20 00:04 | 2011-06-20 18:04 | MooredSubInstallation | 535 | 535 | 1
Turbine Assembly Line 1 | Delay | 26 | 0 | 12840.3791 | 2011-06-20 00:23 | 2011-06-21 02:23 | MooredSubInstallation | 535 | 536 | 2
Towing Group 1 | Positioning Support | 52 | 65000 | 12843.0719 | 2011-06-20 03:04 | 2011-06-20 06:04 | MooredSubInstallation | 535 | 535 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 3 | 12500 | 12843.0719 | 2011-06-20 03:04 | 2011-06-22 07:04 | MooredSubInstallation | 535 | 537 | 3
Array Cable Installation Vessel | Delay | 26 | 130000 | 12847.6948 | 2011-06-20 07:42 | 2011-06-21 09:42 | ArrayCableInstallation | 535 | 536 | 2
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 12850.2967 | 2011-06-20 10:18 | 2011-06-20 17:31 | MooredSubInstallation | 535 | 535 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 12852.3791 | 2011-06-20 12:23 | 2011-06-21 00:23 | MooredSubInstallation | 535 | 536 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 5.991 | 29954.8442 | 12853.6858 | 2011-06-20 13:41 | 2011-06-20 19:41 | ArrayCableInstallation | 535 | 535 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12854.6858 | 2011-06-20 14:41 | 2011-06-20 15:41 | ArrayCableInstallation | 535 | 535 | 1
Turbine Assembly Line 1 | Delay | 32 | 0 | 12884.3791 | 2011-06-21 20:23 | 2011-06-23 04:23 | MooredSubInstallation | 536 | 538 | 3
Array Cable Installation Vessel | Delay | 40 | 200000 | 12894.6858 | 2011-06-22 06:41 | 2011-06-23 22:41 | ArrayCableInstallation | 537 | 538 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 12896.3791 | 2011-06-22 08:23 | 2011-06-22 20:23 | MooredSubInstallation | 537 | 537 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12900.1858 | 2011-06-22 12:11 | 2011-06-22 17:41 | ArrayCableInstallation | 537 | 537 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 12903.3791 | 2011-06-22 15:23 | 2011-06-22 22:23 | MooredSubInstallation | 537 | 537 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12905.6858 | 2011-06-22 17:41 | 2011-06-22 23:11 | ArrayCableInstallation | 537 | 537 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 12907.6858 | 2011-06-22 19:41 | 2011-06-22 21:41 | ArrayCableInstallation | 537 | 537 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 12908.6858 | 2011-06-22 20:41 | 2011-06-22 21:41 | ArrayCableInstallation | 537 | 537 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 12962.3791 | 2011-06-25 02:23 | 2011-07-02 02:23 | MooredSubInstallation | 540 | 547 | 8
Array Cable Installation Vessel | Delay | 80 | 400000 | 12988.6858 | 2011-06-26 04:41 | 2011-06-29 12:41 | ArrayCableInstallation | 541 | 544 | 4
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 12994.1858 | 2011-06-26 10:11 | 2011-06-26 15:41 | ArrayCableInstallation | 541 | 541 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 12999.6858 | 2011-06-26 15:41 | 2011-06-26 21:11 | ArrayCableInstallation | 541 | 541 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 13000.6858 | 2011-06-26 16:41 | 2011-06-26 17:41 | ArrayCableInstallation | 541 | 541 | 1
Turbine Assembly Line 1 | Delay | 99 | 0 | 13002.3791 | 2011-06-26 18:23 | 2011-06-30 21:23 | MooredSubInstallation | 541 | 545 | 5
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13005.8791 | 2011-06-26 21:53 | 2011-06-27 01:23 | MooredSubInstallation | 541 | 542 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13009.3791 | 2011-06-27 01:23 | 2011-06-27 04:53 | MooredSubInstallation | 542 | 542 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 13010.6768 | 2011-06-27 02:41 | 2011-06-27 12:40 | ArrayCableInstallation | 542 | 542 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13011.6768 | 2011-06-27 03:41 | 2011-06-27 04:41 | ArrayCableInstallation | 542 | 542 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13012.8791 | 2011-06-27 04:53 | 2011-06-27 08:23 | MooredSubInstallation | 542 | 542 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13017.1768 | 2011-06-27 09:11 | 2011-06-27 14:41 | ArrayCableInstallation | 542 | 542 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13022.6768 | 2011-06-27 14:41 | 2011-06-27 20:11 | ArrayCableInstallation | 542 | 542 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 13024.6768 | 2011-06-27 16:41 | 2011-06-27 18:41 | ArrayCableInstallation | 542 | 542 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13025.6768 | 2011-06-27 17:41 | 2011-06-27 18:41 | ArrayCableInstallation | 542 | 542 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13031.1768 | 2011-06-27 23:11 | 2011-06-28 04:41 | ArrayCableInstallation | 542 | 543 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13036.6768 | 2011-06-28 04:41 | 2011-06-28 10:11 | ArrayCableInstallation | 543 | 543 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 13036.8791 | 2011-06-28 04:53 | 2011-06-29 04:53 | MooredSubInstallation | 543 | 544 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 589.5825 | 736978.0655 | 13036.8791 | 2011-06-28 04:53 | 2011-07-22 18:28 | MooredSubInstallation | 543 | 567 | 25
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 13037.6768 | 2011-06-28 05:41 | 2011-06-28 06:41 | ArrayCableInstallation | 543 | 543 | 1
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 13042.8791 | 2011-06-28 10:53 | 2011-06-28 16:53 | MooredSubInstallation | 543 | 543 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 13044.8791 | 2011-06-28 12:53 | 2011-06-28 20:53 | MooredSubInstallation | 543 | 543 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 13047.6677 | 2011-06-28 15:40 | 2011-06-29 01:40 | ArrayCableInstallation | 543 | 544 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13048.6677 | 2011-06-28 16:40 | 2011-06-28 17:40 | ArrayCableInstallation | 543 | 543 | 1
Multi-Purpose Support Vessel | Delay | 206 | 858333.3333 | 13049.0719 | 2011-06-28 17:04 | 2011-06-28 23:16 | MooredSubInstallation | 543 | 543 | 1
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 13049.0719 | 2011-06-28 17:04 | 2011-07-07 07:04 | MooredSubInstallation | 543 | 552 | 10
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 13051.0719 | 2011-06-28 19:04 | 2011-06-28 21:04 | MooredSubInstallation | 543 | 543 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13054.1677 | 2011-06-28 22:10 | 2011-06-29 03:40 | ArrayCableInstallation | 543 | 544 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 13056.8791 | 2011-06-29 00:53 | 2011-06-29 12:53 | MooredSubInstallation | 544 | 544 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 13057.0719 | 2011-06-29 01:04 | 2011-06-29 07:04 | MooredSubInstallation | 544 | 544 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13059.6677 | 2011-06-29 03:40 | 2011-06-29 09:10 | ArrayCableInstallation | 544 | 544 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 13061.6677 | 2011-06-29 05:40 | 2011-06-29 07:40 | ArrayCableInstallation | 544 | 544 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13062.6677 | 2011-06-29 06:40 | 2011-06-29 07:40 | ArrayCableInstallation | 544 | 544 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13068.1677 | 2011-06-29 12:10 | 2011-06-29 17:40 | ArrayCableInstallation | 544 | 544 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 13068.8791 | 2011-06-29 12:53 | 2011-06-30 00:53 | MooredSubInstallation | 544 | 545 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13073.6677 | 2011-06-29 17:40 | 2011-06-29 23:10 | ArrayCableInstallation | 544 | 544 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 13074.6677 | 2011-06-29 18:40 | 2011-06-29 19:40 | ArrayCableInstallation | 544 | 544 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 13077.0719 | 2011-06-29 21:04 | 2011-06-30 17:04 | MooredSubInstallation | 544 | 545 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 13080.8791 | 2011-06-30 00:53 | 2011-06-30 12:53 | MooredSubInstallation | 545 | 545 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 13083.0719 | 2011-06-30 03:04 | 2011-06-30 09:04 | MooredSubInstallation | 545 | 545 | 1
Towing Group 2 | Positioning Support | 34 | 42500 | 13083.0719 | 2011-06-30 03:04 | 2011-07-01 13:04 | MooredSubInstallation | 545 | 546 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 13084.6587 | 2011-06-30 04:40 | 2011-06-30 14:39 | ArrayCableInstallation | 545 | 545 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13085.6587 | 2011-06-30 05:40 | 2011-06-30 06:40 | ArrayCableInstallation | 545 | 545 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 13087.8791 | 2011-06-30 07:53 | 2011-06-30 14:53 | MooredSubInstallation | 545 | 545 | 1
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 13090.2967 | 2011-06-30 10:18 | 2011-06-30 17:31 | MooredSubInstallation | 545 | 545 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13091.1587 | 2011-06-30 11:10 | 2011-06-30 16:40 | ArrayCableInstallation | 545 | 545 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13091.3791 | 2011-06-30 11:23 | 2011-06-30 14:53 | MooredSubInstallation | 545 | 545 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13094.8791 | 2011-06-30 14:53 | 2011-06-30 18:23 | MooredSubInstallation | 545 | 545 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13096.6587 | 2011-06-30 16:40 | 2011-06-30 22:10 | ArrayCableInstallation | 545 | 545 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13098.3791 | 2011-06-30 18:23 | 2011-06-30 21:53 | MooredSubInstallation | 545 | 545 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 13098.6587 | 2011-06-30 18:40 | 2011-06-30 20:40 | ArrayCableInstallation | 545 | 545 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13099.6587 | 2011-06-30 19:40 | 2011-06-30 20:40 | ArrayCableInstallation | 545 | 545 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 13122.3791 | 2011-07-01 18:23 | 2011-07-02 18:23 | MooredSubInstallation | 546 | 547 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 452.0825 | 565103.0655 | 13122.3791 | 2011-07-01 18:23 | 2011-07-20 14:28 | MooredSubInstallation | 546 | 565 | 20
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 13130.3791 | 2011-07-02 02:23 | 2011-07-09 02:23 | MooredSubInstallation | 547 | 554 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 8 | 0 | 13130.3791 | 2011-07-02 02:23 | 2011-07-02 10:23 | MooredSubInstallation | 547 | 547 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 13138.3791 | 2011-07-02 10:23 | 2011-07-02 18:23 | MooredSubInstallation | 547 | 547 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 13150.3791 | 2011-07-02 22:23 | 2011-07-03 10:23 | MooredSubInstallation | 547 | 548 | 2
Towing Group 3 | Delay | 29 | 72500 | 13151.3791 | 2011-07-02 23:23 | 2011-07-04 04:23 | MooredSubInstallation | 547 | 549 | 3
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 13157.3791 | 2011-07-03 05:23 | 2011-07-03 11:23 | MooredSubInstallation | 548 | 548 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 13162.3791 | 2011-07-03 10:23 | 2011-07-03 22:23 | MooredSubInstallation | 548 | 548 | 1
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 13163.5719 | 2011-07-03 11:34 | 2011-07-03 17:46 | MooredSubInstallation | 548 | 548 | 1
Multi-Purpose Support Vessel | Delay | 80.5 | 335416.6667 | 13163.5719 | 2011-07-03 11:34 | 2011-07-06 20:04 | MooredSubInstallation | 548 | 551 | 4
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 13165.5719 | 2011-07-03 13:34 | 2011-07-03 15:34 | MooredSubInstallation | 548 | 548 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 13171.5719 | 2011-07-03 19:34 | 2011-07-04 01:34 | MooredSubInstallation | 548 | 549 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 13174.3791 | 2011-07-03 22:23 | 2011-07-04 10:23 | MooredSubInstallation | 548 | 549 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 13181.3791 | 2011-07-04 05:23 | 2011-07-04 12:23 | MooredSubInstallation | 549 | 549 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 62500 | 13186.5719 | 2011-07-04 10:34 | 2011-07-05 01:34 | MooredSubInstallation | 549 | 550 | 2
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 13298.3791 | 2011-07-09 02:23 | 2011-07-16 02:23 | MooredSubInstallation | 554 | 561 | 8
Multi-Purpose Support Vessel | Delay | 141 | 587500 | 13327.5719 | 2011-07-10 07:34 | 2011-07-16 04:34 | MooredSubInstallation | 555 | 561 | 7
Array Cable Installation Vessel | Delay | 231 | 1155000 | 13330.6587 | 2011-07-10 10:40 | 2011-07-20 01:40 | ArrayCableInstallation | 555 | 565 | 11
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 20833.3333 | 13332.5719 | 2011-07-10 12:34 | 2011-07-10 17:34 | MooredSubInstallation | 555 | 555 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13336.1587 | 2011-07-10 16:10 | 2011-07-10 21:40 | ArrayCableInstallation | 555 | 555 | 1
Turbine Assembly Line 1 | Delay | 155 | 0 | 13336.3791 | 2011-07-10 16:23 | 2011-07-17 03:23 | MooredSubInstallation | 555 | 562 | 8
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 13338.5719 | 2011-07-10 18:34 | 2011-07-11 00:34 | MooredSubInstallation | 555 | 556 | 2
Towing Group 3 | Positioning Support | 175 | 218750 | 13338.5719 | 2011-07-10 18:34 | 2011-07-18 01:34 | MooredSubInstallation | 555 | 563 | 9
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13339.8791 | 2011-07-10 19:53 | 2011-07-10 23:23 | MooredSubInstallation | 555 | 555 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13341.6587 | 2011-07-10 21:40 | 2011-07-11 03:10 | ArrayCableInstallation | 555 | 556 | 2
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 13342.6587 | 2011-07-10 22:40 | 2011-07-10 23:40 | ArrayCableInstallation | 555 | 555 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13343.3791 | 2011-07-10 23:23 | 2011-07-11 02:53 | MooredSubInstallation | 555 | 556 | 2
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 13345.7967 | 2011-07-11 01:48 | 2011-07-11 09:01 | MooredSubInstallation | 556 | 556 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13346.8791 | 2011-07-11 02:53 | 2011-07-11 06:23 | MooredSubInstallation | 556 | 556 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 13352.6497 | 2011-07-11 08:39 | 2011-07-11 18:38 | ArrayCableInstallation | 556 | 556 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13353.6497 | 2011-07-11 09:39 | 2011-07-11 10:39 | ArrayCableInstallation | 556 | 556 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13359.1497 | 2011-07-11 15:09 | 2011-07-11 20:39 | ArrayCableInstallation | 556 | 556 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13364.6497 | 2011-07-11 20:39 | 2011-07-12 02:09 | ArrayCableInstallation | 556 | 557 | 2
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 13366.6497 | 2011-07-11 22:39 | 2011-07-12 00:39 | ArrayCableInstallation | 556 | 557 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13367.6497 | 2011-07-11 23:39 | 2011-07-12 00:39 | ArrayCableInstallation | 556 | 557 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 13370.8791 | 2011-07-12 02:53 | 2011-07-13 02:53 | MooredSubInstallation | 557 | 558 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 520.5825 | 650728.0655 | 13370.8791 | 2011-07-12 02:53 | 2011-08-02 19:28 | MooredSubInstallation | 557 | 578 | 22
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13373.1497 | 2011-07-12 05:09 | 2011-07-12 10:39 | ArrayCableInstallation | 557 | 557 | 1
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 13376.8791 | 2011-07-12 08:53 | 2011-07-12 14:53 | MooredSubInstallation | 557 | 557 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13378.6497 | 2011-07-12 10:39 | 2011-07-12 16:09 | ArrayCableInstallation | 557 | 557 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 13378.8791 | 2011-07-12 10:53 | 2011-07-12 18:53 | MooredSubInstallation | 557 | 557 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 13379.6497 | 2011-07-12 11:39 | 2011-07-12 12:39 | ArrayCableInstallation | 557 | 557 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 13383.0719 | 2011-07-12 15:04 | 2011-07-12 21:16 | MooredSubInstallation | 557 | 557 | 1
Multi-Purpose Support Vessel | Delay | 44.5 | 185416.6667 | 13383.0719 | 2011-07-12 15:04 | 2011-07-14 11:34 | MooredSubInstallation | 557 | 559 | 3
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 13385.0719 | 2011-07-12 17:04 | 2011-07-12 19:04 | MooredSubInstallation | 557 | 557 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 13389.6407 | 2011-07-12 21:38 | 2011-07-13 07:38 | ArrayCableInstallation | 557 | 558 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13390.6407 | 2011-07-12 22:38 | 2011-07-12 23:38 | ArrayCableInstallation | 557 | 557 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 13390.8791 | 2011-07-12 22:53 | 2011-07-13 10:53 | MooredSubInstallation | 557 | 558 | 2
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 13391.0719 | 2011-07-12 23:04 | 2011-07-13 05:04 | MooredSubInstallation | 557 | 558 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13396.1407 | 2011-07-13 04:08 | 2011-07-13 09:38 | ArrayCableInstallation | 558 | 558 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13401.6407 | 2011-07-13 09:38 | 2011-07-13 15:08 | ArrayCableInstallation | 558 | 558 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 13402.8791 | 2011-07-13 10:53 | 2011-07-13 22:53 | MooredSubInstallation | 558 | 558 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 13403.6407 | 2011-07-13 11:38 | 2011-07-13 13:38 | ArrayCableInstallation | 558 | 558 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13404.6407 | 2011-07-13 12:38 | 2011-07-13 13:38 | ArrayCableInstallation | 558 | 558 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13410.1407 | 2011-07-13 18:08 | 2011-07-13 23:38 | ArrayCableInstallation | 558 | 558 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 13411.0719 | 2011-07-13 19:04 | 2011-07-14 15:04 | MooredSubInstallation | 558 | 559 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 13414.8791 | 2011-07-13 22:53 | 2011-07-14 10:53 | MooredSubInstallation | 558 | 559 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13415.6407 | 2011-07-13 23:38 | 2011-07-14 05:08 | ArrayCableInstallation | 558 | 559 | 2
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 13416.6407 | 2011-07-14 00:38 | 2011-07-14 01:38 | ArrayCableInstallation | 559 | 559 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 13417.0719 | 2011-07-14 01:04 | 2011-07-14 07:04 | MooredSubInstallation | 559 | 559 | 1
Towing Group 1 | Positioning Support | 34 | 42500 | 13417.0719 | 2011-07-14 01:04 | 2011-07-15 11:04 | MooredSubInstallation | 559 | 560 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 13421.8791 | 2011-07-14 05:53 | 2011-07-14 12:53 | MooredSubInstallation | 559 | 559 | 1
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 13424.2967 | 2011-07-14 08:18 | 2011-07-14 15:31 | MooredSubInstallation | 559 | 559 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13425.3791 | 2011-07-14 09:23 | 2011-07-14 12:53 | MooredSubInstallation | 559 | 559 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 13426.6316 | 2011-07-14 10:38 | 2011-07-14 20:37 | ArrayCableInstallation | 559 | 559 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13427.6316 | 2011-07-14 11:38 | 2011-07-14 12:38 | ArrayCableInstallation | 559 | 559 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13428.8791 | 2011-07-14 12:53 | 2011-07-14 16:23 | MooredSubInstallation | 559 | 559 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13432.3791 | 2011-07-14 16:23 | 2011-07-14 19:53 | MooredSubInstallation | 559 | 559 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13433.1316 | 2011-07-14 17:08 | 2011-07-14 22:38 | ArrayCableInstallation | 559 | 559 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13438.6316 | 2011-07-14 22:38 | 2011-07-15 04:08 | ArrayCableInstallation | 559 | 560 | 2
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 13440.6316 | 2011-07-15 00:38 | 2011-07-15 02:38 | ArrayCableInstallation | 560 | 560 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13441.6316 | 2011-07-15 01:38 | 2011-07-15 02:38 | ArrayCableInstallation | 560 | 560 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13447.1316 | 2011-07-15 07:08 | 2011-07-15 12:38 | ArrayCableInstallation | 560 | 560 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13452.6316 | 2011-07-15 12:38 | 2011-07-15 18:08 | ArrayCableInstallation | 560 | 560 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 13453.6316 | 2011-07-15 13:38 | 2011-07-15 14:38 | ArrayCableInstallation | 560 | 560 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 13456.3791 | 2011-07-15 16:23 | 2011-07-16 16:23 | MooredSubInstallation | 560 | 561 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 366.0825 | 457603.0655 | 13456.3791 | 2011-07-15 16:23 | 2011-07-30 22:28 | MooredSubInstallation | 560 | 575 | 16
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 13462.3791 | 2011-07-15 22:23 | 2011-07-16 04:23 | MooredSubInstallation | 560 | 561 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 13463.6226 | 2011-07-15 23:37 | 2011-07-16 09:37 | ArrayCableInstallation | 560 | 561 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13464.6226 | 2011-07-16 00:37 | 2011-07-16 01:37 | ArrayCableInstallation | 561 | 561 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 13466.3791 | 2011-07-16 02:23 | 2011-07-23 02:23 | MooredSubInstallation | 561 | 568 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 10 | 0 | 13466.3791 | 2011-07-16 02:23 | 2011-07-16 12:23 | MooredSubInstallation | 561 | 561 | 1
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 13468.5719 | 2011-07-16 04:34 | 2011-07-16 10:46 | MooredSubInstallation | 561 | 561 | 1
Multi-Purpose Support Vessel | Delay | 51.5 | 214583.3333 | 13468.5719 | 2011-07-16 04:34 | 2011-07-18 08:04 | MooredSubInstallation | 561 | 563 | 3
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13470.1226 | 2011-07-16 06:07 | 2011-07-16 11:37 | ArrayCableInstallation | 561 | 561 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 13470.5719 | 2011-07-16 06:34 | 2011-07-16 08:34 | MooredSubInstallation | 561 | 561 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 13474.3791 | 2011-07-16 10:23 | 2011-07-16 18:23 | MooredSubInstallation | 561 | 561 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13475.6226 | 2011-07-16 11:37 | 2011-07-16 17:07 | ArrayCableInstallation | 561 | 561 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 13476.5719 | 2011-07-16 12:34 | 2011-07-16 18:34 | MooredSubInstallation | 561 | 561 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 13477.6226 | 2011-07-16 13:37 | 2011-07-16 15:37 | ArrayCableInstallation | 561 | 561 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13478.6226 | 2011-07-16 14:37 | 2011-07-16 15:37 | ArrayCableInstallation | 561 | 561 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13484.1226 | 2011-07-16 20:07 | 2011-07-17 01:37 | ArrayCableInstallation | 561 | 562 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 13486.3791 | 2011-07-16 22:23 | 2011-07-17 10:23 | MooredSubInstallation | 561 | 562 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13489.6226 | 2011-07-17 01:37 | 2011-07-17 07:07 | ArrayCableInstallation | 562 | 562 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 13490.6226 | 2011-07-17 02:37 | 2011-07-17 03:37 | ArrayCableInstallation | 562 | 562 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 13496.5719 | 2011-07-17 08:34 | 2011-07-18 04:34 | MooredSubInstallation | 562 | 563 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 13498.3791 | 2011-07-17 10:23 | 2011-07-17 22:23 | MooredSubInstallation | 562 | 562 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 13500.6136 | 2011-07-17 12:37 | 2011-07-17 22:36 | ArrayCableInstallation | 562 | 562 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13501.6136 | 2011-07-17 13:37 | 2011-07-17 14:37 | ArrayCableInstallation | 562 | 562 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 13502.5719 | 2011-07-17 14:34 | 2011-07-17 20:34 | MooredSubInstallation | 562 | 562 | 1
Towing Group 2 | Positioning Support | 34 | 42500 | 13502.5719 | 2011-07-17 14:34 | 2011-07-19 00:34 | MooredSubInstallation | 562 | 564 | 3
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13507.1136 | 2011-07-17 19:07 | 2011-07-18 00:37 | ArrayCableInstallation | 562 | 563 | 2
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 13509.7967 | 2011-07-17 21:48 | 2011-07-18 05:01 | MooredSubInstallation | 562 | 563 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 13510.3791 | 2011-07-17 22:23 | 2011-07-18 10:23 | MooredSubInstallation | 562 | 563 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13512.6136 | 2011-07-18 00:37 | 2011-07-18 06:07 | ArrayCableInstallation | 563 | 563 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 13514.6136 | 2011-07-18 02:37 | 2011-07-18 04:37 | ArrayCableInstallation | 563 | 563 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13515.6136 | 2011-07-18 03:37 | 2011-07-18 04:37 | ArrayCableInstallation | 563 | 563 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 13517.3791 | 2011-07-18 05:23 | 2011-07-18 12:23 | MooredSubInstallation | 563 | 563 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13520.8791 | 2011-07-18 08:53 | 2011-07-18 12:23 | MooredSubInstallation | 563 | 563 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13521.1136 | 2011-07-18 09:07 | 2011-07-18 14:37 | ArrayCableInstallation | 563 | 563 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13524.3791 | 2011-07-18 12:23 | 2011-07-18 15:53 | MooredSubInstallation | 563 | 563 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13526.6136 | 2011-07-18 14:37 | 2011-07-18 20:07 | ArrayCableInstallation | 563 | 563 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 13527.6136 | 2011-07-18 15:37 | 2011-07-18 16:37 | ArrayCableInstallation | 563 | 563 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13527.8791 | 2011-07-18 15:53 | 2011-07-18 19:23 | MooredSubInstallation | 563 | 563 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 13537.6045 | 2011-07-19 01:36 | 2011-07-19 11:36 | ArrayCableInstallation | 564 | 564 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13538.6045 | 2011-07-19 02:36 | 2011-07-19 03:36 | ArrayCableInstallation | 564 | 564 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13544.1045 | 2011-07-19 08:06 | 2011-07-19 13:36 | ArrayCableInstallation | 564 | 564 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13549.6045 | 2011-07-19 13:36 | 2011-07-19 19:06 | ArrayCableInstallation | 564 | 564 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 13551.6045 | 2011-07-19 15:36 | 2011-07-19 17:36 | ArrayCableInstallation | 564 | 564 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 13551.8791 | 2011-07-19 15:53 | 2011-07-20 15:53 | MooredSubInstallation | 564 | 565 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 206.0825 | 257603.0655 | 13551.8791 | 2011-07-19 15:53 | 2011-07-28 05:58 | MooredSubInstallation | 564 | 573 | 10
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13552.6045 | 2011-07-19 16:36 | 2011-07-19 17:36 | ArrayCableInstallation | 564 | 564 | 1
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 13557.8791 | 2011-07-19 21:53 | 2011-07-20 03:53 | MooredSubInstallation | 564 | 565 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13558.1045 | 2011-07-19 22:06 | 2011-07-20 03:36 | ArrayCableInstallation | 564 | 565 | 2
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 13564.0719 | 2011-07-20 04:04 | 2011-07-20 10:16 | MooredSubInstallation | 565 | 565 | 1
Multi-Purpose Support Vessel | Delay | 61.5 | 256250 | 13564.0719 | 2011-07-20 04:04 | 2011-07-22 17:34 | MooredSubInstallation | 565 | 567 | 3
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 13566.0719 | 2011-07-20 06:04 | 2011-07-20 08:04 | MooredSubInstallation | 565 | 565 | 1
Multi-Purpose Support Vessel | Delay | 6 | 25000 | 13572.0719 | 2011-07-20 12:04 | 2011-07-20 18:04 | MooredSubInstallation | 565 | 565 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 13578.0719 | 2011-07-20 18:04 | 2011-07-21 00:04 | MooredSubInstallation | 565 | 566 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 29166.6667 | 13585.0719 | 2011-07-21 01:04 | 2011-07-21 08:04 | MooredSubInstallation | 566 | 566 | 1
Multi-Purpose Support Vessel | Delay | 8 | 33333.3333 | 13593.0719 | 2011-07-21 09:04 | 2011-07-21 17:04 | MooredSubInstallation | 566 | 566 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 25000 | 13599.0719 | 2011-07-21 15:04 | 2011-07-21 21:04 | MooredSubInstallation | 566 | 566 | 1
Multi-Purpose Support Vessel | Delay | 2 | 8333.3333 | 13601.0719 | 2011-07-21 17:04 | 2011-07-21 19:04 | MooredSubInstallation | 566 | 566 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 29166.6667 | 13608.0719 | 2011-07-22 00:04 | 2011-07-22 07:04 | MooredSubInstallation | 567 | 567 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 13614.0719 | 2011-07-22 06:04 | 2011-07-22 12:04 | MooredSubInstallation | 567 | 567 | 1
Towing Group 3 | Positioning Support | 50 | 62500 | 13614.0719 | 2011-07-22 06:04 | 2011-07-24 08:04 | MooredSubInstallation | 567 | 569 | 3
Array Cable Installation Vessel | Delay | 60 | 300000 | 13618.1045 | 2011-07-22 10:06 | 2011-07-24 22:06 | ArrayCableInstallation | 567 | 569 | 3
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 13621.2967 | 2011-07-22 13:18 | 2011-07-22 20:31 | MooredSubInstallation | 567 | 567 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13623.6045 | 2011-07-22 15:36 | 2011-07-22 21:06 | ArrayCableInstallation | 567 | 567 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 13624.6045 | 2011-07-22 16:36 | 2011-07-22 17:36 | ArrayCableInstallation | 567 | 567 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 13634.3791 | 2011-07-23 02:23 | 2011-07-30 02:23 | MooredSubInstallation | 568 | 575 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 13634.3791 | 2011-07-23 02:23 | 2011-07-26 12:53 | MooredSubInstallation | 568 | 571 | 4
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 13642.3791 | 2011-07-23 10:23 | 2011-07-23 18:23 | MooredSubInstallation | 568 | 568 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 13654.3791 | 2011-07-23 22:23 | 2011-07-24 10:23 | MooredSubInstallation | 568 | 569 | 2
Array Cable Installation Vessel | Delay | 32 | 160000 | 13656.6045 | 2011-07-24 00:36 | 2011-07-25 08:36 | ArrayCableInstallation | 569 | 570 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 13666.3791 | 2011-07-24 10:23 | 2011-07-24 22:23 | MooredSubInstallation | 569 | 569 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 13666.5955 | 2011-07-24 10:36 | 2011-07-24 20:35 | ArrayCableInstallation | 569 | 569 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13667.5955 | 2011-07-24 11:36 | 2011-07-24 12:36 | ArrayCableInstallation | 569 | 569 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13673.0955 | 2011-07-24 17:06 | 2011-07-24 22:36 | ArrayCableInstallation | 569 | 569 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 13678.3791 | 2011-07-24 22:23 | 2011-07-25 10:23 | MooredSubInstallation | 569 | 570 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13678.5955 | 2011-07-24 22:36 | 2011-07-25 04:06 | ArrayCableInstallation | 569 | 570 | 2
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 13680.5955 | 2011-07-25 00:36 | 2011-07-25 02:36 | ArrayCableInstallation | 570 | 570 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13681.5955 | 2011-07-25 01:36 | 2011-07-25 02:36 | ArrayCableInstallation | 570 | 570 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 13685.3791 | 2011-07-25 05:23 | 2011-07-25 12:23 | MooredSubInstallation | 570 | 570 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13687.0955 | 2011-07-25 07:06 | 2011-07-25 12:36 | ArrayCableInstallation | 570 | 570 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13688.8791 | 2011-07-25 08:53 | 2011-07-25 12:23 | MooredSubInstallation | 570 | 570 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13692.3791 | 2011-07-25 12:23 | 2011-07-25 15:53 | MooredSubInstallation | 570 | 570 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13692.5955 | 2011-07-25 12:36 | 2011-07-25 18:06 | ArrayCableInstallation | 570 | 570 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 13693.5955 | 2011-07-25 13:36 | 2011-07-25 14:36 | ArrayCableInstallation | 570 | 570 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13695.8791 | 2011-07-25 15:53 | 2011-07-25 19:23 | MooredSubInstallation | 570 | 570 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 13703.5865 | 2011-07-25 23:35 | 2011-07-26 09:35 | ArrayCableInstallation | 570 | 571 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13704.5865 | 2011-07-26 00:35 | 2011-07-26 01:35 | ArrayCableInstallation | 571 | 571 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13710.0865 | 2011-07-26 06:05 | 2011-07-26 11:35 | ArrayCableInstallation | 571 | 571 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13715.5865 | 2011-07-26 11:35 | 2011-07-26 17:05 | ArrayCableInstallation | 571 | 571 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 13717.5865 | 2011-07-26 13:35 | 2011-07-26 15:35 | ArrayCableInstallation | 571 | 571 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 13719.8791 | 2011-07-26 15:53 | 2011-07-27 15:53 | MooredSubInstallation | 571 | 572 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 295.5825 | 369478.0655 | 13719.8791 | 2011-07-26 15:53 | 2011-08-07 23:28 | MooredSubInstallation | 571 | 583 | 13
Array Cable Installation Vessel | Delay | 3 | 15000 | 13720.5865 | 2011-07-26 16:35 | 2011-07-26 19:35 | ArrayCableInstallation | 571 | 571 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13721.5865 | 2011-07-26 17:35 | 2011-07-26 18:35 | ArrayCableInstallation | 571 | 571 | 1
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 13802.3791 | 2011-07-30 02:23 | 2011-08-06 02:23 | MooredSubInstallation | 575 | 582 | 8
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 13802.3791 | 2011-07-30 02:23 | 2011-08-02 12:53 | MooredSubInstallation | 575 | 578 | 4
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 13810.3791 | 2011-07-30 10:23 | 2011-07-30 18:23 | MooredSubInstallation | 575 | 575 | 1
Towing Group 1 | Delay | 96 | 240000 | 13815.8791 | 2011-07-30 15:53 | 2011-08-03 15:53 | MooredSubInstallation | 575 | 579 | 5
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 13821.8791 | 2011-07-30 21:53 | 2011-07-31 03:53 | MooredSubInstallation | 575 | 576 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 13822.3791 | 2011-07-30 22:23 | 2011-07-31 10:23 | MooredSubInstallation | 575 | 576 | 2
Towing Group 1 | Delay | 18 | 45000 | 13839.8791 | 2011-07-31 15:53 | 2011-08-01 09:53 | MooredSubInstallation | 576 | 577 | 2
Turbine Assembly Line 1 | Delay | 18 | 0 | 13840.3791 | 2011-07-31 16:23 | 2011-08-01 10:23 | MooredSubInstallation | 576 | 577 | 2
Array Cable Installation Vessel | Delay | 123 | 615000 | 13844.5865 | 2011-07-31 20:35 | 2011-08-05 23:35 | ArrayCableInstallation | 576 | 581 | 6
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 13846.0719 | 2011-07-31 22:04 | 2011-08-01 04:16 | MooredSubInstallation | 576 | 577 | 2
Multi-Purpose Support Vessel | Delay | 232 | 966666.6667 | 13846.0719 | 2011-07-31 22:04 | 2011-08-10 14:04 | MooredSubInstallation | 576 | 586 | 11
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 13848.0719 | 2011-08-01 00:04 | 2011-08-01 02:04 | MooredSubInstallation | 577 | 577 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13850.0865 | 2011-08-01 02:05 | 2011-08-01 07:35 | ArrayCableInstallation | 577 | 577 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 13852.3791 | 2011-08-01 04:23 | 2011-08-01 16:23 | MooredSubInstallation | 577 | 577 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 13854.0719 | 2011-08-01 06:04 | 2011-08-01 12:04 | MooredSubInstallation | 577 | 577 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13855.5865 | 2011-08-01 07:35 | 2011-08-01 13:05 | ArrayCableInstallation | 577 | 577 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 13856.5865 | 2011-08-01 08:35 | 2011-08-01 09:35 | ArrayCableInstallation | 577 | 577 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 13864.3791 | 2011-08-01 16:23 | 2011-08-02 04:23 | MooredSubInstallation | 577 | 578 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 13866.5774 | 2011-08-01 18:35 | 2011-08-02 04:34 | ArrayCableInstallation | 577 | 578 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13867.5774 | 2011-08-01 19:35 | 2011-08-01 20:35 | ArrayCableInstallation | 577 | 577 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 13871.3791 | 2011-08-01 23:23 | 2011-08-02 06:23 | MooredSubInstallation | 577 | 578 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13873.0774 | 2011-08-02 01:05 | 2011-08-02 06:35 | ArrayCableInstallation | 578 | 578 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 13874.0719 | 2011-08-02 02:04 | 2011-08-02 22:04 | MooredSubInstallation | 578 | 578 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13874.8791 | 2011-08-02 02:53 | 2011-08-02 06:23 | MooredSubInstallation | 578 | 578 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13878.5774 | 2011-08-02 06:35 | 2011-08-02 12:05 | ArrayCableInstallation | 578 | 578 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 13880.0719 | 2011-08-02 08:04 | 2011-08-02 14:04 | MooredSubInstallation | 578 | 578 | 1
Towing Group 1 | Positioning Support | 34 | 42500 | 13880.0719 | 2011-08-02 08:04 | 2011-08-03 18:04 | MooredSubInstallation | 578 | 579 | 2
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 13880.5774 | 2011-08-02 08:35 | 2011-08-02 10:35 | ArrayCableInstallation | 578 | 578 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13881.5774 | 2011-08-02 09:35 | 2011-08-02 10:35 | ArrayCableInstallation | 578 | 578 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13887.0774 | 2011-08-02 15:05 | 2011-08-02 20:35 | ArrayCableInstallation | 578 | 578 | 1
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 13887.2967 | 2011-08-02 15:18 | 2011-08-02 22:31 | MooredSubInstallation | 578 | 578 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13892.5774 | 2011-08-02 20:35 | 2011-08-03 02:05 | ArrayCableInstallation | 578 | 579 | 2
Turbine Assembly Line 1 | Delay | 18 | 0 | 13892.8791 | 2011-08-02 20:53 | 2011-08-03 14:53 | MooredSubInstallation | 578 | 579 | 2
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 13893.5774 | 2011-08-02 21:35 | 2011-08-02 22:35 | ArrayCableInstallation | 578 | 578 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13896.3791 | 2011-08-03 00:23 | 2011-08-03 03:53 | MooredSubInstallation | 579 | 579 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 13899.8791 | 2011-08-03 03:53 | 2011-08-03 07:23 | MooredSubInstallation | 579 | 579 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 13903.5684 | 2011-08-03 07:34 | 2011-08-03 17:34 | ArrayCableInstallation | 579 | 579 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13904.5684 | 2011-08-03 08:34 | 2011-08-03 09:34 | ArrayCableInstallation | 579 | 579 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13910.0684 | 2011-08-03 14:04 | 2011-08-03 19:34 | ArrayCableInstallation | 579 | 579 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13915.5684 | 2011-08-03 19:34 | 2011-08-04 01:04 | ArrayCableInstallation | 579 | 580 | 2
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 13917.5684 | 2011-08-03 21:34 | 2011-08-03 23:34 | ArrayCableInstallation | 579 | 579 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13918.5684 | 2011-08-03 22:34 | 2011-08-03 23:34 | ArrayCableInstallation | 579 | 579 | 1
Towing Group 2 | Delay: No Completed Assemblies Available | 414.0825 | 517603.0655 | 13923.8791 | 2011-08-04 03:53 | 2011-08-05 03:53 | MooredSubInstallation | 580 | 581 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 13923.8791 | 2011-08-04 03:53 | 2011-08-21 09:58 | MooredSubInstallation | 580 | 597 | 18
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13924.0684 | 2011-08-04 04:04 | 2011-08-04 09:34 | ArrayCableInstallation | 580 | 580 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13929.5684 | 2011-08-04 09:34 | 2011-08-04 15:04 | ArrayCableInstallation | 580 | 580 | 1
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 13929.8791 | 2011-08-04 09:53 | 2011-08-04 15:53 | MooredSubInstallation | 580 | 580 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 13930.5684 | 2011-08-04 10:34 | 2011-08-04 11:34 | ArrayCableInstallation | 580 | 580 | 1
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 13936.0719 | 2011-08-04 16:04 | 2011-08-04 22:16 | MooredSubInstallation | 580 | 580 | 1
Multi-Purpose Support Vessel | Delay | 56 | 233333.3333 | 13936.0719 | 2011-08-04 16:04 | 2011-08-07 00:04 | MooredSubInstallation | 580 | 583 | 4
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 13938.0719 | 2011-08-04 18:04 | 2011-08-04 20:04 | MooredSubInstallation | 580 | 580 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 13940.5594 | 2011-08-04 20:34 | 2011-08-05 06:33 | ArrayCableInstallation | 580 | 581 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13941.5594 | 2011-08-04 21:34 | 2011-08-04 22:34 | ArrayCableInstallation | 580 | 580 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 13944.0719 | 2011-08-05 00:04 | 2011-08-05 06:04 | MooredSubInstallation | 581 | 581 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13947.0594 | 2011-08-05 03:04 | 2011-08-05 08:34 | ArrayCableInstallation | 581 | 581 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 20833.3333 | 13949.0719 | 2011-08-05 05:04 | 2011-08-05 10:04 | MooredSubInstallation | 581 | 581 | 1
Multi-Purpose Support Vessel | Delay | 4 | 16666.6667 | 13953.0719 | 2011-08-05 09:04 | 2011-08-05 13:04 | MooredSubInstallation | 581 | 581 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 12500 | 13956.0719 | 2011-08-05 12:04 | 2011-08-05 15:04 | MooredSubInstallation | 581 | 581 | 1
Multi-Purpose Support Vessel | Delay | 8 | 33333.3333 | 13964.0719 | 2011-08-05 20:04 | 2011-08-06 04:04 | MooredSubInstallation | 581 | 582 | 2
Array Cable Installation Vessel | Delay | 21 | 105000 | 13968.0594 | 2011-08-06 00:04 | 2011-08-06 21:04 | ArrayCableInstallation | 582 | 582 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 13970.3791 | 2011-08-06 02:23 | 2011-08-13 02:23 | MooredSubInstallation | 582 | 589 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 46.5 | 0 | 13970.3791 | 2011-08-06 02:23 | 2011-08-08 00:53 | MooredSubInstallation | 582 | 584 | 3
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13973.5594 | 2011-08-06 05:34 | 2011-08-06 11:04 | ArrayCableInstallation | 582 | 582 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 13975.5594 | 2011-08-06 07:34 | 2011-08-06 09:34 | ArrayCableInstallation | 582 | 582 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 50000 | 13976.0719 | 2011-08-06 08:04 | 2011-08-06 20:04 | MooredSubInstallation | 582 | 582 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 13976.5594 | 2011-08-06 08:34 | 2011-08-06 09:34 | ArrayCableInstallation | 582 | 582 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 13978.3791 | 2011-08-06 10:23 | 2011-08-06 18:23 | MooredSubInstallation | 582 | 582 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 13982.0594 | 2011-08-06 14:04 | 2011-08-06 19:34 | ArrayCableInstallation | 582 | 582 | 1
Towing Group 2 | Positioning Support | 46 | 57500 | 13982.0719 | 2011-08-06 14:04 | 2011-08-06 20:04 | MooredSubInstallation | 582 | 582 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 13982.0719 | 2011-08-06 14:04 | 2011-08-08 12:04 | MooredSubInstallation | 582 | 584 | 3
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 13987.5594 | 2011-08-06 19:34 | 2011-08-07 01:04 | ArrayCableInstallation | 582 | 583 | 2
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 13988.5594 | 2011-08-06 20:34 | 2011-08-06 21:34 | ArrayCableInstallation | 582 | 582 | 1
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 13989.2967 | 2011-08-06 21:18 | 2011-08-07 04:31 | MooredSubInstallation | 582 | 583 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 13990.3791 | 2011-08-06 22:23 | 2011-08-07 10:23 | MooredSubInstallation | 582 | 583 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 14002.3791 | 2011-08-07 10:23 | 2011-08-07 22:23 | MooredSubInstallation | 583 | 583 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 14014.3791 | 2011-08-07 22:23 | 2011-08-08 10:23 | MooredSubInstallation | 583 | 584 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 14021.3791 | 2011-08-08 05:23 | 2011-08-08 12:23 | MooredSubInstallation | 584 | 584 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 35.6959 | 178479.6026 | 14024.2553 | 2011-08-08 08:15 | 2011-08-09 19:57 | ArrayCableInstallation | 584 | 585 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14024.8791 | 2011-08-08 08:53 | 2011-08-08 12:23 | MooredSubInstallation | 584 | 584 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14025.2553 | 2011-08-08 09:15 | 2011-08-08 10:15 | ArrayCableInstallation | 584 | 584 | 1
Turbine Assembly Line 1 | Delay | 5 | 0 | 14029.8791 | 2011-08-08 13:53 | 2011-08-08 18:53 | MooredSubInstallation | 584 | 584 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14030.7553 | 2011-08-08 14:45 | 2011-08-08 20:15 | ArrayCableInstallation | 584 | 584 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14033.3791 | 2011-08-08 17:23 | 2011-08-08 20:53 | MooredSubInstallation | 584 | 584 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14036.2553 | 2011-08-08 20:15 | 2011-08-09 01:45 | ArrayCableInstallation | 584 | 585 | 2
Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | 14040.0248 | 2011-08-09 00:01 | 2011-08-09 03:48 | ArrayCableInstallation | 585 | 585 | 1
Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | 14043.7943 | 2011-08-09 03:48 | 2011-08-09 07:34 | ArrayCableInstallation | 585 | 585 | 1
Array Cable Installation Vessel | Load Cable | 6 | 30000 | 14049.7943 | 2011-08-09 09:48 | 2011-08-09 15:48 | ArrayCableInstallation | 585 | 585 | 1
Array Cable Installation Vessel | Transit | 1 | 5000 | 14050.7943 | 2011-08-09 10:48 | 2011-08-09 11:48 | ArrayCableInstallation | 585 | 585 | 1
Array Cable Installation Vessel | Delay | 30 | 150000 | 14080.7943 | 2011-08-10 16:48 | 2011-08-11 22:48 | ArrayCableInstallation | 586 | 587 | 2
Array Cable Installation Vessel | Transit | 2.7695 | 13847.3913 | 14083.5637 | 2011-08-10 19:34 | 2011-08-10 22:20 | ArrayCableInstallation | 586 | 586 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 14085.5637 | 2011-08-10 21:34 | 2011-08-10 23:34 | ArrayCableInstallation | 586 | 586 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14086.5637 | 2011-08-10 22:34 | 2011-08-10 23:34 | ArrayCableInstallation | 586 | 586 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14092.0637 | 2011-08-11 04:04 | 2011-08-11 09:34 | ArrayCableInstallation | 587 | 587 | 1
Turbine Assembly Line 1 | Delay | 64 | 0 | 14097.3791 | 2011-08-11 09:23 | 2011-08-14 01:23 | MooredSubInstallation | 587 | 590 | 4
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14097.5637 | 2011-08-11 09:34 | 2011-08-11 15:04 | ArrayCableInstallation | 587 | 587 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 14098.5637 | 2011-08-11 10:34 | 2011-08-11 11:34 | ArrayCableInstallation | 587 | 587 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14100.8791 | 2011-08-11 12:53 | 2011-08-11 16:23 | MooredSubInstallation | 587 | 587 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 14124.8791 | 2011-08-12 12:53 | 2011-08-13 12:53 | MooredSubInstallation | 588 | 589 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 503.5825 | 629478.0655 | 14124.8791 | 2011-08-12 12:53 | 2011-09-02 12:28 | MooredSubInstallation | 588 | 609 | 22
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 14130.8791 | 2011-08-12 18:53 | 2011-08-13 00:53 | MooredSubInstallation | 588 | 589 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 35.6959 | 178479.6026 | 14134.2596 | 2011-08-12 22:16 | 2011-08-14 09:57 | ArrayCableInstallation | 588 | 590 | 3
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14135.2596 | 2011-08-12 23:16 | 2011-08-13 00:16 | ArrayCableInstallation | 588 | 589 | 2
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 14137.0719 | 2011-08-13 01:04 | 2011-08-13 07:16 | MooredSubInstallation | 589 | 589 | 1
Multi-Purpose Support Vessel | Delay | 155 | 645833.3333 | 14137.0719 | 2011-08-13 01:04 | 2011-08-19 12:04 | MooredSubInstallation | 589 | 595 | 7
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 14138.3791 | 2011-08-13 02:23 | 2011-08-20 02:23 | MooredSubInstallation | 589 | 596 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | 14138.3791 | 2011-08-13 02:23 | 2011-08-13 15:53 | MooredSubInstallation | 589 | 589 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 14139.0719 | 2011-08-13 03:04 | 2011-08-13 05:04 | MooredSubInstallation | 589 | 589 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14140.7596 | 2011-08-13 04:46 | 2011-08-13 10:16 | ArrayCableInstallation | 589 | 589 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 14145.0719 | 2011-08-13 09:04 | 2011-08-13 15:04 | MooredSubInstallation | 589 | 589 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14146.2596 | 2011-08-13 10:16 | 2011-08-13 15:46 | ArrayCableInstallation | 589 | 589 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 14146.3791 | 2011-08-13 10:23 | 2011-08-13 18:23 | MooredSubInstallation | 589 | 589 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 14148.2596 | 2011-08-13 12:16 | 2011-08-13 14:16 | ArrayCableInstallation | 589 | 589 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14149.2596 | 2011-08-13 13:16 | 2011-08-13 14:16 | ArrayCableInstallation | 589 | 589 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14154.7596 | 2011-08-13 18:46 | 2011-08-14 00:16 | ArrayCableInstallation | 589 | 590 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 14158.3791 | 2011-08-13 22:23 | 2011-08-14 10:23 | MooredSubInstallation | 589 | 590 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14160.2596 | 2011-08-14 00:16 | 2011-08-14 05:46 | ArrayCableInstallation | 590 | 590 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 14161.2596 | 2011-08-14 01:16 | 2011-08-14 02:16 | ArrayCableInstallation | 590 | 590 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 14165.0719 | 2011-08-14 05:04 | 2011-08-15 01:04 | MooredSubInstallation | 590 | 591 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 14170.3791 | 2011-08-14 10:23 | 2011-08-14 22:23 | MooredSubInstallation | 590 | 590 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 14171.0719 | 2011-08-14 11:04 | 2011-08-14 17:04 | MooredSubInstallation | 590 | 590 | 1
Towing Group 3 | Positioning Support | 34 | 42500 | 14171.0719 | 2011-08-14 11:04 | 2011-08-15 21:04 | MooredSubInstallation | 590 | 591 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 14171.2506 | 2011-08-14 11:15 | 2011-08-14 21:14 | ArrayCableInstallation | 590 | 590 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14172.2506 | 2011-08-14 12:15 | 2011-08-14 13:15 | ArrayCableInstallation | 590 | 590 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14177.7506 | 2011-08-14 17:45 | 2011-08-14 23:15 | ArrayCableInstallation | 590 | 590 | 1
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 14178.2967 | 2011-08-14 18:18 | 2011-08-15 01:31 | MooredSubInstallation | 590 | 591 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 14182.3791 | 2011-08-14 22:23 | 2011-08-15 10:23 | MooredSubInstallation | 590 | 591 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14183.2506 | 2011-08-14 23:15 | 2011-08-15 04:45 | ArrayCableInstallation | 590 | 591 | 2
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 14185.2506 | 2011-08-15 01:15 | 2011-08-15 03:15 | ArrayCableInstallation | 591 | 591 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14186.2506 | 2011-08-15 02:15 | 2011-08-15 03:15 | ArrayCableInstallation | 591 | 591 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 14189.3791 | 2011-08-15 05:23 | 2011-08-15 12:23 | MooredSubInstallation | 591 | 591 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14191.7506 | 2011-08-15 07:45 | 2011-08-15 13:15 | ArrayCableInstallation | 591 | 591 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14192.8791 | 2011-08-15 08:53 | 2011-08-15 12:23 | MooredSubInstallation | 591 | 591 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14196.3791 | 2011-08-15 12:23 | 2011-08-15 15:53 | MooredSubInstallation | 591 | 591 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14197.2506 | 2011-08-15 13:15 | 2011-08-15 18:45 | ArrayCableInstallation | 591 | 591 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 14198.2506 | 2011-08-15 14:15 | 2011-08-15 15:15 | ArrayCableInstallation | 591 | 591 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14199.8791 | 2011-08-15 15:53 | 2011-08-15 19:23 | MooredSubInstallation | 591 | 591 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 14208.2416 | 2011-08-16 00:14 | 2011-08-16 10:14 | ArrayCableInstallation | 592 | 592 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14209.2416 | 2011-08-16 01:14 | 2011-08-16 02:14 | ArrayCableInstallation | 592 | 592 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14214.7416 | 2011-08-16 06:44 | 2011-08-16 12:14 | ArrayCableInstallation | 592 | 592 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14220.2416 | 2011-08-16 12:14 | 2011-08-16 17:44 | ArrayCableInstallation | 592 | 592 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 14222.2416 | 2011-08-16 14:14 | 2011-08-16 16:14 | ArrayCableInstallation | 592 | 592 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14223.2416 | 2011-08-16 15:14 | 2011-08-16 16:14 | ArrayCableInstallation | 592 | 592 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 14223.8791 | 2011-08-16 15:53 | 2011-08-17 15:53 | MooredSubInstallation | 592 | 593 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 336.5825 | 420728.0655 | 14223.8791 | 2011-08-16 15:53 | 2011-08-30 16:28 | MooredSubInstallation | 592 | 606 | 15
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14228.7416 | 2011-08-16 20:44 | 2011-08-17 02:14 | ArrayCableInstallation | 592 | 593 | 2
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 14229.8791 | 2011-08-16 21:53 | 2011-08-17 03:53 | MooredSubInstallation | 592 | 593 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14234.2416 | 2011-08-17 02:14 | 2011-08-17 07:44 | ArrayCableInstallation | 593 | 593 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 14235.2416 | 2011-08-17 03:14 | 2011-08-17 04:14 | ArrayCableInstallation | 593 | 593 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 14236.0719 | 2011-08-17 04:04 | 2011-08-17 10:16 | MooredSubInstallation | 593 | 593 | 1
Multi-Purpose Support Vessel | Delay | 65 | 270833.3333 | 14236.0719 | 2011-08-17 04:04 | 2011-08-19 21:04 | MooredSubInstallation | 593 | 595 | 3
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 14238.0719 | 2011-08-17 06:04 | 2011-08-17 08:04 | MooredSubInstallation | 593 | 593 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 14244.0719 | 2011-08-17 12:04 | 2011-08-17 18:04 | MooredSubInstallation | 593 | 593 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 14245.2326 | 2011-08-17 13:14 | 2011-08-17 23:13 | ArrayCableInstallation | 593 | 593 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14246.2326 | 2011-08-17 14:14 | 2011-08-17 15:14 | ArrayCableInstallation | 593 | 593 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14251.7326 | 2011-08-17 19:44 | 2011-08-18 01:14 | ArrayCableInstallation | 593 | 594 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 19 | 79166.6667 | 14263.0719 | 2011-08-18 07:04 | 2011-08-19 02:04 | MooredSubInstallation | 594 | 595 | 2
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 14306.3791 | 2011-08-20 02:23 | 2011-08-27 02:23 | MooredSubInstallation | 596 | 603 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 14306.3791 | 2011-08-20 02:23 | 2011-08-23 12:53 | MooredSubInstallation | 596 | 599 | 4
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 14314.3791 | 2011-08-20 10:23 | 2011-08-20 18:23 | MooredSubInstallation | 596 | 596 | 1
Multi-Purpose Support Vessel | Delay | 52 | 216666.6667 | 14315.0719 | 2011-08-20 11:04 | 2011-08-22 15:04 | MooredSubInstallation | 596 | 598 | 3
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 4166.6667 | 14316.0719 | 2011-08-20 12:04 | 2011-08-20 13:04 | MooredSubInstallation | 596 | 596 | 1
Array Cable Installation Vessel | Delay | 69 | 345000 | 14320.7326 | 2011-08-20 16:44 | 2011-08-23 13:44 | ArrayCableInstallation | 596 | 599 | 4
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 14322.0719 | 2011-08-20 18:04 | 2011-08-21 00:04 | MooredSubInstallation | 596 | 597 | 2
Towing Group 1 | Positioning Support | 86 | 107500 | 14322.0719 | 2011-08-20 18:04 | 2011-08-24 08:04 | MooredSubInstallation | 596 | 600 | 5
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14326.2326 | 2011-08-20 22:14 | 2011-08-21 03:44 | ArrayCableInstallation | 596 | 597 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 14326.3791 | 2011-08-20 22:23 | 2011-08-21 10:23 | MooredSubInstallation | 596 | 597 | 2
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 14328.2326 | 2011-08-21 00:14 | 2011-08-21 02:14 | ArrayCableInstallation | 597 | 597 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14329.2326 | 2011-08-21 01:14 | 2011-08-21 02:14 | ArrayCableInstallation | 597 | 597 | 1
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 14329.2967 | 2011-08-21 01:18 | 2011-08-21 08:31 | MooredSubInstallation | 597 | 597 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14334.7326 | 2011-08-21 06:44 | 2011-08-21 12:14 | ArrayCableInstallation | 597 | 597 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 14338.3791 | 2011-08-21 10:23 | 2011-08-21 22:23 | MooredSubInstallation | 597 | 597 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14340.2326 | 2011-08-21 12:14 | 2011-08-21 17:44 | ArrayCableInstallation | 597 | 597 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 14341.2326 | 2011-08-21 13:14 | 2011-08-21 14:14 | ArrayCableInstallation | 597 | 597 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 14350.3791 | 2011-08-21 22:23 | 2011-08-22 10:23 | MooredSubInstallation | 597 | 598 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 14351.2235 | 2011-08-21 23:13 | 2011-08-22 09:13 | ArrayCableInstallation | 597 | 598 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14352.2235 | 2011-08-22 00:13 | 2011-08-22 01:13 | ArrayCableInstallation | 598 | 598 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 14357.3791 | 2011-08-22 05:23 | 2011-08-22 12:23 | MooredSubInstallation | 598 | 598 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14357.7235 | 2011-08-22 05:43 | 2011-08-22 11:13 | ArrayCableInstallation | 598 | 598 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14360.8791 | 2011-08-22 08:53 | 2011-08-22 12:23 | MooredSubInstallation | 598 | 598 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14363.2235 | 2011-08-22 11:13 | 2011-08-22 16:43 | ArrayCableInstallation | 598 | 598 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14364.3791 | 2011-08-22 12:23 | 2011-08-22 15:53 | MooredSubInstallation | 598 | 598 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 14365.2235 | 2011-08-22 13:13 | 2011-08-22 15:13 | ArrayCableInstallation | 598 | 598 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14366.2235 | 2011-08-22 14:13 | 2011-08-22 15:13 | ArrayCableInstallation | 598 | 598 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14367.8791 | 2011-08-22 15:53 | 2011-08-22 19:23 | MooredSubInstallation | 598 | 598 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14371.7235 | 2011-08-22 19:43 | 2011-08-23 01:13 | ArrayCableInstallation | 598 | 599 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14377.2235 | 2011-08-23 01:13 | 2011-08-23 06:43 | ArrayCableInstallation | 599 | 599 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 14378.2235 | 2011-08-23 02:13 | 2011-08-23 03:13 | ArrayCableInstallation | 599 | 599 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 14388.2145 | 2011-08-23 12:13 | 2011-08-23 22:12 | ArrayCableInstallation | 599 | 599 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14389.2145 | 2011-08-23 13:13 | 2011-08-23 14:13 | ArrayCableInstallation | 599 | 599 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 14391.8791 | 2011-08-23 15:53 | 2011-08-24 15:53 | MooredSubInstallation | 599 | 600 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 402.5825 | 503228.0655 | 14391.8791 | 2011-08-23 15:53 | 2011-09-09 10:28 | MooredSubInstallation | 599 | 616 | 18
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14394.7145 | 2011-08-23 18:43 | 2011-08-24 00:13 | ArrayCableInstallation | 599 | 600 | 2
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 14397.8791 | 2011-08-23 21:53 | 2011-08-24 03:53 | MooredSubInstallation | 599 | 600 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14400.2145 | 2011-08-24 00:13 | 2011-08-24 05:43 | ArrayCableInstallation | 600 | 600 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 14402.2145 | 2011-08-24 02:13 | 2011-08-24 04:13 | ArrayCableInstallation | 600 | 600 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14403.2145 | 2011-08-24 03:13 | 2011-08-24 04:13 | ArrayCableInstallation | 600 | 600 | 1
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 14404.0719 | 2011-08-24 04:04 | 2011-08-24 10:16 | MooredSubInstallation | 600 | 600 | 1
Multi-Purpose Support Vessel | Delay | 82 | 341666.6667 | 14404.0719 | 2011-08-24 04:04 | 2011-08-27 14:04 | MooredSubInstallation | 600 | 603 | 4
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 14406.0719 | 2011-08-24 06:04 | 2011-08-24 08:04 | MooredSubInstallation | 600 | 600 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14408.7145 | 2011-08-24 08:43 | 2011-08-24 14:13 | ArrayCableInstallation | 600 | 600 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 14412.0719 | 2011-08-24 12:04 | 2011-08-24 18:04 | MooredSubInstallation | 600 | 600 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14414.2145 | 2011-08-24 14:13 | 2011-08-24 19:43 | ArrayCableInstallation | 600 | 600 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 14415.2145 | 2011-08-24 15:13 | 2011-08-24 16:13 | ArrayCableInstallation | 600 | 600 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 14425.2055 | 2011-08-25 01:12 | 2011-08-25 11:12 | ArrayCableInstallation | 601 | 601 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14426.2055 | 2011-08-25 02:12 | 2011-08-25 03:12 | ArrayCableInstallation | 601 | 601 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14431.7055 | 2011-08-25 07:42 | 2011-08-25 13:12 | ArrayCableInstallation | 601 | 601 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 14432.0719 | 2011-08-25 08:04 | 2011-08-26 04:04 | MooredSubInstallation | 601 | 602 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14437.2055 | 2011-08-25 13:12 | 2011-08-25 18:42 | ArrayCableInstallation | 601 | 601 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 14438.0719 | 2011-08-25 14:04 | 2011-08-25 20:04 | MooredSubInstallation | 601 | 601 | 1
Towing Group 2 | Positioning Support | 34 | 42500 | 14438.0719 | 2011-08-25 14:04 | 2011-08-27 00:04 | MooredSubInstallation | 601 | 603 | 3
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 14439.2055 | 2011-08-25 15:12 | 2011-08-25 17:12 | ArrayCableInstallation | 601 | 601 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14440.2055 | 2011-08-25 16:12 | 2011-08-25 17:12 | ArrayCableInstallation | 601 | 601 | 1
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 14445.2967 | 2011-08-25 21:18 | 2011-08-26 04:31 | MooredSubInstallation | 601 | 602 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14445.7055 | 2011-08-25 21:42 | 2011-08-26 03:12 | ArrayCableInstallation | 601 | 602 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14451.2055 | 2011-08-26 03:12 | 2011-08-26 08:42 | ArrayCableInstallation | 602 | 602 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 14452.2055 | 2011-08-26 04:12 | 2011-08-26 05:12 | ArrayCableInstallation | 602 | 602 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | 14455.2055 | 2011-08-26 07:12 | 2011-08-26 10:12 | ArrayCableInstallation | 602 | 602 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 14474.3791 | 2011-08-27 02:23 | 2011-09-03 02:23 | MooredSubInstallation | 603 | 610 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 14474.3791 | 2011-08-27 02:23 | 2011-08-30 12:53 | MooredSubInstallation | 603 | 606 | 4
Array Cable Installation Vessel | Delay | 22 | 110000 | 14477.2055 | 2011-08-27 05:12 | 2011-08-28 03:12 | ArrayCableInstallation | 603 | 604 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 2 | 10000 | 14479.2055 | 2011-08-27 07:12 | 2011-08-27 09:12 | ArrayCableInstallation | 603 | 603 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 14482.3791 | 2011-08-27 10:23 | 2011-08-27 18:23 | MooredSubInstallation | 603 | 603 | 1
Array Cable Installation Vessel | Delay | 8 | 40000 | 14487.2055 | 2011-08-27 15:12 | 2011-08-27 23:12 | ArrayCableInstallation | 603 | 603 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | 14491.2055 | 2011-08-27 19:12 | 2011-08-27 23:12 | ArrayCableInstallation | 603 | 603 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 14494.3791 | 2011-08-27 22:23 | 2011-08-28 10:23 | MooredSubInstallation | 603 | 604 | 2
Turbine Assembly Line 1 | Delay | 14 | 0 | 14508.3791 | 2011-08-28 12:23 | 2011-08-29 02:23 | MooredSubInstallation | 604 | 605 | 2
Array Cable Installation Vessel | Delay | 27 | 135000 | 14518.2055 | 2011-08-28 22:12 | 2011-08-30 01:12 | ArrayCableInstallation | 604 | 606 | 3
Array Cable Installation Vessel | Lay/Bury Cable | 0.99097 | 4954.8442 | 14519.1964 | 2011-08-28 23:12 | 2011-08-29 00:11 | ArrayCableInstallation | 604 | 605 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14520.1964 | 2011-08-29 00:12 | 2011-08-29 01:12 | ArrayCableInstallation | 605 | 605 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 14520.3791 | 2011-08-29 00:23 | 2011-08-29 12:23 | MooredSubInstallation | 605 | 605 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14525.6964 | 2011-08-29 05:42 | 2011-08-29 11:12 | ArrayCableInstallation | 605 | 605 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14531.1964 | 2011-08-29 11:12 | 2011-08-29 16:42 | ArrayCableInstallation | 605 | 605 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 14532.3791 | 2011-08-29 12:23 | 2011-08-30 00:23 | MooredSubInstallation | 605 | 606 | 2
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 14533.1964 | 2011-08-29 13:12 | 2011-08-29 15:12 | ArrayCableInstallation | 605 | 605 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14534.1964 | 2011-08-29 14:12 | 2011-08-29 15:12 | ArrayCableInstallation | 605 | 605 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 14539.3791 | 2011-08-29 19:23 | 2011-08-30 02:23 | MooredSubInstallation | 605 | 606 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14539.6964 | 2011-08-29 19:42 | 2011-08-30 01:12 | ArrayCableInstallation | 605 | 606 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14542.8791 | 2011-08-29 22:53 | 2011-08-30 02:23 | MooredSubInstallation | 605 | 606 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14545.1964 | 2011-08-30 01:12 | 2011-08-30 06:42 | ArrayCableInstallation | 606 | 606 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 14546.1964 | 2011-08-30 02:12 | 2011-08-30 03:12 | ArrayCableInstallation | 606 | 606 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | 14550.1964 | 2011-08-30 06:12 | 2011-08-30 10:12 | ArrayCableInstallation | 606 | 606 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 14642.3791 | 2011-09-03 02:23 | 2011-09-10 02:23 | MooredSubInstallation | 610 | 617 | 8
Turbine Assembly Line 1 | Delay | 107 | 0 | 14649.8791 | 2011-09-03 09:53 | 2011-09-07 20:53 | MooredSubInstallation | 610 | 614 | 5
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14653.3791 | 2011-09-03 13:23 | 2011-09-03 16:53 | MooredSubInstallation | 610 | 610 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14656.8791 | 2011-09-03 16:53 | 2011-09-03 20:23 | MooredSubInstallation | 610 | 610 | 1
Array Cable Installation Vessel | Delay | 122 | 610000 | 14672.1964 | 2011-09-04 08:12 | 2011-09-09 10:12 | ArrayCableInstallation | 611 | 616 | 6
Array Cable Installation Vessel | Lay/Bury Cable | 5.991 | 29954.8442 | 14678.1874 | 2011-09-04 14:11 | 2011-09-04 20:11 | ArrayCableInstallation | 611 | 611 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14679.1874 | 2011-09-04 15:11 | 2011-09-04 16:11 | ArrayCableInstallation | 611 | 611 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 14680.8791 | 2011-09-04 16:53 | 2011-09-05 16:53 | MooredSubInstallation | 611 | 612 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 502.5825 | 628228.0655 | 14680.8791 | 2011-09-04 16:53 | 2011-09-25 15:28 | MooredSubInstallation | 611 | 632 | 22
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14684.6874 | 2011-09-04 20:41 | 2011-09-05 02:11 | ArrayCableInstallation | 611 | 612 | 2
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 14686.8791 | 2011-09-04 22:53 | 2011-09-05 04:53 | MooredSubInstallation | 611 | 612 | 2
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 14688.8791 | 2011-09-05 00:53 | 2011-09-05 08:53 | MooredSubInstallation | 612 | 612 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14690.1874 | 2011-09-05 02:11 | 2011-09-05 07:41 | ArrayCableInstallation | 612 | 612 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 14692.1874 | 2011-09-05 04:11 | 2011-09-05 06:11 | ArrayCableInstallation | 612 | 612 | 1
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 14693.0719 | 2011-09-05 05:04 | 2011-09-05 11:16 | MooredSubInstallation | 612 | 612 | 1
Multi-Purpose Support Vessel | Delay | 255 | 1062500 | 14693.0719 | 2011-09-05 05:04 | 2011-09-15 20:04 | MooredSubInstallation | 612 | 622 | 11
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14693.1874 | 2011-09-05 05:11 | 2011-09-05 06:11 | ArrayCableInstallation | 612 | 612 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 14695.0719 | 2011-09-05 07:04 | 2011-09-05 09:04 | MooredSubInstallation | 612 | 612 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14698.6874 | 2011-09-05 10:41 | 2011-09-05 16:11 | ArrayCableInstallation | 612 | 612 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 14700.8791 | 2011-09-05 12:53 | 2011-09-06 00:53 | MooredSubInstallation | 612 | 613 | 2
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 14701.0719 | 2011-09-05 13:04 | 2011-09-05 19:04 | MooredSubInstallation | 612 | 612 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14704.1874 | 2011-09-05 16:11 | 2011-09-05 21:41 | ArrayCableInstallation | 612 | 612 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 14705.1874 | 2011-09-05 17:11 | 2011-09-05 18:11 | ArrayCableInstallation | 612 | 612 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 14712.8791 | 2011-09-06 00:53 | 2011-09-06 12:53 | MooredSubInstallation | 613 | 613 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 14715.1784 | 2011-09-06 03:11 | 2011-09-06 13:10 | ArrayCableInstallation | 613 | 613 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14716.1784 | 2011-09-06 04:11 | 2011-09-06 05:11 | ArrayCableInstallation | 613 | 613 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 14721.0719 | 2011-09-06 09:04 | 2011-09-07 05:04 | MooredSubInstallation | 613 | 614 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14721.6784 | 2011-09-06 09:41 | 2011-09-06 15:11 | ArrayCableInstallation | 613 | 613 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 14724.8791 | 2011-09-06 12:53 | 2011-09-07 00:53 | MooredSubInstallation | 613 | 614 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 14727.0719 | 2011-09-06 15:04 | 2011-09-06 21:04 | MooredSubInstallation | 613 | 613 | 1
Towing Group 3 | Positioning Support | 34 | 42500 | 14727.0719 | 2011-09-06 15:04 | 2011-09-08 01:04 | MooredSubInstallation | 613 | 615 | 3
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14727.1784 | 2011-09-06 15:11 | 2011-09-06 20:41 | ArrayCableInstallation | 613 | 613 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 14729.1784 | 2011-09-06 17:11 | 2011-09-06 19:11 | ArrayCableInstallation | 613 | 613 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14730.1784 | 2011-09-06 18:11 | 2011-09-06 19:11 | ArrayCableInstallation | 613 | 613 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 14731.8791 | 2011-09-06 19:53 | 2011-09-07 02:53 | MooredSubInstallation | 613 | 614 | 2
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 14734.2967 | 2011-09-06 22:18 | 2011-09-07 05:31 | MooredSubInstallation | 613 | 614 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14735.3791 | 2011-09-06 23:23 | 2011-09-07 02:53 | MooredSubInstallation | 613 | 614 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14735.6784 | 2011-09-06 23:41 | 2011-09-07 05:11 | ArrayCableInstallation | 613 | 614 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14738.8791 | 2011-09-07 02:53 | 2011-09-07 06:23 | MooredSubInstallation | 614 | 614 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14741.1784 | 2011-09-07 05:11 | 2011-09-07 10:41 | ArrayCableInstallation | 614 | 614 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 14742.1784 | 2011-09-07 06:11 | 2011-09-07 07:11 | ArrayCableInstallation | 614 | 614 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14742.3791 | 2011-09-07 06:23 | 2011-09-07 09:53 | MooredSubInstallation | 614 | 614 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 14752.1693 | 2011-09-07 16:10 | 2011-09-08 02:10 | ArrayCableInstallation | 614 | 615 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14753.1693 | 2011-09-07 17:10 | 2011-09-07 18:10 | ArrayCableInstallation | 614 | 614 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14758.6693 | 2011-09-07 22:40 | 2011-09-08 04:10 | ArrayCableInstallation | 614 | 615 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14764.1693 | 2011-09-08 04:10 | 2011-09-08 09:40 | ArrayCableInstallation | 615 | 615 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 14766.3791 | 2011-09-08 06:23 | 2011-09-09 06:23 | MooredSubInstallation | 615 | 616 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 437.0825 | 546353.0655 | 14766.3791 | 2011-09-08 06:23 | 2011-09-26 11:28 | MooredSubInstallation | 615 | 633 | 19
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 14772.3791 | 2011-09-08 12:23 | 2011-09-08 18:23 | MooredSubInstallation | 615 | 615 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 14778.5719 | 2011-09-08 18:34 | 2011-09-09 00:46 | MooredSubInstallation | 615 | 616 | 2
Multi-Purpose Support Vessel | Delay | 51.5 | 214583.3333 | 14778.5719 | 2011-09-08 18:34 | 2011-09-10 22:04 | MooredSubInstallation | 615 | 617 | 3
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 14780.5719 | 2011-09-08 20:34 | 2011-09-08 22:34 | MooredSubInstallation | 615 | 615 | 1
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 44 | 0 | 14810.3791 | 2011-09-10 02:23 | 2011-09-17 02:23 | MooredSubInstallation | 617 | 624 | 8
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 14810.3791 | 2011-09-10 02:23 | 2011-09-11 22:23 | MooredSubInstallation | 617 | 618 | 2
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 14818.3791 | 2011-09-10 10:23 | 2011-09-10 18:23 | MooredSubInstallation | 617 | 617 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 14830.3791 | 2011-09-10 22:23 | 2011-09-11 10:23 | MooredSubInstallation | 617 | 618 | 2
Multi-Purpose Support Vessel | Delay | 55 | 229166.6667 | 14835.5719 | 2011-09-11 03:34 | 2011-09-13 10:34 | MooredSubInstallation | 618 | 620 | 3
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 14841.5719 | 2011-09-11 09:34 | 2011-09-11 15:34 | MooredSubInstallation | 618 | 618 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 14842.3791 | 2011-09-11 10:23 | 2011-09-11 22:23 | MooredSubInstallation | 618 | 618 | 1
Array Cable Installation Vessel | Delay | 80 | 400000 | 14844.1693 | 2011-09-11 12:10 | 2011-09-14 20:10 | ArrayCableInstallation | 618 | 621 | 4
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 14846.1693 | 2011-09-11 14:10 | 2011-09-11 16:10 | ArrayCableInstallation | 618 | 618 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14847.1693 | 2011-09-11 15:10 | 2011-09-11 16:10 | ArrayCableInstallation | 618 | 618 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14852.6693 | 2011-09-11 20:40 | 2011-09-12 02:10 | ArrayCableInstallation | 618 | 619 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 14854.3791 | 2011-09-11 22:23 | 2011-09-12 10:23 | MooredSubInstallation | 618 | 619 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14858.1693 | 2011-09-12 02:10 | 2011-09-12 07:40 | ArrayCableInstallation | 619 | 619 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 14859.1693 | 2011-09-12 03:10 | 2011-09-12 04:10 | ArrayCableInstallation | 619 | 619 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 14861.3791 | 2011-09-12 05:23 | 2011-09-12 12:23 | MooredSubInstallation | 619 | 619 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 14861.5719 | 2011-09-12 05:34 | 2011-09-13 01:34 | MooredSubInstallation | 619 | 620 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14864.8791 | 2011-09-12 08:53 | 2011-09-12 12:23 | MooredSubInstallation | 619 | 619 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 14867.5719 | 2011-09-12 11:34 | 2011-09-12 17:34 | MooredSubInstallation | 619 | 619 | 1
Towing Group 1 | Positioning Support | 89 | 111250 | 14867.5719 | 2011-09-12 11:34 | 2011-09-16 04:34 | MooredSubInstallation | 619 | 623 | 5
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14868.3791 | 2011-09-12 12:23 | 2011-09-12 15:53 | MooredSubInstallation | 619 | 619 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 14869.1603 | 2011-09-12 13:10 | 2011-09-12 23:09 | ArrayCableInstallation | 619 | 619 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14870.1603 | 2011-09-12 14:10 | 2011-09-12 15:10 | ArrayCableInstallation | 619 | 619 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 14871.8791 | 2011-09-12 15:53 | 2011-09-12 19:23 | MooredSubInstallation | 619 | 619 | 1
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 14874.7967 | 2011-09-12 18:48 | 2011-09-13 02:01 | MooredSubInstallation | 619 | 620 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14875.6603 | 2011-09-12 19:40 | 2011-09-13 01:10 | ArrayCableInstallation | 619 | 620 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14881.1603 | 2011-09-13 01:10 | 2011-09-13 06:40 | ArrayCableInstallation | 620 | 620 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 14883.1603 | 2011-09-13 03:10 | 2011-09-13 05:10 | ArrayCableInstallation | 620 | 620 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14884.1603 | 2011-09-13 04:10 | 2011-09-13 05:10 | ArrayCableInstallation | 620 | 620 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14889.6603 | 2011-09-13 09:40 | 2011-09-13 15:10 | ArrayCableInstallation | 620 | 620 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14895.1603 | 2011-09-13 15:10 | 2011-09-13 20:40 | ArrayCableInstallation | 620 | 620 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 14895.8791 | 2011-09-13 15:53 | 2011-09-14 15:53 | MooredSubInstallation | 620 | 621 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 450.5825 | 563228.0655 | 14895.8791 | 2011-09-13 15:53 | 2011-10-02 10:28 | MooredSubInstallation | 620 | 639 | 20
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 14896.1603 | 2011-09-13 16:10 | 2011-09-13 17:10 | ArrayCableInstallation | 620 | 620 | 1
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 14901.8791 | 2011-09-13 21:53 | 2011-09-14 03:53 | MooredSubInstallation | 620 | 621 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 8 | 40000 | 14904.1603 | 2011-09-14 00:10 | 2011-09-14 08:10 | ArrayCableInstallation | 621 | 621 | 1
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 14908.0719 | 2011-09-14 04:04 | 2011-09-14 10:16 | MooredSubInstallation | 621 | 621 | 1
Multi-Purpose Support Vessel | Delay | 40.5 | 168750 | 14908.0719 | 2011-09-14 04:04 | 2011-09-15 20:34 | MooredSubInstallation | 621 | 622 | 2
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 14910.0719 | 2011-09-14 06:04 | 2011-09-14 08:04 | MooredSubInstallation | 621 | 621 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 14916.0719 | 2011-09-14 12:04 | 2011-09-14 18:04 | MooredSubInstallation | 621 | 621 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 14936.0719 | 2011-09-15 08:04 | 2011-09-16 04:04 | MooredSubInstallation | 622 | 623 | 2
Array Cable Installation Vessel | Delay | 36 | 180000 | 14940.1603 | 2011-09-15 12:10 | 2011-09-17 00:10 | ArrayCableInstallation | 622 | 624 | 3
Towing Group 2 | Positioning Support | 34 | 42500 | 14942.0719 | 2011-09-15 14:04 | 2011-09-15 20:04 | MooredSubInstallation | 622 | 622 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 14942.0719 | 2011-09-15 14:04 | 2011-09-17 00:04 | MooredSubInstallation | 622 | 624 | 3
Array Cable Installation Vessel | Lay/Bury Cable | 1.991 | 9954.8442 | 14942.1513 | 2011-09-15 14:09 | 2011-09-15 16:09 | ArrayCableInstallation | 622 | 622 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14943.1513 | 2011-09-15 15:09 | 2011-09-15 16:09 | ArrayCableInstallation | 622 | 622 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14948.6513 | 2011-09-15 20:39 | 2011-09-16 02:09 | ArrayCableInstallation | 622 | 623 | 2
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 14949.2967 | 2011-09-15 21:18 | 2011-09-16 04:31 | MooredSubInstallation | 622 | 623 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14954.1513 | 2011-09-16 02:09 | 2011-09-16 07:39 | ArrayCableInstallation | 623 | 623 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 14956.1513 | 2011-09-16 04:09 | 2011-09-16 06:09 | ArrayCableInstallation | 623 | 623 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14957.1513 | 2011-09-16 05:09 | 2011-09-16 06:09 | ArrayCableInstallation | 623 | 623 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14962.6513 | 2011-09-16 10:39 | 2011-09-16 16:09 | ArrayCableInstallation | 623 | 623 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14968.1513 | 2011-09-16 16:09 | 2011-09-16 21:39 | ArrayCableInstallation | 623 | 623 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 14969.1513 | 2011-09-16 17:09 | 2011-09-16 18:09 | ArrayCableInstallation | 623 | 623 | 1
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 14978.3791 | 2011-09-17 02:23 | 2011-09-24 02:23 | MooredSubInstallation | 624 | 631 | 8
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 14978.3791 | 2011-09-17 02:23 | 2011-09-20 12:53 | MooredSubInstallation | 624 | 627 | 4
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 14979.1422 | 2011-09-17 03:09 | 2011-09-17 13:08 | ArrayCableInstallation | 624 | 624 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14980.1422 | 2011-09-17 04:09 | 2011-09-17 05:09 | ArrayCableInstallation | 624 | 624 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14985.6422 | 2011-09-17 09:39 | 2011-09-17 15:09 | ArrayCableInstallation | 624 | 624 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 14986.3791 | 2011-09-17 10:23 | 2011-09-17 18:23 | MooredSubInstallation | 624 | 624 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 14991.1422 | 2011-09-17 15:09 | 2011-09-17 20:39 | ArrayCableInstallation | 624 | 624 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 14993.1422 | 2011-09-17 17:09 | 2011-09-17 19:09 | ArrayCableInstallation | 624 | 624 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 14994.1422 | 2011-09-17 18:09 | 2011-09-17 19:09 | ArrayCableInstallation | 624 | 624 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 14998.3791 | 2011-09-17 22:23 | 2011-09-18 10:23 | MooredSubInstallation | 624 | 625 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 14999.6422 | 2011-09-17 23:39 | 2011-09-18 05:09 | ArrayCableInstallation | 624 | 625 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15005.1422 | 2011-09-18 05:09 | 2011-09-18 10:39 | ArrayCableInstallation | 625 | 625 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 15006.1422 | 2011-09-18 06:09 | 2011-09-18 07:09 | ArrayCableInstallation | 625 | 625 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 15010.3791 | 2011-09-18 10:23 | 2011-09-18 22:23 | MooredSubInstallation | 625 | 625 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 15016.1332 | 2011-09-18 16:08 | 2011-09-19 02:07 | ArrayCableInstallation | 625 | 626 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15017.1332 | 2011-09-18 17:08 | 2011-09-18 18:08 | ArrayCableInstallation | 625 | 625 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 15022.3791 | 2011-09-18 22:23 | 2011-09-19 10:23 | MooredSubInstallation | 625 | 626 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15022.6332 | 2011-09-18 22:38 | 2011-09-19 04:08 | ArrayCableInstallation | 625 | 626 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15028.1332 | 2011-09-19 04:08 | 2011-09-19 09:38 | ArrayCableInstallation | 626 | 626 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 15029.3791 | 2011-09-19 05:23 | 2011-09-19 12:23 | MooredSubInstallation | 626 | 626 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 15030.1332 | 2011-09-19 06:08 | 2011-09-19 08:08 | ArrayCableInstallation | 626 | 626 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15031.1332 | 2011-09-19 07:08 | 2011-09-19 08:08 | ArrayCableInstallation | 626 | 626 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15032.8791 | 2011-09-19 08:53 | 2011-09-19 12:23 | MooredSubInstallation | 626 | 626 | 1
Turbine Assembly Line 1 | Delay | 24 | 0 | 15056.8791 | 2011-09-20 08:53 | 2011-09-21 08:53 | MooredSubInstallation | 627 | 628 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15060.3791 | 2011-09-20 12:23 | 2011-09-20 15:53 | MooredSubInstallation | 627 | 627 | 1
Array Cable Installation Vessel | Delay | 31 | 155000 | 15062.1332 | 2011-09-20 14:08 | 2011-09-21 21:08 | ArrayCableInstallation | 627 | 628 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15063.8791 | 2011-09-20 15:53 | 2011-09-20 19:23 | MooredSubInstallation | 627 | 627 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15067.6332 | 2011-09-20 19:38 | 2011-09-21 01:08 | ArrayCableInstallation | 627 | 628 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15073.1332 | 2011-09-21 01:08 | 2011-09-21 06:38 | ArrayCableInstallation | 628 | 628 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 15074.1332 | 2011-09-21 02:08 | 2011-09-21 03:08 | ArrayCableInstallation | 628 | 628 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 15084.1242 | 2011-09-21 12:07 | 2011-09-21 22:07 | ArrayCableInstallation | 628 | 628 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15085.1242 | 2011-09-21 13:07 | 2011-09-21 14:07 | ArrayCableInstallation | 628 | 628 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 15087.8791 | 2011-09-21 15:53 | 2011-09-22 15:53 | MooredSubInstallation | 628 | 629 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 353.5825 | 441978.0655 | 15087.8791 | 2011-09-21 15:53 | 2011-10-06 09:28 | MooredSubInstallation | 628 | 643 | 16
Towing Group 3 | Delay | 42 | 105000 | 15129.8791 | 2011-09-23 09:53 | 2011-09-25 03:53 | MooredSubInstallation | 630 | 632 | 3
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 15135.8791 | 2011-09-23 15:53 | 2011-09-23 21:53 | MooredSubInstallation | 630 | 630 | 1
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 15142.0719 | 2011-09-23 22:04 | 2011-09-24 04:16 | MooredSubInstallation | 630 | 631 | 2
Multi-Purpose Support Vessel | Delay | 200 | 833333.3333 | 15142.0719 | 2011-09-23 22:04 | 2011-10-02 06:04 | MooredSubInstallation | 630 | 639 | 10
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 15144.0719 | 2011-09-24 00:04 | 2011-09-24 02:04 | MooredSubInstallation | 631 | 631 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 15146.3791 | 2011-09-24 02:23 | 2011-10-01 02:23 | MooredSubInstallation | 631 | 638 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 58.5 | 0 | 15146.3791 | 2011-09-24 02:23 | 2011-09-26 12:53 | MooredSubInstallation | 631 | 633 | 3
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 15150.0719 | 2011-09-24 06:04 | 2011-09-24 12:04 | MooredSubInstallation | 631 | 631 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 15154.3791 | 2011-09-24 10:23 | 2011-09-24 18:23 | MooredSubInstallation | 631 | 631 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 15166.3791 | 2011-09-24 22:23 | 2011-09-25 10:23 | MooredSubInstallation | 631 | 632 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 70833.3333 | 15167.0719 | 2011-09-24 23:04 | 2011-09-25 16:04 | MooredSubInstallation | 631 | 632 | 2
Turbine Assembly Line 1 | Delay | 6 | 0 | 15172.3791 | 2011-09-25 04:23 | 2011-09-25 10:23 | MooredSubInstallation | 632 | 632 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 15184.3791 | 2011-09-25 16:23 | 2011-09-26 04:23 | MooredSubInstallation | 632 | 633 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 15196.3791 | 2011-09-26 04:23 | 2011-09-26 16:23 | MooredSubInstallation | 633 | 633 | 1
Multi-Purpose Support Vessel | Delay | 30 | 125000 | 15197.0719 | 2011-09-26 05:04 | 2011-09-27 11:04 | MooredSubInstallation | 633 | 634 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 12500 | 15200.0719 | 2011-09-26 08:04 | 2011-09-26 11:04 | MooredSubInstallation | 633 | 633 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 15203.3791 | 2011-09-26 11:23 | 2011-09-26 18:23 | MooredSubInstallation | 633 | 633 | 1
Array Cable Installation Vessel | Delay | 120 | 600000 | 15205.1242 | 2011-09-26 13:07 | 2011-10-01 13:07 | ArrayCableInstallation | 633 | 638 | 6
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 15206.0719 | 2011-09-26 14:04 | 2011-09-26 20:04 | MooredSubInstallation | 633 | 633 | 1
Towing Group 3 | Positioning Support | 64 | 80000 | 15206.0719 | 2011-09-26 14:04 | 2011-09-29 06:04 | MooredSubInstallation | 633 | 636 | 4
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15206.8791 | 2011-09-26 14:53 | 2011-09-26 18:23 | MooredSubInstallation | 633 | 633 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15210.3791 | 2011-09-26 18:23 | 2011-09-26 21:53 | MooredSubInstallation | 633 | 633 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15210.6242 | 2011-09-26 18:37 | 2011-09-27 00:07 | ArrayCableInstallation | 633 | 634 | 2
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 15213.2967 | 2011-09-26 21:18 | 2011-09-27 04:31 | MooredSubInstallation | 633 | 634 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15213.8791 | 2011-09-26 21:53 | 2011-09-27 01:23 | MooredSubInstallation | 633 | 634 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15216.1242 | 2011-09-27 00:07 | 2011-09-27 05:37 | ArrayCableInstallation | 634 | 634 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 15237.8791 | 2011-09-27 21:53 | 2011-09-28 21:53 | MooredSubInstallation | 634 | 635 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 363.0825 | 453853.0655 | 15237.8791 | 2011-09-27 21:53 | 2011-10-13 00:58 | MooredSubInstallation | 634 | 650 | 17
Towing Group 1 | Delay | 33 | 82500 | 15270.8791 | 2011-09-29 06:53 | 2011-09-30 15:53 | MooredSubInstallation | 636 | 637 | 2
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 15276.8791 | 2011-09-29 12:53 | 2011-09-29 18:53 | MooredSubInstallation | 636 | 636 | 1
Array Cable Installation Vessel | Delay | 62 | 310000 | 15278.1242 | 2011-09-29 14:07 | 2011-10-02 04:07 | ArrayCableInstallation | 636 | 639 | 4
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 15280.1242 | 2011-09-29 16:07 | 2011-09-29 18:07 | ArrayCableInstallation | 636 | 636 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15281.1242 | 2011-09-29 17:07 | 2011-09-29 18:07 | ArrayCableInstallation | 636 | 636 | 1
Multi-Purpose Support Vessel | Delay | 77 | 320833.3333 | 15283.0719 | 2011-09-29 19:04 | 2011-09-30 01:16 | MooredSubInstallation | 636 | 637 | 2
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 15283.0719 | 2011-09-29 19:04 | 2011-10-03 00:04 | MooredSubInstallation | 636 | 640 | 5
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 15285.0719 | 2011-09-29 21:04 | 2011-09-29 23:04 | MooredSubInstallation | 636 | 636 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15286.6242 | 2011-09-29 22:37 | 2011-09-30 04:07 | ArrayCableInstallation | 636 | 637 | 2
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 15291.0719 | 2011-09-30 03:04 | 2011-09-30 09:04 | MooredSubInstallation | 637 | 637 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15292.1242 | 2011-09-30 04:07 | 2011-09-30 09:37 | ArrayCableInstallation | 637 | 637 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 15293.1242 | 2011-09-30 05:07 | 2011-09-30 06:07 | ArrayCableInstallation | 637 | 637 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 15303.1152 | 2011-09-30 15:07 | 2011-10-01 01:06 | ArrayCableInstallation | 637 | 638 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15304.1152 | 2011-09-30 16:07 | 2011-09-30 17:07 | ArrayCableInstallation | 637 | 637 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15309.6152 | 2011-09-30 21:37 | 2011-10-01 03:07 | ArrayCableInstallation | 637 | 638 | 2
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 15311.0719 | 2011-09-30 23:04 | 2011-10-01 19:04 | MooredSubInstallation | 637 | 638 | 2
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 15314.3791 | 2011-10-01 02:23 | 2011-10-08 02:23 | MooredSubInstallation | 638 | 645 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 76.5 | 0 | 15314.3791 | 2011-10-01 02:23 | 2011-10-04 06:53 | MooredSubInstallation | 638 | 641 | 4
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15315.1152 | 2011-10-01 03:07 | 2011-10-01 08:37 | ArrayCableInstallation | 638 | 638 | 1
Towing Group 1 | Positioning Support | 34 | 42500 | 15317.0719 | 2011-10-01 05:04 | 2011-10-01 11:04 | MooredSubInstallation | 638 | 638 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 15317.0719 | 2011-10-01 05:04 | 2011-10-02 15:04 | MooredSubInstallation | 638 | 639 | 2
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 15317.1152 | 2011-10-01 05:07 | 2011-10-01 07:07 | ArrayCableInstallation | 638 | 638 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15318.1152 | 2011-10-01 06:07 | 2011-10-01 07:07 | ArrayCableInstallation | 638 | 638 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 15322.3791 | 2011-10-01 10:23 | 2011-10-01 18:23 | MooredSubInstallation | 638 | 638 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15323.6152 | 2011-10-01 11:37 | 2011-10-01 17:07 | ArrayCableInstallation | 638 | 638 | 1
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 15324.2967 | 2011-10-01 12:18 | 2011-10-01 19:31 | MooredSubInstallation | 638 | 638 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15329.1152 | 2011-10-01 17:07 | 2011-10-01 22:37 | ArrayCableInstallation | 638 | 638 | 1
Array Cable Installation Vessel | Delay | 2 | 10000 | 15331.1152 | 2011-10-01 19:07 | 2011-10-01 21:07 | ArrayCableInstallation | 638 | 638 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 15332.1152 | 2011-10-01 20:07 | 2011-10-01 21:07 | ArrayCableInstallation | 638 | 638 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 15334.3791 | 2011-10-01 22:23 | 2011-10-02 10:23 | MooredSubInstallation | 638 | 639 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 15342.1061 | 2011-10-02 06:06 | 2011-10-02 16:06 | ArrayCableInstallation | 639 | 639 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15343.1061 | 2011-10-02 07:06 | 2011-10-02 08:06 | ArrayCableInstallation | 639 | 639 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 15346.3791 | 2011-10-02 10:23 | 2011-10-02 22:23 | MooredSubInstallation | 639 | 639 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15348.6061 | 2011-10-02 12:36 | 2011-10-02 18:06 | ArrayCableInstallation | 639 | 639 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15354.1061 | 2011-10-02 18:06 | 2011-10-02 23:36 | ArrayCableInstallation | 639 | 639 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 15356.1061 | 2011-10-02 20:06 | 2011-10-02 22:06 | ArrayCableInstallation | 639 | 639 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15357.1061 | 2011-10-02 21:06 | 2011-10-02 22:06 | ArrayCableInstallation | 639 | 639 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 15358.3791 | 2011-10-02 22:23 | 2011-10-03 10:23 | MooredSubInstallation | 639 | 640 | 2
Turbine Assembly Line 1 | Delay | 7 | 0 | 15365.3791 | 2011-10-03 05:23 | 2011-10-03 12:23 | MooredSubInstallation | 640 | 640 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 15372.3791 | 2011-10-03 12:23 | 2011-10-03 19:23 | MooredSubInstallation | 640 | 640 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15375.8791 | 2011-10-03 15:53 | 2011-10-03 19:23 | MooredSubInstallation | 640 | 640 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15379.3791 | 2011-10-03 19:23 | 2011-10-03 22:53 | MooredSubInstallation | 640 | 640 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15382.8791 | 2011-10-03 22:53 | 2011-10-04 02:23 | MooredSubInstallation | 640 | 641 | 2
Turbine Assembly Line 1 | Delay | 24 | 0 | 15406.8791 | 2011-10-04 22:53 | 2011-10-05 22:53 | MooredSubInstallation | 641 | 642 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 481.5825 | 601978.0655 | 15430.8791 | 2011-10-05 22:53 | 2011-10-06 22:53 | MooredSubInstallation | 642 | 643 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 15430.8791 | 2011-10-05 22:53 | 2011-10-26 00:28 | MooredSubInstallation | 642 | 663 | 22
Towing Group 2 | Delay | 38 | 95000 | 15468.8791 | 2011-10-07 12:53 | 2011-10-09 02:53 | MooredSubInstallation | 644 | 646 | 3
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 15474.8791 | 2011-10-07 18:53 | 2011-10-08 00:53 | MooredSubInstallation | 644 | 645 | 2
Array Cable Installation Vessel | Delay | 119 | 595000 | 15476.1061 | 2011-10-07 20:06 | 2011-10-12 19:06 | ArrayCableInstallation | 644 | 649 | 6
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 15481.0719 | 2011-10-08 01:04 | 2011-10-08 07:16 | MooredSubInstallation | 645 | 645 | 1
Multi-Purpose Support Vessel | Delay | 164 | 683333.3333 | 15481.0719 | 2011-10-08 01:04 | 2011-10-14 21:04 | MooredSubInstallation | 645 | 651 | 7
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15481.6061 | 2011-10-08 01:36 | 2011-10-08 07:06 | ArrayCableInstallation | 645 | 645 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 15482.3791 | 2011-10-08 02:23 | 2011-10-15 02:23 | MooredSubInstallation | 645 | 652 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 51.5 | 0 | 15482.3791 | 2011-10-08 02:23 | 2011-10-10 05:53 | MooredSubInstallation | 645 | 647 | 3
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 15483.0719 | 2011-10-08 03:04 | 2011-10-08 05:04 | MooredSubInstallation | 645 | 645 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15487.1061 | 2011-10-08 07:06 | 2011-10-08 12:36 | ArrayCableInstallation | 645 | 645 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 15488.1061 | 2011-10-08 08:06 | 2011-10-08 09:06 | ArrayCableInstallation | 645 | 645 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 15489.0719 | 2011-10-08 09:04 | 2011-10-08 15:04 | MooredSubInstallation | 645 | 645 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 15490.3791 | 2011-10-08 10:23 | 2011-10-08 18:23 | MooredSubInstallation | 645 | 645 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 15498.0971 | 2011-10-08 18:06 | 2011-10-09 04:05 | ArrayCableInstallation | 645 | 646 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15499.0971 | 2011-10-08 19:06 | 2011-10-08 20:06 | ArrayCableInstallation | 645 | 645 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 15502.3791 | 2011-10-08 22:23 | 2011-10-09 10:23 | MooredSubInstallation | 645 | 646 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15504.5971 | 2011-10-09 00:36 | 2011-10-09 06:06 | ArrayCableInstallation | 646 | 646 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 15509.0719 | 2011-10-09 05:04 | 2011-10-10 01:04 | MooredSubInstallation | 646 | 647 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15510.0971 | 2011-10-09 06:06 | 2011-10-09 11:36 | ArrayCableInstallation | 646 | 646 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 15512.0971 | 2011-10-09 08:06 | 2011-10-09 10:06 | ArrayCableInstallation | 646 | 646 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15513.0971 | 2011-10-09 09:06 | 2011-10-09 10:06 | ArrayCableInstallation | 646 | 646 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 15514.3791 | 2011-10-09 10:23 | 2011-10-09 22:23 | MooredSubInstallation | 646 | 646 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 15515.0719 | 2011-10-09 11:04 | 2011-10-09 17:04 | MooredSubInstallation | 646 | 646 | 1
Towing Group 2 | Positioning Support | 34 | 42500 | 15515.0719 | 2011-10-09 11:04 | 2011-10-10 21:04 | MooredSubInstallation | 646 | 647 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15518.5971 | 2011-10-09 14:36 | 2011-10-09 20:06 | ArrayCableInstallation | 646 | 646 | 1
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 15522.2967 | 2011-10-09 18:18 | 2011-10-10 01:31 | MooredSubInstallation | 646 | 647 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15524.0971 | 2011-10-09 20:06 | 2011-10-10 01:36 | ArrayCableInstallation | 646 | 647 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 15526.3791 | 2011-10-09 22:23 | 2011-10-10 10:23 | MooredSubInstallation | 646 | 647 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 15533.3791 | 2011-10-10 05:23 | 2011-10-10 12:23 | MooredSubInstallation | 647 | 647 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15536.8791 | 2011-10-10 08:53 | 2011-10-10 12:23 | MooredSubInstallation | 647 | 647 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15540.3791 | 2011-10-10 12:23 | 2011-10-10 15:53 | MooredSubInstallation | 647 | 647 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15543.8791 | 2011-10-10 15:53 | 2011-10-10 19:23 | MooredSubInstallation | 647 | 647 | 1
Array Cable Installation Vessel | Delay | 33 | 165000 | 15557.0971 | 2011-10-11 05:06 | 2011-10-12 14:06 | ArrayCableInstallation | 648 | 649 | 2
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 15558.0971 | 2011-10-11 06:06 | 2011-10-11 07:06 | ArrayCableInstallation | 648 | 648 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | 15562.0971 | 2011-10-11 10:06 | 2011-10-11 14:06 | ArrayCableInstallation | 648 | 648 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 15567.8791 | 2011-10-11 15:53 | 2011-10-12 15:53 | MooredSubInstallation | 648 | 649 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 354.5825 | 443228.0655 | 15567.8791 | 2011-10-11 15:53 | 2011-10-26 10:28 | MooredSubInstallation | 648 | 663 | 16
Towing Group 3 | Delay | 54 | 135000 | 15621.8791 | 2011-10-13 21:53 | 2011-10-16 03:53 | MooredSubInstallation | 650 | 653 | 4
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 15627.8791 | 2011-10-14 03:53 | 2011-10-14 09:53 | MooredSubInstallation | 651 | 651 | 1
Multi-Purpose Support Vessel | Delay | 119 | 495833.3333 | 15634.0719 | 2011-10-14 10:04 | 2011-10-14 16:16 | MooredSubInstallation | 651 | 651 | 1
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 15634.0719 | 2011-10-14 10:04 | 2011-10-19 09:04 | MooredSubInstallation | 651 | 656 | 6
Array Cable Installation Vessel | Delay | 73 | 365000 | 15635.0971 | 2011-10-14 11:06 | 2011-10-17 12:06 | ArrayCableInstallation | 651 | 654 | 4
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 15636.0719 | 2011-10-14 12:04 | 2011-10-14 14:04 | MooredSubInstallation | 651 | 651 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 5.991 | 29954.8442 | 15641.0881 | 2011-10-14 17:05 | 2011-10-14 23:05 | ArrayCableInstallation | 651 | 651 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 15642.0719 | 2011-10-14 18:04 | 2011-10-15 00:04 | MooredSubInstallation | 651 | 652 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15642.0881 | 2011-10-14 18:05 | 2011-10-14 19:05 | ArrayCableInstallation | 651 | 651 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15647.5881 | 2011-10-14 23:35 | 2011-10-15 05:05 | ArrayCableInstallation | 651 | 652 | 2
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 15650.3791 | 2011-10-15 02:23 | 2011-10-22 02:23 | MooredSubInstallation | 652 | 659 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | 15650.3791 | 2011-10-15 02:23 | 2011-10-18 12:53 | MooredSubInstallation | 652 | 655 | 4
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15653.0881 | 2011-10-15 05:05 | 2011-10-15 10:35 | ArrayCableInstallation | 652 | 652 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 15655.0881 | 2011-10-15 07:05 | 2011-10-15 09:05 | ArrayCableInstallation | 652 | 652 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15656.0881 | 2011-10-15 08:05 | 2011-10-15 09:05 | ArrayCableInstallation | 652 | 652 | 1
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 15658.3791 | 2011-10-15 10:23 | 2011-10-15 18:23 | MooredSubInstallation | 652 | 652 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15661.5881 | 2011-10-15 13:35 | 2011-10-15 19:05 | ArrayCableInstallation | 652 | 652 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 15662.0719 | 2011-10-15 14:04 | 2011-10-16 10:04 | MooredSubInstallation | 652 | 653 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15667.0881 | 2011-10-15 19:05 | 2011-10-16 00:35 | ArrayCableInstallation | 652 | 653 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 15668.0719 | 2011-10-15 20:04 | 2011-10-16 02:04 | MooredSubInstallation | 652 | 653 | 2
Towing Group 3 | Positioning Support | 34 | 42500 | 15668.0719 | 2011-10-15 20:04 | 2011-10-17 06:04 | MooredSubInstallation | 652 | 654 | 3
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 15668.0881 | 2011-10-15 20:05 | 2011-10-15 21:05 | ArrayCableInstallation | 652 | 652 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 15670.3791 | 2011-10-15 22:23 | 2011-10-16 10:23 | MooredSubInstallation | 652 | 653 | 2
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 15675.2967 | 2011-10-16 03:18 | 2011-10-16 10:31 | MooredSubInstallation | 653 | 653 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 15678.079 | 2011-10-16 06:05 | 2011-10-16 16:04 | ArrayCableInstallation | 653 | 653 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15679.079 | 2011-10-16 07:05 | 2011-10-16 08:05 | ArrayCableInstallation | 653 | 653 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 15682.3791 | 2011-10-16 10:23 | 2011-10-16 22:23 | MooredSubInstallation | 653 | 653 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15684.579 | 2011-10-16 12:35 | 2011-10-16 18:05 | ArrayCableInstallation | 653 | 653 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15690.079 | 2011-10-16 18:05 | 2011-10-16 23:35 | ArrayCableInstallation | 653 | 653 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 15692.079 | 2011-10-16 20:05 | 2011-10-16 22:05 | ArrayCableInstallation | 653 | 653 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15693.079 | 2011-10-16 21:05 | 2011-10-16 22:05 | ArrayCableInstallation | 653 | 653 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 15694.3791 | 2011-10-16 22:23 | 2011-10-17 10:23 | MooredSubInstallation | 653 | 654 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15698.579 | 2011-10-17 02:35 | 2011-10-17 08:05 | ArrayCableInstallation | 654 | 654 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 15701.3791 | 2011-10-17 05:23 | 2011-10-17 12:23 | MooredSubInstallation | 654 | 654 | 1
Turbine Assembly Line 1 | Delay | 9 | 0 | 15710.3791 | 2011-10-17 14:23 | 2011-10-17 23:23 | MooredSubInstallation | 654 | 654 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15713.8791 | 2011-10-17 17:53 | 2011-10-17 21:23 | MooredSubInstallation | 654 | 654 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15717.3791 | 2011-10-17 21:23 | 2011-10-18 00:53 | MooredSubInstallation | 654 | 655 | 2
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15720.8791 | 2011-10-18 00:53 | 2011-10-18 04:23 | MooredSubInstallation | 655 | 655 | 1
Array Cable Installation Vessel | Delay | 32 | 160000 | 15730.579 | 2011-10-18 10:35 | 2011-10-19 18:35 | ArrayCableInstallation | 655 | 656 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15736.079 | 2011-10-18 16:05 | 2011-10-18 21:35 | ArrayCableInstallation | 655 | 655 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 15737.079 | 2011-10-18 17:05 | 2011-10-18 18:05 | ArrayCableInstallation | 655 | 655 | 1
Towing Group 1 | Delay: No Completed Assemblies Available | 420.5825 | 525728.0655 | 15744.8791 | 2011-10-19 00:53 | 2011-10-20 00:53 | MooredSubInstallation | 656 | 657 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 15744.8791 | 2011-10-19 00:53 | 2011-11-05 13:28 | MooredSubInstallation | 656 | 673 | 18
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 15747.07 | 2011-10-19 03:04 | 2011-10-19 13:04 | ArrayCableInstallation | 656 | 656 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15748.07 | 2011-10-19 04:04 | 2011-10-19 05:04 | ArrayCableInstallation | 656 | 656 | 1
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 15750.8791 | 2011-10-19 06:53 | 2011-10-19 12:53 | MooredSubInstallation | 656 | 656 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15753.57 | 2011-10-19 09:34 | 2011-10-19 15:04 | ArrayCableInstallation | 656 | 656 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 15757.0719 | 2011-10-19 13:04 | 2011-10-19 19:16 | MooredSubInstallation | 656 | 656 | 1
Multi-Purpose Support Vessel | Delay | 89 | 370833.3333 | 15757.0719 | 2011-10-19 13:04 | 2011-10-23 06:04 | MooredSubInstallation | 656 | 660 | 5
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15759.07 | 2011-10-19 15:04 | 2011-10-19 20:34 | ArrayCableInstallation | 656 | 656 | 1
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 15759.0719 | 2011-10-19 15:04 | 2011-10-19 17:04 | MooredSubInstallation | 656 | 656 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 15761.07 | 2011-10-19 17:04 | 2011-10-19 19:04 | ArrayCableInstallation | 656 | 656 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15762.07 | 2011-10-19 18:04 | 2011-10-19 19:04 | ArrayCableInstallation | 656 | 656 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 15765.0719 | 2011-10-19 21:04 | 2011-10-20 03:04 | MooredSubInstallation | 656 | 657 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15767.57 | 2011-10-19 23:34 | 2011-10-20 05:04 | ArrayCableInstallation | 656 | 657 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15773.07 | 2011-10-20 05:04 | 2011-10-20 10:34 | ArrayCableInstallation | 657 | 657 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 15774.07 | 2011-10-20 06:04 | 2011-10-20 07:04 | ArrayCableInstallation | 657 | 657 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | 15784.061 | 2011-10-20 16:04 | 2011-10-21 02:03 | ArrayCableInstallation | 657 | 658 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15785.061 | 2011-10-20 17:04 | 2011-10-20 18:04 | ArrayCableInstallation | 657 | 657 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 15785.0719 | 2011-10-20 17:04 | 2011-10-21 13:04 | MooredSubInstallation | 657 | 658 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15790.561 | 2011-10-20 22:34 | 2011-10-21 04:04 | ArrayCableInstallation | 657 | 658 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 15791.0719 | 2011-10-20 23:04 | 2011-10-21 05:04 | MooredSubInstallation | 657 | 658 | 2
Towing Group 1 | Positioning Support | 34 | 42500 | 15791.0719 | 2011-10-20 23:04 | 2011-10-22 09:04 | MooredSubInstallation | 657 | 659 | 3
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15796.061 | 2011-10-21 04:04 | 2011-10-21 09:34 | ArrayCableInstallation | 658 | 658 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 15798.061 | 2011-10-21 06:04 | 2011-10-21 08:04 | ArrayCableInstallation | 658 | 658 | 1
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 15798.2967 | 2011-10-21 06:18 | 2011-10-21 13:31 | MooredSubInstallation | 658 | 658 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15799.061 | 2011-10-21 07:04 | 2011-10-21 08:04 | ArrayCableInstallation | 658 | 658 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15804.561 | 2011-10-21 12:34 | 2011-10-21 18:04 | ArrayCableInstallation | 658 | 658 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15810.061 | 2011-10-21 18:04 | 2011-10-21 23:34 | ArrayCableInstallation | 658 | 658 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 15811.061 | 2011-10-21 19:04 | 2011-10-21 20:04 | ArrayCableInstallation | 658 | 658 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 15818.3791 | 2011-10-22 02:23 | 2011-10-29 02:23 | MooredSubInstallation | 659 | 666 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 73.5 | 0 | 15818.3791 | 2011-10-22 02:23 | 2011-10-25 03:53 | MooredSubInstallation | 659 | 662 | 4
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 15826.3791 | 2011-10-22 10:23 | 2011-10-22 18:23 | MooredSubInstallation | 659 | 659 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 20 | 100000 | 15831.061 | 2011-10-22 15:04 | 2011-10-23 11:04 | ArrayCableInstallation | 659 | 660 | 2
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 15838.3791 | 2011-10-22 22:23 | 2011-10-23 10:23 | MooredSubInstallation | 659 | 660 | 2
Turbine Assembly Line 1 | Delay | 82 | 0 | 15920.3791 | 2011-10-26 08:23 | 2011-10-29 18:23 | MooredSubInstallation | 663 | 666 | 4
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 15932.3791 | 2011-10-26 20:23 | 2011-10-27 08:23 | MooredSubInstallation | 663 | 664 | 2
Turbine Assembly Line 1 | Delay | 12 | 0 | 15944.3791 | 2011-10-27 08:23 | 2011-10-27 20:23 | MooredSubInstallation | 664 | 664 | 1
Array Cable Installation Vessel | Delay | 119 | 595000 | 15950.061 | 2011-10-27 14:04 | 2011-11-01 13:04 | ArrayCableInstallation | 664 | 669 | 6
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 15956.3791 | 2011-10-27 20:23 | 2011-10-28 08:23 | MooredSubInstallation | 664 | 665 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 10.2057 | 51028.4666 | 15960.2667 | 2011-10-28 00:16 | 2011-10-28 10:28 | ArrayCableInstallation | 665 | 665 | 1
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 15963.3791 | 2011-10-28 03:23 | 2011-10-28 10:23 | MooredSubInstallation | 665 | 665 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15966.8791 | 2011-10-28 06:53 | 2011-10-28 10:23 | MooredSubInstallation | 665 | 665 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15970.3791 | 2011-10-28 10:23 | 2011-10-28 13:53 | MooredSubInstallation | 665 | 665 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 15973.8791 | 2011-10-28 13:53 | 2011-10-28 17:23 | MooredSubInstallation | 665 | 665 | 1
Array Cable Installation Vessel | Delay | 23 | 115000 | 15983.2667 | 2011-10-28 23:16 | 2011-10-29 22:16 | ArrayCableInstallation | 665 | 666 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 15984.2667 | 2011-10-29 00:16 | 2011-10-29 01:16 | ArrayCableInstallation | 666 | 666 | 1
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 15986.3791 | 2011-10-29 02:23 | 2011-11-05 02:23 | MooredSubInstallation | 666 | 673 | 8
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 15989.7667 | 2011-10-29 05:46 | 2011-10-29 11:16 | ArrayCableInstallation | 666 | 666 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 15995.2667 | 2011-10-29 11:16 | 2011-10-29 16:46 | ArrayCableInstallation | 666 | 666 | 1
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 15997.8791 | 2011-10-29 13:53 | 2011-10-30 13:53 | MooredSubInstallation | 666 | 667 | 2
Towing Group 2 | Delay: No Completed Assemblies Available | 475.5825 | 594478.0655 | 15997.8791 | 2011-10-29 13:53 | 2011-11-18 09:28 | MooredSubInstallation | 666 | 686 | 21
Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | 15999.0361 | 2011-10-29 15:02 | 2011-10-29 18:48 | ArrayCableInstallation | 666 | 666 | 1
Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | 16003.8791 | 2011-10-29 19:53 | 2011-10-30 01:53 | MooredSubInstallation | 666 | 667 | 2
Array Cable Installation Vessel | Load Cable | 6 | 30000 | 16005.0361 | 2011-10-29 21:02 | 2011-10-30 03:02 | ArrayCableInstallation | 666 | 667 | 2
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 16005.8791 | 2011-10-29 21:53 | 2011-10-30 05:53 | MooredSubInstallation | 666 | 667 | 2
Array Cable Installation Vessel | Transit | 2 | 10000 | 16007.0361 | 2011-10-29 23:02 | 2011-10-30 01:02 | ArrayCableInstallation | 666 | 667 | 2
Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | 16010.0719 | 2011-10-30 02:04 | 2011-10-30 08:16 | MooredSubInstallation | 667 | 667 | 1
Multi-Purpose Support Vessel | Delay | 219 | 912500 | 16010.0719 | 2011-10-30 02:04 | 2011-11-08 05:04 | MooredSubInstallation | 667 | 676 | 10
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 16012.0719 | 2011-10-30 04:04 | 2011-10-30 06:04 | MooredSubInstallation | 667 | 667 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 16017.8791 | 2011-10-30 09:53 | 2011-10-30 21:53 | MooredSubInstallation | 667 | 667 | 1
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 16018.0719 | 2011-10-30 10:04 | 2011-10-30 16:04 | MooredSubInstallation | 667 | 667 | 1
Array Cable Installation Vessel | Delay | 19 | 95000 | 16026.0361 | 2011-10-30 18:02 | 2011-10-31 13:02 | ArrayCableInstallation | 667 | 668 | 2
Array Cable Installation Vessel | Transit | 1.7695 | 8847.3913 | 16027.8056 | 2011-10-30 19:48 | 2011-10-30 21:35 | ArrayCableInstallation | 667 | 667 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 16029.8056 | 2011-10-30 21:48 | 2011-10-30 23:48 | ArrayCableInstallation | 667 | 667 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 16029.8791 | 2011-10-30 21:53 | 2011-10-31 09:53 | MooredSubInstallation | 667 | 668 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 16030.8056 | 2011-10-30 22:48 | 2011-10-30 23:48 | ArrayCableInstallation | 667 | 667 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 16036.3056 | 2011-10-31 04:18 | 2011-10-31 09:48 | ArrayCableInstallation | 668 | 668 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 16038.0719 | 2011-10-31 06:04 | 2011-11-01 02:04 | MooredSubInstallation | 668 | 669 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 16041.8791 | 2011-10-31 09:53 | 2011-10-31 21:53 | MooredSubInstallation | 668 | 668 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 4 | 16666.6667 | 16042.0719 | 2011-10-31 10:04 | 2011-10-31 14:04 | MooredSubInstallation | 668 | 668 | 1
Turbine Assembly Line 1 | Delay | 35 | 0 | 16076.8791 | 2011-11-01 20:53 | 2011-11-03 07:53 | MooredSubInstallation | 669 | 671 | 3
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 16083.8791 | 2011-11-02 03:53 | 2011-11-02 10:53 | MooredSubInstallation | 670 | 670 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 16087.3791 | 2011-11-02 07:23 | 2011-11-02 10:53 | MooredSubInstallation | 670 | 670 | 1
Multi-Purpose Support Vessel | Delay | 48 | 200000 | 16090.0719 | 2011-11-02 10:04 | 2011-11-04 10:04 | MooredSubInstallation | 670 | 672 | 3
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 16090.8791 | 2011-11-02 10:53 | 2011-11-02 14:23 | MooredSubInstallation | 670 | 670 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 2 | 8333.3333 | 16092.0719 | 2011-11-02 12:04 | 2011-11-02 14:04 | MooredSubInstallation | 670 | 670 | 1
Towing Group 2 | Positioning Support | 82 | 102500 | 16092.0719 | 2011-11-02 12:04 | 2011-11-05 22:04 | MooredSubInstallation | 670 | 673 | 4
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 16094.3791 | 2011-11-02 14:23 | 2011-11-02 17:53 | MooredSubInstallation | 670 | 670 | 1
Array Cable Installation Vessel | Delay | 61 | 305000 | 16097.3056 | 2011-11-02 17:18 | 2011-11-05 06:18 | ArrayCableInstallation | 670 | 673 | 4
Towing Group 2 | Transit | 7.2248 | 18062.0833 | 16099.2967 | 2011-11-02 19:18 | 2011-11-03 02:31 | MooredSubInstallation | 670 | 671 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 16102.8056 | 2011-11-02 22:48 | 2011-11-03 04:18 | ArrayCableInstallation | 670 | 671 | 2
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 16103.8056 | 2011-11-02 23:48 | 2011-11-03 00:48 | ArrayCableInstallation | 670 | 671 | 2
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 16118.3791 | 2011-11-03 14:23 | 2011-11-04 14:23 | MooredSubInstallation | 671 | 672 | 2
Towing Group 3 | Delay: No Completed Assemblies Available | 443.0825 | 553853.0655 | 16118.3791 | 2011-11-03 14:23 | 2011-11-22 01:28 | MooredSubInstallation | 671 | 690 | 20
Array Cable Installation Vessel | Lay/Bury Cable | 19 | 95000 | 16122.8056 | 2011-11-03 18:48 | 2011-11-04 13:48 | ArrayCableInstallation | 671 | 672 | 2
Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | 16124.3791 | 2011-11-03 20:23 | 2011-11-04 02:23 | MooredSubInstallation | 671 | 672 | 2
Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | 16154.3791 | 2011-11-05 02:23 | 2011-11-12 02:23 | MooredSubInstallation | 673 | 680 | 8
Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 36 | 0 | 16154.3791 | 2011-11-05 02:23 | 2011-11-06 14:23 | MooredSubInstallation | 673 | 674 | 2
Turbine Assembly Line 1 | Move Substructure | 8 | 0 | 16162.3791 | 2011-11-05 10:23 | 2011-11-05 18:23 | MooredSubInstallation | 673 | 673 | 1
Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | 16174.3791 | 2011-11-05 22:23 | 2011-11-06 10:23 | MooredSubInstallation | 673 | 674 | 2
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 16186.3791 | 2011-11-06 10:23 | 2011-11-06 22:23 | MooredSubInstallation | 674 | 674 | 1
Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | 16198.3791 | 2011-11-06 22:23 | 2011-11-07 10:23 | MooredSubInstallation | 674 | 675 | 2
Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | 16205.3791 | 2011-11-07 05:23 | 2011-11-07 12:23 | MooredSubInstallation | 675 | 675 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 16208.8791 | 2011-11-07 08:53 | 2011-11-07 12:23 | MooredSubInstallation | 675 | 675 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 16212.3791 | 2011-11-07 12:23 | 2011-11-07 15:53 | MooredSubInstallation | 675 | 675 | 1
Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | 16215.8791 | 2011-11-07 15:53 | 2011-11-07 19:23 | MooredSubInstallation | 675 | 675 | 1
Towing Group 3 | Delay | 104 | 260000 | 16228.3791 | 2011-11-08 04:23 | 2011-11-12 12:23 | MooredSubInstallation | 676 | 680 | 5
Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | 16234.5719 | 2011-11-08 10:34 | 2011-11-08 16:46 | MooredSubInstallation | 676 | 676 | 1
Multi-Purpose Support Vessel | Delay | 142.5 | 593750 | 16234.5719 | 2011-11-08 10:34 | 2011-11-14 09:04 | MooredSubInstallation | 676 | 682 | 7
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 16236.5719 | 2011-11-08 12:34 | 2011-11-08 14:34 | MooredSubInstallation | 676 | 676 | 1
Array Cable Installation Vessel | Delay | 115 | 575000 | 16237.8056 | 2011-11-08 13:48 | 2011-11-13 08:48 | ArrayCableInstallation | 676 | 681 | 6
Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | 16239.8791 | 2011-11-08 15:53 | 2011-11-09 15:53 | MooredSubInstallation | 676 | 677 | 2
Towing Group 1 | Delay: No Completed Assemblies Available | 441.5825 | 551978.0655 | 16239.8791 | 2011-11-08 15:53 | 2011-11-27 01:28 | MooredSubInstallation | 676 | 695 | 20
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 16242.5719 | 2011-11-08 18:34 | 2011-11-09 00:34 | MooredSubInstallation | 676 | 677 | 2
Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | 16245.8791 | 2011-11-08 21:53 | 2011-11-09 03:53 | MooredSubInstallation | 676 | 677 | 2
Array Cable Installation Vessel | Lay/Bury Cable | 11.2057 | 56028.4666 | 16249.0113 | 2011-11-09 01:01 | 2011-11-09 12:13 | ArrayCableInstallation | 677 | 677 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 16250.0113 | 2011-11-09 02:01 | 2011-11-09 03:01 | ArrayCableInstallation | 677 | 677 | 1
Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | 16252.0719 | 2011-11-09 04:04 | 2011-11-09 10:16 | MooredSubInstallation | 677 | 677 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 16255.5113 | 2011-11-09 07:31 | 2011-11-09 13:01 | ArrayCableInstallation | 677 | 677 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 16261.0113 | 2011-11-09 13:01 | 2011-11-09 18:31 | ArrayCableInstallation | 677 | 677 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | 16262.5719 | 2011-11-09 14:34 | 2011-11-10 10:34 | MooredSubInstallation | 677 | 678 | 2
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 16263.0113 | 2011-11-09 15:01 | 2011-11-09 17:01 | ArrayCableInstallation | 677 | 677 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 16264.0113 | 2011-11-09 16:01 | 2011-11-09 17:01 | ArrayCableInstallation | 677 | 677 | 1
Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | 16268.5719 | 2011-11-09 20:34 | 2011-11-10 02:34 | MooredSubInstallation | 677 | 678 | 2
Towing Group 3 | Positioning Support | 34 | 42500 | 16268.5719 | 2011-11-09 20:34 | 2011-11-11 06:34 | MooredSubInstallation | 677 | 679 | 3
Towing Group 1 | Queue | 16.5 | 20625 | 16268.5719 | 2011-11-09 20:34 | 2011-11-10 13:04 | MooredSubInstallation | 677 | 678 | 2
Multi-Purpose Support Vessel | Delay | 0 | 0 | 16268.5719 | 2011-11-09 20:34 | 2011-11-09 20:34 | MooredSubInstallation | 677 | 677 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 16269.5113 | 2011-11-09 21:31 | 2011-11-10 03:01 | ArrayCableInstallation | 677 | 678 | 2
Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | 16270.5719 | 2011-11-09 22:34 | 2011-11-10 00:34 | MooredSubInstallation | 677 | 678 | 2
Towing Group 3 | Transit | 7.2248 | 18062.0833 | 16275.7967 | 2011-11-10 03:48 | 2011-11-10 11:01 | MooredSubInstallation | 678 | 678 | 1
Multi-Purpose Support Vessel | Delay | 53 | 220833.3333 | 16323.5719 | 2011-11-12 03:34 | 2011-11-14 08:34 | MooredSubInstallation | 680 | 682 | 3
Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | 16329.5719 | 2011-11-12 09:34 | 2011-11-12 15:34 | MooredSubInstallation | 680 | 680 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 45833.3333 | 16340.5719 | 2011-11-12 20:34 | 2011-11-13 07:34 | MooredSubInstallation | 680 | 681 | 2
Multi-Purpose Support Vessel | Delay | 10 | 41666.6667 | 16350.5719 | 2011-11-13 06:34 | 2011-11-13 16:34 | MooredSubInstallation | 681 | 681 | 1
Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 37500 | 16359.5719 | 2011-11-13 15:34 | 2011-11-14 00:34 | MooredSubInstallation | 681 | 682 | 2
Multi-Purpose Support Vessel | Check Mooring Lines | 5 | 20833.3333 | 16364.5719 | 2011-11-13 20:34 | 2011-11-14 01:34 | MooredSubInstallation | 681 | 682 | 2
Multi-Purpose Support Vessel | Delay | 67 | 279166.6667 | 16431.5719 | 2011-11-16 15:34 | 2011-11-19 10:34 | MooredSubInstallation | 684 | 687 | 4
Multi-Purpose Support Vessel | Check Mooring Lines | 1 | 4166.6667 | 16432.5719 | 2011-11-16 16:34 | 2011-11-16 17:34 | MooredSubInstallation | 684 | 684 | 1
Towing Group 1 | Positioning Support | 164 | 205000 | 16432.5719 | 2011-11-16 16:34 | 2011-11-23 12:34 | MooredSubInstallation | 684 | 691 | 8
Multi-Purpose Support Vessel | Transit | 4.3349 | 18062.0833 | 16436.9068 | 2011-11-16 20:54 | 2011-11-17 01:14 | MooredSubInstallation | 684 | 685 | 2
Array Cable Installation Vessel | Delay | 169 | 845000 | 16438.5113 | 2011-11-16 22:31 | 2011-11-23 23:31 | ArrayCableInstallation | 684 | 691 | 8
Towing Group 1 | Transit | 7.2248 | 18062.0833 | 16439.7967 | 2011-11-16 23:48 | 2011-11-17 07:01 | MooredSubInstallation | 684 | 685 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 16444.0113 | 2011-11-17 04:01 | 2011-11-17 09:31 | ArrayCableInstallation | 685 | 685 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 16445.0113 | 2011-11-17 05:01 | 2011-11-17 06:01 | ArrayCableInstallation | 685 | 685 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 5 | 25000 | 16450.0113 | 2011-11-17 10:01 | 2011-11-17 15:01 | ArrayCableInstallation | 685 | 685 | 1
Array Cable Installation Vessel | Delay | 232 | 1160000 | 16682.0113 | 2011-11-27 02:01 | 2011-12-06 18:01 | ArrayCableInstallation | 695 | 704 | 10
Array Cable Installation Vessel | Lay/Bury Cable | 12 | 60000 | 16694.0113 | 2011-11-27 14:01 | 2011-11-28 02:01 | ArrayCableInstallation | 695 | 696 | 2
Array Cable Installation Vessel | Delay | 213 | 1065000 | 16907.0113 | 2011-12-06 11:01 | 2011-12-15 08:01 | ArrayCableInstallation | 704 | 713 | 10
Array Cable Installation Vessel | Lay/Bury Cable | 7.7753 | 38876.3827 | 16914.7866 | 2011-12-06 18:47 | 2011-12-07 02:34 | ArrayCableInstallation | 704 | 705 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 16915.7866 | 2011-12-06 19:47 | 2011-12-06 20:47 | ArrayCableInstallation | 704 | 704 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 16921.2866 | 2011-12-07 01:17 | 2011-12-07 06:47 | ArrayCableInstallation | 705 | 705 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 16926.7866 | 2011-12-07 06:47 | 2011-12-07 12:17 | ArrayCableInstallation | 705 | 705 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 16928.7866 | 2011-12-07 08:47 | 2011-12-07 10:47 | ArrayCableInstallation | 705 | 705 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 16929.7866 | 2011-12-07 09:47 | 2011-12-07 10:47 | ArrayCableInstallation | 705 | 705 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 16935.2866 | 2011-12-07 15:17 | 2011-12-07 20:47 | ArrayCableInstallation | 705 | 705 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 16940.7866 | 2011-12-07 20:47 | 2011-12-08 02:17 | ArrayCableInstallation | 705 | 706 | 2
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 16941.7866 | 2011-12-07 21:47 | 2011-12-07 22:47 | ArrayCableInstallation | 705 | 705 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 7 | 35000 | 16948.7866 | 2011-12-08 04:47 | 2011-12-08 11:47 | ArrayCableInstallation | 706 | 706 | 1
Array Cable Installation Vessel | Delay | 130 | 650000 | 17078.7866 | 2011-12-13 14:47 | 2011-12-19 00:47 | ArrayCableInstallation | 711 | 717 | 7
Array Cable Installation Vessel | Lay/Bury Cable | 17.7753 | 88876.3827 | 17096.5619 | 2011-12-14 08:34 | 2011-12-15 02:20 | ArrayCableInstallation | 712 | 713 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 17097.5619 | 2011-12-14 09:34 | 2011-12-14 10:34 | ArrayCableInstallation | 712 | 712 | 1
Array Cable Installation Vessel | Delay | 204 | 1020000 | 17301.5619 | 2011-12-22 21:34 | 2011-12-31 09:34 | ArrayCableInstallation | 720 | 729 | 10
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 17307.0619 | 2011-12-23 03:04 | 2011-12-23 08:34 | ArrayCableInstallation | 721 | 721 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 17312.5619 | 2011-12-23 08:34 | 2011-12-23 14:04 | ArrayCableInstallation | 721 | 721 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 17314.5619 | 2011-12-23 10:34 | 2011-12-23 12:34 | ArrayCableInstallation | 721 | 721 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 17315.5619 | 2011-12-23 11:34 | 2011-12-23 12:34 | ArrayCableInstallation | 721 | 721 | 1
Array Cable Installation Vessel | Delay | 218 | 1090000 | 17533.5619 | 2012-01-01 13:34 | 2012-01-10 15:34 | ArrayCableInstallation | 730 | 739 | 10
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 17539.0619 | 2012-01-01 19:04 | 2012-01-02 00:34 | ArrayCableInstallation | 730 | 731 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 17544.5619 | 2012-01-02 00:34 | 2012-01-02 06:04 | ArrayCableInstallation | 731 | 731 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 17545.5619 | 2012-01-02 01:34 | 2012-01-02 02:34 | ArrayCableInstallation | 731 | 731 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | 17549.5619 | 2012-01-02 05:34 | 2012-01-02 09:34 | ArrayCableInstallation | 731 | 731 | 1
Array Cable Installation Vessel | Delay | 156 | 780000 | 17705.5619 | 2012-01-08 17:34 | 2012-01-15 05:34 | ArrayCableInstallation | 737 | 744 | 8
Array Cable Installation Vessel | Lay/Bury Cable | 6 | 30000 | 17711.5619 | 2012-01-08 23:34 | 2012-01-09 05:34 | ArrayCableInstallation | 737 | 738 | 2
Array Cable Installation Vessel | Delay | 85 | 425000 | 17796.5619 | 2012-01-12 12:34 | 2012-01-16 01:34 | ArrayCableInstallation | 741 | 745 | 5
Array Cable Installation Vessel | Lay/Bury Cable | 9.4694 | 47347.1515 | 17806.0313 | 2012-01-12 22:02 | 2012-01-13 07:30 | ArrayCableInstallation | 741 | 742 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 17807.0313 | 2012-01-12 23:02 | 2012-01-13 00:02 | ArrayCableInstallation | 741 | 742 | 2
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 17812.5313 | 2012-01-13 04:32 | 2012-01-13 10:02 | ArrayCableInstallation | 742 | 742 | 1
Array Cable Installation Vessel | Delay | 30 | 150000 | 17842.5313 | 2012-01-14 10:32 | 2012-01-15 16:32 | ArrayCableInstallation | 743 | 744 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 17848.0313 | 2012-01-14 16:02 | 2012-01-14 21:32 | ArrayCableInstallation | 743 | 743 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 17850.0313 | 2012-01-14 18:02 | 2012-01-14 20:02 | ArrayCableInstallation | 743 | 743 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 17851.0313 | 2012-01-14 19:02 | 2012-01-14 20:02 | ArrayCableInstallation | 743 | 743 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 17856.5313 | 2012-01-15 00:32 | 2012-01-15 06:02 | ArrayCableInstallation | 744 | 744 | 1
Array Cable Installation Vessel | Delay | 334 | 1670000 | 18190.5313 | 2012-01-28 22:32 | 2012-02-11 20:32 | ArrayCableInstallation | 757 | 771 | 15
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 18196.0313 | 2012-01-29 04:02 | 2012-01-29 09:32 | ArrayCableInstallation | 758 | 758 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 18197.0313 | 2012-01-29 05:02 | 2012-01-29 06:02 | ArrayCableInstallation | 758 | 758 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 19.4694 | 97347.1515 | 18216.5007 | 2012-01-30 00:30 | 2012-01-30 19:58 | ArrayCableInstallation | 759 | 759 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 18217.5007 | 2012-01-30 01:30 | 2012-01-30 02:30 | ArrayCableInstallation | 759 | 759 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 18223.0007 | 2012-01-30 07:00 | 2012-01-30 12:30 | ArrayCableInstallation | 759 | 759 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 18228.5007 | 2012-01-30 12:30 | 2012-01-30 18:00 | ArrayCableInstallation | 759 | 759 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 18230.5007 | 2012-01-30 14:30 | 2012-01-30 16:30 | ArrayCableInstallation | 759 | 759 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 18231.5007 | 2012-01-30 15:30 | 2012-01-30 16:30 | ArrayCableInstallation | 759 | 759 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 18237.0007 | 2012-01-30 21:00 | 2012-01-31 02:30 | ArrayCableInstallation | 759 | 760 | 2
Array Cable Installation Vessel | Delay | 76 | 380000 | 18313.0007 | 2012-02-03 01:00 | 2012-02-06 05:00 | ArrayCableInstallation | 763 | 766 | 4
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 18318.5007 | 2012-02-03 06:30 | 2012-02-03 12:00 | ArrayCableInstallation | 763 | 763 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 18319.5007 | 2012-02-03 07:30 | 2012-02-03 08:30 | ArrayCableInstallation | 763 | 763 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | 18320.5007 | 2012-02-03 08:30 | 2012-02-03 09:30 | ArrayCableInstallation | 763 | 763 | 1
Array Cable Installation Vessel | Delay | 1 | 5000 | 18321.5007 | 2012-02-03 09:30 | 2012-02-03 10:30 | ArrayCableInstallation | 763 | 763 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 10 | 50000 | 18331.5007 | 2012-02-03 19:30 | 2012-02-04 05:30 | ArrayCableInstallation | 763 | 764 | 2
Array Cable Installation Vessel | Delay | 684 | 3420000 | 19015.5007 | 2012-03-03 07:30 | 2012-03-31 19:30 | ArrayCableInstallation | 792 | 820 | 29
Array Cable Installation Vessel | Lay/Bury Cable | 3.4865 | 17432.5621 | 19018.9872 | 2012-03-03 10:59 | 2012-03-03 14:28 | ArrayCableInstallation | 792 | 792 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 19019.9872 | 2012-03-03 11:59 | 2012-03-03 12:59 | ArrayCableInstallation | 792 | 792 | 1
Array Cable Installation Vessel | Delay | 5 | 25000 | 19024.9872 | 2012-03-03 16:59 | 2012-03-03 21:59 | ArrayCableInstallation | 792 | 792 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 19030.4872 | 2012-03-03 22:29 | 2012-03-04 03:59 | ArrayCableInstallation | 792 | 793 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 19035.9872 | 2012-03-04 03:59 | 2012-03-04 09:29 | ArrayCableInstallation | 793 | 793 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 19037.9872 | 2012-03-04 05:59 | 2012-03-04 07:59 | ArrayCableInstallation | 793 | 793 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 19038.9872 | 2012-03-04 06:59 | 2012-03-04 07:59 | ArrayCableInstallation | 793 | 793 | 1
Array Cable Installation Vessel | Delay | 37 | 185000 | 19075.9872 | 2012-03-05 19:59 | 2012-03-07 08:59 | ArrayCableInstallation | 794 | 796 | 3
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 19081.4872 | 2012-03-06 01:29 | 2012-03-06 06:59 | ArrayCableInstallation | 795 | 795 | 1
Array Cable Installation Vessel | Delay | 56 | 280000 | 19137.4872 | 2012-03-08 09:29 | 2012-03-10 17:29 | ArrayCableInstallation | 797 | 799 | 3
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 19142.9872 | 2012-03-08 14:59 | 2012-03-08 20:29 | ArrayCableInstallation | 797 | 797 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 19143.9872 | 2012-03-08 15:59 | 2012-03-08 16:59 | ArrayCableInstallation | 797 | 797 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 14.4865 | 72432.5621 | 19158.4737 | 2012-03-09 06:28 | 2012-03-09 20:58 | ArrayCableInstallation | 798 | 798 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 19159.4737 | 2012-03-09 07:28 | 2012-03-09 08:28 | ArrayCableInstallation | 798 | 798 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 19164.9737 | 2012-03-09 12:58 | 2012-03-09 18:28 | ArrayCableInstallation | 798 | 798 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 19170.4737 | 2012-03-09 18:28 | 2012-03-09 23:58 | ArrayCableInstallation | 798 | 798 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 19172.4737 | 2012-03-09 20:28 | 2012-03-09 22:28 | ArrayCableInstallation | 798 | 798 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 19173.4737 | 2012-03-09 21:28 | 2012-03-09 22:28 | ArrayCableInstallation | 798 | 798 | 1
Array Cable Installation Vessel | Delay | 384 | 1920000 | 19557.4737 | 2012-03-25 21:28 | 2012-04-10 21:28 | ArrayCableInstallation | 814 | 830 | 17
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 19562.9737 | 2012-03-26 02:58 | 2012-03-26 08:28 | ArrayCableInstallation | 815 | 815 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 19568.4737 | 2012-03-26 08:28 | 2012-03-26 13:58 | ArrayCableInstallation | 815 | 815 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 19569.4737 | 2012-03-26 09:28 | 2012-03-26 10:28 | ArrayCableInstallation | 815 | 815 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 6 | 30000 | 19575.4737 | 2012-03-26 15:28 | 2012-03-26 21:28 | ArrayCableInstallation | 815 | 815 | 1
Array Cable Installation Vessel | Delay | 269 | 1345000 | 19844.4737 | 2012-04-06 20:28 | 2012-04-18 01:28 | ArrayCableInstallation | 826 | 838 | 13
Array Cable Installation Vessel | Lay/Bury Cable | 4.652 | 23259.7959 | 19849.1257 | 2012-04-07 01:08 | 2012-04-07 05:47 | ArrayCableInstallation | 827 | 827 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 19850.1257 | 2012-04-07 02:08 | 2012-04-07 03:08 | ArrayCableInstallation | 827 | 827 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 19855.6257 | 2012-04-07 07:38 | 2012-04-07 13:08 | ArrayCableInstallation | 827 | 827 | 1
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 19861.1257 | 2012-04-07 13:08 | 2012-04-07 18:38 | ArrayCableInstallation | 827 | 827 | 1
Array Cable Installation Vessel | Position Onsite | 2 | 10000 | 19863.1257 | 2012-04-07 15:08 | 2012-04-07 17:08 | ArrayCableInstallation | 827 | 827 | 1
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 19864.1257 | 2012-04-07 16:08 | 2012-04-07 17:08 | ArrayCableInstallation | 827 | 827 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 19869.6257 | 2012-04-07 21:38 | 2012-04-08 03:08 | ArrayCableInstallation | 827 | 828 | 2
Array Cable Installation Vessel | Delay | 48 | 240000 | 19917.6257 | 2012-04-09 21:38 | 2012-04-11 21:38 | ArrayCableInstallation | 829 | 831 | 3
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 19923.1257 | 2012-04-10 03:08 | 2012-04-10 08:38 | ArrayCableInstallation | 830 | 830 | 1
Array Cable Installation Vessel | Lower Cable | 1 | 5000 | 19924.1257 | 2012-04-10 04:08 | 2012-04-10 05:08 | ArrayCableInstallation | 830 | 830 | 1
Array Cable Installation Vessel | Lay/Bury Cable | 10.652 | 53259.7959 | 19934.7777 | 2012-04-10 14:47 | 2012-04-11 01:26 | ArrayCableInstallation | 830 | 831 | 2
Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | 19935.7777 | 2012-04-10 15:47 | 2012-04-10 16:47 | ArrayCableInstallation | 830 | 830 | 1
Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | 19941.2777 | 2012-04-10 21:17 | 2012-04-11 02:47 | ArrayCableInstallation | 830 | 831 | 2
Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | 19946.7777 | 2012-04-11 02:47 | 2012-04-11 08:17 | ArrayCableInstallation | 831 | 831 | 1
Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | 19950.5471 | 2012-04-11 06:33 | 2012-04-11 10:19 | ArrayCableInstallation | 831 | 831 | 1
Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | 19954.3166 | 2012-04-11 10:19 | 2012-04-11 14:05 | ArrayCableInstallation | 831 | 831 | 1