## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | location | phase_name | max_waveheight | max_windspeed | transit_speed | num_vessels
0.5 | Export Cable Installation Vessel | Mobilize | 72 | 180000 | ACTION | 0 | ExportCableInstallation
| Onshore Construction | Onshore Construction | 0 | 1665604.3526 | ACTION | 0 | ExportCableInstallation | Landfall
1 | Mooring System Installation Vessel | Mobilize | 168 | 700000 | ACTION | 0 | MooringSystemInstallation
| Export Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 6 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Delay | 52 | 216666.6667 | ACTION | 52 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 57 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 62 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 57 | 285000 | ACTION | 63 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Tow Plow | 0.4 | 2000 | ACTION | 63.4 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Pull Winch | 0.4 | 2000 | ACTION | 63.8 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 64.8 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 66.3349 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 68.3349 | MooringSystemInstallation
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 70.3 | ExportCableInstallation |  | ExportCableInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 72.3349 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 75.8 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 76.8 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 11 | 55000 | ACTION | 87.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 88.4949 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 92.6549 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 94.6549 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 98.6549 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 20 | 100000 | ACTION | 107.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 114.8149 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 118.9749 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 120.9749 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 124.9749 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 141.1349 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 35 | 175000 | ACTION | 142.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 145.2949 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 147.2949 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 5 | 25000 | ACTION | 147.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 2 | 10000 | ACTION | 149.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 151.2949 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 7 | 35000 | ACTION | 156.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 167.4549 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 11 | 55000 | ACTION | 167.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 171.6149 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 173.6149 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 177.6149 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 153 | 637500 | ACTION | 330.6149 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 346.7749 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 350.9349 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 26 | 108333.3333 | ACTION | 376.9349 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 378.9349 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 382.9349 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 226 | 1130000 | ACTION | 393.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 394.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 399.0949 | MooringSystemInstallation |  | MooringSystemInstallation
| Substation Assembly Line 1 | Substation Substructure Assembly | 0 | 0 | ACTION | 472.5654 | FloatingSubstationInstallation
| Substation Assembly Line 1 | Attach Topside | 24 | 0 | ACTION | 496.5654 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay: Waiting on Completed Assembly | 24 | 100000 | ACTION | 496.5654 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 224 | 933333.3333 | ACTION | 623.0949 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 127 | 529166.6667 | ACTION | 623.5654 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 627.2549 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Tow Substation to Site | 7.2248 | 30103.4722 | ACTION | 630.7902 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 631.5898 | MooringSystemInstallation
| Floating Substation Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 632.7902 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 636.5898 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 636.7902 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 641.5898 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 642.7902 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 645.9247 | MooringSystemInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 646.7902 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 647.9247 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 255 | 1275000 | ACTION | 649.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 651.9247 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 661.9502 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 666.1102 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 668.0847 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 20 | 100000 | ACTION | 669.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 672.2447 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 8 | 33333.3333 | ACTION | 674.1102 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 674.2447 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 56 | 233333.3333 | ACTION | 730.2447 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 734.2447 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 63 | 262500 | ACTION | 737.1102 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 78 | 390000 | ACTION | 747.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 750.4047 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | ACTION | 750.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Connect Mooring Lines | 14 | 58333.3333 | ACTION | 751.1102 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 754.5647 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 756.5647 | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 757.1102 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 760.5647 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 765.1102 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 771.1102 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 775.1102 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 776.7247 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 780.8847 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 782.8847 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 15 | 62500 | ACTION | 790.1102 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 790.8847 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 794.8847 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 805.2702 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 809.4302 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 811.0447 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 815.2047 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 817.2047 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 821.2047 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 16 | 66666.6667 | ACTION | 825.4302 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 99 | 412500 | ACTION | 920.2047 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 104 | 433333.3333 | ACTION | 929.4302 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 6 | 25000 | ACTION | 935.4302 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 936.3647 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 940.5247 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 942.5247 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 946.5247 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 947.4302 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 951.4302 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 962.6847 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 966.5902 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 966.8447 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 970.7502 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 971.1796 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 976.1796 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 226 | 1130000 | ACTION | 976.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 981.1796 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 985.5145 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 987.5145 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 13 | 65000 | ACTION | 989.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 991.5145 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 992.7502 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 4 | 16666.6667 | ACTION | 996.7502 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 113 | 470833.3333 | ACTION | 1104.5145 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1120.6745 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1124.8345 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1126.8345 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1130.8345 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 142 | 591666.6667 | ACTION | 1138.7502 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 8 | 33333.3333 | ACTION | 1146.7502 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1146.9945 | MooringSystemInstallation |  | MooringSystemInstallation
| Floating Substation Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1151.0851 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1151.1545 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1153.1545 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 165 | 825000 | ACTION | 1154.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1157.1545 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1173.3145 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1177.4745 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1179.4745 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1183.4745 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 30 | 150000 | ACTION | 1184.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1199.6345 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1203.7945 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1205.7945 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1209.7945 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1225.9545 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1230.1145 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 46 | 230000 | ACTION | 1230.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1232.1145 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1236.1145 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 16 | 80000 | ACTION | 1246.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1252.2745 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1256.4345 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1260.7694 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1265.7694 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1270.7694 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1275.1043 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1277.1043 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1281.1043 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 43 | 179166.6667 | ACTION | 1324.1043 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1340.2643 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1344.4243 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 69 | 287500 | ACTION | 1413.4243 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1415.4243 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1419.4243 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 180 | 900000 | ACTION | 1426.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | ACTION | 1429.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1435.5843 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 68 | 283333.3333 | ACTION | 1503.5843 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1507.7443 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1509.7443 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1513.7443 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 39 | 162500 | ACTION | 1552.7443 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1568.9043 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 56 | 233333.3333 | ACTION | 1624.9043 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1629.0643 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1631.0643 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 106 | 441666.6667 | ACTION | 1737.0643 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1741.0643 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1757.2243 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1761.3843 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1763.3843 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1767.3843 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 82 | 341666.6667 | ACTION | 1849.3843 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 432 | 2160000 | ACTION | 1861.8 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1865.5443 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1869.7043 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1871.7043 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 11.6922 | 58460.7554 | ACTION | 1873.4922 | ExportCableInstallation |  | ExportCableInstallation | 2 | 25 | 11.5
| Export Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 1875.4922 | ExportCableInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1875.7043 | MooringSystemInstallation |  | MooringSystemInstallation
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 1880.9922 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 1886.4922 | ExportCableInstallation |  | ExportCableInstallation
| Export Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 1890.2616 | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1891.8643 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1896.0243 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1900.3592 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1905.3592 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1910.3592 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 1914.6941 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1916.6941 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1920.6941 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1936.8541 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1941.0141 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1943.0141 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 14 | 58333.3333 | ACTION | 1957.0141 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1961.0141 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1977.1741 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1981.3341 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1983.3341 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1987.3341 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 46 | 191666.6667 | ACTION | 2033.3341 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2049.4941 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2053.6541 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2055.6541 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2059.6541 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 332 | 1383333.3333 | ACTION | 2391.6541 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2407.8141 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2411.9741 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2413.9741 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 18 | 75000 | ACTION | 2431.9741 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2435.9741 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2452.1341 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2456.2941 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2458.2941 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2462.2941 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2478.4541 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2482.6141 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2486.949 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2491.949 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2496.949 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2501.2839 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2503.2839 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2507.2839 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2523.4439 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2527.6039 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2529.6039 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2533.6039 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2549.7639 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2553.9239 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2555.9239 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2559.9239 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2576.0839 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2580.2439 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2582.2439 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2586.2439 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2602.4039 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2606.5639 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2608.5639 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2612.5639 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2628.7239 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2632.8839 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2634.8839 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2638.8839 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 70 | 291666.6667 | ACTION | 2708.8839 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2725.0439 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2729.2039 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 3 | 12500 | ACTION | 2732.2039 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 22 | 91666.6667 | ACTION | 2754.2039 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 1.3349 | 5562.0833 | ACTION | 2755.5388 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2760.5388 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2765.5388 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 2769.8737 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2771.8737 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2775.8737 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 99 | 412500 | ACTION | 2874.8737 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2891.0337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2895.1937 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2897.1937 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2901.1937 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2917.3537 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2921.5137 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2923.5137 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2927.5137 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2943.6737 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2947.8337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2949.8337 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2953.8337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 2966.8337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2982.9937 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2987.1537 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2989.1537 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2993.1537 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3009.3137 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3013.4737 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3015.4737 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3019.4737 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3035.6337 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3039.7937 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3044.1286 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3049.1286 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3054.1286 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3058.4635 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3060.4635 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3064.4635 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3080.6235 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3084.7835 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3086.7835 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3090.7835 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3106.9435 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3111.1035 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3113.1035 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3117.1035 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 16 | 66666.6667 | ACTION | 3133.1035 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3149.2635 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3153.4235 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3155.4235 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3159.4235 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3175.5835 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3179.7435 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3181.7435 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3185.7435 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3201.9035 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3206.0635 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3208.0635 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3212.0635 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3228.2235 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3232.3835 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3236.7184 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3241.7184 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3246.7184 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3251.0533 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3253.0533 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3257.0533 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3273.2133 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3277.3733 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3279.3733 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3283.3733 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3299.5333 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3303.6933 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3305.6933 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3309.6933 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3325.8533 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 3 | 12500 | ACTION | 3328.8533 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3333.0133 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3335.0133 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3339.0133 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 17 | 70833.3333 | ACTION | 3356.0133 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3372.1733 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3376.3333 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3378.3333 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3382.3333 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3398.4933 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3402.6533 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3404.6533 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3408.6533 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3424.8133 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3428.9733 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3433.3082 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3438.3082 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3443.3082 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3447.6431 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3449.6431 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3453.6431 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3469.8031 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3473.9631 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3475.9631 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 3479.9631 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3483.9631 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3500.1231 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3504.2831 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3506.2831 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3510.2831 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3526.4431 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3530.6031 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3532.6031 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3536.6031 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3552.7631 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3556.9231 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3558.9231 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3562.9231 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3579.0831 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3583.2431 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3585.2431 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3589.2431 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3605.4031 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3609.5631 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3613.898 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3618.898 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3623.898 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3628.2329 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3630.2329 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3634.2329 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3650.3929 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3654.5529 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3656.5529 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3660.5529 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3676.7129 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3680.8729 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3682.8729 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3686.8729 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3703.0329 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3707.1929 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3709.1929 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3713.1929 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3729.3529 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3733.5129 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3735.5129 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3739.5129 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3755.6729 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3759.8329 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3761.8329 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3765.8329 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3781.9929 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3786.1529 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3790.4878 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3795.4878 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3800.4878 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 3804.8227 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3806.8227 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3810.8227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3826.9827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3831.1427 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3833.1427 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3837.1427 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3853.3027 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3857.4627 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3859.4627 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3863.4627 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 137 | 570833.3333 | ACTION | 4000.4627 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4016.6227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4020.7827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4022.7827 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4026.7827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 19 | 79166.6667 | ACTION | 4045.7827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4061.9427 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4066.1027 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4068.1027 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4072.1027 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4088.2627 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4092.4227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4094.4227 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4098.4227 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4114.5827 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4118.7427 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4123.0776 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4128.0776 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4133.0776 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4137.4125 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4139.4125 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4143.4125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4159.5725 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4163.7325 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4165.7325 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4169.7325 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4185.8925 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4190.0525 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4192.0525 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4196.0525 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4212.2125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4216.3725 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4218.3725 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4222.3725 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4238.5325 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4242.6925 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4244.6925 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4248.6925 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4264.8525 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4269.0125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4271.0125 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4275.0125 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4291.1725 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4295.3325 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4299.6674 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4304.6674 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4309.6674 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4314.0023 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4316.0023 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4320.0023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4336.1623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4340.3223 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4342.3223 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4346.3223 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4362.4823 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4366.6423 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4368.6423 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4372.6423 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4388.8023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4392.9623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4394.9623 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4398.9623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 87 | 362500 | ACTION | 4485.9623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4502.1223 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4506.2823 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4508.2823 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4512.2823 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4528.4423 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4532.6023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4534.6023 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4538.6023 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4554.7623 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4558.9223 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4563.2572 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4568.2572 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4573.2572 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4577.5921 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4579.5921 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4583.5921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4599.7521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4603.9121 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4605.9121 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4609.9121 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4626.0721 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4630.2321 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4632.2321 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 42 | 175000 | ACTION | 4674.2321 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4678.2321 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4694.3921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4698.5521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4700.5521 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4704.5521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4720.7121 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4724.8721 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4726.8721 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4730.8721 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 10 | 41666.6667 | ACTION | 4740.8721 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4757.0321 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4761.1921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4763.1921 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4767.1921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 123 | 512500 | ACTION | 4890.1921 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4906.3521 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4910.5121 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4914.847 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4919.847 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4924.847 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 4929.1819 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4931.1819 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4935.1819 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4951.3419 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4955.5019 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4957.5019 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4961.5019 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4977.6619 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4981.8219 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4983.8219 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4987.8219 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5003.9819 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5008.1419 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5010.1419 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5014.1419 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5030.3019 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5034.4619 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5036.4619 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5040.4619 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5056.6219 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5060.7819 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5062.7819 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5066.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 5066.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5066.7819 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5074.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5082.9419 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5086.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5087.1019 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5091.4368 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5096.4368 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5101.4368 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5105.7717 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 21 | 0 | ACTION | 5107.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5107.7717 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5111.7717 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5119.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5127.9317 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5131.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5132.0917 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5134.0917 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5138.0917 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 5138.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5154.2517 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5158.4117 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5160.4117 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5164.4117 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 40 | 0 | ACTION | 5178.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5180.5717 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5181.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5184.7317 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5185.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5186.7317 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5188.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5190.7317 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5206.8917 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5211.0517 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5212.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 314.5 | 393125 | ACTION | 5212.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5213.0517 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5217.0517 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 5218.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 5225.0719 | MooredSubInstallation | [5 empty] | 2
1 | Multi-Purpose Support Vessel | Mobilize | 168 | 700000 | ACTION | 5225.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5229.4068 | MooredSubInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 5231.4068 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5233.2117 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5234.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 21.5 | 0 | ACTION | 5234.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5237.3717 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5239.3717 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5242.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5243.3717 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Delay | 20 | 83333.3333 | ACTION | 5251.4068 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5254.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 5257.4068 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5259.5317 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5263.6917 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5266.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5268.0266 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5273.0266 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 5277.4068 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5278.0266 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5278.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5282.3615 | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 5283.4068 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 58.3349 | 72918.625 | ACTION | 5283.4068 | MooredSubInstallation | site |  |  |  |  | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5284.3615 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 5285.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5288.3615 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 5290.6316 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5304.5215 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5308.6815 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5310.6815 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5314.6815 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 42 | 0 | ACTION | 5327.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5330.8415 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5330.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5334.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5335.0015 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5337.0015 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5337.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5341.0015 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5357.1615 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5361.3215 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5361.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 463.5 | 579375 | ACTION | 5361.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5363.3215 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5367.3215 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 5367.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 5374.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 90.6651 | 377771.25 | ACTION | 5374.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 5376.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 5382.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5383.4815 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5387.6415 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5389.6415 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5393.6415 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 5402.0719 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5402.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 40.5 | 0 | ACTION | 5402.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 5408.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 34 | 42500 | ACTION | 5408.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5409.8015 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5410.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5413.9615 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 5415.2967 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5415.9615 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5419.9615 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5422.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5434.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5436.1215 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5440.2815 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5444.6164 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5446.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5449.6164 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 5453.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5454.6164 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5456.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5458.9513 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5460.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5460.9513 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5463.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5464.9513 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5481.1113 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5485.2713 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5487.2713 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5487.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 589.5 | 736875 | ACTION | 5487.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5491.2713 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 5493.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 5500.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 92 | 383333.3333 | ACTION | 5500.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 5502.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5507.4313 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 5508.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5511.5913 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5513.5913 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5517.5913 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 5528.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5533.7513 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 5534.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 34 | 42500 | ACTION | 5534.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5537.9113 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5539.9113 | MooringSystemInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 5541.2967 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5543.9113 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5560.0713 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5564.2313 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5566.2313 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5570.2313 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5570.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 5570.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5578.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5586.3913 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5590.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5590.5513 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5592.5513 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5596.5513 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5602.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5612.7113 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5614.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5616.8713 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5621.2062 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5626.2062 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5631.2062 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5635.5411 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5637.5411 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5641.5411 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 29 | 0 | ACTION | 5643.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 5650.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5653.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5657.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5657.7011 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5660.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5661.8611 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5663.8611 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5667.8611 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5684.0211 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5684.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 394.2476 | 492809.4405 | ACTION | 5684.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5688.1811 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5690.1811 | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 5690.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5694.1811 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 5697.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 163 | 679166.6667 | ACTION | 5697.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 5699.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 5705.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 8333.3333 | ACTION | 5707.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5710.3411 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5714.5011 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 18 | 75000 | ACTION | 5732.5011 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5734.5011 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5738.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 53.5 | 0 | ACTION | 5738.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5738.5011 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Delay | 32 | 133333.3333 | ACTION | 5739.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5746.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5754.6611 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 75000 | ACTION | 5757.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5758.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5758.8211 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5760.8211 | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 5763.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 66 | 82500 | ACTION | 5763.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5764.8211 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 5770.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5770.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5780.9811 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5782.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5785.1411 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5787.1411 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 5789.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5791.1411 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5792.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5796.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5799.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5807.3011 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5811.4611 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5815.796 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5820.796 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5823.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 408.5825 | 510728.0655 | ACTION | 5823.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5825.796 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 5829.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 5830.1309 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5832.1309 | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 5836.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 73 | 304166.6667 | ACTION | 5836.0719 | MooredSubInstallation | Site
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5836.1309 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 5838.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 5844.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 33333.3333 | ACTION | 5852.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5852.2909 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5856.4509 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5858.4509 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5862.4509 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Delay | 21 | 87500 | ACTION | 5873.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5878.6109 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5882.7709 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5884.7709 | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 50000 | ACTION | 5885.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5888.7709 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 5891.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 55 | 68750 | ACTION | 5891.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 5898.2967 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5904.9309 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5906.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 5906.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5909.0909 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5911.0909 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5914.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5915.0909 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5926.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 65 | 270833.3333 | ACTION | 5980.0909 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 59 | 0 | ACTION | 5985.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5996.2509 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 5997.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6000.4109 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6002.4109 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6006.4109 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6009.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6016.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6019.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6022.5709 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6023.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6026.7309 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6026.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6028.7309 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6032.7309 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6048.8909 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6050.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 509.5825 | 636978.0655 | ACTION | 6050.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6053.0509 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 6056.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6057.3858 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6062.3858 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 6063.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 172 | 716666.6667 | ACTION | 6063.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 6065.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6067.3858 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6071.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6071.7207 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6073.7207 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6074.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 23.5 | 0 | ACTION | 6074.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6077.7207 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6082.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 6091.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6093.8807 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6094.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 6097.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 34 | 42500 | ACTION | 6097.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6098.0407 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6100.0407 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6104.0407 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 6104.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6106.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6118.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6120.2007 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6124.3607 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6125.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6126.3607 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 6129.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6130.3607 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6132.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6136.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6139.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6146.5207 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6150.6807 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6152.6807 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6156.6807 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6163.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 393.5825 | 491978.0655 | ACTION | 6163.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 6169.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6172.8407 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 6176.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 79 | 329166.6667 | ACTION | 6176.0719 | MooredSubInstallation | Site
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6177.0007 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 6178.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6179.0007 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6183.0007 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6184.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6199.1607 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6203.3207 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 6204.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6205.3207 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6209.3207 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 6210.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 34 | 42500 | ACTION | 6210.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 6217.2967 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6225.4807 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6229.6407 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6233.9756 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6238.9756 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6242.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 78.5 | 0 | ACTION | 6242.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6243.9756 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6248.3105 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6250.3105 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6250.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6254.3105 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6262.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6270.4705 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6274.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6274.6305 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6276.6305 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6280.6305 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6286.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6293.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6296.7905 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6296.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6300.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6300.9505 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6302.9505 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6303.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6306.9505 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6323.1105 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6327.2705 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6327.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 429.5825 | 536978.0655 | ACTION | 6327.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6329.2705 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6333.2705 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 6333.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 6340.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 130 | 541666.6667 | ACTION | 6340.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 6342.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6348.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6349.4305 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6353.5905 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6355.5905 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6359.5905 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 6368.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 6374.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 34 | 42500 | ACTION | 6374.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6375.7505 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6379.9105 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 6381.2967 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6381.9105 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6385.9105 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6402.0705 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6406.2305 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6410.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 6410.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6410.5654 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6415.5654 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6418.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6420.5654 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6424.9003 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6426.9003 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6430.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6430.9003 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6442.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6447.0603 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6454.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6461.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6464.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 6468.0603 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6468.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6471.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6472.2203 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6474.2203 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6478.2203 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6495.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 391.5825 | 489478.0655 | ACTION | 6495.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 46 | 191666.6667 | ACTION | 6524.2203 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6540.3803 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6544.5403 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6546.5403 | MooringSystemInstallation
| Towing Group 3 | Delay | 51 | 127500 | ACTION | 6546.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6550.5403 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 6552.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 6559.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 185 | 770833.3333 | ACTION | 6559.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 6561.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6566.7003 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6567.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 12500 | ACTION | 6570.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6570.8603 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6572.8603 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6576.8603 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6578.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 6578.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6586.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6593.0203 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Delay | 26 | 108333.3333 | ACTION | 6596.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6597.1803 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6598.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 12500 | ACTION | 6599.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6599.1803 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6603.1803 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6610.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6622.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6629.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 50 | 0 | ACTION | 6679.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 78 | 325000 | ACTION | 6681.1803 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6682.8791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 85 | 354166.6667 | ACTION | 6684.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6686.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6689.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6697.3403 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 58333.3333 | ACTION | 6698.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6701.5003 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6703.5003 | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 6704.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 145 | 181250 | ACTION | 6704.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6707.5003 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 6711.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6713.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 496.5825 | 620728.0655 | ACTION | 6713.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 6719.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6723.6603 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 6726.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 22 | 91666.6667 | ACTION | 6726.0719 | MooredSubInstallation | Site
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6727.8203 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 6728.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6732.1552 | MooringSystemInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6734.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6737.1552 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6742.1552 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6746.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 32.5 | 0 | ACTION | 6746.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6746.4901 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6748.4901 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6752.4901 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 6754.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6754.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 6760.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 34 | 42500 | ACTION | 6760.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6766.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 6767.2967 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6768.6501 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6772.8101 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6774.8101 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6778.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6778.8101 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6790.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 41 | 0 | ACTION | 6831.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 53 | 220833.3333 | ACTION | 6831.8101 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6838.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 6842.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6845.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6847.9701 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6849.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6852.1301 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6852.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6854.1301 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6858.1301 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6874.2901 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6876.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 495.5825 | 619478.0655 | ACTION | 6876.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6878.4501 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6880.4501 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 6882.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6884.4501 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 6889.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 129 | 537500 | ACTION | 6889.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 6891.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6900.6101 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6904.7701 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 6906.7701 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6908.7701 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6912.7701 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6914.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 37.5 | 0 | ACTION | 6914.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6922.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6928.9301 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6933.0901 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6934.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6935.0901 | MooringSystemInstallation
| Multi-Purpose Support Vessel | Delay | 48 | 200000 | ACTION | 6939.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6939.0901 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 6945.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6946.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 8333.3333 | ACTION | 6947.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6955.2501 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 6958.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6959.4101 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6963.745 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 6965.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6968.745 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6973.745 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 6978.0799 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6980.0799 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6984.0799 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Delay | 43 | 179166.6667 | ACTION | 6990.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 28 | 0 | ACTION | 6993.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6996.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7000.2399 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7000.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7003.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7004.3999 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7006.3999 | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 75000 | ACTION | 7008.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7010.3999 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 7014.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 125 | 156250 | ACTION | 7014.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 7021.2967 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7026.5599 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7027.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 316.5825 | 395728.0655 | ACTION | 7027.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7030.7199 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7032.7199 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7036.7199 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7052.8799 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7057.0399 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7059.0399 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7063.0399 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7082.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 54.5 | 0 | ACTION | 7082.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7090.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7102.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 7114.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7126.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7138.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7145.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7148.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7152.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7155.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7179.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 412.5825 | 515728.0655 | ACTION | 7179.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 179 | 745833.3333 | ACTION | 7242.0399 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Delay | 220 | 550000 | ACTION | 7247.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 1 | Delay | 68 | 170000 | ACTION | 7247.8791 | MooredSubInstallation | [5 empty] | 2
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7250.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 70.5 | 0 | ACTION | 7250.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 7253.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 7253.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7258.1999 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7258.3791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 7260.0719 | MooredSubInstallation | [5 empty] | 2
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 7260.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 246 | 1025000 | ACTION | 7260.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 7262.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7262.3599 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7264.3599 | MooringSystemInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7268.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7268.3599 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7270.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 33333.3333 | ACTION | 7276.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 2 | 8333.3333 | ACTION | 7278.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 7278.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7284.5199 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7288.6799 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 50000 | ACTION | 7290.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7290.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7290.6799 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7294.6799 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 7296.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 36 | 45000 | ACTION | 7296.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 1 | Queue | 36 | 45000 | ACTION | 7296.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Delay | 0 | 0 | ACTION | 7296.0719 | MooredSubInstallation | Site
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 7298.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 4 | 16666.6667 | ACTION | 7300.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 7302.0719 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 7303.2967 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7308.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7310.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7310.8399 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7314.9999 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7317.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 45833.3333 | ACTION | 7319.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 7319.3348 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7320.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7324.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7327.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7351.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 330.5825 | 413228.0655 | ACTION | 7351.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 49 | 204166.6667 | ACTION | 7368.3348 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Delay | 21 | 52500 | ACTION | 7372.8791 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 54 | 225000 | ACTION | 7373.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7373.3348 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7378.3348 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 7378.8791 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 37500 | ACTION | 7382.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 7382.6697 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7384.6697 | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 7385.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 7388.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 92 | 115000 | ACTION | 7388.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 2 | Queue | 3 | 3750 | ACTION | 7388.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Delay | 0 | 0 | ACTION | 7388.0719 | MooredSubInstallation | Site
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7388.6697 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 7390.0719 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 7395.2967 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7396.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7404.8297 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7408.9897 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 54166.6667 | ACTION | 7409.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7410.9897 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7414.9897 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7418.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 66.5 | 0 | ACTION | 7418.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7426.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7431.1497 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Delay | 23 | 95833.3333 | ACTION | 7432.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7435.3097 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7437.3097 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7438.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 29166.6667 | ACTION | 7439.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 2 | 8333.3333 | ACTION | 7441.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7441.3097 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 7446.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 8 | 33333.3333 | ACTION | 7449.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 4 | 16666.6667 | ACTION | 7453.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 65 | 81250 | ACTION | 7453.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7457.4697 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7458.3791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 7460.2967 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7461.6297 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7463.6297 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7467.6297 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7470.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7477.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7480.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7483.7897 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7484.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7487.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7487.9497 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7489.9497 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7493.9497 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7511.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 208.5825 | 260728.0655 | ACTION | 7511.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 61 | 254166.6667 | ACTION | 7554.9497 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Delay | 47 | 117500 | ACTION | 7558.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 7564.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 7571.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 118 | 491666.6667 | ACTION | 7571.0719 | MooredSubInstallation | Site
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7571.1097 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 7573.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7575.2697 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7577.2697 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7581.2697 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7586.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 74.5 | 0 | ACTION | 7586.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7594.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 24 | 100000 | ACTION | 7605.2697 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7606.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7621.4297 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7625.5897 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 7629.9246 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7634.9246 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 18 | 75000 | ACTION | 7652.9246 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7657.9246 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 7662.2595 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7664.2595 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7668.2595 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 71 | 0 | ACTION | 7677.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7689.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 25 | 104166.6667 | ACTION | 7693.2595 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Delay | 128 | 533333.3333 | ACTION | 7701.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7701.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7707.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7708.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7709.4195 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7711.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7713.5795 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 29166.6667 | ACTION | 7714.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7715.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7715.5795 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7718.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7719.5795 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7742.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 347.5825 | 434478.0655 | ACTION | 7742.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7754.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 11.5 | 0 | ACTION | 7754.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 41 | 170833.3333 | ACTION | 7760.5795 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7762.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7774.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7776.7395 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7786.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7798.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7805.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7808.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7812.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7815.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 44 | 183333.3333 | ACTION | 7820.7395 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7824.8995 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7826.8995 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7830.8995 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7839.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 379.5825 | 474478.0655 | ACTION | 7839.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 28 | 116666.6667 | ACTION | 7858.8995 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Delay | 120 | 300000 | ACTION | 7862.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 2 | Delay | 23 | 57500 | ACTION | 7862.8791 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 149 | 620833.3333 | ACTION | 7863.0719 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 7868.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 7868.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7875.0595 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 7875.0719 | MooredSubInstallation | [5 empty] | 2
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 7875.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 54166.6667 | ACTION | 7876.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7879.2195 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7881.2195 | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 7882.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 311 | 388750 | ACTION | 7882.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 1 | Queue | 7 | 8750 | ACTION | 7882.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Delay | 0 | 0 | ACTION | 7882.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 7884.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7885.2195 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 7889.2967 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7890.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7901.3795 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7905.5395 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7907.5395 | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 7910.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7911.5395 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 7916.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 34 | 42500 | ACTION | 7916.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 2 | Queue | 41 | 51250 | ACTION | 7916.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Delay | 0 | 0 | ACTION | 7916.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 7918.0719 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7922.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 7922.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 7923.2967 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 8 | 33333.3333 | ACTION | 7926.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7927.6995 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7930.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7931.8595 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 7932.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7933.8595 | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 8333.3333 | ACTION | 7934.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7937.8595 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7942.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7954.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 7966.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 30 | 125000 | ACTION | 7967.8595 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 7973.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7976.8791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 43 | 179166.6667 | ACTION | 7977.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7980.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7983.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7984.0195 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7988.1795 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 7992.5144 | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 75000 | ACTION | 7995.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7997.5144 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 8001.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 85 | 106250 | ACTION | 8001.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8002.5144 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 8006.8493 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8007.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 118.5825 | 148228.0655 | ACTION | 8007.8791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 8008.2967 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8008.8493 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8012.8493 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 27 | 112500 | ACTION | 8039.8493 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8056.0093 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8060.1693 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8062.1693 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 8064.1693 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8068.1693 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Delay | 71 | 177500 | ACTION | 8078.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8084.3293 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 8084.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8088.4893 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8090.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 8090.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8090.4893 | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 8091.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 90 | 375000 | ACTION | 8091.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 8093.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8094.4893 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8098.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 8099.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 29166.6667 | ACTION | 8106.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8110.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 8116.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 24 | 100000 | ACTION | 8118.4893 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Delay | 18 | 75000 | ACTION | 8124.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8128.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8134.6493 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 54166.6667 | ACTION | 8137.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8138.8093 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 3 | 12500 | ACTION | 8140.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8140.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8140.8093 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8144.8093 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 8146.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 9 | 37500 | ACTION | 8149.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 3 | 12500 | ACTION | 8152.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 61 | 76250 | ACTION | 8152.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 8153.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 8159.2967 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8160.9693 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8165.1293 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8167.1293 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 42 | 0 | ACTION | 8195.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8198.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8202.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8205.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8229.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 306.5825 | 383228.0655 | ACTION | 8229.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 68 | 283333.3333 | ACTION | 8235.1293 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8239.1293 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Delay | 11 | 27500 | ACTION | 8240.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 8246.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 8253.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 101 | 420833.3333 | ACTION | 8253.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 8255.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8255.2893 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8258.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 28.5 | 0 | ACTION | 8258.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8259.4493 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 8261.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8261.4493 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8265.4493 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8266.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8278.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 8281.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8281.6093 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8285.7693 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 8287.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 34 | 42500 | ACTION | 8287.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 8290.1042 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8290.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 8294.2967 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8295.1042 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8300.1042 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8302.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 8304.4391 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8306.4391 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 8309.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8310.4391 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8312.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8316.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8319.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8326.5991 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8330.7591 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8332.7591 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8336.7591 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8343.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 335.5825 | 419478.0655 | ACTION | 8343.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 35 | 145833.3333 | ACTION | 8371.7591 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Delay | 42 | 105000 | ACTION | 8385.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8387.9191 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 8391.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8392.0791 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8394.0791 | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 8398.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 111 | 462500 | ACTION | 8398.0719 | MooredSubInstallation | Site
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8398.0791 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 8400.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 8406.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8414.2391 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 50000 | ACTION | 8418.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8418.3991 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8420.3991 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8426.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 8426.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8434.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8446.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 31 | 129166.6667 | ACTION | 8451.3991 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8455.3991 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8458.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 21 | 0 | ACTION | 8479.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8491.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 8498.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 21 | 0 | ACTION | 8519.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8522.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 68 | 283333.3333 | ACTION | 8523.3991 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8526.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 110 | 458333.3333 | ACTION | 8528.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8529.8791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 33333.3333 | ACTION | 8536.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8539.5591 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 8542.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 144 | 180000 | ACTION | 8542.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8543.7191 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8545.7191 | MooringSystemInstallation
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 8549.2967 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8549.7191 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8553.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 394.5825 | 493228.0655 | ACTION | 8553.8791 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 8559.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8565.8791 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8594.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 40.5 | 0 | ACTION | 8594.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8602.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8614.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 8630.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8642.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8654.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 94 | 391666.6667 | ACTION | 8659.8791 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 8661.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8664.0391 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8664.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8666.0391 | MooringSystemInstallation
| Towing Group 3 | Delay | 108 | 270000 | ACTION | 8667.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8670.0391 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 8674.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 132 | 550000 | ACTION | 8674.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 8676.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 61 | 0 | ACTION | 8725.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8729.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8732.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 64 | 266666.6667 | ACTION | 8734.0391 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Delay | 73 | 304166.6667 | ACTION | 8749.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8750.1991 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8754.3591 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 8755.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8756.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 462.5825 | 578228.0655 | ACTION | 8756.8791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 12500 | ACTION | 8758.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 8758.694 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8762.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 5.5 | 0 | ACTION | 8762.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 10 | 41666.6667 | ACTION | 8768.694 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8770.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 13 | 54166.6667 | ACTION | 8771.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8773.694 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 12500 | ACTION | 8774.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8782.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8794.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8806.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 37 | 154166.6667 | ACTION | 8810.694 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 8813.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8815.694 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8816.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 62 | 155000 | ACTION | 8818.8791 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 45 | 187500 | ACTION | 8819.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 8820.0289 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8820.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8822.0289 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8823.8791 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 8824.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8826.0289 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 8831.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 58333.3333 | ACTION | 8833.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8847.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 298.5825 | 373228.0655 | ACTION | 8847.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 25 | 104166.6667 | ACTION | 8851.0289 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Delay | 31 | 129166.6667 | ACTION | 8864.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 2 | 8333.3333 | ACTION | 8866.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8867.1889 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Delay | 20 | 50000 | ACTION | 8867.8791 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 2 | 8333.3333 | ACTION | 8868.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8871.3489 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 4 | 16666.6667 | ACTION | 8872.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 198 | 247500 | ACTION | 8872.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 1 | Queue | 41 | 51250 | ACTION | 8872.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Delay | 0 | 0 | ACTION | 8872.0719 | MooredSubInstallation | Site
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8873.3489 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 8873.8791 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 8874.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8877.3489 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 8879.2967 | MooredSubInstallation | [5 empty] | 2
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 8880.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 8880.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 54166.6667 | ACTION | 8893.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8893.5089 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8897.6689 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8899.6689 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 26 | 108333.3333 | ACTION | 8925.6689 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8929.6689 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8930.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 8930.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8938.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8950.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 8952.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 28 | 116666.6667 | ACTION | 8957.6689 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Delay | 70 | 291666.6667 | ACTION | 8963.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8964.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 29166.6667 | ACTION | 8970.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8973.8289 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 8976.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 104 | 130000 | ACTION | 8976.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 2 | Queue | 96 | 120000 | ACTION | 8976.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Delay | 0 | 0 | ACTION | 8976.0719 | MooredSubInstallation | Site
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 8976.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8977.9889 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 8978.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8979.9889 | MooringSystemInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 8983.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 8983.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8983.9889 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 8984.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8986.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8990.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8993.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9000.1489 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 9004.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9004.3089 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9006.3089 | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 9010.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 34 | 42500 | ACTION | 9010.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9010.3089 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 9017.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9017.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 138.5825 | 173228.0655 | ACTION | 9017.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 26 | 108333.3333 | ACTION | 9036.3089 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9052.4689 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9056.6289 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9058.6289 | MooringSystemInstallation
| Towing Group 3 | Delay | 42 | 105000 | ACTION | 9059.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9062.6289 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 9065.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 9072.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 62 | 258333.3333 | ACTION | 9072.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 9074.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9078.7889 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 9080.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9082.9489 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 9087.2838 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9092.2838 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9097.2838 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9098.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 80.5 | 0 | ACTION | 9098.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 9100.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 9101.6187 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9103.6187 | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 9106.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 34 | 42500 | ACTION | 9106.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9106.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9107.6187 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 9113.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9118.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9123.7787 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9127.9387 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9129.9387 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 9130.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9133.9387 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 9142.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 9149.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9150.0987 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9152.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9154.2587 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9156.2587 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9156.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9159.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9160.2587 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9183.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 200.5825 | 250728.0655 | ACTION | 9183.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9266.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 9266.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9274.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9286.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 9298.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 143 | 595833.3333 | ACTION | 9303.2587 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 9310.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 9317.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9319.4187 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Delay | 136 | 340000 | ACTION | 9319.8791 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9320.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9323.5787 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9324.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9325.5787 | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 9325.8791 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9327.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9329.5787 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 9332.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 226 | 941666.6667 | ACTION | 9332.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 9334.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 9340.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9345.7387 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9349.8987 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9351.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 334.5825 | 418228.0655 | ACTION | 9351.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9351.8987 | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 54166.6667 | ACTION | 9353.0719 | MooredSubInstallation
| Towing Group 2 | Delay | 3 | 7500 | ACTION | 9354.8791 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 2 | 8333.3333 | ACTION | 9355.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9355.8987 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 9360.8791 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 29166.6667 | ACTION | 9362.0719 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 9367.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 9368.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 36 | 45000 | ACTION | 9368.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 2 | Queue | 1 | 1250 | ACTION | 9368.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Delay | 0 | 0 | ACTION | 9368.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 9370.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9372.0587 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 9375.2967 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 9376.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9376.2187 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 8333.3333 | ACTION | 9378.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9378.2187 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9382.2187 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9398.3787 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Delay | 21 | 87500 | ACTION | 9399.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9402.5387 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 9406.8736 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9411.8736 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9416.8736 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 75000 | ACTION | 9417.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 9421.2085 | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 9423.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 55 | 68750 | ACTION | 9423.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9423.2085 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9427.2085 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 9430.2967 | MooredSubInstallation | [5 empty] | 2
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9434.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 9434.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9442.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9443.3685 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9447.5285 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9449.5285 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9453.5285 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9454.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 9466.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 9478.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 31 | 129166.6667 | ACTION | 9484.5285 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 9485.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9488.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9492.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9495.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9500.6885 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9504.8485 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9506.8485 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9510.8485 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9519.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 406.5825 | 508228.0655 | ACTION | 9519.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 2 | 5000 | ACTION | 9521.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9527.0085 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 9527.8791 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9531.1685 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9533.1685 | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 9534.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 111 | 462500 | ACTION | 9534.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 9536.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9537.1685 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 9542.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9553.3285 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9557.4885 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9559.4885 | MooringSystemInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 9562.0719 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9563.4885 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 9568.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 34 | 42500 | ACTION | 9568.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 9575.2967 | MooredSubInstallation | [5 empty] | 2
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9579.6485 | MooringSystemInstallation |  | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9602.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 9602.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 29 | 120833.3333 | ACTION | 9608.6485 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9610.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9612.8085 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9614.8085 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9618.8085 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9622.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 9634.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9634.9685 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9639.1285 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 9643.4634 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 9646.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9648.4634 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 9652.7983 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 9653.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9654.7983 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9658.7983 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 65 | 270833.3333 | ACTION | 9723.7983 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 75 | 0 | ACTION | 9728.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9731.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9735.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9738.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9739.9583 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9744.1183 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9746.1183 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9750.1183 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9762.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 387.5825 | 484478.0655 | ACTION | 9762.8791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9766.2783 | MooringSystemInstallation |  | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 9768.8791 | MooredSubInstallation | [5 empty] | 2
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9770.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 7.5 | 0 | ACTION | 9770.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9770.4383 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9772.4383 | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 9775.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 207 | 862500 | ACTION | 9775.0719 | MooredSubInstallation | Site
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9776.4383 | MooringSystemInstallation |  | MooringSystemInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 9777.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9778.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 9783.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9790.3791 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9792.5983 | MooringSystemInstallation |  | MooringSystemInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9796.7583 | MooringSystemInstallation |  | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 9802.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 9803.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 9809.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 34 | 42500 | ACTION | 9809.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 9814.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 9816.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 9821.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 40 | 0 | ACTION | 9861.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9864.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9868.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9871.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9895.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 465.5825 | 581978.0655 | ACTION | 9895.8791 | MooredSubInstallation
| Towing Group 2 | Delay | 28 | 70000 | ACTION | 9923.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 9929.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 9936.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 127 | 529166.6667 | ACTION | 9936.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 9938.0719 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9938.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 42.5 | 0 | ACTION | 9938.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9946.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9958.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 9970.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 40 | 166666.6667 | ACTION | 9978.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 9982.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 9984.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 9989.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9992.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9996.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 62500 | ACTION | 9999.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 6 | 25000 | ACTION | 10005.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 9 | 0 | ACTION | 10005.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10008.8791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 20833.3333 | ACTION | 10010.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 5 | 20833.3333 | ACTION | 10015.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 3 | 12500 | ACTION | 10018.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 1 | 4166.6667 | ACTION | 10019.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 83 | 103750 | ACTION | 10019.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 10026.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10032.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 457.5825 | 571978.0655 | ACTION | 10032.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10106.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 73.5 | 0 | ACTION | 10106.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10114.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10126.3791 | MooredSubInstallation
| Towing Group 3 | Delay | 103 | 257500 | ACTION | 10135.8791 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 10138.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 10141.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 10148.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 129 | 537500 | ACTION | 10148.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 10150.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 10150.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 10156.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 10157.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 12500 | ACTION | 10159.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 54 | 0 | ACTION | 10211.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10214.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10218.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10221.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10245.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 429.5825 | 536978.0655 | ACTION | 10245.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 4 | 10000 | ACTION | 10249.8791 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 91 | 379166.6667 | ACTION | 10250.0719 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 10255.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 10262.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 70833.3333 | ACTION | 10267.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 10273.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 125 | 156250 | ACTION | 10273.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 1 | Queue | 11 | 13750 | ACTION | 10273.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Delay | 0 | 0 | ACTION | 10273.0719 | MooredSubInstallation | Site
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10274.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 28.5 | 0 | ACTION | 10274.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 10275.0719 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 10280.2967 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 10281.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10282.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10294.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 10301.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 10306.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 10307.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 34 | 42500 | ACTION | 10307.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 10314.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 10318.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 10325.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10328.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10332.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10335.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10359.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 333.5825 | 416978.0655 | ACTION | 10359.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 10365.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 10372.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 65 | 270833.3333 | ACTION | 10372.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 10374.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 10380.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 37500 | ACTION | 10389.0719 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10442.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 10442.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 55 | 229166.6667 | ACTION | 10444.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10450.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 37500 | ACTION | 10453.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10462.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 24 | 0 | ACTION | 10486.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 10498.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 10510.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 10524.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 10531.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10534.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10538.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10541.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10565.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 285.5825 | 356978.0655 | ACTION | 10565.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10610.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 44.5 | 0 | ACTION | 10610.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10618.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10630.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 10641.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 10653.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 10665.3791 | MooredSubInstallation
0.5 | Array Cable Installation Vessel | Mobilize | 72 | 180000 | ACTION | 10669.0879 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 10672.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 10675.0879 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10675.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10679.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10682.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10706.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 392.5825 | 490728.0655 | ACTION | 10706.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10778.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 71.5 | 0 | ACTION | 10778.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10786.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10798.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 10810.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 10816.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 10828.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 10835.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10838.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10842.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10845.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 294 | 735000 | ACTION | 10859.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 1 | Delay | 153 | 382500 | ACTION | 10859.8791 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 407 | 1695833.3333 | ACTION | 10860.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 8333.3333 | ACTION | 10862.0719 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 10865.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 10865.8791 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 10868.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 496 | 620000 | ACTION | 10868.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10869.8791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 10872.0719 | MooredSubInstallation | [5 empty] | 2
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 10872.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 4 | 16666.6667 | ACTION | 10872.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 10874.0719 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 10875.2967 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 10880.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 205 | 1025000 | ACTION | 10880.0879 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 10881.2967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 10883.8574 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 10887.4894 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 58333.3333 | ACTION | 10894.0719 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10946.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 76.5 | 0 | ACTION | 10946.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10954.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10966.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 21 | 0 | ACTION | 10987.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 102 | 425000 | ACTION | 10996.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 10999.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 25000 | ACTION | 11002.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 120 | 600000 | ACTION | 11003.8574 | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11005.8574 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11006.8574 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 11008.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 136 | 170000 | ACTION | 11008.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 1 | Queue | 136 | 170000 | ACTION | 11008.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Delay | 0 | 0 | ACTION | 11008.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 11010.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 11011.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11012.3574 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 11015.2967 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 11016.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11017.8574 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 11018.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11018.8574 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11021.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 7 | 35000 | ACTION | 11025.8574 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 54166.6667 | ACTION | 11029.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 25 | 0 | ACTION | 11046.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11050.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11053.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11077.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 62.5825 | 78228.0655 | ACTION | 11077.8791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11114.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 36.5 | 0 | ACTION | 11114.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11122.3791 | MooredSubInstallation
| Towing Group 3 | Delay | 54 | 135000 | ACTION | 11131.8791 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 103 | 429166.6667 | ACTION | 11132.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11134.3791 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 11137.8791 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 29166.6667 | ACTION | 11139.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 115 | 575000 | ACTION | 11140.8574 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 2.991 | 14954.8442 | ACTION | 11143.8484 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 11144.0719 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11144.8484 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 11145.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 137 | 171250 | ACTION | 11145.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 2 | Queue | 257.5825 | 321978.0655 | ACTION | 11145.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Delay | 0 | 0 | ACTION | 11145.0719 | MooredSubInstallation | Site
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 11146.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 11147.0719 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 11152.2967 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 11153.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 11158.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 11165.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 11166.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11169.8791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 70833.3333 | ACTION | 11170.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11173.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11176.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11200.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 48.5825 | 60728.0655 | ACTION | 11200.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 6 | 15000 | ACTION | 11206.8791 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 37 | 154166.6667 | ACTION | 11207.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 12500 | ACTION | 11210.0719 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 11212.8791 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 11216.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 71 | 88750 | ACTION | 11216.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 3 | Queue | 72 | 90000 | ACTION | 11216.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Delay | 0 | 0 | ACTION | 11216.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 11218.0719 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 11219.0719 | MooredSubInstallation | [5 empty] | 2
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 11223.2967 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 7 | 29166.6667 | ACTION | 11225.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 11231.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 11251.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 11257.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 41 | 51250 | ACTION | 11257.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 1 | Queue | 38 | 47500 | ACTION | 11257.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Delay | 0 | 0 | ACTION | 11257.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 11259.0719 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 11264.2967 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 17 | 70833.3333 | ACTION | 11276.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 11282.0719 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11282.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 81.5 | 0 | ACTION | 11282.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11290.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 11302.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11302.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 161 | 805000 | ACTION | 11305.8484 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 11308.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 51 | 63750 | ACTION | 11308.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11311.3484 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 11314.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 11315.2967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11316.8484 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11318.8484 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11319.8484 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11325.3484 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 11326.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11330.8484 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11331.8484 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 11333.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11336.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11340.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11341.8393 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11342.8393 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11343.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11367.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 144.5825 | 180728.0655 | ACTION | 11367.8791 | MooredSubInstallation
| Towing Group 2 | Delay | 2 | 5000 | ACTION | 11369.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 11375.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Delay | 37 | 185000 | ACTION | 11379.8393 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 11382.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 74 | 308333.3333 | ACTION | 11382.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 11384.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11385.3393 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 11390.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11390.8393 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11392.8393 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11393.8393 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11399.3393 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11404.8393 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11405.8393 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 11410.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 6 | 30000 | ACTION | 11411.8393 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 11416.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 34 | 42500 | ACTION | 11416.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Delay | 8 | 40000 | ACTION | 11419.8393 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | ACTION | 11422.8393 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 11423.2967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Delay | 21 | 105000 | ACTION | 11443.8393 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 0.99097 | 4954.8442 | ACTION | 11444.8303 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11445.8303 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11450.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 11450.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11451.3303 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11456.8303 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11458.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11458.8303 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11459.8303 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11465.3303 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11470.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11470.8303 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11471.8303 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11481.8213 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 11482.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11482.8213 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11488.3213 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11493.8213 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 11494.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11495.8213 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11496.8213 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 11501.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 11509.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11512.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11516.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11519.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11543.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 279.5825 | 349478.0655 | ACTION | 11543.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 5 | 12500 | ACTION | 11548.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 11554.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 11561.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 145 | 604166.6667 | ACTION | 11561.0719 | MooredSubInstallation | Site
| Array Cable Installation Vessel | Delay | 66 | 330000 | ACTION | 11562.8213 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 11563.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11568.3213 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 11569.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11573.8213 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11574.8213 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9 | 45000 | ACTION | 11583.8213 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 11589.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 2 | 8333.3333 | ACTION | 11591.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 20 | 83333.3333 | ACTION | 11611.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 4 | 16666.6667 | ACTION | 11615.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 54 | 67500 | ACTION | 11615.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11618.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 74.5 | 0 | ACTION | 11618.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 11622.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11626.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11638.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 11646.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 74 | 370000 | ACTION | 11657.8213 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 11658.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 0.99097 | 4954.8442 | ACTION | 11658.8122 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11659.8122 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11665.3122 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 11670.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11670.8122 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11672.8122 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11673.8122 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 11677.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11679.3122 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11680.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11684.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11684.8122 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11685.8122 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11687.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5 | 25000 | ACTION | 11690.8122 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Delay | 30 | 0 | ACTION | 11717.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11741.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 426.5825 | 533228.0655 | ACTION | 11741.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 1 | 2500 | ACTION | 11742.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 11748.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Delay | 64 | 320000 | ACTION | 11754.8122 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 11755.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 140 | 583333.3333 | ACTION | 11755.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 11757.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.991 | 24954.8442 | ACTION | 11759.8032 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11760.8032 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 11763.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11766.3032 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11771.8032 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11773.8032 | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 5 | 25000 | ACTION | 11778.8032 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11779.8032 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 11783.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11785.3032 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11786.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 44.5 | 0 | ACTION | 11786.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 11789.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 34 | 42500 | ACTION | 11789.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11790.8032 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11791.8032 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11794.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 11796.2967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11801.7942 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11802.7942 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11806.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11808.2942 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11813.7942 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11815.7942 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11816.7942 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 11818.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11822.2942 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11827.7942 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11828.7942 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 11830.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5 | 25000 | ACTION | 11833.7942 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 11837.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 43 | 0 | ACTION | 11880.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 49 | 245000 | ACTION | 11882.7942 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11883.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11887.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.991 | 24954.8442 | ACTION | 11887.7852 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11888.7852 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11890.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11894.2852 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11899.7852 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11901.7852 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11902.7852 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11908.2852 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11913.7852 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11914.7852 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11914.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 491.5825 | 614478.0655 | ACTION | 11914.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 11920.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 11924.7761 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11925.7761 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 11927.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 138 | 575000 | ACTION | 11927.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 11929.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11931.2761 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 11935.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 16666.6667 | ACTION | 11939.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 14 | 58333.3333 | ACTION | 11953.0719 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11954.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 39.5 | 0 | ACTION | 11954.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 25000 | ACTION | 11959.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 1 | 4166.6667 | ACTION | 11960.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11962.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 10 | 41666.6667 | ACTION | 11970.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 42 | 210000 | ACTION | 11973.2761 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11974.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 11976.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 49 | 61250 | ACTION | 11976.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11978.7761 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 11980.7761 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 11981.7761 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 11983.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 11986.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 11987.2761 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 11992.7761 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 11993.7761 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 11998.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12003.7671 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12004.7671 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 12005.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12008.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12010.2671 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12012.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12015.7671 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12015.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12017.7671 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12018.7671 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12024.2671 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12029.7671 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12030.7671 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12039.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 417.5825 | 521978.0655 | ACTION | 12039.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12040.7581 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12041.7581 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 12045.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12047.2581 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 12052.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 76 | 316666.6667 | ACTION | 12052.0719 | MooredSubInstallation | Site
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12052.7581 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 12054.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12054.7581 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12055.7581 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 12060.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 45833.3333 | ACTION | 12071.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 37 | 154166.6667 | ACTION | 12108.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 37500 | ACTION | 12117.0719 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12122.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 12122.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 12123.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 71 | 88750 | ACTION | 12123.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 12130.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12130.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12142.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 12144.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 12156.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 12168.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 12175.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 12189.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12192.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12196.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12199.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 157 | 785000 | ACTION | 12212.7581 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12218.2581 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12223.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 427.5825 | 534478.0655 | ACTION | 12223.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 2 | 5000 | ACTION | 12225.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Delay | 11 | 55000 | ACTION | 12229.2581 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 12231.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12234.7581 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12235.7581 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 12238.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 115 | 479166.6667 | ACTION | 12238.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 12240.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9 | 45000 | ACTION | 12244.7581 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 12246.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 25000 | ACTION | 12252.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 20 | 83333.3333 | ACTION | 12272.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 36 | 180000 | ACTION | 12280.7581 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 0.99097 | 4954.8442 | ACTION | 12281.749 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12282.749 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 58333.3333 | ACTION | 12286.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12288.249 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12290.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 66.5 | 0 | ACTION | 12290.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 12292.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 54 | 67500 | ACTION | 12292.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12293.749 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12295.749 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12296.749 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12298.3791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 12299.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12310.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 18 | 0 | ACTION | 12328.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 12340.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 51 | 255000 | ACTION | 12347.749 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 12352.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12353.249 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 12359.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 7 | 35000 | ACTION | 12360.249 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12362.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12365.749 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12366.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12366.749 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12369.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12393.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 410.5825 | 513228.0655 | ACTION | 12393.8791 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 12399.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Delay | 38 | 190000 | ACTION | 12404.749 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 12406.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 114 | 475000 | ACTION | 12406.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 12408.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 12414.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12414.74 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12415.74 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12421.24 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12426.74 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12428.74 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12429.74 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 12434.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12435.24 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 12440.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 34 | 42500 | ACTION | 12440.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12440.74 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12441.74 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 12447.2967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12451.731 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12452.731 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12458.231 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12458.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 64.5 | 0 | ACTION | 12458.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12463.731 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12465.731 | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12466.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12466.731 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12472.231 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12477.731 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12478.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12478.731 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12488.7219 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12489.7219 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 12490.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12495.2219 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12500.7219 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 12502.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12502.7219 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12503.7219 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12509.2219 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 12509.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12512.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12514.7219 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12515.7219 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12516.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12519.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12525.7129 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12526.7129 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12532.2129 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12537.7129 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12539.7129 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12540.7129 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12543.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 413.5825 | 516978.0655 | ACTION | 12543.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 73 | 182500 | ACTION | 12616.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 12622.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Delay | 84 | 420000 | ACTION | 12624.7129 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12626.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 12626.3791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 12629.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 189 | 787500 | ACTION | 12629.0719 | MooredSubInstallation | Site
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12630.2129 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 12631.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12634.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12635.7129 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12636.7129 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 12637.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12646.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12646.7039 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12647.7039 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12653.2039 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 12657.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 12658.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12658.7039 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12660.7039 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12661.7039 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 12663.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 34 | 42500 | ACTION | 12663.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12667.2039 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 12670.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 12670.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12672.7039 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12673.7039 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 12677.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12680.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 12683.6948 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12684.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12684.6948 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12687.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12690.1948 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12695.6948 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12697.6948 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12698.6948 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12711.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 412.5825 | 515728.0655 | ACTION | 12711.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 67 | 167500 | ACTION | 12778.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 12784.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 12791.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 128 | 533333.3333 | ACTION | 12791.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 12793.0719 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12794.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 12794.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 12799.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12802.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 107 | 535000 | ACTION | 12805.6948 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12811.1948 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12814.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12816.6948 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 12817.6948 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 12819.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | ACTION | 12821.6948 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Multi-Purpose Support Vessel | Check Mooring Lines | 3 | 12500 | ACTION | 12822.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 18 | 75000 | ACTION | 12840.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 26 | 0 | ACTION | 12840.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 3 | 12500 | ACTION | 12843.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 52 | 65000 | ACTION | 12843.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Delay | 26 | 130000 | ACTION | 12847.6948 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 12850.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 12852.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.991 | 29954.8442 | ACTION | 12853.6858 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12854.6858 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 32 | 0 | ACTION | 12884.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 40 | 200000 | ACTION | 12894.6858 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 12896.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12900.1858 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 12903.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12905.6858 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 12907.6858 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 12908.6858 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12962.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 80 | 400000 | ACTION | 12988.6858 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 12994.1858 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 12999.6858 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13000.6858 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 99 | 0 | ACTION | 13002.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13005.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13009.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13010.6768 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13011.6768 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13012.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13017.1768 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13022.6768 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13024.6768 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13025.6768 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13031.1768 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13036.6768 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13036.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 589.5825 | 736978.0655 | ACTION | 13036.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13037.6768 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 13042.8791 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13044.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13047.6677 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13048.6677 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 13049.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 206 | 858333.3333 | ACTION | 13049.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 13051.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13054.1677 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13056.8791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 13057.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13059.6677 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13061.6677 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13062.6677 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13068.1677 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 13068.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13073.6677 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13074.6677 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 13077.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 13080.8791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 13083.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 34 | 42500 | ACTION | 13083.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13084.6587 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13085.6587 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 13087.8791 | MooredSubInstallation
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 13090.2967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13091.1587 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13091.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13094.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13096.6587 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13098.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13098.6587 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13099.6587 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13122.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 452.0825 | 565103.0655 | ACTION | 13122.3791 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13130.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 8 | 0 | ACTION | 13130.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13138.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13150.3791 | MooredSubInstallation
| Towing Group 3 | Delay | 29 | 72500 | ACTION | 13151.3791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 13157.3791 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 13162.3791 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 13163.5719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 80.5 | 335416.6667 | ACTION | 13163.5719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 13165.5719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 13171.5719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 13174.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 13181.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 62500 | ACTION | 13186.5719 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13298.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 141 | 587500 | ACTION | 13327.5719 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 231 | 1155000 | ACTION | 13330.6587 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 20833.3333 | ACTION | 13332.5719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13336.1587 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 155 | 0 | ACTION | 13336.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 13338.5719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 175 | 218750 | ACTION | 13338.5719 | MooredSubInstallation | site |  |  |  |  | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13339.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13341.6587 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13342.6587 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13343.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 13345.7967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13346.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13352.6497 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13353.6497 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13359.1497 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13364.6497 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13366.6497 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13367.6497 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13370.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 520.5825 | 650728.0655 | ACTION | 13370.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13373.1497 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 13376.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13378.6497 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13378.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13379.6497 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 13383.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 44.5 | 185416.6667 | ACTION | 13383.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 13385.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13389.6407 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13390.6407 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13390.8791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 13391.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13396.1407 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13401.6407 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 13402.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13403.6407 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13404.6407 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13410.1407 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 13411.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 13414.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13415.6407 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13416.6407 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 13417.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 34 | 42500 | ACTION | 13417.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 13421.8791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 13424.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13425.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13426.6316 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13427.6316 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13428.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13432.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13433.1316 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13438.6316 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13440.6316 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13441.6316 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13447.1316 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13452.6316 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13453.6316 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13456.3791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 366.0825 | 457603.0655 | ACTION | 13456.3791 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 13462.3791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13463.6226 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13464.6226 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13466.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 10 | 0 | ACTION | 13466.3791 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 13468.5719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 51.5 | 214583.3333 | ACTION | 13468.5719 | MooredSubInstallation | Site
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13470.1226 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 13470.5719 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13474.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13475.6226 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 13476.5719 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13477.6226 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13478.6226 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13484.1226 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13486.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13489.6226 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13490.6226 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 13496.5719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 13498.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13500.6136 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13501.6136 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 13502.5719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 34 | 42500 | ACTION | 13502.5719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13507.1136 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 13509.7967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 13510.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13512.6136 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13514.6136 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13515.6136 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 13517.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13520.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13521.1136 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13524.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13526.6136 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13527.6136 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13527.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13537.6045 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13538.6045 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13544.1045 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13549.6045 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13551.6045 | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13551.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 206.0825 | 257603.0655 | ACTION | 13551.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13552.6045 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 13557.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13558.1045 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 13564.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 61.5 | 256250 | ACTION | 13564.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 13566.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 6 | 25000 | ACTION | 13572.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 13578.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 29166.6667 | ACTION | 13585.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 8 | 33333.3333 | ACTION | 13593.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 25000 | ACTION | 13599.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 2 | 8333.3333 | ACTION | 13601.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 29166.6667 | ACTION | 13608.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 13614.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 50 | 62500 | ACTION | 13614.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Delay | 60 | 300000 | ACTION | 13618.1045 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 13621.2967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13623.6045 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13624.6045 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13634.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 13634.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13642.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13654.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 32 | 160000 | ACTION | 13656.6045 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 13666.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13666.5955 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13667.5955 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13673.0955 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 13678.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13678.5955 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13680.5955 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13681.5955 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 13685.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13687.0955 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13688.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13692.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13692.5955 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13693.5955 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13695.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13703.5865 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13704.5865 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13710.0865 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13715.5865 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13717.5865 | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13719.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 295.5825 | 369478.0655 | ACTION | 13719.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 3 | 15000 | ACTION | 13720.5865 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13721.5865 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13802.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 13802.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13810.3791 | MooredSubInstallation
| Towing Group 1 | Delay | 96 | 240000 | ACTION | 13815.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 13821.8791 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13822.3791 | MooredSubInstallation
| Towing Group 1 | Delay | 18 | 45000 | ACTION | 13839.8791 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Delay | 18 | 0 | ACTION | 13840.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 123 | 615000 | ACTION | 13844.5865 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 13846.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 232 | 966666.6667 | ACTION | 13846.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 13848.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13850.0865 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 13852.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 13854.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13855.5865 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13856.5865 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 13864.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13866.5774 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13867.5774 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 13871.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13873.0774 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 13874.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13874.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13878.5774 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 13880.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 34 | 42500 | ACTION | 13880.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13880.5774 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13881.5774 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13887.0774 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 13887.2967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13892.5774 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 18 | 0 | ACTION | 13892.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13893.5774 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13896.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13899.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13903.5684 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13904.5684 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13910.0684 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13915.5684 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13917.5684 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13918.5684 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13923.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 414.0825 | 517603.0655 | ACTION | 13923.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13924.0684 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13929.5684 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 13929.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13930.5684 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 13936.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 56 | 233333.3333 | ACTION | 13936.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 13938.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 13940.5594 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13941.5594 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 13944.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13947.0594 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 20833.3333 | ACTION | 13949.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 4 | 16666.6667 | ACTION | 13953.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 12500 | ACTION | 13956.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 8 | 33333.3333 | ACTION | 13964.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 21 | 105000 | ACTION | 13968.0594 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13970.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 46.5 | 0 | ACTION | 13970.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13973.5594 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 13975.5594 | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 50000 | ACTION | 13976.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 13976.5594 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13978.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 13982.0594 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 13982.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 46 | 57500 | ACTION | 13982.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 13987.5594 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 13988.5594 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 13989.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13990.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 14002.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 14014.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 14021.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 35.6959 | 178479.6026 | ACTION | 14024.2553 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14024.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14025.2553 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 14029.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14030.7553 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14033.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14036.2553 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 14040.0248 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 14043.7943 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 14049.7943 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 1 | 5000 | ACTION | 14050.7943 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 30 | 150000 | ACTION | 14080.7943 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 2.7695 | 13847.3913 | ACTION | 14083.5637 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14085.5637 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14086.5637 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14092.0637 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Delay | 64 | 0 | ACTION | 14097.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14097.5637 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14098.5637 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14100.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14124.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 503.5825 | 629478.0655 | ACTION | 14124.8791 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 14130.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Lay/Bury Cable | 35.6959 | 178479.6026 | ACTION | 14134.2596 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14135.2596 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 14137.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 155 | 645833.3333 | ACTION | 14137.0719 | MooredSubInstallation | Site
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14138.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 14138.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 14139.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14140.7596 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 14145.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14146.2596 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14146.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14148.2596 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14149.2596 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14154.7596 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14158.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14160.2596 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14161.2596 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 14165.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 14170.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 14171.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 34 | 42500 | ACTION | 14171.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14171.2506 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14172.2506 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14177.7506 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 14178.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 14182.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14183.2506 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14185.2506 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14186.2506 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 14189.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14191.7506 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14192.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14196.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14197.2506 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14198.2506 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14199.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14208.2416 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14209.2416 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14214.7416 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14220.2416 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14222.2416 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14223.2416 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14223.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 336.5825 | 420728.0655 | ACTION | 14223.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14228.7416 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 14229.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14234.2416 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14235.2416 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 14236.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 65 | 270833.3333 | ACTION | 14236.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 14238.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 14244.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14245.2326 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14246.2326 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14251.7326 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 19 | 79166.6667 | ACTION | 14263.0719 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14306.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 14306.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14314.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 52 | 216666.6667 | ACTION | 14315.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 4166.6667 | ACTION | 14316.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 69 | 345000 | ACTION | 14320.7326 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 14322.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 86 | 107500 | ACTION | 14322.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14326.2326 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14326.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14328.2326 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14329.2326 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 14329.2967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14334.7326 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 14338.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14340.2326 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14341.2326 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 14350.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14351.2235 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14352.2235 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 14357.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14357.7235 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14360.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14363.2235 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14364.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14365.2235 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14366.2235 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14367.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14371.7235 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14377.2235 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14378.2235 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14388.2145 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14389.2145 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14391.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 402.5825 | 503228.0655 | ACTION | 14391.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14394.7145 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 14397.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14400.2145 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14402.2145 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14403.2145 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 14404.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 82 | 341666.6667 | ACTION | 14404.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 14406.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14408.7145 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 14412.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14414.2145 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14415.2145 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14425.2055 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14426.2055 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14431.7055 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 14432.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14437.2055 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 14438.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 34 | 42500 | ACTION | 14438.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14439.2055 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14440.2055 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 14445.2967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14445.7055 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14451.2055 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14452.2055 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 15000 | ACTION | 14455.2055 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14474.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 14474.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 22 | 110000 | ACTION | 14477.2055 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 10000 | ACTION | 14479.2055 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14482.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 8 | 40000 | ACTION | 14487.2055 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | ACTION | 14491.2055 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14494.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 14508.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 27 | 135000 | ACTION | 14518.2055 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 0.99097 | 4954.8442 | ACTION | 14519.1964 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14520.1964 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 14520.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14525.6964 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14531.1964 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 14532.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14533.1964 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14534.1964 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 14539.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14539.6964 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14542.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14545.1964 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14546.1964 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | ACTION | 14550.1964 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14642.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 107 | 0 | ACTION | 14649.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14653.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14656.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 122 | 610000 | ACTION | 14672.1964 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 5.991 | 29954.8442 | ACTION | 14678.1874 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14679.1874 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14680.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 502.5825 | 628228.0655 | ACTION | 14680.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14684.6874 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 14686.8791 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14688.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14690.1874 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14692.1874 | ArrayCableInstallation
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 14693.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 255 | 1062500 | ACTION | 14693.0719 | MooredSubInstallation | Site
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14693.1874 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 14695.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14698.6874 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14700.8791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 14701.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14704.1874 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14705.1874 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 14712.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14715.1784 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14716.1784 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 14721.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14721.6784 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 14724.8791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 14727.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 34 | 42500 | ACTION | 14727.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14727.1784 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14729.1784 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14730.1784 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 14731.8791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 14734.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14735.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14735.6784 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14738.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14741.1784 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14742.1784 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14742.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14752.1693 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14753.1693 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14758.6693 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14764.1693 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14766.3791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 437.0825 | 546353.0655 | ACTION | 14766.3791 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 14772.3791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 14778.5719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 51.5 | 214583.3333 | ACTION | 14778.5719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 14780.5719 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14810.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 44 | 0 | ACTION | 14810.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14818.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14830.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 55 | 229166.6667 | ACTION | 14835.5719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 14841.5719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 14842.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 80 | 400000 | ACTION | 14844.1693 | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14846.1693 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14847.1693 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14852.6693 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 14854.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14858.1693 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14859.1693 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 14861.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 14861.5719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14864.8791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 14867.5719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 89 | 111250 | ACTION | 14867.5719 | MooredSubInstallation | site |  |  |  |  | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14868.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14869.1603 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14870.1603 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14871.8791 | MooredSubInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 14874.7967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14875.6603 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14881.1603 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14883.1603 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14884.1603 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14889.6603 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14895.1603 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14895.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 450.5825 | 563228.0655 | ACTION | 14895.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14896.1603 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 14901.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Lay/Bury Cable | 8 | 40000 | ACTION | 14904.1603 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 14908.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 40.5 | 168750 | ACTION | 14908.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 14910.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 14916.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 14936.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 36 | 180000 | ACTION | 14940.1603 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 14942.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 34 | 42500 | ACTION | 14942.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 1.991 | 9954.8442 | ACTION | 14942.1513 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14943.1513 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14948.6513 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 14949.2967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14954.1513 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14956.1513 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14957.1513 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14962.6513 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14968.1513 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 14969.1513 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14978.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 14978.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 14979.1422 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14980.1422 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14985.6422 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14986.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 14991.1422 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 14993.1422 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 14994.1422 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14998.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 14999.6422 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15005.1422 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15006.1422 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 15010.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 15016.1332 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15017.1332 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 15022.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15022.6332 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15028.1332 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 15029.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15030.1332 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15031.1332 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15032.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 24 | 0 | ACTION | 15056.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15060.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 31 | 155000 | ACTION | 15062.1332 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15063.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15067.6332 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15073.1332 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15074.1332 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 15084.1242 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15085.1242 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15087.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 353.5825 | 441978.0655 | ACTION | 15087.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 42 | 105000 | ACTION | 15129.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 15135.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 15142.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 200 | 833333.3333 | ACTION | 15142.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 15144.0719 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15146.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 58.5 | 0 | ACTION | 15146.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 15150.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15154.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15166.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 70833.3333 | ACTION | 15167.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 15172.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 15184.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 15196.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 30 | 125000 | ACTION | 15197.0719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 12500 | ACTION | 15200.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 15203.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 120 | 600000 | ACTION | 15205.1242 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 15206.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 64 | 80000 | ACTION | 15206.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15206.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15210.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15210.6242 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 15213.2967 | MooredSubInstallation | [5 empty] | 2
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15213.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15216.1242 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15237.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 363.0825 | 453853.0655 | ACTION | 15237.8791 | MooredSubInstallation
| Towing Group 1 | Delay | 33 | 82500 | ACTION | 15270.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 15276.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Delay | 62 | 310000 | ACTION | 15278.1242 | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15280.1242 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15281.1242 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 15283.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 77 | 320833.3333 | ACTION | 15283.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 15285.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15286.6242 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 15291.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15292.1242 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15293.1242 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 15303.1152 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15304.1152 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15309.6152 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 15311.0719 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15314.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 76.5 | 0 | ACTION | 15314.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15315.1152 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 15317.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 34 | 42500 | ACTION | 15317.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15317.1152 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15318.1152 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15322.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15323.6152 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 15324.2967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15329.1152 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 2 | 10000 | ACTION | 15331.1152 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15332.1152 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15334.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 15342.1061 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15343.1061 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 15346.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15348.6061 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15354.1061 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15356.1061 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15357.1061 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 15358.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 15365.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 15372.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15375.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15379.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15382.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 24 | 0 | ACTION | 15406.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15430.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 481.5825 | 601978.0655 | ACTION | 15430.8791 | MooredSubInstallation
| Towing Group 2 | Delay | 38 | 95000 | ACTION | 15468.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 15474.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Delay | 119 | 595000 | ACTION | 15476.1061 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 15481.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 164 | 683333.3333 | ACTION | 15481.0719 | MooredSubInstallation | Site
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15481.6061 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15482.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 51.5 | 0 | ACTION | 15482.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 15483.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15487.1061 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15488.1061 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 15489.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15490.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 15498.0971 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15499.0971 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15502.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15504.5971 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 15509.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15510.0971 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15512.0971 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15513.0971 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 15514.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 15515.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 34 | 42500 | ACTION | 15515.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15518.5971 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 15522.2967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15524.0971 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 15526.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 15533.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15536.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15540.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15543.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 33 | 165000 | ACTION | 15557.0971 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15558.0971 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | ACTION | 15562.0971 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15567.8791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 354.5825 | 443228.0655 | ACTION | 15567.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 54 | 135000 | ACTION | 15621.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 15627.8791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 15634.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 119 | 495833.3333 | ACTION | 15634.0719 | MooredSubInstallation | Site
| Array Cable Installation Vessel | Delay | 73 | 365000 | ACTION | 15635.0971 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 15636.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.991 | 29954.8442 | ACTION | 15641.0881 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 15642.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15642.0881 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15647.5881 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15650.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 82.5 | 0 | ACTION | 15650.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15653.0881 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15655.0881 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15656.0881 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15658.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15661.5881 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 15662.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15667.0881 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 15668.0719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 34 | 42500 | ACTION | 15668.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15668.0881 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15670.3791 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 15675.2967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 15678.079 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15679.079 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 15682.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15684.579 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15690.079 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15692.079 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15693.079 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 15694.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15698.579 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 15701.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 9 | 0 | ACTION | 15710.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15713.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15717.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15720.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 32 | 160000 | ACTION | 15730.579 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15736.079 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15737.079 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15744.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 420.5825 | 525728.0655 | ACTION | 15744.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 15747.07 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15748.07 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 15750.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15753.57 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 15757.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 89 | 370833.3333 | ACTION | 15757.0719 | MooredSubInstallation | Site
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15759.07 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 15759.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15761.07 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15762.07 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 15765.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15767.57 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15773.07 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15774.07 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 9.991 | 49954.8442 | ACTION | 15784.061 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15785.061 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 15785.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15790.561 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 15791.0719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 34 | 42500 | ACTION | 15791.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15796.061 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 15798.061 | ArrayCableInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 15798.2967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15799.061 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15804.561 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15810.061 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 15811.061 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15818.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 73.5 | 0 | ACTION | 15818.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15826.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 20 | 100000 | ACTION | 15831.061 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15838.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 82 | 0 | ACTION | 15920.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 15932.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 15944.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 119 | 595000 | ACTION | 15950.061 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 15956.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.2057 | 51028.4666 | ACTION | 15960.2667 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 15963.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15966.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15970.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15973.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 23 | 115000 | ACTION | 15983.2667 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 15984.2667 | ArrayCableInstallation |  | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15986.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 15989.7667 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 15995.2667 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15997.8791 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Assemblies Available | 475.5825 | 594478.0655 | ACTION | 15997.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 15999.0361 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 15000 | ACTION | 16003.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Load Cable | 6 | 30000 | ACTION | 16005.0361 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16005.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Transit | 2 | 10000 | ACTION | 16007.0361 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 16010.0719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 219 | 912500 | ACTION | 16010.0719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 16012.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16017.8791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 16018.0719 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 19 | 95000 | ACTION | 16026.0361 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 1.7695 | 8847.3913 | ACTION | 16027.8056 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 16029.8056 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 16029.8791 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16030.8056 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16036.3056 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 16038.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 16041.8791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 4 | 16666.6667 | ACTION | 16042.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 35 | 0 | ACTION | 16076.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 16083.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16087.3791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 48 | 200000 | ACTION | 16090.0719 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16090.8791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 2 | 8333.3333 | ACTION | 16092.0719 | MooredSubInstallation
| Towing Group 2 | Positioning Support | 82 | 102500 | ACTION | 16092.0719 | MooredSubInstallation | site |  |  |  |  | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16094.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 61 | 305000 | ACTION | 16097.3056 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 2 | Transit | 7.2248 | 18062.0833 | ACTION | 16099.2967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16102.8056 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 16103.8056 | ArrayCableInstallation |  | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16118.3791 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Assemblies Available | 443.0825 | 553853.0655 | ACTION | 16118.3791 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 19 | 95000 | ACTION | 16122.8056 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Towing Group 3 | Ballast to Towing Draft | 6 | 15000 | ACTION | 16124.3791 | MooredSubInstallation | [5 empty] | 2
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16154.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 36 | 0 | ACTION | 16154.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16162.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16174.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 16186.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 12 | 0 | ACTION | 16198.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 7 | 0 | ACTION | 16205.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16208.8791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16212.3791 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16215.8791 | MooredSubInstallation
| Towing Group 3 | Delay | 104 | 260000 | ACTION | 16228.3791 | MooredSubInstallation | [5 empty] | 2
| Towing Group 3 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 16234.5719 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 142.5 | 593750 | ACTION | 16234.5719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 16236.5719 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 115 | 575000 | ACTION | 16237.8056 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16239.8791 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Assemblies Available | 441.5825 | 551978.0655 | ACTION | 16239.8791 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 16242.5719 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 15000 | ACTION | 16245.8791 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Lay/Bury Cable | 11.2057 | 56028.4666 | ACTION | 16249.0113 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16250.0113 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Tow Substructure | 6.1927 | 15481.7857 | ACTION | 16252.0719 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16255.5113 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16261.0113 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 83333.3333 | ACTION | 16262.5719 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 16263.0113 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16264.0113 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 6 | 25000 | ACTION | 16268.5719 | MooredSubInstallation
| Towing Group 3 | Positioning Support | 34 | 42500 | ACTION | 16268.5719 | MooredSubInstallation | site |  |  |  |  | 1
| Towing Group 1 | Queue | 16.5 | 20625 | ACTION | 16268.5719 | MooredSubInstallation | Site
| Multi-Purpose Support Vessel | Delay | 0 | 0 | ACTION | 16268.5719 | MooredSubInstallation | Site
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16269.5113 | ArrayCableInstallation |  | ArrayCableInstallation
| Multi-Purpose Support Vessel | Position Substructure | 2 | 8333.3333 | ACTION | 16270.5719 | MooredSubInstallation
| Towing Group 3 | Transit | 7.2248 | 18062.0833 | ACTION | 16275.7967 | MooredSubInstallation | [5 empty] | 2
| Multi-Purpose Support Vessel | Delay | 53 | 220833.3333 | ACTION | 16323.5719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 16329.5719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 45833.3333 | ACTION | 16340.5719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 10 | 41666.6667 | ACTION | 16350.5719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 37500 | ACTION | 16359.5719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 5 | 20833.3333 | ACTION | 16364.5719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Delay | 67 | 279166.6667 | ACTION | 16431.5719 | MooredSubInstallation
| Multi-Purpose Support Vessel | Check Mooring Lines | 1 | 4166.6667 | ACTION | 16432.5719 | MooredSubInstallation
| Towing Group 1 | Positioning Support | 164 | 205000 | ACTION | 16432.5719 | MooredSubInstallation | site |  |  |  |  | 1
| Multi-Purpose Support Vessel | Transit | 4.3349 | 18062.0833 | ACTION | 16436.9068 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 169 | 845000 | ACTION | 16438.5113 | ArrayCableInstallation |  | ArrayCableInstallation
| Towing Group 1 | Transit | 7.2248 | 18062.0833 | ACTION | 16439.7967 | MooredSubInstallation | [5 empty] | 2
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16444.0113 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 16445.0113 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5 | 25000 | ACTION | 16450.0113 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 232 | 1160000 | ACTION | 16682.0113 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 12 | 60000 | ACTION | 16694.0113 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 213 | 1065000 | ACTION | 16907.0113 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 7.7753 | 38876.3827 | ACTION | 16914.7866 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16915.7866 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16921.2866 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16926.7866 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 16928.7866 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 16929.7866 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 16935.2866 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 16940.7866 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 16941.7866 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 7 | 35000 | ACTION | 16948.7866 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 130 | 650000 | ACTION | 17078.7866 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 17.7753 | 88876.3827 | ACTION | 17096.5619 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 17097.5619 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 204 | 1020000 | ACTION | 17301.5619 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 17307.0619 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 17312.5619 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 17314.5619 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 17315.5619 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 218 | 1090000 | ACTION | 17533.5619 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 17539.0619 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 17544.5619 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 17545.5619 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 20000 | ACTION | 17549.5619 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 156 | 780000 | ACTION | 17705.5619 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 6 | 30000 | ACTION | 17711.5619 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 85 | 425000 | ACTION | 17796.5619 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 9.4694 | 47347.1515 | ACTION | 17806.0313 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 17807.0313 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 17812.5313 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 30 | 150000 | ACTION | 17842.5313 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 17848.0313 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 17850.0313 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 17851.0313 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 17856.5313 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 334 | 1670000 | ACTION | 18190.5313 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 18196.0313 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 18197.0313 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 19.4694 | 97347.1515 | ACTION | 18216.5007 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 18217.5007 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 18223.0007 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 18228.5007 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 18230.5007 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 18231.5007 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 18237.0007 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 76 | 380000 | ACTION | 18313.0007 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 18318.5007 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 18319.5007 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 1 | 5000 | ACTION | 18320.5007 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 1 | 5000 | ACTION | 18321.5007 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 10 | 50000 | ACTION | 18331.5007 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 684 | 3420000 | ACTION | 19015.5007 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 3.4865 | 17432.5621 | ACTION | 19018.9872 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 19019.9872 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 5 | 25000 | ACTION | 19024.9872 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 19030.4872 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 19035.9872 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 19037.9872 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 19038.9872 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 37 | 185000 | ACTION | 19075.9872 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 19081.4872 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 56 | 280000 | ACTION | 19137.4872 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 19142.9872 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 19143.9872 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 14.4865 | 72432.5621 | ACTION | 19158.4737 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 19159.4737 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 19164.9737 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 19170.4737 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 19172.4737 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 19173.4737 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 384 | 1920000 | ACTION | 19557.4737 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 19562.9737 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 19568.4737 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 19569.4737 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 6 | 30000 | ACTION | 19575.4737 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 269 | 1345000 | ACTION | 19844.4737 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 4.652 | 23259.7959 | ACTION | 19849.1257 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 19850.1257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 19855.6257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 19861.1257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 10000 | ACTION | 19863.1257 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 19864.1257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 19869.6257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 48 | 240000 | ACTION | 19917.6257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 19923.1257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 5000 | ACTION | 19924.1257 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 10.652 | 53259.7959 | ACTION | 19934.7777 | ArrayCableInstallation |  | ArrayCableInstallation | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 5000 | ACTION | 19935.7777 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 27500 | ACTION | 19941.2777 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 27500 | ACTION | 19946.7777 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 19950.5471 | ArrayCableInstallation |  | ArrayCableInstallation
| Array Cable Installation Vessel | Transit | 3.7695 | 18847.3913 | ACTION | 19954.3166 | ArrayCableInstallation |  | ArrayCableInstallation