## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | include_onshore_construction | max_waveheight | max_windspeed | transit_speed | num_vessels | num_ahts_vessels
0.5 | Export Cable Installation Vessel | Mobilize | 72 | 450000 | ACTION | 0 | ExportCableInstallation
1 | Mooring System Installation Vessel | Mobilize | 168 | 700000 | ACTION | 0 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Load Cable | 6 | 75000 | ACTION | 6 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8 | 33333.3333 | ACTION | 18 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 30 | 125000 | ACTION | 48 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 35 | 145833.3333 | ACTION | 83 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 87 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 32.4783 | 135326.25 | ACTION | 119.4783 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 121.4783 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 125.4783 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 141.6383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 22 | 91666.6667 | ACTION | 163.6383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 167.7983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 169.7983 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 173.7983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 194.7983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 210.9583 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 215.1183 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 217.1183 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 221.1183 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 222 | 2775000 | ACTION | 228 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Tow Plow | 0.4 | 5000 | ACTION | 228.4 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Pull Winch | 0.4 | 5000 | ACTION | 228.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Prepare Cable | 1 | 12500 | ACTION | 229.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 235.3 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 237.2783 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 240.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 241.4383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lower Cable | 1 | 12500 | ACTION | 241.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 243.4383 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 247.4383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 17 | 212500 | ACTION | 258.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 263.5983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 274.5983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 278.7583 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 280.7583 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 284.7583 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 300.9183 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 305.0783 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 48 | 600000 | ACTION | 306.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 307.0783 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 311.0783 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 327.2383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 331.3983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 49 | 612500 | ACTION | 355.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 75 | 312500 | ACTION | 406.3983 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 35 | 145833.3333 | ACTION | 441.3983 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 0.4783 | 1992.9167 | ACTION | 441.8766 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 446.8766 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 18 | 75000 | ACTION | 464.8766 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 469.8766 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 21 | 87500 | ACTION | 490.8766 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 50 | 208333.3333 | ACTION | 540.8766 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 54.4783 | 226992.9167 | ACTION | 595.3549 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 597.3549 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 601.3549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 617.5149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 621.6749 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 623.6749 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 627.6749 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 643.8349 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substation Assembly Line 1 | Substation Substructure Assembly | 0 | 0 | ACTION | 644.1179 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 647.9949 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 649.9949 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 653.9949 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 309 | 3862500 | ACTION | 664.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 3 | 37500 | ACTION | 667.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Substation Assembly Line 1 | Attach Topside | 24 | 0 | ACTION | 668.1179 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay: Waiting on Substation Assembly | 24 | 100000 | ACTION | 668.1179 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 670.1549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 674.3149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 676.3149 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 680.3149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 696.4749 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 700.6349 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 702.6349 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 723.6349 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 727.6349 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 743.7949 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 747.9549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 749.9549 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 753.9549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 770.1149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 104 | 1300000 | ACTION | 771.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 774.2749 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 14 | 175000 | ACTION | 785.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 49 | 204166.6667 | ACTION | 823.2749 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 12 | 50000 | ACTION | 835.2749 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 9 | 37500 | ACTION | 844.2749 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 1 | 4166.6667 | ACTION | 845.2749 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 17.4783 | 72826.25 | ACTION | 862.7532 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 867.7532 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 872.7532 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 112 | 1400000 | ACTION | 897.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 7 | 87500 | ACTION | 904.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 38 | 158333.3333 | ACTION | 910.7532 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 47 | 195833.3333 | ACTION | 957.7532 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 84 | 1050000 | ACTION | 988.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 37.4783 | 156159.5833 | ACTION | 995.2315 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 997.2315 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1001.2315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1017.3915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1021.5515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1023.5515 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1027.5515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 40 | 500000 | ACTION | 1028.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1043.7115 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1047.8715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1049.8715 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1053.8715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 95 | 395833.3333 | ACTION | 1148.8715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1165.0315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1169.1915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1171.1915 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1175.1915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 539 | 2245833.3333 | ACTION | 1207.1179 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 32 | 133333.3333 | ACTION | 1207.1915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 194 | 2425000 | ACTION | 1222.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1223.3515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1227.5115 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1229.5115 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1233.5115 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 20 | 250000 | ACTION | 1242.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Delay | 2 | 25000 | ACTION | 1244.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1249.6715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 5 | 62500 | ACTION | 1249.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1253.8315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1255.8315 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1259.8315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1275.9915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1280.1515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Tow Substation to Site | 125.7972 | 524154.8611 | ACTION | 1332.915 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1334.915 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 64 | 266666.6667 | ACTION | 1344.1515 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 16 | 66666.6667 | ACTION | 1360.1515 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 11.4783 | 47826.25 | ACTION | 1371.6298 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 39 | 162500 | ACTION | 1373.915 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1376.6298 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 130 | 1625000 | ACTION | 1379.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1379.915 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1381.6298 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1383.915 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 15 | 187500 | ACTION | 1394.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 1399.075 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1403.235 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 24 | 100000 | ACTION | 1405.6298 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 75 | 312500 | ACTION | 1480.6298 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 84 | 350000 | ACTION | 1487.235 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 107 | 1337500 | ACTION | 1501.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1509.235 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1521.235 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1525.235 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 28 | 350000 | ACTION | 1529.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Delay | 1 | 12500 | ACTION | 1530.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 51.4783 | 214492.9167 | ACTION | 1532.1081 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 3 | 37500 | ACTION | 1533.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1534.1081 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1538.1081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 1540.395 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1544.555 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1554.2681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1558.4281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1560.4281 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1564.4281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1566.555 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 42 | 525000 | ACTION | 1575.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1578.555 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1580.5881 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1582.555 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1584.7481 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1586.7481 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1590.7481 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 1597.715 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1601.875 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1606.9081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 34.0382 | 425477.8329 | ACTION | 1609.8382 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1611.0681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Position Onsite | 2 | 25000 | ACTION | 1611.8382 | ExportCableInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1613.0681 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1617.0681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1623.875 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 7 | 29166.6667 | ACTION | 1630.875 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1633.2281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1637.3881 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1639.3881 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 1647.3881 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1651.3881 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 19 | 79166.6667 | ACTION | 1670.3881 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 52 | 216666.6667 | ACTION | 1682.875 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1686.5481 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Check Mooring Lines | 5 | 20833.3333 | ACTION | 1687.875 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1690.7081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1692.7081 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1696.7081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Transit | 11 | 45833.3333 | ACTION | 1698.875 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay | 186 | 775000 | ACTION | 1884.875 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 189 | 787500 | ACTION | 1885.7081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1901.8681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Transit | 20 | 83333.3333 | ACTION | 1904.875 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay | 15 | 62500 | ACTION | 1919.875 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 19 | 79166.6667 | ACTION | 1920.8681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1925.0281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Transit | 28 | 116666.6667 | ACTION | 1947.875 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 23 | 95833.3333 | ACTION | 1948.0281 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 80 | 333333.3333 | ACTION | 2027.875 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 80 | 333333.3333 | ACTION | 2028.0281 | MooringSystemInstallation
| Floating Substation Installation Vessel | Transit | 9 | 37500 | ACTION | 2036.875 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 9 | 37500 | ACTION | 2037.0281 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 26 | 108333.3333 | ACTION | 2062.875 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 26 | 108333.3333 | ACTION | 2063.0281 | MooringSystemInstallation
| Floating Substation Installation Vessel | Transit | 6 | 25000 | ACTION | 2068.875 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 6 | 25000 | ACTION | 2069.0281 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 24 | 100000 | ACTION | 2092.875 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 24 | 100000 | ACTION | 2093.0281 | MooringSystemInstallation
| Floating Substation Installation Vessel | Transit | 1.4783 | 6159.5833 | ACTION | 2094.3533 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 509 | 6362500 | ACTION | 2120.8382 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 2126.3382 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Transit | 37.4783 | 156159.5833 | ACTION | 2130.5064 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2135.5064 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2140.5064 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 31 | 129166.6667 | ACTION | 2171.5064 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 54 | 225000 | ACTION | 2225.5064 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 116 | 1450000 | ACTION | 2242.3382 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 2247.8382 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Transit | 20 | 250000 | ACTION | 2267.8382 | ExportCableInstallation
| Mooring System Installation Vessel | Transit | 44.4783 | 185326.25 | ACTION | 2269.9847 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2271.9847 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2275.9847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 91 | 379166.6667 | ACTION | 2366.9847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 111 | 1387500 | ACTION | 2378.8382 | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2383.1447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2387.3047 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2389.3047 | MooringSystemInstallation
| Export Cable Installation Vessel | Transit | 14 | 175000 | ACTION | 2392.8382 | ExportCableInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2393.3047 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2409.4647 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2413.6247 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2415.6247 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2419.6247 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2435.7847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2439.9447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2441.9447 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2445.9447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2462.1047 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2466.2647 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2468.2647 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2472.2647 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2488.4247 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2492.5847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2494.5847 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2498.5847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2514.7447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2518.9047 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 152 | 1900000 | ACTION | 2544.8382 | ExportCableInstallation
| Export Cable Installation Vessel | Transit | 31.6333 | 395416.3043 | ACTION | 2576.4715 | ExportCableInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 2594.383 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2599.383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2604.383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 2679.8613 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2681.8613 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2685.8613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2702.0213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2706.1813 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2708.1813 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2712.1813 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2728.3413 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2732.5013 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2734.5013 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2738.5013 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2754.6613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2758.8213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2760.8213 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2764.8213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2780.9813 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2785.1413 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2787.1413 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2791.1413 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2807.3013 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2811.4613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2813.4613 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2817.4613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2833.6213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2837.7813 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 2913.2596 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2918.2596 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2923.2596 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 22 | 91666.6667 | ACTION | 2945.2596 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 22 | 91666.6667 | ACTION | 2967.2596 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 53.4783 | 222826.25 | ACTION | 3020.7379 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3022.7379 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3026.7379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3042.8979 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3047.0579 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3049.0579 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3053.0579 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3069.2179 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3073.3779 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3075.3779 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3079.3779 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3095.5379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3099.6979 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3101.6979 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3105.6979 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3121.8579 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3126.0179 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3128.0179 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3132.0179 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3148.1779 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3152.3379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3154.3379 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3158.3379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3174.4979 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3178.6579 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 3254.1362 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3259.1362 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3264.1362 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 3339.6145 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3341.6145 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3345.6145 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3361.7745 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3365.9345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3367.9345 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3371.9345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3388.0945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3392.2545 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3394.2545 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3398.2545 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3414.4145 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3418.5745 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3420.5745 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3424.5745 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3440.7345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3444.8945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3446.8945 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3450.8945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3467.0545 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3471.2145 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3473.2145 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3477.2145 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3493.3745 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3497.5345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 3573.0128 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3578.0128 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3583.0128 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 3658.4911 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3660.4911 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3664.4911 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3680.6511 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3684.8111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3686.8111 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3690.8111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3706.9711 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3711.1311 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3713.1311 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3717.1311 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3733.2911 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3737.4511 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3739.4511 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3743.4511 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3759.6111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3763.7711 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3765.7711 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3769.7711 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3785.9311 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3790.0911 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3792.0911 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3796.0911 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 3809.0911 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3825.2511 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3829.4111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 3904.8894 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3909.8894 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3914.8894 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 52 | 216666.6667 | ACTION | 3966.8894 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 46 | 191666.6667 | ACTION | 4012.8894 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 23.4783 | 97826.25 | ACTION | 4036.3677 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4038.3677 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4042.3677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4058.5277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4062.6877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4064.6877 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4068.6877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4084.8477 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4089.0077 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4091.0077 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4095.0077 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4111.1677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4115.3277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4117.3277 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4121.3277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4137.4877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4141.6477 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4143.6477 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4147.6477 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4163.8077 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4167.9677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4169.9677 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4173.9677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4190.1277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4194.2877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 4269.766 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4274.766 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4279.766 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 4355.2443 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4357.2443 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4361.2443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4377.4043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4381.5643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4383.5643 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4387.5643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4403.7243 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4407.8843 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4409.8843 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4413.8843 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4430.0443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4434.2043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4436.2043 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4440.2043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 108 | 450000 | ACTION | 4548.2043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4564.3643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4568.5243 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4570.5243 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4574.5243 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4590.6843 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4594.8443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4596.8443 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4600.8443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4617.0043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4621.1643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 4696.6426 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4701.6426 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4706.6426 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 4782.1209 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4784.1209 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4788.1209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4804.2809 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4808.4409 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4810.4409 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4814.4409 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4830.6009 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4834.7609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4836.7609 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4840.7609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4856.9209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4861.0809 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4863.0809 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4867.0809 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4883.2409 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4887.4009 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4889.4009 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4893.4009 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4909.5609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4913.7209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4915.7209 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4919.7209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4935.8809 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4940.0409 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 44 | 183333.3333 | ACTION | 4984.0409 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 50 | 208333.3333 | ACTION | 5034.0409 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 31.4783 | 131159.5833 | ACTION | 5065.5192 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5070.5192 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5075.5192 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 5150.9975 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5152.9975 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5156.9975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5173.1575 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5177.3175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5179.3175 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5183.3175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5199.4775 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5203.6375 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5205.6375 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5209.6375 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5225.7975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5229.9575 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5231.9575 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5235.9575 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5252.1175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5256.2775 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5258.2775 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5262.2775 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5278.4375 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5282.5975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5284.5975 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5288.5975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5304.7575 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5308.9175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 5384.3958 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5389.3958 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5394.3958 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 5469.8741 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5471.8741 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5475.8741 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5492.0341 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5496.1941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5498.1941 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5502.1941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5518.3541 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5522.5141 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5524.5141 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5528.5141 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5544.6741 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5548.8341 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5550.8341 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5554.8341 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5570.9941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5575.1541 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5577.1541 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5581.1541 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5597.3141 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5601.4741 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5603.4741 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5607.4741 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5623.6341 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5627.7941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 5703.2724 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5708.2724 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5713.2724 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 5788.7507 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5790.7507 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5794.7507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 97 | 404166.6667 | ACTION | 5891.7507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5907.9107 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5912.0707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5914.0707 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5918.0707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5934.2307 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5938.3907 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5940.3907 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5944.3907 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5960.5507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5964.7107 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5966.7107 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5970.7107 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5986.8707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5991.0307 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5993.0307 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5997.0307 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6013.1907 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6017.3507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6019.3507 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6023.3507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 39 | 162500 | ACTION | 6062.3507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6078.5107 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6082.6707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 6158.149 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6163.149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6168.149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 6243.6273 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6245.6273 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6249.6273 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6265.7873 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6269.9473 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6271.9473 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6275.9473 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6292.1073 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6296.2673 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6298.2673 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6302.2673 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6318.4273 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6322.5873 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6324.5873 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6328.5873 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 27 | 112500 | ACTION | 6355.5873 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6371.7473 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6375.9073 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6377.9073 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6381.9073 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6398.0673 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6402.2273 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6404.2273 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6408.2273 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6424.3873 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6428.5473 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 41 | 170833.3333 | ACTION | 6469.5473 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 32 | 133333.3333 | ACTION | 6501.5473 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 34.4783 | 143659.5833 | ACTION | 6536.0256 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6541.0256 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6546.0256 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 73 | 304166.6667 | ACTION | 6619.0256 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 15 | 62500 | ACTION | 6634.0256 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2.4783 | 10326.25 | ACTION | 6636.5039 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6638.5039 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6642.5039 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 6649.5039 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6665.6639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 34 | 141666.6667 | ACTION | 6699.6639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6703.8239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6705.8239 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6709.8239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6725.9839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6730.1439 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6732.1439 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6736.1439 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6752.3039 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6756.4639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6758.4639 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6762.4639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 15 | 62500 | ACTION | 6777.4639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6793.6239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6797.7839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6799.7839 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6803.7839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 48 | 200000 | ACTION | 6851.7839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6867.9439 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6872.1039 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6874.1039 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6878.1039 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6894.2639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6898.4239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 6973.9022 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6978.9022 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6983.9022 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 7059.3805 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7061.3805 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7065.3805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7081.5405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7085.7005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7087.7005 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7091.7005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7107.8605 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7112.0205 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 47 | 195833.3333 | ACTION | 7159.0205 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7161.0205 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7165.0205 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7181.1805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7185.3405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7187.3405 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7191.3405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7207.5005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7211.6605 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7213.6605 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7217.6605 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7233.8205 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7237.9805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7239.9805 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7243.9805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7260.1405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7264.3005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 24 | 100000 | ACTION | 7288.3005 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 35 | 145833.3333 | ACTION | 7323.3005 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 51 | 212500 | ACTION | 7374.3005 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 27 | 112500 | ACTION | 7401.3005 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 0.4783 | 1992.9167 | ACTION | 7401.7788 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7406.7788 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7411.7788 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 7421.7788 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7425.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 7425.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7433.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7445.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7449.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7453.183 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 35 | 145833.3333 | ACTION | 7456.7788 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7457.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7461.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7473.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7476.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7480.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7483.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7507.683 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.4783 | 272826.25 | ACTION | 7522.2571 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7524.2571 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7528.2571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 25 | 104166.6667 | ACTION | 7553.2571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7569.4171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7573.5771 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7575.5771 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7579.5771 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7579.683 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 322.5 | 2553125 | ACTION | 7579.683 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7585.683 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7593.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 7593.183 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7595.7371 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7599.8971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7601.183 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7601.8971 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7605.8971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7613.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7617.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7621.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7625.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7629.183 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 32 | 133333.3333 | ACTION | 7637.8971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7641.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7644.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7648.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7651.683 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7654.0571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7658.2171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7660.2171 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7664.2171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7675.683 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7680.3771 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7684.5371 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7686.5371 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7690.5371 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7706.6971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7747.683 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 490.5 | 3883125 | ACTION | 7747.683 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 13 | 102916.6667 | ACTION | 7760.683 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7761.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 7761.183 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 55 | 229166.6667 | ACTION | 7761.6971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7765.8571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7766.683 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7767.8571 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7769.183 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7771.8571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7781.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7785.183 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7788.0171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7789.183 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7792.1771 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7793.183 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8 | 33333.3333 | ACTION | 7800.1771 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 49 | 0 | ACTION | 7842.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7846.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7858.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7861.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7865.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7868.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7892.683 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 108 | 450000 | ACTION | 7908.1771 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7929.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7964.683 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 707.5 | 5601041.6667 | ACTION | 7964.683 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 57 | 237500 | ACTION | 7965.1771 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7972.683 | MooredSubInstallation
| Towing Group 3 | Delay | 12 | 95000 | ACTION | 7976.683 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 12 | 50000 | ACTION | 7977.1771 | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7982.683 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7984.683 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 10.4783 | 43659.5833 | ACTION | 7987.6554 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7988.683 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7992.6554 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7992.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7996.683 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7997.6554 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8000.683 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8 | 33333.3333 | ACTION | 8005.6554 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 29 | 120833.3333 | ACTION | 8034.6554 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 6 | 25000 | ACTION | 8040.6554 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8097.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 111 | 0 | ACTION | 8111.683 | MooredSubInstallation
| Towing Group 1 | Delay | 531 | 4203750 | ACTION | 8116.683 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 350 | 2770833.3333 | ACTION | 8116.683 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 134 | 1060833.3333 | ACTION | 8116.683 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 77 | 320833.3333 | ACTION | 8117.6554 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8123.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8127.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8130.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8134.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8158.183 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 61.4783 | 256159.5833 | ACTION | 8179.1337 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8181.1337 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8185.1337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8201.2937 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8205.4537 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8207.4537 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8211.4537 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8227.6137 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8230.183 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8231.7737 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8233.7737 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8237.7737 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8238.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8250.183 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 8253.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 8253.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 8253.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8253.9337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8254.183 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 8255.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 8255.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 8255.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8258.0937 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8258.183 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8260.0937 | MooringSystemInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8261.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8261.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8261.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8262.183 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8264.0937 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8265.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8266.183 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 95000 | ACTION | 8273.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 95000 | ACTION | 8273.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 95000 | ACTION | 8273.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8278.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 21 | 0 | ACTION | 8299.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8302.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8306.183 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 43 | 179166.6667 | ACTION | 8307.0937 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8309.683 | MooredSubInstallation
| Towing Group 1 | Delay | 38 | 300833.3333 | ACTION | 8311.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 38 | 300833.3333 | ACTION | 8311.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 38 | 300833.3333 | ACTION | 8311.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 63333.3333 | ACTION | 8319.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 63333.3333 | ACTION | 8319.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 63333.3333 | ACTION | 8319.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8323.2537 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 8325.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 8325.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 8325.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8327.4137 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8329.4137 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8333.4137 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8333.683 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8349.5737 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8353.7337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 28 | 221666.6667 | ACTION | 8353.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 28 | 221666.6667 | ACTION | 8353.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 28 | 221666.6667 | ACTION | 8353.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8355.7337 | MooringSystemInstallation
| Towing Group 1 | Delay | 4 | 31666.6667 | ACTION | 8357.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 4 | 31666.6667 | ACTION | 8357.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 4 | 31666.6667 | ACTION | 8357.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 3 | 12500 | ACTION | 8358.7337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8362.7337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 5 | 39583.3333 | ACTION | 8362.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 5 | 39583.3333 | ACTION | 8362.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 5 | 39583.3333 | ACTION | 8362.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 7 | 55416.6667 | ACTION | 8369.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 7 | 55416.6667 | ACTION | 8369.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 7 | 55416.6667 | ACTION | 8369.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 8370.7337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8386.8937 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 20.9131 | 165561.8155 | ACTION | 8390.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 20.9131 | 165561.8155 | ACTION | 8390.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 20.9131 | 165561.8155 | ACTION | 8390.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8391.0537 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8396.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8405.683 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 14.8537 | 117591.4421 | ACTION | 8405.683 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8411.683 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8413.683 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 34 | 141666.6667 | ACTION | 8425.0537 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8425.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8429.683 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8433.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8433.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8437.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8441.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 78 | 0 | ACTION | 8519.683 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 102 | 425000 | ACTION | 8527.0537 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8531.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8535.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8538.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8542.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8566.183 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 40 | 166666.6667 | ACTION | 8567.0537 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 19 | 79166.6667 | ACTION | 8586.0537 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 1.4783 | 6159.5833 | ACTION | 8587.532 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8592.532 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8597.532 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8601.183 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 24 | 100000 | ACTION | 8621.532 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8638.183 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 247.3537 | 1958216.4421 | ACTION | 8638.183 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 5 | 39583.3333 | ACTION | 8643.183 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 22 | 91666.6667 | ACTION | 8643.532 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8646.183 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8649.183 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8658.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8662.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8666.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8670.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8674.183 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 34 | 141666.6667 | ACTION | 8677.532 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8686.183 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 9 | 37500 | ACTION | 8686.532 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 1 | 4166.6667 | ACTION | 8687.532 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 8689.532 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 8694.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8697.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8701.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8704.683 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 16.4783 | 68659.5833 | ACTION | 8706.0103 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8728.683 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 57 | 237500 | ACTION | 8763.0103 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8765.0103 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8769.0103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8769.183 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8785.1703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8789.3303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8791.3303 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8795.3303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 71 | 0 | ACTION | 8799.683 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8811.4903 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 8824.4903 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8828.6503 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8830.6503 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8834.6503 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8850.8103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8871.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8879.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8891.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8895.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8899.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8903.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8907.683 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 62 | 258333.3333 | ACTION | 8912.8103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8916.9703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8918.9703 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8919.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 8920.683 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8922.9703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8924.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8927.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8931.183 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8937.183 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8939.1303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8943.2903 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8945.2903 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8949.2903 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8955.183 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8965.4503 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 47 | 195833.3333 | ACTION | 9012.4503 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9016.6103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9018.6103 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9022.6103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9027.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9035.183 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9038.7703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9042.9303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9047.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9051.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9055.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9059.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9063.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9075.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9078.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9082.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9085.683 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9105.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9109.683 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 68 | 283333.3333 | ACTION | 9110.9303 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 27 | 112500 | ACTION | 9137.9303 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 7.4783 | 31159.5833 | ACTION | 9145.4086 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9150.4086 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9155.4086 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 24 | 100000 | ACTION | 9179.4086 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 46 | 191666.6667 | ACTION | 9225.4086 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 9 | 37500 | ACTION | 9234.4086 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9273.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 175 | 0 | ACTION | 9284.683 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 91 | 379166.6667 | ACTION | 9325.4086 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 18 | 75000 | ACTION | 9343.4086 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9356.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9364.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9376.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9380.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9384.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9388.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9392.683 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 56 | 233333.3333 | ACTION | 9399.4086 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9404.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9408.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9411.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9415.183 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 24.4783 | 101992.9167 | ACTION | 9423.8869 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9425.8869 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9429.8869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9439.183 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9441.183 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9446.0469 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9450.2069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9452.2069 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9456.2069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9472.3669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9476.5269 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9478.5269 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9482.5269 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9498.6869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9502.8469 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9504.8469 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9508.8469 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9511.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9519.183 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9525.0069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9529.1669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9531.1669 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9531.183 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9535.1669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9535.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9539.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9543.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9547.183 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9551.3269 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9555.4869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9557.4869 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9559.183 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9561.4869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9562.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9566.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9569.683 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9577.6469 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9581.8069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 3 | 12500 | ACTION | 9584.8069 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9593.683 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 9595.8069 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9609.183 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 59 | 245833.3333 | ACTION | 9654.8069 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 65 | 0 | ACTION | 9658.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9730.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9738.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9750.683 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 98 | 408333.3333 | ACTION | 9752.8069 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9754.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9758.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9762.683 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 13.4783 | 56159.5833 | ACTION | 9766.2852 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9766.683 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9771.2852 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9776.2852 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9777.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9778.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9782.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9785.683 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9789.183 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 20 | 83333.3333 | ACTION | 9796.2852 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 19 | 0 | ACTION | 9808.183 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9832.183 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 38 | 158333.3333 | ACTION | 9834.2852 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 9844.2852 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 24 | 100000 | ACTION | 9868.2852 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9904.183 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 45.4783 | 189492.9167 | ACTION | 9913.7635 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9915.7635 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9919.7635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9945.183 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 40 | 166666.6667 | ACTION | 9959.7635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9975.9235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9980.0835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9982.0835 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9986.0835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10002.2435 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10006.4035 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10008.4035 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10012.4035 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10113.183 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 226 | 941666.6667 | ACTION | 10238.4035 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10254.5635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10258.7235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10260.7235 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10264.7235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10280.8835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10281.183 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10285.0435 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10287.0435 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10291.0435 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10307.2035 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10311.3635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10313.3635 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10317.3635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10333.5235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 33 | 137500 | ACTION | 10366.5235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10370.6835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 56 | 233333.3333 | ACTION | 10426.6835 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 10 | 41666.6667 | ACTION | 10436.6835 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 19.4783 | 81159.5833 | ACTION | 10456.1618 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 70 | 291666.6667 | ACTION | 10526.1618 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10531.1618 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10536.1618 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 14 | 58333.3333 | ACTION | 10550.1618 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 82 | 341666.6667 | ACTION | 10632.1618 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 49 | 204166.6667 | ACTION | 10681.1618 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 35 | 145833.3333 | ACTION | 10716.1618 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 12.4783 | 51992.9167 | ACTION | 10728.6401 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10730.6401 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10734.6401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 44 | 183333.3333 | ACTION | 10778.6401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10794.8001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10798.9601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10800.9601 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10804.9601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10821.1201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 168 | 700000 | ACTION | 10989.1201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10993.2801 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10995.2801 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10999.2801 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 2621 | 20749583.3333 | ACTION | 11032.683 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 2636 | 20868333.3333 | ACTION | 11032.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 2384 | 18873333.3333 | ACTION | 11033.183 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 34 | 141666.6667 | ACTION | 11033.2801 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11049.4401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11053.6001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11055.6001 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11059.6001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11075.7601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11079.9201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11081.9201 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11085.9201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11102.0801 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11106.2401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11108.2401 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11112.2401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11128.4001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11132.5601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 11169.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 11170.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 11170.4163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 11171.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 11172.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 11172.4163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11177.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11178.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11178.4163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11197.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11198.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11198.4163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 11203.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 11204.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 11204.4163 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 11208.0384 | MooringSystemInstallation
| Towing Group 3 | Transit | 6 | 47500 | ACTION | 11210.4163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7 | 55416.6667 | ACTION | 11210.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7 | 55416.6667 | ACTION | 11211.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11213.0384 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 11215.0384 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 5 | 39583.3333 | ACTION | 11215.4163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 5 | 39583.3333 | ACTION | 11215.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 5 | 39583.3333 | ACTION | 11216.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11220.0384 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 9 | 71250 | ACTION | 11224.4163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 9 | 71250 | ACTION | 11224.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 9 | 71250 | ACTION | 11225.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 9 | 37500 | ACTION | 11229.0384 | MooringSystemInstallation
| Towing Group 3 | Delay | 10 | 79166.6667 | ACTION | 11234.4163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 10 | 79166.6667 | ACTION | 11234.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 6 | 25000 | ACTION | 11235.0384 | MooringSystemInstallation
| Towing Group 1 | Delay | 10 | 79166.6667 | ACTION | 11235.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 1 | 7916.6667 | ACTION | 11235.4163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 1 | 7916.6667 | ACTION | 11235.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 1 | 4166.6667 | ACTION | 11236.0384 | MooringSystemInstallation
| Towing Group 1 | Transit | 1 | 7916.6667 | ACTION | 11236.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 44 | 348333.3333 | ACTION | 11279.4163 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 44 | 348333.3333 | ACTION | 11279.9163 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 44 | 183333.3333 | ACTION | 11280.0384 | MooringSystemInstallation
| Towing Group 1 | Delay | 44 | 348333.3333 | ACTION | 11280.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 36.9131 | 292228.4821 | ACTION | 11316.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay: No Assembly Storage Available | 1412.6463 | 0 | ACTION | 11316.8294 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 1035.6463 | 0 | ACTION | 11316.8294 | MooredSubInstallation
| Towing Group 1 | Transit | 36.9131 | 292228.4821 | ACTION | 11316.9757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 37.9131 | 300145.1488 | ACTION | 11317.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11322.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11322.9757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11323.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11324.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11336.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11340.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11344.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.4783 | 272826.25 | ACTION | 11345.5167 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11347.5167 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11348.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11351.5167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11352.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11364.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11367.6767 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11368.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11371.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11371.8367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11373.8367 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11375.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11377.8367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11393.9967 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11398.1567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11399.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11400.1567 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11404.1567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11420.3167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11424.4767 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11426.4767 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11430.4767 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11446.6367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11450.7967 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11452.7967 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11456.7967 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 11460.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 11460.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 11460.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 11462.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 11462.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 11462.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11468.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11468.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11468.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11471.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11472.9567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11477.1167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11479.1167 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11479.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11483.1167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11484.8294 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11488.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11488.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11488.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11491.3294 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 11494.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 11494.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 11494.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11495.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11499.2767 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11499.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11503.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11503.4367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11507.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11519.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11522.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11526.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11529.8294 | MooredSubInstallation
| Towing Group 2 | Transit | 53.9131 | 426811.8155 | ACTION | 11547.9757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 53.9131 | 426811.8155 | ACTION | 11548.1221 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 53.9131 | 426811.8155 | ACTION | 11548.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11553.8294 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11553.9757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11554.1221 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11554.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 11578.915 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11583.915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11588.915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11625.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 39 | 162500 | ACTION | 11627.915 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 3 | 12500 | ACTION | 11630.915 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11633.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11645.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11649.8294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11652.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11653.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11657.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11661.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 36.4783 | 151992.9167 | ACTION | 11667.3933 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11669.3933 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11673.3933 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11673.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 11679.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11683.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11686.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11689.5533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11690.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11693.7133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11695.7133 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11699.7133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11714.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11715.8733 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11720.0333 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11722.0333 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11726.0333 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11742.1933 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11746.3533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11748.3533 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11752.3533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11768.5133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11772.6733 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11774.6733 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11778.6733 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11786.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11794.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11794.8333 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11798.9933 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11800.9933 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11804.9933 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11806.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 11814.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11818.3294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11820.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11821.1533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11822.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11825.3133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11826.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11830.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11842.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 41 | 170833.3333 | ACTION | 11866.3133 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 54 | 225000 | ACTION | 11920.3133 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 86 | 0 | ACTION | 11928.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11931.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11935.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11938.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 34.4783 | 143659.5833 | ACTION | 11954.7916 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11959.7916 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11962.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11964.7916 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11988.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12034.8294 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 46 | 0 | ACTION | 12034.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 12040.2699 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12042.2699 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12042.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12046.2699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12054.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12062.4299 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 9 | 0 | ACTION | 12063.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12066.5899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12067.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12068.5899 | MooringSystemInstallation
| Towing Group 3 | Delay | 529 | 4187916.6667 | ACTION | 12083.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 12083.8294 | MooredSubInstallation
| Towing Group 2 | Delay | 530 | 4195833.3333 | ACTION | 12083.9757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 530 | 4195833.3333 | ACTION | 12084.1221 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 16 | 66666.6667 | ACTION | 12084.5899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12087.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12088.5899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12091.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12095.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12104.7499 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12107.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12108.9099 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12110.9099 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12111.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12114.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12114.9099 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12118.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12131.0699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12135.2299 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12137.2299 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12141.2299 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12142.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12157.3899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12161.5499 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12163.5499 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12167.5499 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12183.7099 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12187.8699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12189.8699 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12193.8699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12202.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12210.0299 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12214.1899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12214.3294 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 11.5 | 0 | ACTION | 12214.3294 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 12220.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 12221.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 12221.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12222.3294 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 12222.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 12223.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 12223.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12228.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12229.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12229.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12234.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12238.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12242.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12246.3294 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 12248.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 12249.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 12249.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12250.3294 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 5 | 39583.3333 | ACTION | 12254.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 5 | 39583.3333 | ACTION | 12254.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 12254.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 2 | 15833.3333 | ACTION | 12256.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 48 | 200000 | ACTION | 12262.1899 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 6 | 25000 | ACTION | 12268.1899 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 19 | 0 | ACTION | 12269.3294 | MooredSubInstallation
| Towing Group 3 | Delay | 13 | 102916.6667 | ACTION | 12269.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 20 | 158333.3333 | ACTION | 12274.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 20 | 158333.3333 | ACTION | 12274.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 1 | 7916.6667 | ACTION | 12275.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 1 | 7916.6667 | ACTION | 12275.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12281.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12284.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12288.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12291.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 27.4783 | 114492.9167 | ACTION | 12295.6682 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12300.6682 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12305.6682 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12315.8294 | MooredSubInstallation
| Towing Group 3 | Transit | 51.9131 | 410978.4821 | ACTION | 12321.6221 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12327.6221 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 53.9131 | 426811.8155 | ACTION | 12329.1221 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 53.9131 | 426811.8155 | ACTION | 12329.2684 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12335.1221 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12335.2684 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 12381.1465 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12382.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12383.1465 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12387.1465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12387.8294 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 5.5 | 0 | ACTION | 12387.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12395.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12403.3065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12407.4665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12407.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12409.4665 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12411.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12413.4665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12415.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12419.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12423.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12429.6265 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12433.7865 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12435.7865 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12435.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12439.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12439.7865 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12442.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12446.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12455.9465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12460.1065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12462.1065 | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 12464.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12466.1065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 12466.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12470.3294 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 12472.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 12472.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12472.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 12474.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 12474.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12480.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12480.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12482.2665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12486.4265 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 63333.3333 | ACTION | 12488.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12488.4265 | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 63333.3333 | ACTION | 12488.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 126666.6667 | ACTION | 12488.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 2 | 15833.3333 | ACTION | 12490.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 2 | 15833.3333 | ACTION | 12490.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 2 | 15833.3333 | ACTION | 12490.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7916.6667 | ACTION | 12491.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7916.6667 | ACTION | 12491.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7916.6667 | ACTION | 12491.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12492.4265 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 3 | 23750 | ACTION | 12494.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 3 | 23750 | ACTION | 12494.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 3 | 23750 | ACTION | 12494.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 12497.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 12503.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 87083.3333 | ACTION | 12505.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 87083.3333 | ACTION | 12505.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12508.5865 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 12511.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 12511.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12512.7465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12514.7465 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12518.7465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12534.9065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12539.0665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12542.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12550.3294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12555.8294 | MooredSubInstallation
| Towing Group 3 | Transit | 53.9131 | 426811.8155 | ACTION | 12557.7684 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12562.3294 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12563.7684 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 53.9131 | 426811.8155 | ACTION | 12565.2684 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 53.9131 | 426811.8155 | ACTION | 12565.4148 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12566.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12570.3294 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12571.2684 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12571.4148 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12574.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12578.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12590.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12593.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12597.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12600.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 12614.5448 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12619.5448 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12624.5448 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12624.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 3 | 12500 | ACTION | 12627.5448 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 12631.5448 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2 | 8333.3333 | ACTION | 12633.5448 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 6 | 25000 | ACTION | 12639.5448 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 70.4783 | 293659.5833 | ACTION | 12710.0231 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12712.0231 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12716.0231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12723.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 43 | 179166.6667 | ACTION | 12759.0231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12775.1831 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 6 | 25000 | ACTION | 12781.1831 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12785.3431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12787.3431 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12791.3431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12807.5031 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12811.6631 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12813.6631 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12817.6631 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12833.8231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 228 | 0 | ACTION | 12852.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 23 | 95833.3333 | ACTION | 12856.8231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12860.9831 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12862.9831 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12866.9831 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 301 | 2382916.6667 | ACTION | 12872.2684 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 301 | 2382916.6667 | ACTION | 12872.4148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 309 | 2446250 | ACTION | 12872.7684 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12883.1431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12887.3031 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12889.3031 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12893.3031 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12909.4631 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12913.6231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12915.6231 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12919.6231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12924.8294 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 201 | 0 | ACTION | 12924.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12932.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12935.7831 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12939.9431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12944.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12948.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12952.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12956.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12960.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12972.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12976.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12979.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12983.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13007.3294 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 13009.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 13009.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 13010.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 13011.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 13011.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 13012.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 13015.4214 | MooringSystemInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13017.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13017.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13018.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 13020.4214 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 13025.4214 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13037.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13037.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13038.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 13043.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 13043.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 13044.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13079.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13087.3294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13092.8294 | MooredSubInstallation
| Towing Group 2 | Transit | 53.9131 | 426811.8155 | ACTION | 13097.4148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 53.9131 | 426811.8155 | ACTION | 13097.5611 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 53.9131 | 426811.8155 | ACTION | 13097.9148 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13099.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 13100.8997 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13102.8997 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13103.3294 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13103.4148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13103.5611 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13103.9148 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13106.8997 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13107.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13111.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13115.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13123.0597 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13127.2197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13127.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13129.2197 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13130.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13133.2197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13134.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13137.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13149.3797 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13153.5397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13155.5397 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13159.5397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13161.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13175.6997 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13179.8597 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13181.8597 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13185.8597 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13202.0197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13206.1797 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13208.1797 | MooringSystemInstallation
| Towing Group 2 | Delay | 105 | 831250 | ACTION | 13208.4148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 105 | 831250 | ACTION | 13208.5611 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 105 | 831250 | ACTION | 13208.9148 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13212.1797 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13228.3397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13232.4997 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13233.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13234.4997 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13238.4997 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13241.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13253.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13254.6597 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13257.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13258.8197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13260.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13261.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13265.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13269.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13281.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13285.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13288.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13292.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13316.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 13334.298 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 13339.298 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 13344.298 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 13345.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 13345.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 13346.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 13347.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 13347.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 13348.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13353.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13353.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13354.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 19 | 150416.6667 | ACTION | 13372.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 19 | 150416.6667 | ACTION | 13372.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 19 | 150416.6667 | ACTION | 13373.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 3 | 23750 | ACTION | 13375.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 3 | 23750 | ACTION | 13375.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 3 | 23750 | ACTION | 13376.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7916.6667 | ACTION | 13376.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7916.6667 | ACTION | 13376.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7916.6667 | ACTION | 13377.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 13382.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 13382.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 13383.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13388.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13396.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13408.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13412.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13416.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 13419.7763 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13420.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13421.7763 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13424.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13425.7763 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13428.8294 | MooredSubInstallation
| Towing Group 2 | Transit | 50 | 395833.3333 | ACTION | 13432.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 50 | 395833.3333 | ACTION | 13432.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 50 | 395833.3333 | ACTION | 13433.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 13435.3294 | MooredSubInstallation
| Towing Group 2 | Delay | 3 | 23750 | ACTION | 13435.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 3 | 23750 | ACTION | 13435.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 3 | 23750 | ACTION | 13436.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 3.9131 | 30978.4821 | ACTION | 13439.5611 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 3.9131 | 30978.4821 | ACTION | 13439.7075 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 3.9131 | 30978.4821 | ACTION | 13440.0611 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13441.9363 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13445.5611 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13445.7075 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13446.0963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13447.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13448.0963 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13452.0963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13468.2563 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13472.4163 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13474.4163 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13478.4163 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 47 | 372083.3333 | ACTION | 13492.5611 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 47 | 372083.3333 | ACTION | 13492.7075 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13494.5763 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13498.7363 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 53 | 0 | ACTION | 13500.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13500.7363 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13503.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13504.7363 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13507.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13510.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13520.8963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13525.0563 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13527.0563 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13531.0563 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13534.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13547.2163 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13551.3763 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13553.3763 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13557.3763 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13573.5363 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13577.6963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13596.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13606.8294 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 166.7683 | 1320248.8772 | ACTION | 13606.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 10 | 0 | ACTION | 13606.8294 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13612.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13614.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13626.8294 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 13629.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 13629.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13630.8294 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 13631.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 13631.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13634.8294 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13637.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13637.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13638.8294 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 13640.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 13640.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 2 | 15833.3333 | ACTION | 13642.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 2 | 15833.3333 | ACTION | 13642.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7916.6667 | ACTION | 13643.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7916.6667 | ACTION | 13643.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 3 | 23750 | ACTION | 13646.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 3 | 23750 | ACTION | 13646.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 13649.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 13649.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 3 | 23750 | ACTION | 13652.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 3 | 23750 | ACTION | 13652.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 13653.1746 | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 15833.3333 | ACTION | 13654.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 15833.3333 | ACTION | 13654.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 13658.1746 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 13663.1746 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 1 | 4166.6667 | ACTION | 13664.1746 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 50 | 0 | ACTION | 13688.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13692.8294 | MooredSubInstallation
| Towing Group 3 | Delay | 83 | 657083.3333 | ACTION | 13695.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 32 | 133333.3333 | ACTION | 13696.1746 | MooringSystemInstallation
| Towing Group 2 | Delay | 48 | 380000 | ACTION | 13702.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 48 | 380000 | ACTION | 13702.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13704.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13708.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13711.8294 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 87083.3333 | ACTION | 13713.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 87083.3333 | ACTION | 13713.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13715.3294 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 13719.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 13719.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13739.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 74.4783 | 310326.25 | ACTION | 13770.6529 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13772.6529 | MooringSystemInstallation
| Towing Group 2 | Transit | 53.9131 | 426811.8155 | ACTION | 13773.7075 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 53.9131 | 426811.8155 | ACTION | 13773.8538 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13774.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13776.6529 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13792.8129 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13796.9729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13798.9729 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13802.9729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13811.3294 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 37.6219 | 297840.3193 | ACTION | 13811.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 36.5 | 0 | ACTION | 13811.3294 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13817.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13819.1329 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13819.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13823.2929 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13825.2929 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13829.2929 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13831.3294 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 13833.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 13835.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13835.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13839.3294 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13841.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13843.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13845.4529 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13847.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13849.6129 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13851.6129 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13855.6129 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13859.3294 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13861.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 13867.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13871.7729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13875.9329 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13877.9329 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13881.9329 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13898.0929 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 32 | 253333.3333 | ACTION | 13899.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 82 | 649166.6667 | ACTION | 13899.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 1 | 7916.6667 | ACTION | 13900.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13902.2529 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13904.2529 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13908.2529 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 21.9131 | 173478.4821 | ACTION | 13921.9757 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13924.4129 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13928.5729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 85 | 0 | ACTION | 13944.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13947.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13951.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13954.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13978.8294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13979.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 14004.0512 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 14009.0512 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 14014.0512 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 14036.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 14038.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14044.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14050.8294 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 276.9756 | 2192723.428 | ACTION | 14050.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 71.5 | 0 | ACTION | 14050.8294 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14056.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14058.8294 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14064.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 14070.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14070.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14074.8294 | MooredSubInstallation
| Towing Group 2 | Transit | 7 | 55416.6667 | ACTION | 14077.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 3 | 23750 | ACTION | 14080.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 14080.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14084.8294 | MooredSubInstallation
| Towing Group 2 | Transit | 6 | 47500 | ACTION | 14086.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 14089.5295 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 14091.5295 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 14095.5295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 29 | 120833.3333 | ACTION | 14124.5295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 40 | 316666.6667 | ACTION | 14126.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 70 | 554166.6667 | ACTION | 14126.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 42 | 0 | ACTION | 14126.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14130.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14134.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 14140.6895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 14144.8495 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14146.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 14146.8495 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14150.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 14150.8495 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14153.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 14167.0095 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 40.9131 | 323895.1488 | ACTION | 14167.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 14171.1695 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 14173.1695 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 14177.1695 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 14193.3295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 14197.4895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 45 | 0 | ACTION | 14198.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 14199.4895 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14202.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 14203.4895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14218.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 14219.6495 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 14223.8095 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 14225.8095 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14226.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 14229.8095 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 14245.9695 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 14250.1295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 14252.1295 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 14256.1295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 14264.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 14266.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14272.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 14272.2895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 14276.4495 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14292.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 14298.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14298.3294 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 376.3537 | 2979466.4421 | ACTION | 14298.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 79.5 | 0 | ACTION | 14298.3294 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14304.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14306.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14318.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14322.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14326.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14330.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14334.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14346.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14349.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 14351.9278 | MooringSystemInstallation
| Towing Group 1 | Transit | 53.9131 | 426811.8155 | ACTION | 14351.9757 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14353.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14356.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 14356.9278 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14380.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75 | 312500 | ACTION | 14431.9278 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 3 | 12500 | ACTION | 14434.9278 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 0.4783 | 1992.9167 | ACTION | 14435.4061 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 14437.4061 | MooringSystemInstallation
| Towing Group 3 | Delay | 134 | 1060833.3333 | ACTION | 14438.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 14441.4061 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14452.8294 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 285.3537 | 2259049.7754 | ACTION | 14452.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 14457.5661 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14458.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14460.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 14461.7261 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 14463.7261 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14466.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 14467.7261 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14472.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14476.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14480.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 14483.8861 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14484.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 14488.0461 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14488.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 14490.0461 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 14494.0461 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14500.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14504.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14507.8294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 14510.2061 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14511.3294 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 14514.3661 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14535.3294 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 14575.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 14577.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14583.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 14596.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 14598.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14603.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14604.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14607.3294 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 255.3537 | 2021549.7754 | ACTION | 14607.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 14609.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14613.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14615.3294 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14624.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14627.3294 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 14630.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14631.3294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14634.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14635.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14639.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14643.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14655.3294 | MooredSubInstallation
| Towing Group 3 | Transit | 53.9131 | 426811.8155 | ACTION | 14663.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 53.9131 | 426811.8155 | ACTION | 14683.9757 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 37 | 0 | ACTION | 14692.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14695.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14699.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14702.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14726.8294 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 14750.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 14752.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14758.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14778.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 14784.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14798.8294 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 135.3537 | 1071549.7754 | ACTION | 14798.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14802.3294 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14804.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14806.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14818.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14822.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14826.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14830.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14834.8294 | MooredSubInstallation
| Towing Group 1 | Transit | 53.9131 | 426811.8155 | ACTION | 14838.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14846.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 38 | 0 | ACTION | 14884.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14888.3294 | MooredSubInstallation
| Towing Group 3 | Delay | 85 | 672916.6667 | ACTION | 14889.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14891.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14895.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14919.3294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14970.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14991.3294 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 307.3537 | 2433216.4421 | ACTION | 14991.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 21 | 0 | ACTION | 14991.3294 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14997.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14999.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15011.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15015.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15019.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15023.3294 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 15027.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15027.3294 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 15029.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15035.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15039.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15042.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15046.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15049.8294 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 15055.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 15061.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15073.8294 | MooredSubInstallation
| Towing Group 3 | Transit | 53.9131 | 426811.8155 | ACTION | 15114.9757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 15134.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 15136.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15142.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 15145.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15145.8294 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 307.3537 | 2433216.4421 | ACTION | 15145.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 5 | 39583.3333 | ACTION | 15150.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 15153.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15153.8294 | MooredSubInstallation
| Towing Group 2 | Delay | 2 | 15833.3333 | ACTION | 15155.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 10 | 79166.6667 | ACTION | 15155.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15159.3294 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15161.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15165.8294 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 110833.3333 | ACTION | 15169.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15169.8294 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 4 | 31666.6667 | ACTION | 15173.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15173.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 15176.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15180.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15184.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15196.8294 | MooredSubInstallation
| Towing Group 2 | Delay | 68 | 538333.3333 | ACTION | 15241.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 46 | 0 | ACTION | 15242.8294 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 2 | 15833.3333 | ACTION | 15243.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15246.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15249.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15253.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15277.3294 | MooredSubInstallation
| Towing Group 2 | Transit | 53.9131 | 426811.8155 | ACTION | 15297.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15327.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15349.3294 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 234.3537 | 1855299.7754 | ACTION | 15349.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 22 | 0 | ACTION | 15349.3294 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15355.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15357.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15369.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15373.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15377.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 15382.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15386.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15390.3294 | MooredSubInstallation
| Towing Group 3 | Delay | 45 | 356250 | ACTION | 15400.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 239 | 1892083.3333 | ACTION | 15400.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15402.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15405.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15409.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15412.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15436.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15508.8294 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 211.3537 | 1673216.4421 | ACTION | 15508.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15514.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15516.8294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15517.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15528.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15532.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15536.8294 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 15537.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 15538.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 15539.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 15540.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15540.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15544.8294 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15545.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15546.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15556.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15560.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15563.8294 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 15565.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 15566.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15567.3294 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 15571.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 15572.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15591.3294 | MooredSubInstallation
| Towing Group 3 | Transit | 53.9131 | 426811.8155 | ACTION | 15625.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 53.9131 | 426811.8155 | ACTION | 15625.9757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 15652.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 15654.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15660.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15663.3294 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 37.8537 | 299674.7754 | ACTION | 15663.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15669.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15671.3294 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 15680.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15683.3294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15685.3294 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 15686.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15687.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15691.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15695.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15699.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15711.3294 | MooredSubInstallation
| Towing Group 2 | Transit | 30 | 237500 | ACTION | 15716.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 40 | 0 | ACTION | 15751.3294 | MooredSubInstallation
| Towing Group 3 | Delay | 85 | 672916.6667 | ACTION | 15754.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15754.8294 | MooredSubInstallation
| Towing Group 2 | Delay | 39 | 308750 | ACTION | 15755.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15758.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15761.8294 | MooredSubInstallation
| Towing Group 2 | Transit | 23.9131 | 189311.8155 | ACTION | 15778.9757 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15785.8294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15853.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15857.8294 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 231.8537 | 1835508.1088 | ACTION | 15857.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 4.5 | 0 | ACTION | 15857.8294 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15863.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15865.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15877.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15881.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15885.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15889.8294 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 15891.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 15893.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15893.8294 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15899.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15905.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15909.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15912.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15916.3294 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 15919.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 15925.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15940.3294 | MooredSubInstallation
| Towing Group 3 | Transit | 53.9131 | 426811.8155 | ACTION | 15979.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 16001.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 16003.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 16009.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16012.3294 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 233.3537 | 1847383.1088 | ACTION | 16012.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 16018.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16020.3294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16025.8294 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 16029.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16032.3294 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 16035.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16036.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16040.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16044.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16048.3294 | MooredSubInstallation
| Towing Group 1 | Transit | 23 | 182083.3333 | ACTION | 16058.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 20 | 158333.3333 | ACTION | 16078.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 2 | 15833.3333 | ACTION | 16080.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 32 | 0 | ACTION | 16080.3294 | MooredSubInstallation
| Towing Group 1 | Delay | 1 | 7916.6667 | ACTION | 16081.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16092.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16095.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16099.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16102.8294 | MooredSubInstallation
| Towing Group 1 | Transit | 28.9131 | 228895.1488 | ACTION | 16109.9757 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16126.8294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16193.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16198.8294 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 219.3537 | 1736549.7754 | ACTION | 16198.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 5 | 0 | ACTION | 16198.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16206.8294 | MooredSubInstallation
| Towing Group 3 | Delay | 11 | 87083.3333 | ACTION | 16209.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 16215.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16218.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16222.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16226.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16230.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16234.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16246.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 16252.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16256.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16259.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16263.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16287.3294 | MooredSubInstallation
| Towing Group 2 | Delay | 280 | 2216666.6667 | ACTION | 16298.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 83 | 657083.3333 | ACTION | 16298.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16359.3294 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 249.3537 | 1974049.7754 | ACTION | 16359.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 16365.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16366.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16367.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16379.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16383.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16387.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16391.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16395.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16407.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16410.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16414.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16417.8294 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 16435.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 16436.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 16437.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 16438.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16441.8294 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 16443.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 16444.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 16463.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 16464.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 16469.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 16470.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 17 | 134583.3333 | ACTION | 16486.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 17 | 134583.3333 | ACTION | 16487.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16534.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 125 | 0 | ACTION | 16566.8294 | MooredSubInstallation
| Towing Group 2 | Delay | 114 | 902500 | ACTION | 16600.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 114 | 902500 | ACTION | 16601.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 36.9131 | 292228.4821 | ACTION | 16637.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 36.9131 | 292228.4821 | ACTION | 16637.9757 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16638.8294 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 1.3537 | 10716.4421 | ACTION | 16638.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 104 | 0 | ACTION | 16638.8294 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 16644.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16646.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16658.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16662.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16666.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16670.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16674.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16686.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16690.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16693.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16697.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16721.3294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16806.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 174 | 0 | ACTION | 16895.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16967.3294 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 329.3537 | 2607383.1088 | ACTION | 16967.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 160.5 | 0 | ACTION | 16967.3294 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 16973.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16975.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16987.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 20 | 0 | ACTION | 17007.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17011.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17015.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17019.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17023.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17035.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 17040.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17043.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17047.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17050.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17074.8294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 17135.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17146.8294 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 11.5 | 0 | ACTION | 17146.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17154.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17166.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17170.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17174.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17178.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 17192.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17196.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17208.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17212.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17215.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17219.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17243.3294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 17314.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 152 | 0 | ACTION | 17395.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17467.3294 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 152.5 | 0 | ACTION | 17467.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17475.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17487.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17491.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17495.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17499.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17503.3294 | MooredSubInstallation
| Towing Group 1 | Delay | 1142 | 9040833.3333 | ACTION | 17507.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 534 | 4227500 | ACTION | 17507.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 863 | 6832083.3333 | ACTION | 17507.8294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17515.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17518.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17522.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17525.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17549.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17621.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17629.8294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 17635.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17641.8294 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 17644.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 17644.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 17645.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17645.8294 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 17646.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 17646.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 17647.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17649.8294 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 17652.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 17652.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 17653.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17653.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17657.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17669.8294 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 17672.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 17672.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 17673.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17673.3294 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 1 | 7916.6667 | ACTION | 17673.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 1 | 7916.6667 | ACTION | 17673.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 1 | 7916.6667 | ACTION | 17674.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17676.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17680.3294 | MooredSubInstallation
| Towing Group 1 | Delay | 29 | 229583.3333 | ACTION | 17702.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 29 | 229583.3333 | ACTION | 17702.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 29 | 229583.3333 | ACTION | 17703.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17704.3294 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 5 | 39583.3333 | ACTION | 17707.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 5 | 39583.3333 | ACTION | 17707.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 5 | 39583.3333 | ACTION | 17708.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 43 | 340416.6667 | ACTION | 17750.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 43 | 340416.6667 | ACTION | 17750.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 43 | 340416.6667 | ACTION | 17751.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17776.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17784.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17796.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17800.3294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 17803.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17804.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17808.3294 | MooredSubInstallation
| Towing Group 1 | Delay | 61 | 482916.6667 | ACTION | 17811.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 61 | 482916.6667 | ACTION | 17811.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 61 | 482916.6667 | ACTION | 17812.0627 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17812.3294 | MooredSubInstallation
| Towing Group 1 | Transit | 10.9131 | 86395.1488 | ACTION | 17822.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 10.9131 | 86395.1488 | ACTION | 17822.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 10.9131 | 86395.1488 | ACTION | 17822.9757 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17824.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17827.8294 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 17828.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 17828.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 17828.9757 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17831.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17834.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17858.8294 | MooredSubInstallation
| Towing Group 1 | Delay | 35 | 277083.3333 | ACTION | 17863.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 35 | 277083.3333 | ACTION | 17863.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 35 | 277083.3333 | ACTION | 17863.9757 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17930.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17938.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17950.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17954.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17958.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17962.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17966.8294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 17971.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17978.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17982.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17985.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17989.3294 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 18000.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 18000.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 18001.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 18002.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 18002.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 18003.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 18013.3294 | MooredSubInstallation
| Towing Group 2 | Delay | 18 | 142500 | ACTION | 18021.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 19 | 150416.6667 | ACTION | 18021.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 19 | 150416.6667 | ACTION | 18021.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 18027.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 18027.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 18027.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 18047.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 18047.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 18047.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 18053.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 18053.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 18053.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 27 | 213750 | ACTION | 18080.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 27 | 213750 | ACTION | 18080.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 27 | 213750 | ACTION | 18080.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 71 | 0 | ACTION | 18084.3294 | MooredSubInstallation
| Towing Group 2 | Delay | 34 | 269166.6667 | ACTION | 18114.209 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 34 | 269166.6667 | ACTION | 18114.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 34 | 269166.6667 | ACTION | 18114.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 18139.3294 | MooredSubInstallation
| Towing Group 2 | Transit | 26.9131 | 213061.8155 | ACTION | 18141.1221 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 26.9131 | 213061.8155 | ACTION | 18141.6221 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 26.9131 | 213061.8155 | ACTION | 18141.6221 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 18147.1221 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 18147.6221 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 18156.3294 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 14.7073 | 116432.8842 | ACTION | 18156.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 17 | 0 | ACTION | 18156.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 18164.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 18176.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18180.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18184.3294 | MooredSubInstallation
| Towing Group 3 | Delay | 29 | 229583.3333 | ACTION | 18185.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18188.3294 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 18191.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18192.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 18204.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 18206.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18209.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18213.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18216.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 18240.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 18312.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 18320.8294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 18324.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 18332.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18336.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18340.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18344.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18348.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 18360.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18364.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18367.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18371.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 18395.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 18467.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 18475.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 18487.3294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 18492.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 31 | 0 | ACTION | 18518.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18522.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 18535.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18539.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 43 | 0 | ACTION | 18582.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18586.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18590.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 30 | 0 | ACTION | 18620.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 18632.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18635.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18639.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18642.8294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 18660.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 18666.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 18738.8294 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 78.5 | 0 | ACTION | 18738.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 18746.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 18758.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18762.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18766.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18770.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18774.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 18786.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18790.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18793.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18797.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 18821.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 18893.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 18901.3294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 18906.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 18913.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18917.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18921.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18925.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18929.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 18941.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18944.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18948.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18951.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 18975.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 19047.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 19055.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 19067.8294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 19074.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 19081.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19085.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19089.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19093.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19097.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 19109.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19113.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19116.8294 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19120.3294 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 19144.3294 | MooredSubInstallation
| Towing Group 3 | Delay | 1011 | 8003750 | ACTION | 19202.3294 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 1055 | 8352083.3333 | ACTION | 19202.6221 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 1056 | 8360000 | ACTION | 19203.1221 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 19216.3294 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 19242.8294 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 19339.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 19339.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 19340.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 19341.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 19341.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 19342.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 19347.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 19347.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 19348.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 19367.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 19367.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 19368.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 19373.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 19373.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 19374.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 38 | 300833.3333 | ACTION | 19412.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 39 | 308750 | ACTION | 19412.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 39 | 308750 | ACTION | 19412.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 16 | 126666.6667 | ACTION | 19428.3554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 16 | 126666.6667 | ACTION | 19428.5627 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 16 | 126666.6667 | ACTION | 19428.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 14.9131 | 118061.8155 | ACTION | 19443.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay: No Assembly Storage Available | 227.1463 | 0 | ACTION | 19443.4757 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 200.6463 | 0 | ACTION | 19443.4757 | MooredSubInstallation
| Towing Group 1 | Transit | 14.9131 | 118061.8155 | ACTION | 19443.7684 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 15.9131 | 125978.4821 | ACTION | 19444.2684 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 19449.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 19449.7684 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 19451.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 19463.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 38 | 0 | ACTION | 19501.4757 | MooredSubInstallation
| Towing Group 2 | Delay | 58 | 459166.6667 | ACTION | 19502.2684 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 53 | 419583.3333 | ACTION | 19502.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 53 | 419583.3333 | ACTION | 19502.7684 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19505.4757 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 19508.2684 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19509.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19513.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19517.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 19529.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19532.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19536.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19539.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 19563.9757 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 19611.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 19635.9757 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 24.5 | 0 | ACTION | 19635.9757 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 19639.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 19640.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 19641.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 19642.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 19643.9757 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 19645.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 19647.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 19647.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 19648.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 19653.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 19655.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19659.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19663.9757 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 19667.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19667.9757 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 19668.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19671.9757 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 19673.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 19673.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 19674.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 19679.5017 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 19683.9757 | MooredSubInstallation
0.5 | Array Cable Installation Vessel | Mobilize | 72 | 337500 | ACTION | 19686.4709 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19687.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19690.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 56250 | ACTION | 19692.4709 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19694.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 19718.4757 | MooredSubInstallation
| Towing Group 3 | Transit | 53.9131 | 426811.8155 | ACTION | 19727.6221 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 53.9131 | 426811.8155 | ACTION | 19727.9148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 53.9131 | 426811.8155 | ACTION | 19733.4148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 19733.6221 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 19733.9148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 19739.4148 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Transit | 65.6333 | 615312.2283 | ACTION | 19758.1042 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19760.1042 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19761.1042 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19766.6042 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19772.1042 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19773.1042 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 14 | 131250 | ACTION | 19787.1042 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Delay | 73 | 0 | ACTION | 19791.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 10 | 93750 | ACTION | 19797.1042 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 2.1123 | 19803.2152 | ACTION | 19799.2165 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19800.2165 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 19803.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19805.7165 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19811.2165 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19813.2165 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19814.2165 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19819.7165 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 19863.4757 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 59.5 | 0 | ACTION | 19863.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 19871.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 19883.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 19886.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19890.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 9 | 0 | ACTION | 19899.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19903.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19907.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19911.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 103 | 965625 | ACTION | 19922.7165 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 19923.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19926.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19928.2165 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19929.2165 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19930.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19933.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 12 | 112500 | ACTION | 19941.2165 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 19957.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 19971.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 50 | 468750 | ACTION | 19991.2165 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 4.1123 | 38553.2152 | ACTION | 19995.3289 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19996.3289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20001.8289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 20031.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 20043.9757 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 12.5 | 0 | ACTION | 20043.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 20051.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 20063.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 31 | 0 | ACTION | 20094.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20098.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20102.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20106.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 20118.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20122.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 20134.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 141 | 1321875 | ACTION | 20142.8289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 20145.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20148.3289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20149.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20150.3289 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20151.3289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20152.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20156.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20156.8289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20162.3289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20163.3289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20168.353 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20169.353 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20174.853 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 20180.4757 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 20211.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 85 | 0 | ACTION | 20265.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 102 | 956250 | ACTION | 20276.853 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20282.353 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20284.353 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20285.353 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20290.853 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20296.353 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20297.353 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20302.3771 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20303.3771 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20308.8771 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20314.3771 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20316.3771 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20317.3771 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20322.8771 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20328.3771 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20329.3771 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20334.4012 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20335.4012 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 20337.4757 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 125.5 | 0 | ACTION | 20337.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20340.9012 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 20345.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20346.4012 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20348.4012 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20349.4012 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20354.9012 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 20357.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20360.4012 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20361.4012 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20361.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20365.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20366.4253 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20367.4253 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 20372.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20376.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 76 | 0 | ACTION | 20452.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20456.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 98 | 918750 | ACTION | 20465.4253 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 20468.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20470.9253 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 20505.4757 | MooredSubInstallation
| Towing Group 2 | Delay | 784 | 6206666.6667 | ACTION | 20523.4148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 790 | 6254166.6667 | ACTION | 20523.6221 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 790 | 6254166.6667 | ACTION | 20523.9148 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 60 | 0 | ACTION | 20528.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 59 | 553125 | ACTION | 20529.9253 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20531.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20535.4253 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 20535.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20537.4253 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20538.4253 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20539.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20542.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20543.9253 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20549.4253 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20550.4253 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20555.4494 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20556.4494 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20561.9494 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 20566.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20567.4494 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20569.4494 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20570.4494 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20575.9494 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20581.4494 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20582.4494 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20587.4735 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20588.4735 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20593.9735 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20599.4735 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20601.4735 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20602.4735 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20607.9735 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20613.4735 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20614.4735 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20619.4977 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20620.4977 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20625.9977 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20631.4977 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20633.4977 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20634.4977 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 20638.9757 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 133.5 | 0 | ACTION | 20638.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20639.9977 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20645.4977 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20646.4977 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 20646.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20651.5218 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20652.5218 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20658.0218 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 20658.9757 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 20660.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 20660.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 20661.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 20662.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 20662.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20662.9757 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 20663.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20663.5218 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20665.5218 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20666.5218 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20666.9757 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 20668.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 20668.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 20669.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20670.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20672.0218 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20674.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20677.5218 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20678.5218 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20683.5459 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20684.5459 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 20686.9757 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 20688.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 20688.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 20689.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20690.0459 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20690.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20693.9757 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 20694.648 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 20694.8554 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 20695.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20695.5459 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20697.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20697.5459 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20698.5459 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20704.0459 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20709.5459 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20710.5459 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20715.57 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20716.57 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 20721.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20722.07 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20727.57 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20729.57 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20730.57 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20736.07 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20741.57 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20742.57 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 37500 | ACTION | 20746.57 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Towing Group 2 | Transit | 53.9131 | 426811.8155 | ACTION | 20748.5611 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 53.9131 | 426811.8155 | ACTION | 20748.7684 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 53.9131 | 426811.8155 | ACTION | 20749.0611 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 20754.5611 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 20754.7684 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 20755.0611 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 23 | 215625 | ACTION | 20769.57 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.0241 | 9601.0518 | ACTION | 20770.5941 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20771.5941 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20777.0941 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20782.5941 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20784.5941 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20785.5941 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20791.0941 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 20793.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20796.5941 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20797.5941 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 20801.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20802.6182 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20803.6182 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 20806.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20809.1182 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 20813.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20814.6182 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20816.6182 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20817.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20817.6182 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20821.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20823.1182 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20825.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20828.6182 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20829.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20829.6182 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20834.6423 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20835.6423 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20841.1423 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 20841.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20844.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20846.6423 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20848.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20848.6423 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20849.6423 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20851.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20855.1423 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20860.6423 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20861.6423 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 28125 | ACTION | 20864.6423 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Delay | 29 | 0 | ACTION | 20880.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 20904.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 44 | 412500 | ACTION | 20908.6423 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 2.0241 | 18976.0518 | ACTION | 20910.6664 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20911.6664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Delay | 206 | 1630833.3333 | ACTION | 20960.5611 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 206 | 1630833.3333 | ACTION | 20960.7684 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 206 | 1630833.3333 | ACTION | 20961.0611 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 20974.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 20976.9757 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 2 | 0 | ACTION | 20976.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 20984.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 20996.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21000.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21004.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21008.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21012.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 102 | 956250 | ACTION | 21013.6664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21019.1664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21024.6664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 21024.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21026.6664 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21027.6664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21028.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21031.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21033.1664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21035.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21038.6664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21039.6664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21044.6906 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21045.6906 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21051.1906 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21056.6906 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21058.6906 | ArrayCableInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 21059.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21059.6906 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21065.1906 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 5 | 46875 | ACTION | 21070.1906 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21075.6906 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21076.6906 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21081.7147 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21082.7147 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21088.2147 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21093.7147 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21095.7147 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21096.7147 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 21097.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 21098.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 21098.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 21099.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 21100.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 21100.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21102.2147 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 21105.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 21106.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 21106.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21107.7147 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21108.7147 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21113.7388 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21114.7388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21120.2388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21125.7388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 21125.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 21126.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 21126.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21127.7388 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21128.7388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 21131.4757 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 21131.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 21132.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 21132.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 7 | 65625 | ACTION | 21135.7388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 21139.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21141.2388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 21144.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 21151.4757 | MooredSubInstallation
| Towing Group 1 | Transit | 22 | 174166.6667 | ACTION | 21154.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 23 | 182083.3333 | ACTION | 21154.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 23 | 182083.3333 | ACTION | 21155.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 3 | 23750 | ACTION | 21157.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 21157.4757 | MooredSubInstallation
| Towing Group 2 | Delay | 3 | 23750 | ACTION | 21157.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 3 | 23750 | ACTION | 21158.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21161.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21165.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21169.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21173.4757 | MooredSubInstallation
| Towing Group 1 | Transit | 20 | 158333.3333 | ACTION | 21177.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 20 | 158333.3333 | ACTION | 21177.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 20 | 158333.3333 | ACTION | 21178.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 2 | 15833.3333 | ACTION | 21179.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 2 | 15833.3333 | ACTION | 21179.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 2 | 15833.3333 | ACTION | 21180.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 2 | 15833.3333 | ACTION | 21181.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 2 | 15833.3333 | ACTION | 21181.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 2 | 15833.3333 | ACTION | 21182.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 3 | 23750 | ACTION | 21184.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 21184.4757 | MooredSubInstallation
| Towing Group 2 | Delay | 3 | 23750 | ACTION | 21184.7944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 3 | 23750 | ACTION | 21185.0017 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 48 | 450000 | ACTION | 21189.2388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 8.9131 | 70561.8155 | ACTION | 21193.7075 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 8.9131 | 70561.8155 | ACTION | 21193.9148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 9.9131 | 78478.4821 | ACTION | 21194.2075 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21194.7388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21195.7388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 21196.4757 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 21199.7075 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 21199.9148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 21200.2075 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5 | 46875 | ACTION | 21200.7388 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Delay | 56 | 0 | ACTION | 21252.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21255.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21259.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21262.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 21286.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 107 | 0 | ACTION | 21393.9757 | MooredSubInstallation
| Towing Group 1 | Delay | 250 | 1979166.6667 | ACTION | 21450.2075 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 251 | 1987083.3333 | ACTION | 21450.7075 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 251 | 1987083.3333 | ACTION | 21450.9148 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 21465.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 268 | 2512500 | ACTION | 21468.7388 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 0.024112 | 226.0518 | ACTION | 21468.7629 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21469.7629 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 21473.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21475.2629 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21480.7629 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21482.7629 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21483.7629 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 21485.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21489.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21493.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21497.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21501.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 27 | 253125 | ACTION | 21510.7629 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 21513.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21516.2629 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21517.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21520.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21521.7629 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21522.7629 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21524.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21527.787 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21528.787 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21534.287 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21539.787 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21541.787 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21542.787 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21548.287 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 21548.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21553.787 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21554.787 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21559.8111 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21560.8111 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21566.3111 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21571.8111 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21573.8111 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21574.8111 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21580.3111 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21585.8111 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21586.8111 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 21587.4407 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 21587.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 21588.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 21589.4407 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 21589.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 21590.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21591.8352 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21592.8352 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 21595.4407 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 21595.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 21596.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21598.3352 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21603.8352 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21605.8352 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21606.8352 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21612.3352 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 21615.4407 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 21615.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 21616.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21617.8352 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21618.8352 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 21620.4757 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 21621.4407 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 21621.9407 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 21622.148 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21623.8593 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21624.8593 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 21628.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21630.3593 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21635.8593 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21637.8593 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21638.8593 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 21640.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21644.3593 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21644.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21648.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21649.8593 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21650.8593 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21652.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21655.8834 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21656.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21656.8834 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21662.3834 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21667.8834 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 21668.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21669.8834 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21670.8834 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21671.9757 | MooredSubInstallation
| Towing Group 1 | Transit | 53.9131 | 426811.8155 | ACTION | 21675.3538 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21675.4757 | MooredSubInstallation
| Towing Group 2 | Transit | 53.9131 | 426811.8155 | ACTION | 21675.8538 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 53.9131 | 426811.8155 | ACTION | 21676.0611 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21676.3834 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21678.9757 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 21681.3538 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 21681.8538 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21681.8834 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 21682.0611 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21682.8834 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21687.9076 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21688.9076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21694.4076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21699.9076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21701.9076 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21702.9076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 21702.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21708.4076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21713.9076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21714.9076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21719.9317 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21720.9317 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21726.4317 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21731.9317 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21733.9317 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21734.9317 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21740.4317 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 9 | 84375 | ACTION | 21749.4317 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Delay | 70 | 554166.6667 | ACTION | 21751.3538 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 70 | 554166.6667 | ACTION | 21751.8538 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 70 | 554166.6667 | ACTION | 21752.0611 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21754.9317 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21755.9317 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21760.9558 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21761.9558 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21767.4558 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21772.9558 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21774.9558 | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 21774.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21775.9558 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21781.4558 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 21782.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 21794.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21798.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21802.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21806.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21810.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 31 | 290625 | ACTION | 21812.4558 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21817.9558 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21818.9558 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 21822.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21823.9799 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21824.9799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21826.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21829.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21830.4799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21833.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21835.9799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21837.9799 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21838.9799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21844.4799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21849.9799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21850.9799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21856.004 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21857.004 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 21857.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21862.504 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21868.004 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21870.004 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21871.004 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21876.504 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21882.004 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21883.004 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21888.0281 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 21888.5871 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21889.0281 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 21889.0871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 21889.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 21890.5871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 21891.0871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 21891.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21894.5281 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 21896.5871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 21897.0871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 21897.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21900.0281 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21902.0281 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21903.0281 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21908.5281 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21914.0281 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21915.0281 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 21916.5871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 21917.0871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 21917.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21920.0522 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21921.0522 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 21922.5871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 21923.0871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 21923.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21926.5522 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 21929.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21932.0522 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 21937.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 21949.4757 | MooredSubInstallation
| Towing Group 3 | Transit | 27 | 213750 | ACTION | 21950.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 28 | 221666.6667 | ACTION | 21950.5871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 28 | 221666.6667 | ACTION | 21951.0871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 7 | 55416.6667 | ACTION | 21957.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 7 | 55416.6667 | ACTION | 21957.5871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 7 | 55416.6667 | ACTION | 21958.0871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 1 | 7916.6667 | ACTION | 21958.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 1 | 7916.6667 | ACTION | 21958.5871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 1 | 7916.6667 | ACTION | 21959.0871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 10 | 79166.6667 | ACTION | 21968.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 10 | 79166.6667 | ACTION | 21968.5871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 10 | 79166.6667 | ACTION | 21969.0871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 1 | 7916.6667 | ACTION | 21969.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 1 | 7916.6667 | ACTION | 21969.5871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 1 | 7916.6667 | ACTION | 21970.0871 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 103 | 0 | ACTION | 22052.4757 | MooredSubInstallation
| Towing Group 3 | Delay | 85 | 672916.6667 | ACTION | 22054.2944 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 85 | 672916.6667 | ACTION | 22054.5871 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 85 | 672916.6667 | ACTION | 22055.0871 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 22056.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 22060.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 22064.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 22068.4757 | MooredSubInstallation
| Towing Group 1 | Transit | 23.9131 | 189311.8155 | ACTION | 22078.5001 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 23.9131 | 189311.8155 | ACTION | 22079.0001 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 24.9131 | 197228.4821 | ACTION | 22079.2075 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 22080.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 22083.9757 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 22084.5001 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 22085.0001 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 22085.2075 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 22087.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 22090.9757 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 159 | 1490625 | ACTION | 22091.0522 | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22093.0522 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22094.0522 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22099.5522 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22105.0522 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22106.0522 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22111.0763 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22112.0763 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 22114.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 22186.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 22194.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 22206.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 22210.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 22214.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 22218.9757 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 22221.7334 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 22222.2334 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 22222.4407 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 22222.9757 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 22223.7334 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 22224.2334 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 22224.4407 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 22229.7334 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 22230.2334 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 22230.4407 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 22234.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 22238.4757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 22241.9757 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 22245.4757 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 22249.7334 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 22250.2334 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 22250.4407 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 22255.7334 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 22256.2334 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 22256.4407 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 145 | 1359375 | ACTION | 22257.0763 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22262.5763 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22268.0763 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 22269.4757 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22270.0763 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22271.0763 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22276.5763 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22282.0763 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22283.0763 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22288.1005 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22289.1005 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22294.6005 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22300.1005 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22302.1005 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22303.1005 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22308.6005 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 53.9131 | 426811.8155 | ACTION | 22309.6465 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 53.9131 | 426811.8155 | ACTION | 22310.1465 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 53.9131 | 426811.8155 | ACTION | 22310.3538 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22314.1005 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22315.1005 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 22315.6465 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 37500 | ACTION | 22319.1005 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 22341.4757 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 31.3292 | 248023.2035 | ACTION | 22341.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 47 | 372083.3333 | ACTION | 22388.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 22394.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 95 | 890625 | ACTION | 22414.1005 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.0241 | 9601.0518 | ACTION | 22415.1246 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22416.1246 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22421.6246 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22427.1246 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22429.1246 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22430.1246 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22435.6246 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22441.1246 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22442.1246 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22447.1487 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22448.1487 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22453.6487 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22459.1487 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22461.1487 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22462.1487 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22467.6487 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22473.1487 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22474.1487 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22479.1728 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22480.1728 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22485.6728 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22491.1728 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Delay | 174 | 1377500 | ACTION | 22568.4757 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 253 | 2002916.6667 | ACTION | 22568.6465 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 93 | 871875 | ACTION | 22584.1728 | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22586.1728 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22587.1728 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22592.6728 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22598.1728 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22599.1728 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22604.1969 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22605.1969 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22610.6969 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22616.1969 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22618.1969 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22619.1969 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22624.6969 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22630.1969 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22631.1969 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22636.221 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22637.221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22642.721 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22648.221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22650.221 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22651.221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22656.721 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22662.221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22663.221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22668.2451 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22669.2451 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22674.7451 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22680.2451 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22682.2451 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22683.2451 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22688.7451 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 8 | 75000 | ACTION | 22696.7451 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22702.2451 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22703.2451 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 22705.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 1086430.0758 | ACTION | 22705.8798 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 22707.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 22707.8798 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22708.2692 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22709.2692 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 22713.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 22713.8798 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22714.7692 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22720.2692 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22722.2692 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22723.2692 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22728.7692 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 22733.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 22733.8798 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22734.2692 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22735.2692 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 22739.709 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 22739.8798 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22740.2934 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22741.2934 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22746.7934 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22752.2934 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22754.2934 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22755.2934 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22760.7934 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22766.2934 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22767.2934 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22772.3175 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22773.3175 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22778.8175 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22784.3175 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22786.3175 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22787.3175 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22792.8175 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 53.9131 | 426811.8155 | ACTION | 22793.6221 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 53.9131 | 426811.8155 | ACTION | 22793.7928 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22798.3175 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22799.3175 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22804.3416 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22805.3416 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22810.8416 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22816.3416 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22818.3416 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22819.3416 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22824.8416 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22830.3416 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22831.3416 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22836.3657 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22837.3657 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22842.8657 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22848.3657 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22850.3657 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22851.3657 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22856.8657 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22862.3657 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22863.3657 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22868.3898 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22869.3898 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22874.8898 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22880.3898 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22882.3898 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22883.3898 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22888.8898 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22894.3898 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22895.3898 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22900.4139 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22901.4139 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22906.9139 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22912.4139 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22914.4139 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22915.4139 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22920.9139 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22926.4139 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22927.4139 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22932.438 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22933.438 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22938.938 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22944.438 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22946.438 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22947.438 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22952.938 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22958.438 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22959.438 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22964.4621 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22965.4621 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22970.9621 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22976.4621 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22978.4621 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22979.4621 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22984.9621 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22990.4621 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22991.4621 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22996.4863 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22997.4863 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23002.9863 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23008.4863 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23010.4863 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23011.4863 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23016.9863 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23022.4863 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23023.4863 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 23028.5104 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23029.5104 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23035.0104 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23040.5104 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23042.5104 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23043.5104 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 86 | 806250 | ACTION | 23129.5104 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23135.0104 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23140.5104 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23141.5104 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 23146.5345 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23147.5345 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23153.0345 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23158.5345 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23160.5345 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23161.5345 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23167.0345 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23172.5345 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23173.5345 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 23178.5586 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23179.5586 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23185.0586 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23190.5586 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23192.5586 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23193.5586 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23199.0586 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23204.5586 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23205.5586 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 23210.5827 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23211.5827 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23217.0827 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23222.5827 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23224.5827 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23225.5827 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23231.0827 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23236.5827 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23237.5827 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 23242.6068 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23243.6068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23249.1068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23254.6068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23256.6068 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23257.6068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23263.1068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23268.6068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23269.6068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 23274.6309 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23275.6309 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23281.1309 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23286.6309 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23288.6309 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23289.6309 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23295.1309 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23300.6309 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23301.6309 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 23306.655 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23307.655 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23313.155 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23318.655 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23320.655 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23321.655 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23327.155 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23332.655 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23333.655 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 23338.6792 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23339.6792 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23345.1792 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23350.6792 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23352.6792 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23353.6792 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23359.1792 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23364.6792 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23365.6792 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 23370.7033 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23371.7033 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23377.2033 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23382.7033 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23384.7033 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23385.7033 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23391.2033 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23396.7033 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23397.7033 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 23402.7274 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23403.7274 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23409.2274 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23414.7274 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23416.7274 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23417.7274 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23423.2274 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23428.7274 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23429.7274 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 23434.7515 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23435.7515 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23441.2515 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23446.7515 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23448.7515 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23449.7515 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23455.2515 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23460.7515 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23461.7515 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 12.133 | 113746.4839 | ACTION | 23473.8844 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23474.8844 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23480.3844 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23485.8844 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23487.8844 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23488.8844 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23494.3844 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23499.8844 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23500.8844 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 12.133 | 113746.4839 | ACTION | 23513.0174 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23514.0174 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 39 | 365625 | ACTION | 23553.0174 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23558.5174 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 51 | 478125 | ACTION | 23609.5174 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23615.0174 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23617.0174 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23618.0174 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23623.5174 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23629.0174 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23630.0174 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8.3958 | 78710.3425 | ACTION | 23638.4132 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23639.4132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23644.9132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23650.4132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23652.4132 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23653.4132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23658.9132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23664.4132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23665.4132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8.3958 | 78710.3425 | ACTION | 23673.8089 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23674.8089 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23680.3089 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23685.8089 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23687.8089 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23688.8089 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23694.3089 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23699.8089 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23700.8089 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.5199 | 51748.6401 | ACTION | 23706.3288 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23707.3288 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23712.8288 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23718.3288 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23720.3288 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23721.3288 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23726.8288 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23732.3288 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23733.3288 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.5199 | 51748.6401 | ACTION | 23738.8487 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23739.8487 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23745.3487 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23750.8487 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 65.6333 | 615312.2283 | ACTION | 23816.482 | ArrayCableInstallation | ArrayCableInstallation | FALSE