## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | include_onshore_construction | max_waveheight | max_windspeed | transit_speed | num_vessels | num_ahts_vessels
0.5 | Export Cable Installation Vessel | Mobilize | 72 | 450000 | ACTION | 0 | ExportCableInstallation
1 | Mooring System Installation Vessel | Mobilize | 168 | 700000 | ACTION | 0 | MooringSystemInstallation
| Export Cable Installation Vessel | Load Cable | 6 | 75000 | ACTION | 6 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Delay | 77 | 320833.3333 | ACTION | 77 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 82 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 87 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 85 | 1062500 | ACTION | 91 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Tow Plow | 0.4 | 5000 | ACTION | 91.4 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Pull Winch | 0.4 | 5000 | ACTION | 91.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 92 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Prepare Cable | 1 | 12500 | ACTION | 92.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 97 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5 | 20833.3333 | ACTION | 102 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 116 | 483333.3333 | ACTION | 218 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 0.0051 | 21.25 | ACTION | 218.0051 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 220.0051 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 224.0051 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 89 | 370833.3333 | ACTION | 313.0051 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 327.9786 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 330.9521 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 332.9521 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 336.9521 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 351.9256 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 354.8991 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 356.8991 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 360.8991 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 375.8726 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 378.8461 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 380.8461 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 384.8461 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 18 | 75000 | ACTION | 402.8461 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 417.8196 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 420.7931 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 328 | 4100000 | ACTION | 420.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 422.7931 | MooringSystemInstallation
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 426.3 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 426.7931 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 431.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Lower Cable | 1 | 12500 | ACTION | 432.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 6 | 75000 | ACTION | 438.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 441.7666 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 444.7401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 457.7401 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 459.7401 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 463.7401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 82 | 341666.6667 | ACTION | 545.7401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 560.7136 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 563.6871 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 565.6871 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 569.6871 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 82 | 341666.6667 | ACTION | 651.6871 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 666.6606 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 669.6341 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 232 | 2900000 | ACTION | 670.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 671.6341 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 675.6341 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 690.6076 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 693.5811 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 695.5811 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 699.5811 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 714.5546 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 717.5281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 719.5281 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 723.5281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 64 | 800000 | ACTION | 734.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 738.5016 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 741.4751 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 743.4751 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 747.4751 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 12 | 50000 | ACTION | 759.4751 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 774.4486 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 777.4221 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 779.4221 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 783.4221 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 796.4221 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 811.3956 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 814.3691 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 819.3742 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 824.3742 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 829.3742 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 96 | 1200000 | ACTION | 830.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 834.3742 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 839.3742 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 11 | 137500 | ACTION | 841.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 844.3793 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 846.3793 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 850.3793 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substation Assembly Line 1 | Substation Substructure Assembly | 336 | 0 | ACTION | 903.1903 | FloatingSubstationInstallation
| Substation Assembly Line 1 | Attach Topside | 24 | 0 | ACTION | 927.1903 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay: Waiting on Substation Assembly | 360 | 1500000 | ACTION | 927.1903 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay | 16 | 66666.6667 | ACTION | 943.1903 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 93 | 387500 | ACTION | 943.3793 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Tow Substation to Site | 8.3418 | 34757.6389 | ACTION | 951.5321 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 953.5321 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 113 | 1412500 | ACTION | 954.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 958.3528 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 959.5321 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 961.3263 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 8 | 100000 | ACTION | 962.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 963.3263 | MooringSystemInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 963.5321 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 967.3263 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 58 | 241666.6667 | ACTION | 1021.5321 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 55 | 229166.6667 | ACTION | 1022.3263 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 13.9735 | 58222.9167 | ACTION | 1035.5056 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1037.2998 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1038.4791 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1040.2733 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 2 | 8333.3333 | ACTION | 1040.4791 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1042.2733 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 35 | 145833.3333 | ACTION | 1077.2733 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1081.2733 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 48 | 200000 | ACTION | 1088.4791 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 7 | 29166.6667 | ACTION | 1095.4791 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1096.2468 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1099.2203 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1101.2203 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 26 | 108333.3333 | ACTION | 1127.2203 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1131.2203 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 10 | 41666.6667 | ACTION | 1141.2203 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1156.1938 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1159.1673 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 64 | 266666.6667 | ACTION | 1159.4791 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1161.1673 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1165.1673 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 9 | 37500 | ACTION | 1168.4791 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 52 | 216666.6667 | ACTION | 1217.1673 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1232.1408 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 65 | 270833.3333 | ACTION | 1233.4791 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1235.1143 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 3 | 12500 | ACTION | 1236.4791 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1237.1143 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 1 | 4166.6667 | ACTION | 1237.4791 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 1 | 4166.6667 | ACTION | 1238.4791 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 2 | 8333.3333 | ACTION | 1240.4791 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1241.1143 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 1244.4791 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 10 | 41666.6667 | ACTION | 1254.4791 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1256.0878 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1258.4791 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1259.0613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1261.0613 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1265.0613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 13.9735 | 58222.9167 | ACTION | 1272.4526 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1275.4261 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 32 | 133333.3333 | ACTION | 1297.0613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 30 | 125000 | ACTION | 1305.4261 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1312.0348 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1315.0083 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1317.0083 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1321.0083 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1327.4261 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1335.9818 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1338.9553 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1339.4261 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1340.9553 | MooringSystemInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1343.4261 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1344.9553 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 13.9735 | 58222.9167 | ACTION | 1357.3996 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1359.9288 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1360.3731 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1362.9023 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1364.9023 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 12 | 50000 | ACTION | 1376.9023 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1380.9023 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1395.8758 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1398.8493 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1400.8493 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 42 | 175000 | ACTION | 1402.3731 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1404.8493 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 4 | 16666.6667 | ACTION | 1406.3731 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1419.8228 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1422.7963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1424.7963 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1428.7963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 24 | 100000 | ACTION | 1430.3731 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1443.7698 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1446.7433 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 18 | 75000 | ACTION | 1448.3731 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 1451.7484 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1456.7484 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1460.3731 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1461.7484 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 1465.3782 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1466.7484 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1471.7484 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 1476.7535 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 514 | 6425000 | ACTION | 1476.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1478.7535 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1482.7535 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1497.727 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1500.7005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1502.7005 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1506.7005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1521.674 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1524.6475 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1526.6475 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1530.6475 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 64 | 800000 | ACTION | 1540.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1545.621 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1548.5945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1550.5945 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1554.5945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 20 | 250000 | ACTION | 1560.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 3 | 37500 | ACTION | 1563.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Delay | 2 | 25000 | ACTION | 1565.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1569.568 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1572.5415 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1574.5415 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 12 | 150000 | ACTION | 1577.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1578.5415 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1593.515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1596.4885 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1598.4885 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1602.4885 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 28 | 350000 | ACTION | 1605.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1617.462 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1620.4355 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 15 | 187500 | ACTION | 1620.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1622.4355 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 128 | 533333.3333 | ACTION | 1750.4355 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1754.4355 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1769.409 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1772.3825 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1774.3825 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 46 | 191666.6667 | ACTION | 1820.3825 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1824.3825 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 214 | 2675000 | ACTION | 1834.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1839.356 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1842.3295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1844.3295 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1848.3295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1863.303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1866.2765 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1868.2765 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1872.2765 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1887.25 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1890.2235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1892.2235 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1896.2235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1911.197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1914.1705 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 81 | 1012500 | ACTION | 1915.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1916.1705 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1920.1705 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 15 | 187500 | ACTION | 1930.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1935.144 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1938.1175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 9 | 112500 | ACTION | 1939.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 1943.1226 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1948.1226 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1953.1226 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 15 | 187500 | ACTION | 1954.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1958.1226 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1963.1226 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 1968.1277 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1970.1277 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1974.1277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 1989.1012 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 1992.0747 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1994.0747 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1998.0747 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2013.0482 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2016.0217 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2018.0217 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2022.0217 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2036.9952 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2039.9687 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2041.9687 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 91 | 1137500 | ACTION | 2045.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2045.9687 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2060.9422 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2063.9157 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2065.9157 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2069.9157 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2084.8892 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2087.8627 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2089.8627 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2093.8627 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2108.8362 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2111.8097 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2113.8097 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2117.8097 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2132.7832 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2135.7567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2137.7567 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2141.7567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2156.7302 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2159.7037 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2161.7037 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2165.7037 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 124 | 1550000 | ACTION | 2169.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2180.6772 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2183.6507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 14 | 175000 | ACTION | 2183.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2185.6507 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2189.6507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 16 | 200000 | ACTION | 2199.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 3 | 37500 | ACTION | 2202.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2204.6242 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2207.5977 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2209.5977 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2213.5977 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 21 | 262500 | ACTION | 2223.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2228.5712 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2231.5447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 8 | 100000 | ACTION | 2231.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2233.5447 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2237.5447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 6 | 75000 | ACTION | 2237.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 13.6089 | 170111.807 | ACTION | 2251.4089 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2252.5182 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Position Onsite | 2 | 25000 | ACTION | 2253.4089 | ExportCableInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2255.4917 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 2258.9089 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 2260.4968 | MooringSystemInstallation
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 2264.4089 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2265.4968 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Transit | 4.3523 | 54403.2609 | ACTION | 2268.7612 | ExportCableInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2270.4968 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2275.4968 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2280.4968 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 2285.5019 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2287.5019 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2291.5019 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2306.4754 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2309.4489 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2311.4489 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2315.4489 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2330.4224 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2333.3959 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2335.3959 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2339.3959 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2354.3694 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2357.3429 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2359.3429 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2363.3429 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2378.3164 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2381.2899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2383.2899 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2387.2899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2402.2634 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2405.2369 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2407.2369 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2411.2369 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2426.2104 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2429.1839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2431.1839 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2435.1839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2450.1574 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2453.1309 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2455.1309 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2459.1309 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2474.1044 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2477.0779 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2479.0779 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2483.0779 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 54 | 225000 | ACTION | 2537.0779 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2552.0514 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2555.0249 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2557.0249 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 2564.0249 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2568.0249 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2582.9984 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2585.9719 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2587.9719 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2591.9719 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2606.9454 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2609.9189 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2611.9189 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2615.9189 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2630.8924 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2633.8659 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 2638.871 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2643.871 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2648.871 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2653.871 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2658.871 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 2663.8761 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2665.8761 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2669.8761 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2684.8496 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2687.8231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2689.8231 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2693.8231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2708.7966 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2711.7701 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2713.7701 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2717.7701 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 6 | 25000 | ACTION | 2723.7701 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 2725.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 2725.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 2733.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2738.7436 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2741.7171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2743.7171 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 2745.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2747.7171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 2749.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 2753.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 2757.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2762.6906 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 2764.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2765.6641 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2767.6641 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 2768.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2771.6641 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 2780.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2783.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2786.6376 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2787.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2789.6111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2790.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2791.6111 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2795.6111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2810.5846 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2813.5581 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 2814.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2815.5581 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2819.5581 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2834.5316 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2837.5051 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2839.5051 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2843.5051 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2858.4786 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2861.4521 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2863.4521 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2867.4521 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2882.4256 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2885.3991 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 2886.9061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 329.5 | 2333958.3333 | ACTION | 2886.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2887.3991 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2891.3991 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 2892.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 2893.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 6.5 | 0 | ACTION | 2893.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 2901.4061 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 2902.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 2904.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2906.3726 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2909.3461 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 2910.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2911.3461 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 2913.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2915.3461 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 2917.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 2921.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 2925.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 2929.4061 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 2930.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2930.3196 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2933.2931 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2935.2931 | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 2936.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2939.2931 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 2939.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 2941.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2944.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2948.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 2954.2666 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 2957.2401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 10 | 0 | ACTION | 2958.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 2961.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 2962.2452 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2967.2452 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2972.2452 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2977.2452 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2982.2452 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 2985.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 2987.2503 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2989.2503 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2993.2503 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3008.2238 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3011.1973 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3013.1973 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3017.1973 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3032.1708 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3035.1443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3037.1443 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3041.1443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3056.1178 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 3057.9061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 500.5 | 3545208.3333 | ACTION | 3057.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3059.0913 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3061.0913 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3061.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 3.5 | 0 | ACTION | 3061.4061 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 3063.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3065.0913 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3069.4061 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 3073.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 3075.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3080.0648 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 3081.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3081.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3083.0383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3085.0383 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3085.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3089.0383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3089.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3093.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3097.4061 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 3101.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3104.0118 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3106.9853 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 3107.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3108.9853 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 3109.4061 | MooredSubInstallation
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 3110.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3112.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3112.9853 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3116.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3127.9588 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3130.9323 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 3131.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3132.9323 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3134.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3136.9323 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3151.9058 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3154.8793 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3156.8793 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3158.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3160.8793 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3175.8528 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3178.8263 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3180.8263 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3184.8263 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3199.7998 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3202.7733 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3204.7733 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3208.7733 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3223.7468 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3226.7203 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3228.7203 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3229.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 3230.9061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 673.5 | 4770625 | ACTION | 3230.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3232.7203 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 3236.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3238.9061 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 3246.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3247.6938 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 3248.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3250.6673 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3250.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3252.6673 | MooringSystemInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 3254.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3254.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3256.6673 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3258.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3262.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3266.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3271.6408 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 3274.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3274.6143 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 3278.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 3279.6194 | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 3280.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3282.4061 | MooredSubInstallation
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 3283.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3284.6194 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3285.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3289.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3289.6194 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3294.6194 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3299.6194 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 3304.6245 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3306.6245 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3310.6245 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3313.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3325.598 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3328.5715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3330.5715 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3334.5715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3349.545 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3352.5185 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3354.5185 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3358.5185 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3373.492 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3376.4655 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3378.4655 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3382.4655 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 3385.4061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 445.8247 | 3157925.2895 | ACTION | 3385.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 3391.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3397.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 12 | 0 | ACTION | 3397.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3397.439 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3400.4125 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 3400.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3402.4125 | MooringSystemInstallation
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 3402.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3405.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3406.4125 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 3408.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3417.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3421.386 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3421.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3424.3595 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3425.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3426.3595 | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 3428.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3429.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3430.3595 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3433.4061 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 3434.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 3438.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3445.333 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 3445.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3448.3065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3448.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3450.3065 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3452.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3454.3065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3455.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3469.28 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3472.2535 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3474.2535 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3478.2535 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3479.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3493.227 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3496.2005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3498.2005 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3502.2005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3517.174 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3520.1475 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3522.1475 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3526.1475 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3541.121 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3544.0945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3546.0945 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3550.0945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 76 | 0 | ACTION | 3555.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3565.068 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3565.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3568.0415 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3570.0415 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3574.0415 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3589.015 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3591.9885 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 3 | 12500 | ACTION | 3594.9885 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 3607.9885 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2.0051 | 8354.5833 | ACTION | 3609.9936 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3614.9936 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3619.9936 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3624.9936 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 3627.9061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 517.3247 | 3664383.6228 | ACTION | 3627.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 5 | 35416.6667 | ACTION | 3632.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 9 | 37500 | ACTION | 3633.9936 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3635.9061 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 3638.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3638.9936 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 3643.9987 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3645.9987 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3647.9061 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 3648.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3649.9987 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 3650.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3651.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3655.9061 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 3656.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3659.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3663.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3664.9722 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3667.9457 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3669.9457 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3673.9457 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 3675.9061 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 3676.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3679.4061 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 3682.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3682.9061 | MooredSubInstallation
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 3685.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3686.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3688.9192 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3691.8927 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3693.8927 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3697.8927 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3710.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3712.8662 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3715.8397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3717.8397 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3721.8397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3733.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3736.8132 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3739.7867 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3741.7867 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3745.7867 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3760.7602 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3763.7337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3765.7337 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3769.7337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 3782.4061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 498.8247 | 3533341.9562 | ACTION | 3782.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3784.7072 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3787.6807 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 3788.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3789.6807 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3790.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3793.6807 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 3797.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 3799.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3802.4061 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 3805.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3806.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3808.6542 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3810.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3811.6277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3813.6277 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3814.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3817.6277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3818.4061 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 3825.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 3830.4061 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 3831.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3832.6012 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3833.9061 | MooredSubInstallation
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 3835.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3835.5747 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3837.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3837.5747 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3840.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3841.5747 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3856.5482 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3859.5217 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3861.5217 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3864.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3865.5217 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3880.4952 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3883.4687 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3885.4687 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3889.4687 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3901.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3904.4422 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3907.4157 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3909.4157 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3913.4157 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3928.3892 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3931.3627 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 3936.3678 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 3936.9061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 498.8247 | 3533341.9562 | ACTION | 3936.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3941.3678 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 3942.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3944.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3946.3678 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3951.3678 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 3952.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 3954.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3956.3678 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3956.9061 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 3960.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3960.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 3961.3729 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3963.3729 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3964.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3967.3729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3968.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3972.9061 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 3980.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 3982.3464 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 3984.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 3985.3199 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 3986.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3987.3199 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3988.4061 | MooredSubInstallation
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 3989.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3991.3199 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3991.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3995.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4006.2934 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4009.2669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4011.2669 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4015.2669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4019.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4030.2404 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4033.2139 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4035.2139 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4039.2139 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4054.1874 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4057.1609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4059.1609 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4063.1609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4069.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4078.1344 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4081.1079 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4083.1079 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4087.1079 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4091.4061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 405.8247 | 2874591.9562 | ACTION | 4091.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 4097.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4099.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4102.0814 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4105.0549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 4106.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4107.0549 | MooringSystemInstallation
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 4108.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4111.0549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4111.4061 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 4114.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4115.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4119.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4123.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4126.0284 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4127.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4129.0019 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4131.0019 | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 4134.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4135.0019 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4139.4061 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 4140.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4142.9061 | MooredSubInstallation
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 4144.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4146.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4149.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4149.9754 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4152.9489 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4154.9489 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4158.9489 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4173.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4173.9224 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4176.8959 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4178.8959 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4182.8959 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4197.8694 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4200.8429 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4202.8429 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4206.8429 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4221.8164 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4224.7899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4226.7899 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4230.7899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4237.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4245.7634 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4245.9061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 410.8247 | 2910008.6228 | ACTION | 4245.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4248.7369 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 4251.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 4253.742 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4253.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4258.742 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 4261.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 4263.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4263.742 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4265.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4268.742 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 4269.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4269.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4273.742 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4273.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4277.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 4278.7471 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4280.7471 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4281.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4284.7471 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 4289.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4299.7206 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 20 | 0 | ACTION | 4301.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4302.6941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4304.6941 | MooringSystemInstallation
| Towing Group 3 | Delay | 16 | 113333.3333 | ACTION | 4305.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4308.6941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 4311.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4313.9061 | MooredSubInstallation
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 4314.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4317.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4320.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4323.6676 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4324.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4326.6411 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4328.6411 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4332.6411 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4347.6146 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4348.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4350.5881 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4352.5881 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4356.5881 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4371.5616 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4374.5351 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4376.5351 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4380.5351 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4395.5086 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4398.4821 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4400.4821 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4404.4821 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4405.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4419.4556 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4420.4061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 430.8247 | 3051675.2895 | ACTION | 4420.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4422.4291 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4424.4291 | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 4426.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4428.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4428.4291 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 4435.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 4437.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4440.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4443.4026 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 4443.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4444.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4446.3761 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4448.3761 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4448.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4452.3761 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4452.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4456.4061 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 4463.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4467.3496 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4468.4061 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 4469.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4470.3231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4471.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4472.3231 | MooringSystemInstallation
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 4473.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4475.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4476.3231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4478.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4491.2966 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4494.2701 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4496.2701 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4500.2701 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4502.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4515.2436 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4518.2171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4520.2171 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4524.2171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4539.1906 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4542.1641 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4544.1641 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4548.1641 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4563.1376 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4566.1111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 4571.1162 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4573.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4574.9061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 430.8247 | 3051675.2895 | ACTION | 4574.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4576.1162 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 4580.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4581.1162 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4582.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4586.1162 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 4590.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4591.1162 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 4592.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4594.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 4596.1213 | MooringSystemInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 4598.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4598.1213 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4598.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4602.1213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4602.9061 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 35416.6667 | ACTION | 4603.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 7 | 49583.3333 | ACTION | 4610.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 4612.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 4615.9061 | MooredSubInstallation
| Towing Group 2 | Delay | 4 | 28333.3333 | ACTION | 4616.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4617.0948 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4619.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4620.0683 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4622.0683 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4623.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4626.0683 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 92083.3333 | ACTION | 4629.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 4635.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4635.9061 | MooredSubInstallation
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 4638.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4639.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4641.0418 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4642.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4644.0153 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4646.0153 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4646.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4650.0153 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4664.9888 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4667.9623 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4669.9623 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4670.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4673.9623 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4688.9358 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4691.9093 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4693.9093 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4697.9093 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4712.8828 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4715.8563 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4717.8563 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4721.8563 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4736.8298 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4739.8033 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4741.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4741.8033 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4742.4061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 427.8247 | 3030425.2895 | ACTION | 4742.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4745.8033 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 4748.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4750.4061 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 4757.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 4759.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4760.7768 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4762.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4763.7503 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 4765.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4765.7503 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4766.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4769.7503 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4770.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4774.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4778.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4784.7238 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 4785.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4787.6973 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4789.6973 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4790.4061 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 4791.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4793.6973 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4793.9061 | MooredSubInstallation
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 4795.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4797.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4808.6708 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4811.6443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4813.6443 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4817.6443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4832.6178 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4835.5913 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4837.5913 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4841.5913 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 54 | 0 | ACTION | 4851.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4854.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4856.5648 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4859.5383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4861.5383 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4865.5383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4878.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4880.5118 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4883.4853 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 4888.4904 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4893.4904 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4898.4904 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4903.4904 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4908.4904 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4909.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 4913.4955 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4915.4955 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4919.4955 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4934.469 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4937.4425 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4939.4425 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4943.4425 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4950.9061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 477.8247 | 3384591.9562 | ACTION | 4950.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 4956.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4958.416 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4958.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4961.3895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4963.3895 | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 4966.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4967.3895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 4968.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4970.9061 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 4974.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4974.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4978.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 4982.363 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4982.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 4985.3365 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4986.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4987.3365 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4991.3365 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 4994.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 1 | 7083.3333 | ACTION | 4995.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 4998.9061 | MooredSubInstallation
| Towing Group 1 | Delay | 4 | 28333.3333 | ACTION | 4999.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 5 | 35416.6667 | ACTION | 5004.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5006.31 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 5007.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5009.2835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5010.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5011.2835 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5015.2835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5030.257 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5033.2305 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5035.2305 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5039.2305 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5054.204 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5057.1775 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5059.1775 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5063.1775 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5077.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5078.151 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5081.1245 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5083.1245 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5087.1245 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5102.098 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5105.0715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5107.0715 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5111.0715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5126.045 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5129.0185 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5131.0185 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5135.0185 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 138 | 0 | ACTION | 5148.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5149.992 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5152.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5152.9655 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5154.9655 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5155.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5158.9655 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5159.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5173.939 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5176.9125 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5178.9125 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5182.9125 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5183.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5197.886 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5200.8595 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 5205.8646 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5210.8646 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5215.8646 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5220.8646 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5225.8646 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 5230.8697 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5232.8697 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5236.8697 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5245.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5251.8432 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5254.8167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5255.4061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 616.8247 | 4369175.2895 | ACTION | 5255.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5256.8167 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5260.8167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 5261.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5263.4061 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 5270.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 5272.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5275.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5275.7902 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 5278.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5278.7637 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5279.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5280.7637 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5283.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5284.7637 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5287.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5291.4061 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 5298.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 1 | 7083.3333 | ACTION | 5299.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5299.7372 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 1 | 7083.3333 | ACTION | 5300.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 1 | 7083.3333 | ACTION | 5301.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5302.7107 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5304.7107 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5308.7107 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 16 | 113333.3333 | ACTION | 5317.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 4 | 28333.3333 | ACTION | 5321.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5323.6842 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5326.6577 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5328.6577 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5332.6577 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 14 | 99166.6667 | ACTION | 5335.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 5339.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5347.6312 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5350.6047 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5352.6047 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5356.6047 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5371.5782 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5374.5517 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5376.5517 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5380.5517 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 93 | 0 | ACTION | 5384.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5395.5252 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5396.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5398.4987 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5400.4987 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5404.4987 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5413.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5419.4722 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5422.4457 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5424.4457 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5428.4457 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 34 | 0 | ACTION | 5430.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5433.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5437.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5440.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5443.4192 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5446.3927 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5448.3927 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5452.3927 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5464.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5467.3662 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5470.3397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5472.3397 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5476.3397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5491.3132 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5494.2867 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5496.2867 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5500.2867 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5515.2602 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5518.2337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 5523.2388 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5528.2388 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5533.2388 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5536.9061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 741.8247 | 5254591.9562 | ACTION | 5536.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5538.2388 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 5542.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5543.2388 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5544.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 5548.2439 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5550.2439 | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 5552.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 5554.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5554.2439 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5556.9061 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 5560.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5560.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5564.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5568.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5569.2174 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5572.1909 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5572.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5574.1909 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5578.1909 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 5580.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5581.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5584.9061 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 5586.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5588.4061 | MooredSubInstallation
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 5589.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5593.1644 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5596.1379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5598.1379 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 5601.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5602.1379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5604.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5608.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5617.1114 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5620.0849 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5622.0849 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5626.0849 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5632.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5641.0584 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5644.0319 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5646.0319 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5650.0319 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5665.0054 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5667.9789 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5669.9789 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5673.9789 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5688.9524 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5691.9259 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5693.9259 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5697.9259 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5704.4061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 696.8247 | 4935841.9562 | ACTION | 5704.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 5710.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5712.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5712.8994 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5715.8729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5717.8729 | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 5719.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 5721.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5721.8729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5724.4061 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 5727.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5728.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5732.4061 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 56666.6667 | ACTION | 5735.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5736.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5736.8464 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 3 | 21250 | ACTION | 5738.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 5739.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5739.8199 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5741.8199 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5743.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5745.8199 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5749.4061 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 85000 | ACTION | 5750.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5755.4061 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 5 | 35416.6667 | ACTION | 5755.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5760.7934 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 6 | 42500 | ACTION | 5761.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 1 | 7083.3333 | ACTION | 5762.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5763.7669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5765.7669 | MooringSystemInstallation
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 5766.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5769.7669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 22 | 0 | ACTION | 5777.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5780.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5784.7404 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 5786.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5787.7139 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5789.7139 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5790.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5793.7139 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5793.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5808.6874 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5811.6609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5813.6609 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5817.6609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5817.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5832.6344 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5835.6079 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 5840.613 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5845.613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5850.613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5855.613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5860.613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 5865.6181 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5867.6181 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5871.6181 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5886.5916 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5889.5651 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5889.9061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 550.8247 | 3901675.2895 | ACTION | 5889.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5891.5651 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5895.5651 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 5895.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5897.9061 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 5905.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 5907.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5909.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5910.5386 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 5913.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5913.5121 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5913.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5915.5121 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5917.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5917.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5919.5121 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5921.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5925.9061 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 5933.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5934.4856 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5937.4591 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5937.9061 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 5939.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5939.4591 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5941.4061 | MooredSubInstallation
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 5942.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5943.4591 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5944.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5948.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5958.4326 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5961.4061 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5963.4061 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5967.4061 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5972.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 5982.3796 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 5985.3531 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5987.3531 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5991.3531 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 6006.3266 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 6009.3001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6011.3001 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6015.3001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 6030.2736 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 6033.2471 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6035.2471 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6039.2471 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6044.4061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 454.8247 | 3221675.2895 | ACTION | 6044.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6050.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6052.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 6054.2206 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 6057.1941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6059.1941 | MooringSystemInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 6059.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 6061.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6063.1941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6064.4061 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6067.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6068.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6072.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6076.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 6078.1676 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6080.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 6081.1411 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6083.1411 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6085.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6087.1411 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 6087.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6092.4061 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 6093.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6095.9061 | MooredSubInstallation
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 6097.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6099.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 6102.1146 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6102.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 6105.0881 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6107.0881 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6111.0881 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 6126.0616 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6126.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 6129.0351 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6131.0351 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6135.0351 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 6150.0086 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 6152.9821 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 6157.9872 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6162.9872 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6167.9872 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6172.9872 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5.0051 | 20854.5833 | ACTION | 6177.9923 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6179.9923 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6183.9923 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6198.9061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 432.8247 | 3065841.9562 | ACTION | 6198.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 6198.9658 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 6201.9393 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6203.9393 | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6204.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6206.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6207.9393 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 6214.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 6216.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6218.9061 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6222.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6222.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 6222.9128 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 6225.8863 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6226.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6227.8863 | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 56666.6667 | ACTION | 6230.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 6230.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6231.8863 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6234.9061 | MooredSubInstallation
| Towing Group 1 | Delay | 8 | 56666.6667 | ACTION | 6238.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6238.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 6246.8598 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 6249.8333 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 85000 | ACTION | 6250.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6250.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6251.8333 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6253.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6254.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6255.8333 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 6256.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6257.9061 | MooredSubInstallation
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 6259.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 6270.8068 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 6273.7803 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6275.7803 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6279.7803 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 6294.7538 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 6297.7273 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6299.7273 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6303.7273 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 6318.7008 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 6321.6743 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6323.6743 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6327.6743 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 84 | 0 | ACTION | 6341.9061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 6342.6478 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6345.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 6345.6213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6347.6213 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6351.6213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 6366.5948 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6369.4061 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 6369.5683 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6371.5683 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6375.5683 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 14.9735 | 62389.5833 | ACTION | 6390.5418 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 2.9735 | 12389.5833 | ACTION | 6393.5153 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6421.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6441.4061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 498.8247 | 3533341.9562 | ACTION | 6441.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6447.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6449.4061 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 6456.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 6458.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6461.4061 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6464.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6465.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6469.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6473.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6477.4061 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 6484.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6489.4061 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 6490.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 6494.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 6505.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6508.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6512.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6515.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6539.9061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6589.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6611.9061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 514.8247 | 3646675.2895 | ACTION | 6611.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6617.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6619.9061 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 6627.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 6629.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6631.9061 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6635.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6635.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6639.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6643.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6647.9061 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 6655.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6659.9061 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 6661.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6663.4061 | MooredSubInstallation
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 6664.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6666.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6670.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6694.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 6699.4061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6757.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6771.4061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 511.8247 | 3625425.2895 | ACTION | 6771.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6777.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6779.4061 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 6786.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 6788.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6791.4061 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6794.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6795.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6799.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6803.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6807.4061 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 6814.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6819.4061 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 6820.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 6824.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 6832.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6835.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6839.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6842.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6866.9061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6925.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6938.9061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 444.8247 | 3150841.9562 | ACTION | 6938.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6944.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6946.9061 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 6954.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 6956.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6958.9061 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6962.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6962.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6966.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6970.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6974.9061 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 6982.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6986.9061 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 6988.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6990.4061 | MooredSubInstallation
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 6991.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6993.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6997.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7021.4061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7093.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7093.4061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 428.8247 | 3037508.6228 | ACTION | 7093.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7099.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7101.4061 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 7108.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 7110.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7113.4061 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 7116.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7117.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7121.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7125.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7129.4061 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 7136.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7141.4061 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 7142.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7144.9061 | MooredSubInstallation
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 7146.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7148.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7151.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7175.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7247.9061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 423.8247 | 3002091.9562 | ACTION | 7247.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7255.9061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7261.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7267.9061 | MooredSubInstallation
| Towing Group 1 | Delay | 21 | 148750 | ACTION | 7268.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7271.9061 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7274.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7275.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7279.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7283.9061 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 7284.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 7286.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 7292.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7295.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7299.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7302.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7306.4061 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 7312.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 7318.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 7321.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7330.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7402.4061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 410.8247 | 2910008.6228 | ACTION | 7402.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7408.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7410.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7422.4061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7429.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 45 | 0 | ACTION | 7467.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7471.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 7478.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7482.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 7485.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7489.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7493.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7505.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 7510.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7513.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 7527.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7531.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7534.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7558.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 7573.9061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7597.4061 | MooredSubInstallation
| Towing Group 2 | Delay | 209 | 1480416.6667 | ACTION | 7617.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 7626.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 7628.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 7634.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 10 | 70833.3333 | ACTION | 7644.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7645.9061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 499.8247 | 3540425.2895 | ACTION | 7645.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7651.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7653.9061 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 7661.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7665.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 10 | 0 | ACTION | 7675.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7679.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7683.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7687.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7691.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7703.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7707.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7710.9061 | MooredSubInstallation
| Towing Group 2 | Delay | 69 | 488750 | ACTION | 7713.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 53 | 375416.6667 | ACTION | 7714.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7714.4061 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 7716.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 7722.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 10 | 70833.3333 | ACTION | 7723.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 7724.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7738.4061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7765.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7810.4061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 488.8247 | 3462508.6228 | ACTION | 7810.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7816.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7818.4061 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 7825.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 103 | 729583.3333 | ACTION | 7826.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 1 | 7083.3333 | ACTION | 7826.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 103 | 729583.3333 | ACTION | 7827.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 7828.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7830.4061 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 7832.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7834.4061 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 7834.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 7836.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7838.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7842.4061 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 127500 | ACTION | 7845.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7846.4061 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 7851.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 7854.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 7854.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7858.4061 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 7860.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7861.9061 | MooredSubInstallation
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 7864.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7865.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7868.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7892.9061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7933.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7964.9061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 128.8247 | 912508.6228 | ACTION | 7964.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7970.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7972.9061 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 7980.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 7982.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7984.9061 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 7988.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7988.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7992.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7996.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8000.9061 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 127500 | ACTION | 8006.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8012.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8016.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8019.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8023.4061 | MooredSubInstallation
| Towing Group 2 | Delay | 31 | 219583.3333 | ACTION | 8037.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 8039.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 8045.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8047.4061 | MooredSubInstallation
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 8048.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8101.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8119.4061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 264.8247 | 1875841.9562 | ACTION | 8119.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 8125.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8127.4061 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 8134.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8139.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8143.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8147.4061 | MooredSubInstallation
| Towing Group 3 | Delay | 14 | 99166.6667 | ACTION | 8148.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 8150.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8151.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8155.4061 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 8156.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 35416.6667 | ACTION | 8161.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8167.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8170.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8174.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8177.9061 | MooredSubInstallation
| Towing Group 3 | Delay | 29 | 205416.6667 | ACTION | 8190.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 63750 | ACTION | 8199.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8201.9061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8269.4061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8437.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 288 | 0 | ACTION | 8489.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8561.9061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 697.8247 | 4942925.2895 | ACTION | 8561.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 4 | 28333.3333 | ACTION | 8565.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8569.9061 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 8571.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8581.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8585.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8589.9061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8605.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 31 | 0 | ACTION | 8620.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8624.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8628.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8640.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 8656.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8660.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8663.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8667.4061 | MooredSubInstallation
| Towing Group 1 | Delay | 98 | 694166.6667 | ACTION | 8669.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 8679.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 482 | 3414166.6667 | ACTION | 8681.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 3 | 21250 | ACTION | 8682.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 8684.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 42500 | ACTION | 8687.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 8690.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8691.4061 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 8693.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 42500 | ACTION | 8696.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 8697.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 5 | 35416.6667 | ACTION | 8701.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 63750 | ACTION | 8710.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8773.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 157 | 0 | ACTION | 8848.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8920.4061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 871.8247 | 6175425.2895 | ACTION | 8920.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8928.4061 | MooredSubInstallation
| Towing Group 2 | Delay | 19 | 134583.3333 | ACTION | 8939.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8940.4061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8941.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8944.4061 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 8945.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8948.4061 | MooredSubInstallation
| Towing Group 1 | Delay | 240 | 1700000 | ACTION | 8950.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8952.4061 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 8954.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 35416.6667 | ACTION | 8955.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8956.4061 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 8956.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 8961.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 8962.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 8964.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8968.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8971.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8975.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8978.9061 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 8982.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 8988.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 8992.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9002.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 9029.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9101.9061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 404.8247 | 2867508.6228 | ACTION | 9101.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9107.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9109.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9109.9061 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 9117.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 9119.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9121.9061 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9125.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9125.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9129.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9133.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9137.9061 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 120416.6667 | ACTION | 9142.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9149.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 9153.9061 | MooredSubInstallation
| Towing Group 3 | Delay | 15 | 106250 | ACTION | 9157.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9157.4061 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 21250 | ACTION | 9160.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9160.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9164.4061 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 9166.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 9169.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9188.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9260.4061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 295.8247 | 2095425.2895 | ACTION | 9260.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9268.4061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9277.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9280.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 9296.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9300.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9304.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9308.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 28 | 0 | ACTION | 9336.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9340.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9352.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 9379.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9382.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9386.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9389.9061 | MooredSubInstallation
| Towing Group 1 | Delay | 136 | 963333.3333 | ACTION | 9396.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9402.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 9411.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9413.9061 | MooredSubInstallation
| Towing Group 1 | Delay | 10 | 70833.3333 | ACTION | 9421.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 9423.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9429.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9445.4061 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 113333.3333 | ACTION | 9445.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9485.9061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 493.8247 | 3497925.2895 | ACTION | 9485.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 40.5 | 0 | ACTION | 9485.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9493.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9505.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9509.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9513.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9517.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9521.9061 | MooredSubInstallation
| Towing Group 2 | Delay | 46 | 325833.3333 | ACTION | 9531.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9533.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9537.4061 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9537.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9540.9061 | MooredSubInstallation
| Towing Group 1 | Delay | 97 | 687083.3333 | ACTION | 9542.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9544.4061 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 28333.3333 | ACTION | 9546.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 9547.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 9549.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 9552.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9555.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 9556.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9568.4061 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 9575.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 9581.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 9584.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9640.4061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 470.8247 | 3335008.6228 | ACTION | 9640.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9646.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9648.4061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9653.9061 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 9655.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 9657.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9660.4061 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9663.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9664.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9668.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9672.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9676.4061 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 9683.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9688.4061 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 9689.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9691.9061 | MooredSubInstallation
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 9693.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9695.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9698.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9722.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9794.9061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 238.8247 | 1691675.2895 | ACTION | 9794.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9800.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9802.9061 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 9810.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 9812.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9814.9061 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9818.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9818.9061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9821.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9822.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9826.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9830.9061 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 9838.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9842.9061 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 9844.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 1 | 7083.3333 | ACTION | 9845.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 13 | 92083.3333 | ACTION | 9858.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 2.5751 | 18240.0893 | ACTION | 9860.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 23 | 0 | ACTION | 9865.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9869.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9872.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9876.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9900.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9972.4061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 387.8247 | 2747091.9562 | ACTION | 9972.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9978.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9980.4061 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 9987.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9989.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9992.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9996.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10000.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10004.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10008.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10020.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10023.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10027.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10030.9061 | MooredSubInstallation
| Towing Group 2 | Delay | 56 | 396666.6667 | ACTION | 10043.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 10045.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 10051.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10054.9061 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 49583.3333 | ACTION | 10058.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 33 | 233750 | ACTION | 10091.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 92083.3333 | ACTION | 10104.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 5 | 35416.6667 | ACTION | 10109.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10126.9061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 433.8247 | 3072925.2895 | ACTION | 10126.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 10132.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10134.9061 | MooredSubInstallation
| Towing Group 3 | Delay | 10 | 70833.3333 | ACTION | 10142.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10146.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10150.9061 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 10152.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10154.9061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10157.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10158.9061 | MooredSubInstallation
| Towing Group 2 | Delay | 50 | 354166.6667 | ACTION | 10159.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 8 | 56666.6667 | ACTION | 10160.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 1 | 7083.3333 | ACTION | 10160.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 10162.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10162.9061 | MooredSubInstallation
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 10164.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 10168.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10174.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10178.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10181.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10185.4061 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 10188.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 10194.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 10197.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10209.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10281.4061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 420.8247 | 2980841.9562 | ACTION | 10281.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 10287.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10289.4061 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 10296.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10301.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10305.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10309.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10313.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10317.4061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10325.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10329.4061 | MooredSubInstallation
| Towing Group 1 | Delay | 49 | 347083.3333 | ACTION | 10345.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 17 | 0 | ACTION | 10346.4061 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 10347.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10349.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10353.4061 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 10353.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10356.9061 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 77916.6667 | ACTION | 10364.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 25 | 0 | ACTION | 10381.9061 | MooredSubInstallation
| Towing Group 1 | Delay | 31 | 219583.3333 | ACTION | 10395.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 63750 | ACTION | 10404.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10405.9061 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 10410.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 10414.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10493.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 116 | 0 | ACTION | 10521.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10593.9061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 429.8247 | 3044591.9562 | ACTION | 10593.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 100 | 0 | ACTION | 10593.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10601.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10613.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10617.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 20 | 0 | ACTION | 10637.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10641.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10645.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10649.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 43 | 0 | ACTION | 10692.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10704.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10708.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10711.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10715.4061 | MooredSubInstallation
| Towing Group 2 | Delay | 142 | 1005833.3333 | ACTION | 10735.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10739.4061 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 10741.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 10751.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 10753.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 7 | 49583.3333 | ACTION | 10760.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10761.9061 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 10766.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 42500 | ACTION | 10772.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10811.4061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 613.8247 | 4347925.2895 | ACTION | 10811.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 49.5 | 0 | ACTION | 10811.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10819.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10831.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10835.4061 | MooredSubInstallation
| Towing Group 3 | Delay | 25 | 177083.3333 | ACTION | 10836.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10839.4061 | MooredSubInstallation
| Towing Group 2 | Delay | 70 | 495833.3333 | ACTION | 10842.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 10842.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10843.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10847.4061 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 10851.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 10853.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 99166.6667 | ACTION | 10856.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10859.4061 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 10859.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 10862.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10862.9061 | MooredSubInstallation
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 10865.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10866.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10869.9061 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 10879.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 10885.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 10889.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10893.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10965.9061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 551.8247 | 3908758.6228 | ACTION | 10965.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10973.9061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10979.4061 | MooredSubInstallation
| Towing Group 1 | Delay | 20 | 141666.6667 | ACTION | 10985.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10985.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10989.9061 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 10991.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10993.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10997.9061 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 11001.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11001.9061 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 11003.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11009.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11013.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11017.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11020.9061 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 85000 | ACTION | 11021.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11024.4061 | MooredSubInstallation
| Towing Group 1 | Delay | 8 | 56666.6667 | ACTION | 11029.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 42500 | ACTION | 11035.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11048.4061 | MooredSubInstallation
| Towing Group 1 | Delay | 20 | 141666.6667 | ACTION | 11055.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 11057.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 11063.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 11066.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 64 | 0 | ACTION | 11112.4061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11147.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11184.4061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 318.8247 | 2258341.9562 | ACTION | 11184.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 37 | 0 | ACTION | 11184.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11192.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11204.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11208.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11212.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11216.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11220.4061 | MooredSubInstallation
| Towing Group 2 | Delay | 37 | 262083.3333 | ACTION | 11221.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11227.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11232.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11235.9061 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 11236.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11239.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11242.9061 | MooredSubInstallation
| Towing Group 2 | Delay | 19 | 134583.3333 | ACTION | 11255.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 11257.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11263.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11266.9061 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 11283.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 11289.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 11293.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11338.9061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 449.8247 | 3186258.6228 | ACTION | 11338.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11344.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11346.9061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11352.4061 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 11354.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 11356.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11358.9061 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11362.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11362.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11366.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11370.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11374.9061 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 113333.3333 | ACTION | 11378.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11386.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11390.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11393.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11397.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11421.4061 | MooredSubInstallation
| Towing Group 3 | Delay | 56 | 396666.6667 | ACTION | 11434.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 28333.3333 | ACTION | 11438.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 11444.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 11447.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11493.4061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 426.8247 | 3023341.9562 | ACTION | 11493.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11501.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11513.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11517.4061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11520.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11521.4061 | MooredSubInstallation
| Towing Group 1 | Delay | 29 | 205416.6667 | ACTION | 11522.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11525.4061 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11528.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11529.4061 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 11537.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 11539.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11541.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11544.9061 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11545.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11548.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11551.9061 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 11565.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 11571.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 11575.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11575.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11647.9061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 354.8247 | 2513341.9562 | ACTION | 11647.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11653.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11655.9061 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 11663.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 11665.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11667.9061 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11671.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11671.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11675.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11679.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11683.9061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11688.4061 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 11691.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11695.9061 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 11697.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11699.4061 | MooredSubInstallation
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 11700.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11702.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11706.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11730.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11802.4061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 354.8247 | 2513341.9562 | ACTION | 11802.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11808.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11810.4061 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 11817.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 11819.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11822.4061 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11825.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11826.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11830.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11834.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11838.4061 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 11845.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11850.4061 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 11851.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11853.9061 | MooredSubInstallation
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 11855.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11856.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11857.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11860.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11884.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11956.9061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 381.8247 | 2704591.9562 | ACTION | 11956.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11962.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11964.9061 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 11972.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 11974.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11976.9061 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11980.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11980.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11984.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11988.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11992.9061 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 12000.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12004.9061 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 12006.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12008.4061 | MooredSubInstallation
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 12009.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12011.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12015.4061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12024.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12039.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12111.4061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 410.8247 | 2910008.6228 | ACTION | 12111.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12117.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12119.4061 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 12126.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 12128.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12131.4061 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12134.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12135.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12139.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12143.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12147.4061 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 12154.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12159.4061 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 12160.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12162.9061 | MooredSubInstallation
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 12164.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12166.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12169.9061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12192.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12193.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12265.9061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 410.8247 | 2910008.6228 | ACTION | 12265.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12271.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12273.9061 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 12281.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 12283.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12285.9061 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12289.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12289.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12293.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12297.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12301.9061 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 12309.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12313.9061 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 12315.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12317.4061 | MooredSubInstallation
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 12318.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 25 | 0 | ACTION | 12342.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12345.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12349.4061 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12360.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12373.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12445.4061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 435.8247 | 3087091.9562 | ACTION | 12445.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12453.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12465.4061 | MooredSubInstallation
| Towing Group 1 | Delay | 22 | 155833.3333 | ACTION | 12467.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 12467.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12471.4061 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12473.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 17 | 0 | ACTION | 12488.4061 | MooredSubInstallation
| Towing Group 1 | Delay | 15 | 106250 | ACTION | 12488.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12492.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12496.4061 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 12497.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 12499.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12500.4061 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12505.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12512.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12515.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12519.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12522.9061 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 12525.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12528.4061 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 12531.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 12535.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12546.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12618.9061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 454.8247 | 3221675.2895 | ACTION | 12618.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12624.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12626.9061 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 12634.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 12636.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12638.9061 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12642.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12642.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12646.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12650.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12654.9061 | MooredSubInstallation
0.5 | Array Cable Installation Vessel | Mobilize | 72 | 337500 | ACTION | 12659.1463 | ArrayCableInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 12662.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Load Cable | 6 | 56250 | ACTION | 12665.1463 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12666.9061 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 12668.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Transit | 4.3523 | 40802.4457 | ACTION | 12669.4986 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12670.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12671.4986 | ArrayCableInstallation
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 12671.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12672.4986 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12677.9986 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 10 | 0 | ACTION | 12680.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12683.4986 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12683.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 12684.4986 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12687.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 7 | 65625 | ACTION | 12691.4986 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12696.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12711.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 53 | 496875 | ACTION | 12744.4986 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 9.2512 | 86729.8348 | ACTION | 12753.7498 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12754.7498 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12760.2498 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12765.7498 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12767.7498 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12768.7498 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12774.2498 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12779.7498 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 12780.7498 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12783.4061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 464.8247 | 3292508.6228 | ACTION | 12783.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12789.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12791.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 16.2512 | 152354.8348 | ACTION | 12797.0009 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12798.0009 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 12798.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 12800.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12803.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12803.5009 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12806.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12807.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12809.0009 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12811.0009 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12811.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12812.0009 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12815.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12817.5009 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12819.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12823.0009 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 12824.0009 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 12826.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 12829.1639 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12830.1639 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12831.4061 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 12832.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12834.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12835.6639 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 12836.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12838.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12841.1639 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12841.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12843.1639 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12844.1639 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12849.6639 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12855.1639 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 12856.1639 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 12861.3269 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12862.3269 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12864.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12865.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12867.8269 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12873.3269 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12875.3269 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12876.3269 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12881.8269 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12887.3269 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 12888.3269 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 12893.4898 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12894.4898 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12899.9898 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12905.4898 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12907.4898 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12908.4898 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12913.9898 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12919.4898 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 12920.4898 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 12925.6528 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12926.6528 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12932.1528 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12937.6528 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12937.9061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 402.8247 | 2853341.9562 | ACTION | 12937.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12939.6528 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12940.6528 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12943.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12945.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12946.1528 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12951.6528 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 12952.6528 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 12953.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 12955.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 12957.8157 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12957.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12958.8157 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12961.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12961.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12964.3157 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12965.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 12969.8157 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12969.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 12971.8157 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 12972.8157 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12973.9061 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 120416.6667 | ACTION | 12978.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 12978.3157 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13032.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 62 | 581250 | ACTION | 13040.3157 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Delay | 63 | 446250 | ACTION | 13041.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 21250 | ACTION | 13044.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13045.8157 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13046.8157 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 5 | 35416.6667 | ACTION | 13049.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13051.9787 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13052.9787 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 82 | 0 | ACTION | 13055.9061 | MooredSubInstallation
| Towing Group 1 | Delay | 7 | 49583.3333 | ACTION | 13056.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 1 | 7083.3333 | ACTION | 13057.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13058.4787 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 13060.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13063.9787 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13065.9787 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13066.9787 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13067.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13071.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13072.4787 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13077.9787 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13078.9787 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 13082.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13084.1416 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13085.1416 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13085.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13089.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13090.6416 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13096.1416 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13098.1416 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13099.1416 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13104.6416 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13110.1416 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13111.1416 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13113.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13116.3046 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13117.3046 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13122.8046 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13128.3046 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13130.3046 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13131.3046 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13136.8046 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13142.3046 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13143.3046 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13148.4675 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13149.4675 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13154.9675 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13160.4675 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13162.4675 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13163.4675 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13168.9675 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13174.4675 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13175.4675 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13180.6305 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13181.6305 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13185.4061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 513.8247 | 3639591.9562 | ACTION | 13185.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13187.1305 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13191.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13192.6305 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13193.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13194.6305 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13195.6305 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13200.4061 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 13200.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13201.1305 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 13202.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13205.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13206.6305 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13207.6305 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13208.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13209.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13212.7934 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13213.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13213.7934 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13217.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13219.2934 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13221.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13224.7934 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13226.7934 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13227.7934 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13228.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13233.2934 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13233.4061 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 13234.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 13237.4061 | MooredSubInstallation
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 13238.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13238.7934 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13239.7934 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13240.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13244.9564 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13245.9564 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 10 | 0 | ACTION | 13250.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13251.4564 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13254.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13256.9564 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13257.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13258.9564 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13259.9564 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13265.4564 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13270.9564 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13271.9564 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13277.1193 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13278.1193 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13281.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13283.6193 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13289.1193 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13291.1193 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13292.1193 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13297.6193 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13303.1193 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13304.1193 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13309.2823 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13310.2823 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13315.7823 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13321.2823 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13323.2823 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13324.2823 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13329.7823 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13335.2823 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13336.2823 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13341.4452 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13342.4452 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13347.9452 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13353.4452 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13353.9061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 517.8247 | 3667925.2895 | ACTION | 13353.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13355.4452 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13356.4452 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13359.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13361.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13361.9452 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13367.4452 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13368.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13368.4452 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 13369.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 13371.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13373.6082 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13373.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13374.6082 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13377.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13377.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13380.1082 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13381.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13385.6082 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13385.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13387.6082 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13388.6082 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13389.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13394.1082 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13397.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13399.6082 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13400.6082 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13401.9061 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 13403.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13405.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13405.7711 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 13406.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13406.7711 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13408.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13412.2711 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13412.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13417.7711 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13419.7711 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13420.7711 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13426.2711 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13431.7711 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13432.7711 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13436.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13437.9341 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13438.9341 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13444.4341 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13449.9341 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13451.9341 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13452.9341 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13458.4341 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13463.9341 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13464.9341 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13470.097 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13471.097 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13476.597 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13482.097 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13484.097 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13485.097 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13490.597 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13496.097 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13497.097 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13502.26 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13503.26 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13508.4061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 447.8247 | 3172091.9562 | ACTION | 13508.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13508.76 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13514.26 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13514.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13516.26 | ArrayCableInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13516.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13517.26 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13522.76 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 13523.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 13525.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13528.26 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13528.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13529.26 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13531.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13532.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13534.4229 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13535.4229 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13536.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13536.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13540.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13540.9229 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13544.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13546.4229 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13548.4229 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13549.4229 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13551.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13554.9229 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13556.4061 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 13557.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13559.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13560.4229 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 13561.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13561.4229 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13563.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13566.5859 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13566.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13567.5859 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13573.0859 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13578.5859 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13580.5859 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13581.5859 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13587.0859 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13590.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13592.5859 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13593.5859 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13598.7488 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13599.7488 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13605.2488 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13662.9061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 424.8247 | 3009175.2895 | ACTION | 13662.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 7 | 49583.3333 | ACTION | 13669.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13670.9061 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13675.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13682.9061 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 13685.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 80 | 750000 | ACTION | 13685.2488 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13686.9061 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 13687.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13690.7488 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13690.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13692.7488 | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13693.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13693.7488 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13694.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13698.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13699.2488 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13704.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13704.7488 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13705.7488 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13710.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13710.9118 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13711.9118 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13713.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13714.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13717.4118 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13717.9061 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 13719.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13721.4061 | MooredSubInstallation
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 13722.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13722.9118 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13724.9118 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13725.9118 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13731.4118 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13736.9118 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13737.9118 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13743.0747 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13744.0747 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13745.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13749.5747 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13755.0747 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13757.0747 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13758.0747 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13763.5747 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13769.0747 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13770.0747 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13775.2377 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13776.2377 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13781.7377 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13787.2377 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13789.2377 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13790.2377 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13795.7377 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13801.2377 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13802.2377 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13807.4006 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13808.4006 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13813.9006 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13817.4061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 410.8247 | 2910008.6228 | ACTION | 13817.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13819.4006 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Delay | 7 | 49583.3333 | ACTION | 13824.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13825.4061 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13830.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13837.4061 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 13839.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13841.4061 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 13841.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13845.4061 | MooredSubInstallation
| Towing Group 3 | Delay | 6 | 42500 | ACTION | 13847.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 13848.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 30 | 281250 | ACTION | 13849.4006 | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13851.4006 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13852.4006 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13852.4061 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13853.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13856.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13857.9006 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13863.4006 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13864.4006 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13868.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13869.5636 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13870.5636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13872.4061 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13873.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13876.0636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 13879.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13881.5636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 13883.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13883.5636 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13884.5636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13890.0636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 25 | 0 | ACTION | 13893.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13895.5636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13896.5636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13896.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13900.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13901.7265 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13902.7265 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13903.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13908.2265 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13913.7265 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13915.7265 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13916.7265 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13922.2265 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13927.7265 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13927.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13928.7265 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13933.8895 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13934.8895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13940.3895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13945.8895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13947.8895 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13948.8895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13954.3895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13959.8895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13960.8895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13966.0524 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13967.0524 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13972.5524 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13978.0524 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 13980.0524 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13981.0524 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 13986.5524 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 13992.0524 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 13993.0524 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 13998.2154 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 13999.2154 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13999.9061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 438.8247 | 3108341.9562 | ACTION | 13999.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14004.7154 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14005.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14007.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14010.2154 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14012.2154 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14013.2154 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 14015.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 14017.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14018.7154 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14019.9061 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14023.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14023.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14024.2154 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14025.2154 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14027.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14030.3784 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14031.3784 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14031.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14035.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14036.8784 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14040.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14042.3784 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14043.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14044.3784 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14045.3784 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14047.9061 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 14049.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14050.8784 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14051.4061 | MooredSubInstallation
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 14052.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14054.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14056.3784 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14057.3784 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14058.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14062.5413 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14063.5413 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14069.0413 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14074.5413 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14076.5413 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14077.5413 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14082.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14083.0413 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14088.5413 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14089.5413 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14094.7043 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14095.7043 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14101.2043 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14106.7043 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14108.7043 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14109.7043 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14115.2043 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14120.7043 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14121.7043 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14126.8672 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14127.8672 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14133.3672 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14138.8672 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14140.8672 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14141.8672 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14147.3672 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14152.8672 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14153.8672 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14154.4061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 431.8247 | 3058758.6228 | ACTION | 14154.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14159.0302 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14160.0302 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14160.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14162.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14165.5302 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 14169.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14171.0302 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 14171.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14173.0302 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14174.0302 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14174.4061 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14177.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14178.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14179.5302 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14182.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14185.0302 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14186.0302 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14186.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14190.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14191.1931 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14192.1931 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14197.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14197.6931 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14202.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14203.1931 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 14203.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14205.1931 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14205.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14206.1931 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 14207.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14209.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14211.6931 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14212.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14217.1931 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14218.1931 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14223.3561 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14224.3561 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14229.8561 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14235.3561 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14236.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14237.3561 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14238.3561 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14243.8561 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14249.3561 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14250.3561 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14255.519 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14256.519 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14262.019 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14267.519 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14269.519 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14270.519 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14308.9061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 425.8247 | 3016258.6228 | ACTION | 14308.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 6 | 42500 | ACTION | 14314.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14316.9061 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14320.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 3 | 21250 | ACTION | 14323.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14328.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14332.9061 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 14333.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 63 | 590625 | ACTION | 14333.519 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 14335.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14336.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14339.019 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14340.9061 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14341.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14344.519 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14344.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14345.519 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14350.682 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14351.682 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14356.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14357.182 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14360.4061 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14361.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14362.682 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14363.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14364.682 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14365.682 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 14367.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14367.4061 | MooredSubInstallation
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 14370.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14371.182 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14376.682 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14377.682 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14382.8449 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14383.8449 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14389.3449 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14391.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14394.8449 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14396.8449 | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 6 | 56250 | ACTION | 14402.8449 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14403.8449 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14409.3449 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14414.8449 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14415.8449 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14421.0079 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14422.0079 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14427.5079 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14433.0079 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14435.0079 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14436.0079 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14441.5079 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14447.0079 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14448.0079 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14453.1708 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14454.1708 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14459.6708 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14463.4061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 410.8247 | 2910008.6228 | ACTION | 14463.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14465.1708 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14469.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14471.4061 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 14478.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 14480.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 17 | 159375 | ACTION | 14482.1708 | ArrayCableInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14483.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14484.1708 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14485.1708 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14486.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14487.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14490.6708 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14491.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14495.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14496.1708 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14497.1708 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14499.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14502.3338 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14503.3338 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14506.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14508.8338 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14511.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 14512.4061 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 14512.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14514.3338 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14515.9061 | MooredSubInstallation
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 14516.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14516.3338 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14517.3338 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14519.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14522.8338 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14522.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14528.3338 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14529.3338 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14534.4967 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14535.4967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14540.9967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14546.4967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14546.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14548.4967 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14549.4967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14554.9967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14560.4967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14561.4967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14566.6597 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14567.6597 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14573.1597 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14578.6597 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14580.6597 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14581.6597 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 50 | 0 | ACTION | 14596.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 46 | 431250 | ACTION | 14627.6597 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14633.1597 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14638.6597 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14639.6597 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14644.8226 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14645.8226 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14651.3226 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14656.8226 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14658.8226 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14659.8226 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14665.3226 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14668.9061 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 461.8247 | 3271258.6228 | ACTION | 14668.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14670.8226 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14671.8226 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14674.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14676.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14676.9856 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14677.9856 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14683.4856 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 14684.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 14686.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14688.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14688.9856 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14690.9856 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14691.9856 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14692.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14692.9061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14696.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14697.4856 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14700.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14702.9856 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14703.9856 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14704.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14709.1485 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14710.1485 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14712.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14715.6485 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14716.9061 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 14718.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14720.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14721.1485 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 3.5751 | 25323.4226 | ACTION | 14721.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14723.1485 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14723.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14724.1485 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14727.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14729.6485 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14735.1485 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14736.1485 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14741.3115 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14742.3115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14747.8115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14751.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14753.3115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14755.3115 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14756.3115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14761.8115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14767.3115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14768.3115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14773.4744 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14774.4744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14779.9744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14785.4744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14787.4744 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14788.4744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 44 | 0 | ACTION | 14795.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 12 | 112500 | ACTION | 14800.4744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14805.9744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 24 | 225000 | ACTION | 14829.9744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14835.4744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14836.4744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14841.6374 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14842.6374 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14848.1374 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14853.6374 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14855.6374 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14856.6374 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14862.1374 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14867.4061 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 496.8247 | 3519175.2895 | ACTION | 14867.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14867.6374 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14868.6374 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14873.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14873.8003 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14874.8003 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14875.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14887.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 14893.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14897.4061 | MooredSubInstallation
| Towing Group 3 | Delay | 43 | 304583.3333 | ACTION | 14916.4061 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 19 | 0 | ACTION | 14916.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 44 | 412500 | ACTION | 14918.8003 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14920.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14924.3003 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14924.4061 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 14925.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 3 | 21250 | ACTION | 14928.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 14929.4061 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 14930.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14933.4061 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14936.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 13 | 121875 | ACTION | 14937.3003 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14942.8003 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14944.8003 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14945.4061 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14945.8003 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14948.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14951.3003 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14952.4061 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14955.9061 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14956.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14956.8003 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14957.8003 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 14962.5063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14962.9633 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14963.9633 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 3.5751 | 25323.4226 | ACTION | 14966.0814 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14969.4633 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14974.9633 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 14976.9633 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14977.9633 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14979.9061 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 14983.4633 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 14988.9633 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 14989.9633 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 14995.1262 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 14996.1262 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15001.6262 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15007.1262 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15009.1262 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15010.1262 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15015.6262 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15021.1262 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15022.1262 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 15027.2892 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15028.2892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15033.7892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15039.2892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15041.2892 | ArrayCableInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15051.9061 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 535.8247 | 3795425.2895 | ACTION | 15051.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 15057.9061 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 9.1002 | 64459.6212 | ACTION | 15067.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 15069.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 72 | 675000 | ACTION | 15113.2892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15114.2892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Delay | 80 | 566666.6667 | ACTION | 15149.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 37 | 346875 | ACTION | 15151.2892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 15155.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15156.7892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15162.2892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15163.2892 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 15168.4521 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15169.4521 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15174.9521 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 15175.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15180.4521 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 15181.0063 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15182.4521 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15183.4521 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 3.5751 | 25323.4226 | ACTION | 15184.5814 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15188.9521 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 47 | 440625 | ACTION | 15235.9521 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15241.4521 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15242.4521 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.163 | 48402.6713 | ACTION | 15247.6151 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15248.6151 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15254.1151 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15259.6151 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15261.6151 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15262.6151 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15268.1151 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15273.6151 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15274.6151 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 12.2718 | 115048.1035 | ACTION | 15286.8869 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15287.8869 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15293.3869 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15298.8869 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15300.8869 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15301.8869 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15307.3869 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15312.8869 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15313.8869 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 12.2718 | 115048.1035 | ACTION | 15326.1587 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15327.1587 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15332.6587 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15338.1587 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15340.1587 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15341.1587 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15346.6587 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15352.1587 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15353.1587 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8.5346 | 80011.9621 | ACTION | 15361.6933 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15362.6933 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15368.1933 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15373.6933 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15375.6933 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15376.6933 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15382.1933 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15387.6933 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15388.6933 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8.5346 | 80011.9621 | ACTION | 15397.2279 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15398.2279 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15403.7279 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15409.2279 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15411.2279 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15412.2279 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15417.7279 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15423.2279 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15424.2279 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.6587 | 53050.2597 | ACTION | 15429.8866 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15430.8866 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15436.3866 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15441.8866 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15443.8866 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15444.8866 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15450.3866 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 182 | 1706250 | ACTION | 15632.3866 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15637.8866 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15638.8866 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.6587 | 53050.2597 | ACTION | 15644.5453 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15645.5453 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15651.0453 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15656.5453 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 4.3523 | 40802.4457 | ACTION | 15660.8976 | ArrayCableInstallation | ArrayCableInstallation | FALSE