## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | include_onshore_construction | max_waveheight | max_windspeed | transit_speed | num_vessels | num_ahts_vessels
0.5 | Export Cable Installation Vessel | Mobilize | 72 | 450000 | ACTION | 0 | ExportCableInstallation
1 | Mooring System Installation Vessel | Mobilize | 168 | 700000 | ACTION | 0 | MooringSystemInstallation
| Export Cable Installation Vessel | Load Cable | 6 | 75000 | ACTION | 6 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Delay | 73 | 304166.6667 | ACTION | 73 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 78 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 83 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 86 | 1075000 | ACTION | 92 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Tow Plow | 0.4 | 5000 | ACTION | 92.4 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Pull Winch | 0.4 | 5000 | ACTION | 92.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Prepare Cable | 1 | 12500 | ACTION | 93.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Transit | 21 | 87500 | ACTION | 104 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 117 | 487500 | ACTION | 221 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 19 | 79166.6667 | ACTION | 240 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 31 | 129166.6667 | ACTION | 271 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 18 | 75000 | ACTION | 289 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 36 | 150000 | ACTION | 325 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 15 | 62500 | ACTION | 340 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 76 | 316666.6667 | ACTION | 416 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2.4783 | 10326.25 | ACTION | 418.4783 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 420.4783 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 424.4783 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 343 | 4287500 | ACTION | 436.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 440.6383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 442.3 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 444.7983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 446.7983 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 450.7983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 466.9583 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 471.1183 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 473.1183 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 477.1183 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 69 | 287500 | ACTION | 546.1183 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 562.2783 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 123 | 1537500 | ACTION | 565.3 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 566.4383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 568.4383 | MooringSystemInstallation
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 570.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Lower Cable | 1 | 12500 | ACTION | 571.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 572.4383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 13 | 162500 | ACTION | 584.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 588.5983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 592.7583 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 594.7583 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 59 | 245833.3333 | ACTION | 653.7583 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 657.7583 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 673.9183 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 678.0783 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 95 | 1187500 | ACTION | 679.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 680.0783 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 684.0783 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 12 | 150000 | ACTION | 691.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 700.2383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 11 | 137500 | ACTION | 702.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 704.3983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 43 | 537500 | ACTION | 745.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 779.8766 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 36 | 450000 | ACTION | 781.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 784.8766 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 789.8766 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 24 | 300000 | ACTION | 805.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Substation Assembly Line 1 | Substation Substructure Assembly | 336 | 0 | ACTION | 808.3679 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 26 | 325000 | ACTION | 831.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Substation Assembly Line 1 | Attach Topside | 24 | 0 | ACTION | 832.3679 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay: Waiting on Substation Assembly | 360 | 1500000 | ACTION | 832.3679 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 17 | 212500 | ACTION | 848.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 865.3549 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 867.3549 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 871.3549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 74 | 308333.3333 | ACTION | 945.3549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 107 | 1337500 | ACTION | 955.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 961.5149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 965.6749 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 10 | 125000 | ACTION | 965.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 967.6749 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 971.6749 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 49 | 204166.6667 | ACTION | 1020.6749 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1036.8349 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1040.9949 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1042.9949 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1046.9949 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 33 | 137500 | ACTION | 1079.9949 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1096.1549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1100.3149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1102.3149 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1106.3149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 45 | 187500 | ACTION | 1151.3149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1167.4749 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1171.6349 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1173.6349 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1177.6349 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 5 | 20833.3333 | ACTION | 1182.6349 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1198.7949 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 18 | 75000 | ACTION | 1216.7949 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1220.9549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1222.9549 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1226.9549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 272 | 3400000 | ACTION | 1237.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1243.1149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1247.2749 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 29 | 362500 | ACTION | 1266.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 34 | 141666.6667 | ACTION | 1281.2749 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 23 | 95833.3333 | ACTION | 1304.2749 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 41.4783 | 172826.25 | ACTION | 1345.7532 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1350.7532 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1355.7532 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 12 | 50000 | ACTION | 1367.7532 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 621 | 2587500 | ACTION | 1453.3679 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 86 | 358333.3333 | ACTION | 1453.7532 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 198 | 2475000 | ACTION | 1464.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 63.4783 | 264492.9167 | ACTION | 1517.2315 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1519.2315 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1523.2315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1539.3915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1543.5515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1545.5515 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1549.5515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 87.0382 | 1087977.8329 | ACTION | 1551.8382 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Position Onsite | 2 | 25000 | ACTION | 1553.8382 | ExportCableInstallation
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 1559.3382 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 1564.8382 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1565.7115 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Transit | 4 | 50000 | ACTION | 1568.8382 | ExportCableInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1569.8715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1571.8715 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1575.8715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Tow Substation to Site | 125.7972 | 524154.8611 | ACTION | 1579.165 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1581.165 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1587.165 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1591.165 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1592.0315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1596.1915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1598.1915 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1602.1915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 36 | 450000 | ACTION | 1604.8382 | ExportCableInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 1606.325 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1610.485 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1618.3515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 9 | 37500 | ACTION | 1619.485 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Transit | 15 | 187500 | ACTION | 1619.8382 | ExportCableInstallation
| Mooring System Installation Vessel | Delay | 15 | 62500 | ACTION | 1633.3515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1637.5115 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1639.5115 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1643.5115 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 27 | 112500 | ACTION | 1670.5115 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1686.6715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1690.8315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1692.8315 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 63 | 262500 | ACTION | 1755.8315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1759.8315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 142 | 591666.6667 | ACTION | 1761.485 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 11 | 45833.3333 | ACTION | 1772.485 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1775.9915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 32 | 133333.3333 | ACTION | 1807.9915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1812.1515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 6 | 25000 | ACTION | 1818.1515 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 1820.1515 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 6 | 25000 | ACTION | 1826.1515 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 3 | 12500 | ACTION | 1829.1515 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 63 | 262500 | ACTION | 1835.485 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 2 | 8333.3333 | ACTION | 1837.485 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 223 | 2787500 | ACTION | 1842.8382 | ExportCableInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1849.485 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1853.485 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 1868.645 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1872.805 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Transit | 46.6333 | 582916.3043 | ACTION | 1889.4715 | ExportCableInstallation
| Mooring System Installation Vessel | Transit | 63.4783 | 264492.9167 | ACTION | 1892.6298 | MooringSystemInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1894.805 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1897.6298 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1902.6298 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1906.805 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1910.805 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 1925.965 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1930.125 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 5 | 20833.3333 | ACTION | 1935.125 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay | 5 | 20833.3333 | ACTION | 1940.125 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 17 | 70833.3333 | ACTION | 1957.125 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1969.125 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 1978.1081 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1980.1081 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1984.1081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2000.2681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2004.4281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2006.4281 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2010.4281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2026.5881 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2030.7481 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2032.7481 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2036.7481 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 2044.6033 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2052.9081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2057.0681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2059.0681 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 81 | 337500 | ACTION | 2140.0681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2144.0681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2160.2281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 39 | 162500 | ACTION | 2199.2281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2203.3881 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2205.3881 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2209.3881 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2225.5481 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2229.7081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2231.7081 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2235.7081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2251.8681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2256.0281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 2331.5064 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2336.5064 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2341.5064 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 2416.9847 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2418.9847 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2422.9847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2439.1447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2443.3047 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2445.3047 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2449.3047 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2465.4647 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2469.6247 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2471.6247 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2475.6247 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2491.7847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2495.9447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2497.9447 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2501.9447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 31 | 129166.6667 | ACTION | 2532.9447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2549.1047 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2553.2647 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2555.2647 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2559.2647 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 2570.2647 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2586.4247 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2590.5847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2592.5847 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 9 | 37500 | ACTION | 2601.5847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2605.5847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 27 | 112500 | ACTION | 2632.5847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2648.7447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2652.9047 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 43 | 179166.6667 | ACTION | 2695.9047 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 29 | 120833.3333 | ACTION | 2724.9047 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 32.4783 | 135326.25 | ACTION | 2757.383 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2762.383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 17 | 70833.3333 | ACTION | 2779.383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2784.383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 2859.8613 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2861.8613 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2865.8613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2882.0213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2886.1813 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2888.1813 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2892.1813 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2908.3413 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2912.5013 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2914.5013 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2918.5013 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2934.6613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2938.8213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2940.8213 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2944.8213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 18 | 75000 | ACTION | 2962.8213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2978.9813 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2983.1413 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2985.1413 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2989.1413 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3005.3013 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3009.4613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3011.4613 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3015.4613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3031.6213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3035.7813 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 3 | 12500 | ACTION | 3038.7813 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 3042.7813 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2 | 8333.3333 | ACTION | 3044.7813 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 3057.7813 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 70.4783 | 293659.5833 | ACTION | 3128.2596 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3133.2596 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3138.2596 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 3213.7379 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3215.7379 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 16 | 66666.6667 | ACTION | 3231.7379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3235.7379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3251.8979 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3256.0579 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3258.0579 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3262.0579 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3278.2179 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3282.3779 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3284.3779 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3288.3779 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3304.5379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3308.6979 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3310.6979 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3314.6979 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3330.8579 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3335.0179 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3337.0179 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3341.0179 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3357.1779 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3361.3379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3363.3379 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3367.3379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3383.4979 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3387.6579 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 3463.1362 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3468.1362 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3473.1362 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 3548.6145 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3550.6145 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3554.6145 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3570.7745 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3574.9345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3576.9345 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3580.9345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 77 | 320833.3333 | ACTION | 3657.9345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3674.0945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3678.2545 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3680.2545 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3684.2545 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3700.4145 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3704.5745 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3706.5745 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3710.5745 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3726.7345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3730.8945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3732.8945 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3736.8945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3753.0545 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 75 | 312500 | ACTION | 3828.0545 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3832.2145 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3834.2145 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3838.2145 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3854.3745 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3858.5345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 3934.0128 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3939.0128 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3944.0128 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 4019.4911 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4021.4911 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4025.4911 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4041.6511 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4045.8111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4047.8111 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4051.8111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4067.9711 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4072.1311 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4074.1311 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4078.1311 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4094.2911 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4098.4511 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4100.4511 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4104.4511 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4120.6111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4124.7711 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4126.7711 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4130.7711 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4146.9311 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4151.0911 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4153.0911 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4157.0911 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4173.2511 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4177.4111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 4252.8894 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4257.8894 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4262.8894 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 4338.3677 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4340.3677 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4344.3677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4360.5277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4364.6877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4366.6877 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 20 | 83333.3333 | ACTION | 4386.6877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4390.6877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4406.8477 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4411.0077 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4413.0077 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4417.0077 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4433.1677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4437.3277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4439.3277 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4443.3277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4459.4877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4463.6477 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4465.6477 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4469.6477 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4485.8077 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4489.9677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4491.9677 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4495.9677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4512.1277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4516.2877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 4591.766 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4596.766 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4601.766 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 4677.2443 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4679.2443 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4683.2443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 4694.2443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4710.4043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4714.5643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4716.5643 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4720.5643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4736.7243 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4740.8843 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4742.8843 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4746.8843 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4763.0443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4767.2043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4769.2043 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4773.2043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4789.3643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4793.5243 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4795.5243 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4799.5243 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4815.6843 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4819.8443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4821.8443 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4825.8443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 4833.8443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4850.0043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4854.1643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 4929.6426 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4934.6426 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4939.6426 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 36 | 150000 | ACTION | 4975.6426 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 34 | 141666.6667 | ACTION | 5009.6426 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 39.4783 | 164492.9167 | ACTION | 5049.1209 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5051.1209 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5055.1209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5071.2809 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5075.4409 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5077.4409 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5081.4409 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5097.6009 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5101.7609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5103.7609 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5107.7609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5123.9209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 27 | 112500 | ACTION | 5150.9209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5155.0809 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5157.0809 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5161.0809 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5177.2409 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5181.4009 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5183.4009 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5187.4009 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5203.5609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5207.7209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5209.7209 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5213.7209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5229.8809 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5234.0409 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 48 | 200000 | ACTION | 5282.0409 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 5 | 20833.3333 | ACTION | 5287.0409 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 27.4783 | 114492.9167 | ACTION | 5314.5192 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5319.5192 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5324.5192 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 5399.9975 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5401.9975 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5405.9975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5422.1575 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5426.3175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5428.3175 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5432.3175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5448.4775 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5452.6375 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5454.6375 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5458.6375 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5474.7975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5478.9575 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5480.9575 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5484.9575 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5501.1175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 5508.1175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5512.2775 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5514.2775 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5518.2775 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5534.4375 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5538.5975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5540.5975 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5544.5975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5560.7575 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5564.9175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 5640.3958 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5645.3958 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5650.3958 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 5725.8741 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5727.8741 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5731.8741 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5748.0341 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5752.1941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5754.1941 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5758.1941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5774.3541 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5778.5141 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5780.5141 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5784.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 5784.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5784.5141 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5792.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5800.6741 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5804.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5804.8341 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5806.8341 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 5816.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 5817.8341 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5820.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5821.8341 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5824.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5828.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5832.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5837.9941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 5839.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5842.1541 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5844.1541 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5848.1541 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5851.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5864.3141 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5868.4741 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5870.4741 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5874.4741 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5890.6341 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5894.7941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 53 | 0 | ACTION | 5904.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5907.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5911.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5914.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5938.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5952.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 5970.2724 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5975.2724 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5980.2724 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6010.6464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 394.5 | 2794375 | ACTION | 6010.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6016.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6018.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6030.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6034.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6038.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6042.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6046.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 6055.7507 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6057.7507 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6058.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6061.7507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6062.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 6077.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6077.9107 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6080.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6082.0707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6084.0707 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6084.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6088.0707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6104.2307 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6108.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6108.3907 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6110.3907 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6114.3907 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6120.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6130.5507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6134.7107 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6136.7107 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6140.7107 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 6153.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 6155.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6156.8707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6161.0307 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6161.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6163.0307 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6167.0307 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6180.1464 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 564 | 3995000 | ACTION | 6180.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 6181.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6183.1907 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6186.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6187.3507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 6187.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6188.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6189.3507 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6193.3507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6200.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6204.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6208.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6209.5107 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6212.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6213.6707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6216.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6228.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6231.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6235.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6238.6464 | MooredSubInstallation
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 6241.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 51 | 212500 | ACTION | 6264.6707 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 31 | 0 | ACTION | 6269.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 9 | 37500 | ACTION | 6273.6707 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6288.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 16 | 66666.6667 | ACTION | 6289.6707 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6293.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 6300.6707 | MooringSystemInstallation
| Towing Group 2 | Delay | 122 | 864166.6667 | ACTION | 6308.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 8.4783 | 35326.25 | ACTION | 6309.149 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6314.149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6319.149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6365.6464 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 749.5 | 5308958.3333 | ACTION | 6365.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6371.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6373.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6385.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6389.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6393.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 6394.6273 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6396.6273 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6397.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6400.6273 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6401.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6413.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6416.7873 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6417.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6420.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6420.9473 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6422.9473 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6424.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6426.9473 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6443.1073 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 6445.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6447.2673 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 6447.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6448.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6449.2673 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6453.2673 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6453.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6456.1464 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 21250 | ACTION | 6456.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 21 | 0 | ACTION | 6469.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 20 | 83333.3333 | ACTION | 6473.2673 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 33 | 233750 | ACTION | 6489.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6489.4273 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6493.5873 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6495.5873 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6499.5873 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 120416.6667 | ACTION | 6506.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 6512.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6515.7473 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6519.9073 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6521.9073 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6525.9073 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6541.1464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 299.3537 | 2120421.7289 | ACTION | 6541.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6542.0673 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6546.2273 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6547.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6548.2273 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6549.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6552.2273 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6561.1464 | MooredSubInstallation
| Towing Group 2 | Transit | 51 | 361250 | ACTION | 6563.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 5 | 35416.6667 | ACTION | 6568.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6568.3873 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 1 | 7083.3333 | ACTION | 6569.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6572.5473 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 4 | 16666.6667 | ACTION | 6576.5473 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 5 | 20833.3333 | ACTION | 6581.5473 | MooringSystemInstallation
| Towing Group 2 | Delay | 18 | 127500 | ACTION | 6587.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 6588.1464 | MooredSubInstallation
| Towing Group 2 | Transit | 1.9131 | 13550.9226 | ACTION | 6589.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6592.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 23 | 0 | ACTION | 6615.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6619.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6623.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6624.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6627.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6639.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 71.4783 | 297826.25 | ACTION | 6653.0256 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6658.0256 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6663.0256 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 11 | 45833.3333 | ACTION | 6674.0256 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 6 | 25000 | ACTION | 6680.0256 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 42 | 175000 | ACTION | 6722.0256 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 6729.0256 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 5 | 20833.3333 | ACTION | 6734.0256 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 3 | 12500 | ACTION | 6737.0256 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 17.4783 | 72826.25 | ACTION | 6754.5039 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6756.5039 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6760.5039 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 130 | 0 | ACTION | 6769.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6772.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6776.6639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6780.8239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6782.8239 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6786.8239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6792.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6802.9839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6807.1439 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6809.1439 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6813.1439 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 50 | 0 | ACTION | 6822.6464 | MooredSubInstallation
| Towing Group 3 | Delay | 452 | 3201666.6667 | ACTION | 6823.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 6824.1439 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 277 | 1962083.3333 | ACTION | 6824.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6826.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6829.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6840.3039 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6844.4639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6846.4639 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6850.4639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6853.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6866.6239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6870.7839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6872.7839 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6876.7839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6892.9439 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6897.1039 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6899.1039 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6903.1039 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6919.2639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6923.4239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6925.6464 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 336.3537 | 2382505.0622 | ACTION | 6925.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6931.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6933.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6945.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6949.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6953.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6957.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6960.1464 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 6960.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 6961.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6961.6464 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 6962.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 6963.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6968.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6969.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6973.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6977.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6980.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6984.1464 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 6988.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 6989.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 6994.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 6995.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 6998.9022 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7003.9022 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7008.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7008.9022 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 40 | 283333.3333 | ACTION | 7035.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 41 | 290416.6667 | ACTION | 7035.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 28 | 116666.6667 | ACTION | 7036.9022 | MooringSystemInstallation
| Towing Group 1 | Delay | 22 | 155833.3333 | ACTION | 7057.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 126 | 892500 | ACTION | 7057.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 22 | 155833.3333 | ACTION | 7057.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 22 | 91666.6667 | ACTION | 7058.9022 | MooringSystemInstallation
| Towing Group 3 | Transit | 12.9131 | 91467.5893 | ACTION | 7070.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 13.9131 | 98550.9226 | ACTION | 7071.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7080.1464 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 9.3537 | 66255.0622 | ACTION | 7080.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7086.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7088.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7100.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7104.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 47.4783 | 197826.25 | ACTION | 7106.3805 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7108.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7108.3805 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7112.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7112.3805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7116.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7128.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7128.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7128.5405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7131.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7132.7005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7134.7005 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7135.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7138.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7138.7005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7154.8605 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7159.0205 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7161.0205 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7162.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7165.0205 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7181.1805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7185.3405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7187.3405 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7191.3405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 7194.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 7196.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 7202.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7207.5005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7211.6605 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7213.6605 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7217.6605 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 7222.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 7223.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 7225.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 7228.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 7231.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7233.8205 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7234.6464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 163.3537 | 1157088.3956 | ACTION | 7234.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7237.9805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7239.9805 | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7240.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7242.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7243.9805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 120416.6667 | ACTION | 7248.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7254.6464 | MooredSubInstallation
| Towing Group 2 | Transit | 26 | 184166.6667 | ACTION | 7254.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7258.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7262.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7266.6464 | MooredSubInstallation
| Towing Group 1 | Delay | 28 | 198333.3333 | ACTION | 7268.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 14 | 99166.6667 | ACTION | 7268.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 26 | 108333.3333 | ACTION | 7269.9805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7270.6464 | MooredSubInstallation
| Towing Group 3 | Delay | 34 | 240833.3333 | ACTION | 7282.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7282.6464 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 21250 | ACTION | 7285.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7286.1405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7286.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7289.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7290.3005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 7291.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7293.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7296.1464 | MooredSubInstallation
| Towing Group 2 | Transit | 27.9131 | 197717.5893 | ACTION | 7296.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7317.1464 | MooredSubInstallation
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 7345.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 7365.7788 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7370.7788 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7375.7788 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7389.1464 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 92.3537 | 654171.7289 | ACTION | 7389.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7395.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7397.1464 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 7405.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 7407.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7409.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7413.1464 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 7413.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7417.1464 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 35416.6667 | ACTION | 7418.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 55 | 229166.6667 | ACTION | 7430.7788 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7464.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 50 | 0 | ACTION | 7467.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7471.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 7475.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7479.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7491.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7494.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7498.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 9 | 0 | ACTION | 7507.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7510.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7534.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 131 | 545833.3333 | ACTION | 7561.7788 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 37 | 0 | ACTION | 7571.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 20.4783 | 85326.25 | ACTION | 7582.2571 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7584.2571 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 30 | 125000 | ACTION | 7614.2571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7618.2571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 204 | 1445000 | ACTION | 7622.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7632.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7634.4171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 106250 | ACTION | 7637.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7638.5771 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7640.5771 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7643.6464 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 298.3537 | 2113338.3956 | ACTION | 7643.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 7643.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7644.5771 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7649.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7651.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7660.7371 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7663.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7664.8971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7666.8971 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7667.6464 | MooredSubInstallation
| Towing Group 1 | Transit | 24 | 170000 | ACTION | 7667.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7670.8971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 7675.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7679.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7683.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7687.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7699.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7703.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7706.6464 | MooredSubInstallation
| Towing Group 1 | Delay | 41 | 290416.6667 | ACTION | 7708.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 39 | 162500 | ACTION | 7709.8971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7710.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7726.0571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7730.2171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7732.2171 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7734.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7736.2171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 29.9131 | 211884.256 | ACTION | 7738.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 22 | 91666.6667 | ACTION | 7758.2171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7774.3771 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7778.5371 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7780.5371 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7784.5371 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7800.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7800.6971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7804.8571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7806.1464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 67.3537 | 477088.3956 | ACTION | 7806.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7806.8571 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7810.8571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7812.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7814.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7826.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7827.0171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7830.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7831.1771 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7834.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7838.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7842.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7854.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7857.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7861.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7864.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 45 | 187500 | ACTION | 7876.1771 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 7878.1771 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7888.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 30.4783 | 126992.9167 | ACTION | 7908.6554 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7913.6554 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7918.6554 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7960.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7968.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7968.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7980.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7984.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7988.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7992.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 7994.1337 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7996.1337 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7996.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8000.1337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8008.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8012.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8015.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8019.1464 | MooredSubInstallation
| Towing Group 3 | Delay | 372 | 2635000 | ACTION | 8021.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 22 | 91666.6667 | ACTION | 8022.1337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 627 | 4441250 | ACTION | 8022.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 210 | 1487500 | ACTION | 8022.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8038.2937 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8042.4537 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8043.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8044.4537 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8048.4537 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8064.6137 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8068.7737 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8070.7737 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8074.7737 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8090.9337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8095.0937 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8097.0937 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8101.0937 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8115.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8117.2537 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8121.4137 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8123.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8123.4137 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8127.4137 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8135.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8136.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8139.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8143.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8143.5737 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8147.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8147.7337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8149.7337 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8151.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8153.7337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 8158.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 8159.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 8159.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8163.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8166.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8169.8937 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8170.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8173.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8174.0537 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 31 | 219583.3333 | ACTION | 8190.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 31 | 219583.3333 | ACTION | 8190.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 32 | 226666.6667 | ACTION | 8190.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 8192.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 8192.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 8192.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8197.6464 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 8198.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 8198.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 8198.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 37 | 154166.6667 | ACTION | 8211.0537 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 8222.0537 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 29 | 120833.3333 | ACTION | 8251.0537 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8269.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8277.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 32 | 133333.3333 | ACTION | 8283.0537 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4 | 16666.6667 | ACTION | 8287.0537 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8289.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8304.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 18 | 0 | ACTION | 8307.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8311.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8315.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 8326.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8330.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 26 | 0 | ACTION | 8356.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8360.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 25 | 0 | ACTION | 8385.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8397.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8401.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8404.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8408.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8432.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8472.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 60 | 0 | ACTION | 8492.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 255 | 1062500 | ACTION | 8542.0537 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 5.4783 | 22826.25 | ACTION | 8547.532 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8552.532 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8564.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 8565.532 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8570.532 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8572.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8584.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 17 | 70833.3333 | ACTION | 8587.532 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8588.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8592.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 5 | 20833.3333 | ACTION | 8592.532 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8596.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 6 | 25000 | ACTION | 8598.532 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8600.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8640.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 55 | 0 | ACTION | 8655.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8667.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 72 | 300000 | ACTION | 8670.532 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8670.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8674.1464 | MooredSubInstallation
| Towing Group 2 | Delay | 478 | 3385833.3333 | ACTION | 8676.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 478 | 3385833.3333 | ACTION | 8676.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 478 | 3385833.3333 | ACTION | 8676.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8677.6464 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 8696.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 8696.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 8696.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 1 | 7083.3333 | ACTION | 8697.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 1 | 7083.3333 | ACTION | 8697.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 1 | 7083.3333 | ACTION | 8697.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8701.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 48 | 200000 | ACTION | 8718.532 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8808.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 146 | 0 | ACTION | 8847.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 169 | 704166.6667 | ACTION | 8887.532 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.4783 | 18659.5833 | ACTION | 8892.0103 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8894.0103 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8919.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8927.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 42 | 175000 | ACTION | 8936.0103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8939.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8940.0103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8943.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8947.6464 | MooredSubInstallation
| Towing Group 2 | Delay | 252 | 1785000 | ACTION | 8949.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 252 | 1785000 | ACTION | 8949.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 252 | 1785000 | ACTION | 8949.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8951.6464 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 5 | 35416.6667 | ACTION | 8954.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 5 | 35416.6667 | ACTION | 8954.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 5 | 35416.6667 | ACTION | 8954.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8955.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8956.1703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8960.3303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8962.3303 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8966.3303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8967.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8971.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8974.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8976.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8978.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8982.4903 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 32 | 226666.6667 | ACTION | 8986.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 32 | 226666.6667 | ACTION | 8986.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8986.6503 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 32 | 226666.6667 | ACTION | 8986.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 2 | 14166.6667 | ACTION | 8988.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 2 | 14166.6667 | ACTION | 8988.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8988.6503 | MooringSystemInstallation
| Towing Group 3 | Delay | 2 | 14166.6667 | ACTION | 8988.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 4 | 28333.3333 | ACTION | 8992.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 4 | 28333.3333 | ACTION | 8992.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8992.6503 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 4 | 28333.3333 | ACTION | 8992.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 2 | 14166.6667 | ACTION | 8994.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 2 | 14166.6667 | ACTION | 8994.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 2 | 14166.6667 | ACTION | 8994.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9002.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9008.8103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 15 | 106250 | ACTION | 9009.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 15 | 106250 | ACTION | 9009.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 15 | 106250 | ACTION | 9009.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 45 | 0 | ACTION | 9047.1464 | MooredSubInstallation
| Towing Group 2 | Delay | 44 | 311666.6667 | ACTION | 9053.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 44 | 311666.6667 | ACTION | 9053.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 44 | 311666.6667 | ACTION | 9053.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 46 | 191666.6667 | ACTION | 9054.8103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 2.9131 | 20634.256 | ACTION | 9056.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 2.9131 | 20634.256 | ACTION | 9056.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 2.9131 | 20634.256 | ACTION | 9056.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9058.9703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9060.9703 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9062.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9062.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9062.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9064.9703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9081.1303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9085.2903 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9087.2903 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9091.2903 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9107.4503 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9111.6103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9113.6103 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9117.6103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9119.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9127.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9133.7703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9137.9303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9139.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9143.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9144.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9147.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9151.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9155.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9167.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9170.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9174.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9177.6464 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 9199.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 9199.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 9200.0261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 9201.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 9201.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9201.6464 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 9202.0261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9207.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9207.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9208.0261 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 9213.4086 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9218.4086 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9223.4086 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 9227.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 9227.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 9228.0261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 9233.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 9233.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 9234.0261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 12 | 85000 | ACTION | 9245.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 12 | 85000 | ACTION | 9245.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 12 | 85000 | ACTION | 9246.0261 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 25 | 104166.6667 | ACTION | 9248.4086 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 85 | 0 | ACTION | 9286.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9312.1464 | MooredSubInstallation
| Towing Group 2 | Delay | 112 | 793333.3333 | ACTION | 9357.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 112 | 793333.3333 | ACTION | 9357.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 112 | 793333.3333 | ACTION | 9358.0261 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 110 | 458333.3333 | ACTION | 9358.4086 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9358.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9366.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9378.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9382.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9386.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9390.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9394.6464 | MooredSubInstallation
| Towing Group 2 | Transit | 41.9131 | 296884.256 | ACTION | 9399.4391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 41.9131 | 296884.256 | ACTION | 9399.4391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 41.9131 | 296884.256 | ACTION | 9399.9391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9405.4391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9405.4391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9405.9391 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9406.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 50.4783 | 210326.25 | ACTION | 9408.8869 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9410.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9410.8869 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9413.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9414.8869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9417.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9431.0469 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9435.2069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9437.2069 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9441.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9441.2069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9457.3669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9461.5269 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9463.5269 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9467.5269 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9480.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9483.6869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9487.8469 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9489.8469 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9493.8469 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9510.0069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9513.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9514.1669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9516.1669 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9520.1669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9521.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9533.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9536.3269 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9537.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9540.4869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9541.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9542.4869 | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 9542.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 9542.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 9543.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9545.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9546.4869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9549.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 17 | 70833.3333 | ACTION | 9563.4869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9579.6469 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 15 | 62500 | ACTION | 9594.6469 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9598.8069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 53 | 0 | ACTION | 9602.1464 | MooredSubInstallation
| Towing Group 3 | Delay | 61 | 432083.3333 | ACTION | 9604.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 62 | 439166.6667 | ACTION | 9604.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 62 | 439166.6667 | ACTION | 9604.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 9606.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 9606.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 9606.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9612.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9612.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9612.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9614.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9617.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9621.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9624.6464 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 9632.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 9632.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 9632.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 9638.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 9638.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 9638.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9648.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9648.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 9674.2852 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9679.2852 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9684.2852 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 9692.0855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 9692.5855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 9692.5855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9698.0855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9698.5855 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9720.6464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 28.061 | 198765.1867 | ACTION | 9720.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9726.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9728.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9740.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9744.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9748.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9752.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9756.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 9759.7635 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9761.7635 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9765.7635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9768.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9772.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9775.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9779.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9781.9235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9786.0835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9788.0835 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9792.0835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9803.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9808.2435 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9812.4035 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9814.4035 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9816.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9818.4035 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9834.5635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 9835.3187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 9835.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 9837.3187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 9837.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9838.7235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9840.7235 | MooringSystemInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9843.3187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9843.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9844.7235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 9845.3187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 9845.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 51 | 0 | ACTION | 9854.1464 | MooredSubInstallation
| Towing Group 3 | Delay | 13 | 92083.3333 | ACTION | 9858.3187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 13 | 92083.3333 | ACTION | 9858.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9860.8835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9865.0435 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9867.0435 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9871.0435 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 120416.6667 | ACTION | 9875.3187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 120416.6667 | ACTION | 9875.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9887.2035 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 12 | 50000 | ACTION | 9899.2035 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9903.3635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9905.3635 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9909.3635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 35 | 247916.6667 | ACTION | 9910.3187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 35 | 247916.6667 | ACTION | 9910.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 9911.3187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 9911.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 9917.3187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 9917.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9925.5235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9926.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9929.6835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9934.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9946.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9950.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9954.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9958.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9962.1464 | MooredSubInstallation
| Towing Group 3 | Transit | 46 | 325833.3333 | ACTION | 9963.3187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 46 | 325833.3333 | ACTION | 9963.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 35 | 145833.3333 | ACTION | 9964.6835 | MooringSystemInstallation
| Towing Group 3 | Delay | 7 | 49583.3333 | ACTION | 9970.3187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 7 | 49583.3333 | ACTION | 9970.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 9971.6835 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9974.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9977.6464 | MooredSubInstallation
| Towing Group 3 | Transit | 7.9131 | 56050.9226 | ACTION | 9978.2318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 7.9131 | 56050.9226 | ACTION | 9978.7318 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9981.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9984.1464 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9984.2318 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9984.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 36 | 150000 | ACTION | 10007.6835 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10008.6464 | MooredSubInstallation
| Towing Group 3 | Delay | 54 | 382500 | ACTION | 10038.2318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 312 | 2210000 | ACTION | 10038.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 32 | 133333.3333 | ACTION | 10039.6835 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.4783 | 18659.5833 | ACTION | 10044.1618 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10049.1618 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10054.1618 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10080.6464 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 101.9146 | 721895.2489 | ACTION | 10080.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 10086.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10088.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10100.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10104.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10108.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10112.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10116.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10128.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 10129.6401 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10131.6401 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10132.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10135.6401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10135.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10139.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10151.8001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10152.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10155.9601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10157.9601 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10161.9601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10163.1464 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 10175.4651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 10175.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 10177.4651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 10177.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10178.1201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10182.2801 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 10183.4651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 10183.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10184.2801 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10188.2801 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 10203.4651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 10203.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10204.4401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10208.6001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 10209.4651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 10209.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10210.6001 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10214.6001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 10223.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10230.7601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10234.9201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10235.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10236.9201 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10240.9201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10243.1464 | MooredSubInstallation
| Towing Group 3 | Transit | 40 | 283333.3333 | ACTION | 10249.4651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 40 | 283333.3333 | ACTION | 10249.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 3 | 21250 | ACTION | 10252.4651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 3 | 21250 | ACTION | 10252.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 10253.9201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10255.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10259.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10263.1464 | MooredSubInstallation
| Towing Group 3 | Transit | 13.9131 | 98550.9226 | ACTION | 10266.3782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 13.9131 | 98550.9226 | ACTION | 10266.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10267.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10270.0801 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10271.1464 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 10272.3782 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10274.2401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10276.2401 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10280.2401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10283.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 10286.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10289.6464 | MooredSubInstallation
| Towing Group 2 | Delay | 69 | 488750 | ACTION | 10292.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10293.1464 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 10294.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10296.4001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10296.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10300.5601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 10300.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10320.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10320.6464 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 10320.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 10326.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 10376.0384 | MooringSystemInstallation
| Towing Group 2 | Transit | 53 | 375416.6667 | ACTION | 10379.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10381.0384 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10386.0384 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 11 | 77916.6667 | ACTION | 10390.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 0.91307 | 6467.5893 | ACTION | 10391.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10392.6464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 125.8537 | 891463.3956 | ACTION | 10392.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 10398.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10400.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10412.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10416.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10420.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10424.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10428.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10440.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10444.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10447.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10451.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 10461.5167 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10463.5167 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10488.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 67 | 0 | ACTION | 10518.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10542.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10614.1464 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 222.3537 | 1575005.0622 | ACTION | 10614.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 4 | 28333.3333 | ACTION | 10618.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 155 | 645833.3333 | ACTION | 10618.5167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10622.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10622.5167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 10624.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10634.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10638.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10638.6767 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10642.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10642.8367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10644.8367 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10646.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10650.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10656.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10662.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10665.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10669.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 27 | 112500 | ACTION | 10671.8367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10672.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10675.8367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10691.9967 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10696.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 47 | 195833.3333 | ACTION | 10738.9967 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10743.1567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10745.1567 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10749.1567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10765.3167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10768.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10769.4767 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10771.4767 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10775.4767 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10776.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10788.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10791.6367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10792.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10795.7967 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10796.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10797.7967 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10800.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10801.7967 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10804.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10816.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10824.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 20 | 0 | ACTION | 10836.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10840.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 39 | 162500 | ACTION | 10840.7967 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10843.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 10849.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10853.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10856.9567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10861.1167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10863.1167 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10867.1167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10877.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10883.2767 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10887.4367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10949.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 69 | 287500 | ACTION | 10956.4367 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10957.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10969.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10973.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10977.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10981.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10985.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 33 | 137500 | ACTION | 10989.4367 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10992.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 6.4783 | 26992.9167 | ACTION | 10995.915 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10997.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11000.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11000.915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11004.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11005.915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11007.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 17 | 70833.3333 | ACTION | 11022.915 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 11024.915 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11031.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 58.4783 | 243659.5833 | ACTION | 11083.3933 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11085.3933 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11089.3933 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11103.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11105.5533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11109.7133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11111.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11111.7133 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 10 | 41666.6667 | ACTION | 11121.7133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11123.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11125.7133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11127.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11131.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11135.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11139.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11141.8733 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11146.0333 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11148.0333 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11151.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11152.0333 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11155.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11158.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11160.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11162.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11168.1933 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11172.3533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11174.3533 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11178.3533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11186.1464 | MooredSubInstallation
| Towing Group 3 | Delay | 956 | 6771666.6667 | ACTION | 11228.3782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 830 | 5879166.6667 | ACTION | 11228.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 605 | 4285416.6667 | ACTION | 11229.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 51 | 212500 | ACTION | 11229.3533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11245.5133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11249.6733 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11251.6733 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11255.6733 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11258.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11266.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11271.8333 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11275.9933 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11277.9933 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11278.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11281.9933 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11282.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11286.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11290.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11294.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11298.1533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11302.3133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11306.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11309.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11313.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11316.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11328.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11340.6464 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 11365.6114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 11365.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 11366.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 11367.6114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 11367.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 11368.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11373.6114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11373.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11374.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 11377.7916 | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 56666.6667 | ACTION | 11382.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 63750 | ACTION | 11382.6114 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11382.7916 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 63750 | ACTION | 11382.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11387.7916 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11412.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11420.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11432.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11436.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 50 | 208333.3333 | ACTION | 11437.7916 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11440.6464 | MooredSubInstallation
| Towing Group 2 | Delay | 61 | 432083.3333 | ACTION | 11443.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 61 | 432083.3333 | ACTION | 11443.6114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 61 | 432083.3333 | ACTION | 11443.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11444.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11448.6464 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 77916.6667 | ACTION | 11454.6114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 77916.6667 | ACTION | 11454.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 85000 | ACTION | 11455.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 11460.6114 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11460.6464 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 11460.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 11461.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 1 | 7083.3333 | ACTION | 11462.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 2 | 14166.6667 | ACTION | 11462.6114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 2 | 14166.6667 | ACTION | 11462.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 8 | 56666.6667 | ACTION | 11470.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 8 | 56666.6667 | ACTION | 11470.6114 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 10 | 0 | ACTION | 11470.6464 | MooredSubInstallation
| Towing Group 1 | Delay | 8 | 56666.6667 | ACTION | 11470.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11474.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11477.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11481.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11496.1464 | MooredSubInstallation
| Towing Group 2 | Transit | 29 | 205416.6667 | ACTION | 11499.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 29 | 205416.6667 | ACTION | 11499.6114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 29 | 205416.6667 | ACTION | 11499.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 63 | 262500 | ACTION | 11500.7916 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11505.1464 | MooredSubInstallation
| Towing Group 2 | Delay | 28 | 198333.3333 | ACTION | 11527.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 28 | 198333.3333 | ACTION | 11527.6114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 28 | 198333.3333 | ACTION | 11527.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 28 | 116666.6667 | ACTION | 11528.7916 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 12.4783 | 51992.9167 | ACTION | 11541.2699 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11543.2699 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11547.2699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 22.9131 | 162300.9226 | ACTION | 11550.5245 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 22.9131 | 162300.9226 | ACTION | 11550.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 23.9131 | 169384.256 | ACTION | 11551.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11556.5245 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11556.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11557.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11563.4299 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11567.5899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11569.5899 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11573.5899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 82 | 0 | ACTION | 11587.1464 | MooredSubInstallation
| Towing Group 2 | Delay | 32 | 226666.6667 | ACTION | 11589.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 33 | 233750 | ACTION | 11589.5245 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11589.7499 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 33 | 233750 | ACTION | 11589.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11593.9099 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11595.9099 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11599.9099 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11616.0699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11620.2299 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11622.2299 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11626.2299 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11642.3899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11646.5499 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11648.5499 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11652.5499 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11659.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11664.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11667.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11668.7099 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11672.8699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11674.8699 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11678.8699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11679.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11683.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11687.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11691.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11695.0299 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11695.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11699.1899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11707.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11710.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11714.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11717.6464 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 11726.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 11726.7578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 11727.0261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 11728.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 11728.7578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 11729.0261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11734.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11734.7578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11735.0261 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11741.6464 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 11754.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 11754.7578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 11755.0261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 11760.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 11760.7578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 11761.0261 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 11774.6682 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11779.6682 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11784.6682 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11813.6464 | MooredSubInstallation
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 11814.4391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 11814.6708 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 11814.9391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11820.4391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11820.6708 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11820.9391 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11821.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11832.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11833.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11837.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11841.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11845.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11849.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 11860.1465 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11861.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11862.1465 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11865.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11866.1465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11868.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11872.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11882.3065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11886.4665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11888.4665 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11892.4665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11896.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11908.6265 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11912.7865 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11914.7865 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11918.7865 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11934.9465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11939.1065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11941.1065 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11945.1065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 11957.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 11957.9041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 11958.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 11959.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 11959.9041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 11960.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11961.2665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11965.4265 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11965.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11965.9041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11966.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11967.4265 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11968.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11971.4265 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11976.1464 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 11985.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 11985.9041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 11986.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11987.5865 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11988.1464 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 11991.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11991.7465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 11991.9041 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11992.1464 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 11992.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11993.7465 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11996.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11997.7465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12000.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12000.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12004.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12013.9065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12016.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12018.0665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 35 | 247916.6667 | ACTION | 12027.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 36 | 255000 | ACTION | 12027.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 36 | 255000 | ACTION | 12027.9041 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 13 | 54166.6667 | ACTION | 12031.0665 | MooringSystemInstallation
| Towing Group 1 | Delay | 51 | 361250 | ACTION | 12078.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 51 | 361250 | ACTION | 12078.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 51 | 361250 | ACTION | 12078.9041 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 48 | 200000 | ACTION | 12079.0665 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 73 | 0 | ACTION | 12089.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12092.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12096.1464 | MooredSubInstallation
| Towing Group 2 | Transit | 17.9131 | 126884.256 | ACTION | 12096.5855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 17.9131 | 126884.256 | ACTION | 12096.8172 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 18.9131 | 133967.5893 | ACTION | 12097.0855 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 12098.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12101.6464 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12102.5855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12102.8172 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12125.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 62.4783 | 260326.25 | ACTION | 12141.5448 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12146.5448 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12151.5448 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12168.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12197.6464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 100.561 | 712306.8534 | ACTION | 12197.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 29.5 | 0 | ACTION | 12197.6464 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12203.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12205.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12217.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12221.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12225.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 12227.0231 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12229.0231 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12229.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12233.0231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12233.6464 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 12239.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 12240.0505 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 12241.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 12242.0505 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12245.6464 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12247.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12248.0505 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12249.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12249.1831 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12252.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12253.3431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12255.3431 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12256.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12259.3431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 12267.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 12268.0505 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 12273.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 12274.0505 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12275.5031 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12279.6631 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12280.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12281.6631 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12285.6631 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12301.8231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12305.9831 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12307.9831 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12311.9831 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 12327.7318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 12327.9635 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12328.1431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12332.3031 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12334.3031 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12338.3031 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 12340.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 4 | 28333.3333 | ACTION | 12344.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 12346.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12352.1464 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 24.4146 | 172936.9156 | ACTION | 12352.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12352.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12354.4631 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12358.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12358.6231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12360.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12360.6231 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12364.6231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12365.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12372.1464 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 12372.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12376.1464 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 12378.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12380.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12380.7831 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12384.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12384.9431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12388.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12400.1464 | MooredSubInstallation
| Towing Group 1 | Transit | 28 | 198333.3333 | ACTION | 12406.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 27 | 112500 | ACTION | 12411.9431 | MooringSystemInstallation
| Towing Group 1 | Delay | 54 | 382500 | ACTION | 12460.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 61 | 0 | ACTION | 12461.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 50 | 208333.3333 | ACTION | 12461.9431 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12464.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12468.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12471.6464 | MooredSubInstallation
| Towing Group 1 | Transit | 25.9131 | 183550.9226 | ACTION | 12486.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12495.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 48.4783 | 201992.9167 | ACTION | 12510.4214 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12515.4214 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12520.4214 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12533.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12567.6464 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 239.6829 | 1697753.8934 | ACTION | 12567.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 34 | 0 | ACTION | 12567.6464 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12573.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12575.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 60 | 250000 | ACTION | 12580.4214 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12587.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 9 | 0 | ACTION | 12596.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12600.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12604.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12608.6464 | MooredSubInstallation
| Towing Group 3 | Delay | 37 | 262083.3333 | ACTION | 12610.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 253 | 1792083.3333 | ACTION | 12611.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 31 | 129166.6667 | ACTION | 12611.4214 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12612.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12624.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 15.4783 | 64492.9167 | ACTION | 12626.8997 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12628.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12628.8997 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12631.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12632.8997 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12635.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12649.0597 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12653.2197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12655.2197 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12659.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12659.2197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12675.3797 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12679.5397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12681.5397 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12685.5397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12701.6997 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12705.8597 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12707.8597 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12711.8597 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12728.0197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12731.1464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 244.3537 | 1730838.3956 | ACTION | 12731.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12732.1797 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12734.1797 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12735.6464 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12737.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12738.1797 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12739.1464 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 12747.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 12748.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 12749.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 12750.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12751.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12754.3397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12755.1464 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12755.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12756.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12758.4997 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12759.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12760.4997 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12763.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12764.4997 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12767.1464 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 12775.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 12776.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12779.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12780.6597 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 12781.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 12782.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12782.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12784.8197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12786.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12789.6464 | MooredSubInstallation
| Towing Group 2 | Transit | 26 | 184166.6667 | ACTION | 12808.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 27 | 191250 | ACTION | 12808.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 4 | 28333.3333 | ACTION | 12812.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 4 | 28333.3333 | ACTION | 12812.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 1 | 7083.3333 | ACTION | 12813.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12813.6464 | MooredSubInstallation
| Towing Group 3 | Transit | 1 | 7083.3333 | ACTION | 12813.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 12 | 85000 | ACTION | 12825.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 12 | 85000 | ACTION | 12825.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 25.9131 | 183550.9226 | ACTION | 12851.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 26.9131 | 190634.256 | ACTION | 12852.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 12860.298 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12865.298 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12870.298 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12885.6464 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 33.8537 | 239796.7289 | ACTION | 12885.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12891.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12893.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12903.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12905.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 67 | 279166.6667 | ACTION | 12937.298 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 12948.298 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.4783 | 35326.25 | ACTION | 12956.7763 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12958.7763 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12962.7763 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 12969.7763 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 68 | 0 | ACTION | 12973.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12977.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12981.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12985.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12985.9363 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12989.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12990.0963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12992.0963 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12996.0963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13001.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 13005.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13009.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13012.2563 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13012.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13016.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13016.4163 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13018.4163 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13022.4163 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13038.5763 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13040.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13042.7363 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13044.7363 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13048.7363 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13064.8963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13069.0563 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13071.0563 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13071.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13075.0563 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 184 | 1303333.3333 | ACTION | 13075.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 339 | 2401250 | ACTION | 13076.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13091.2163 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13095.3763 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13097.3763 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13101.3763 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13112.1464 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 259.8537 | 1840630.0622 | ACTION | 13112.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 40.5 | 0 | ACTION | 13112.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13117.5363 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13118.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13120.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13121.6963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13132.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13136.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13140.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13144.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13148.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13160.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 13187.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13190.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 13197.1746 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 13202.1746 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 13207.1746 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 13212.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 13213.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 13214.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 13215.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 30 | 0 | ACTION | 13220.6464 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13220.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13221.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13224.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13227.6464 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13240.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13241.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 13246.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 13247.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13251.6464 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 13255.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 13257.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13263.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13280.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 13282.6529 | MooringSystemInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13283.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13284.6529 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13288.6529 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 13289.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 13300.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 13301.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13304.8129 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13308.9729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13310.9729 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13314.9729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13323.6464 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 22.8537 | 161880.0622 | ACTION | 13323.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 43.5 | 0 | ACTION | 13323.6464 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13329.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13331.1329 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13331.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13335.2929 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13337.2929 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13341.2929 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 13343.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13343.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13347.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13351.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13355.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13357.4529 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13359.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13361.6129 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13363.6129 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13367.6129 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13371.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13375.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13378.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13382.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13383.7729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13387.9329 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13389.9329 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13393.9329 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13406.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13410.0929 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13414.2529 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13416.2529 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13420.2529 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13436.4129 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13440.5729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 13466.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 13468.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13474.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13478.1464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 176.8537 | 1252713.3956 | ACTION | 13478.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13484.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13486.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13491.6464 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13494.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13498.1464 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 13500.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13502.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13506.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13510.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13514.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 13516.0512 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 13521.0512 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 13526.0512 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13526.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 13531.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13534.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13538.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 13544.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13547.6464 | MooredSubInstallation
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 13554.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13571.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 13601.5295 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13603.5295 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13607.5295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13623.6895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13627.8495 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13629.8495 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13633.8495 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13643.6464 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 300.3537 | 2127505.0622 | ACTION | 13643.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13651.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13659.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13663.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 13676.6464 | MooredSubInstallation
| Towing Group 2 | Delay | 35 | 247916.6667 | ACTION | 13678.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 195 | 1381250 | ACTION | 13679.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 46 | 191666.6667 | ACTION | 13679.8495 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13680.6464 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13684.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13684.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13688.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13692.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13696.0095 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13700.1695 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13702.1695 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13704.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13706.1695 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13722.3295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13726.4895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13728.4895 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13732.4895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 30 | 0 | ACTION | 13734.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13738.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13741.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13745.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13748.6495 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13752.8095 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13754.8095 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13758.8095 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13769.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13774.9695 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13779.1295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13781.1295 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13785.1295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13801.2895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13805.4495 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 13816.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 13818.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 13821.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 13823.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13824.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13827.6464 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13829.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13841.1464 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 286.3537 | 2028338.3956 | ACTION | 13841.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 13.5 | 0 | ACTION | 13841.1464 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13844.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13847.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13849.1464 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13849.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 13850.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 13855.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13861.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13865.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13869.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13873.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13877.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 13880.9278 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 13885.9278 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13889.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13892.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13896.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13899.6464 | MooredSubInstallation
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 13904.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 13909.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13923.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 13961.4061 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13963.4061 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13967.4061 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13983.5661 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 13984.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 13986.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13987.7261 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13989.7261 | MooringSystemInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13992.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13993.7261 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13995.6464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 91.3537 | 647088.3956 | ACTION | 13995.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14001.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14003.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14009.1464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 14009.8861 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14012.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 14014.0461 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14015.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 14016.0461 | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 14018.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14019.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 14020.0461 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14023.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14027.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14031.6464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 14036.2061 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 14040.3661 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14043.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14047.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14050.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14054.1464 | MooredSubInstallation
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 14072.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14078.1464 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 14138.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 14140.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14146.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14150.1464 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 240.3537 | 1702505.0622 | ACTION | 14150.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14156.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14158.1464 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14166.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14170.1464 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 14172.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14174.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14177.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14178.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14182.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14186.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14198.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14201.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14205.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14208.6464 | MooredSubInstallation
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 14226.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14232.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14304.6464 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 232.3537 | 1645838.3956 | ACTION | 14304.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14312.6464 | MooredSubInstallation
| Towing Group 3 | Delay | 13 | 92083.3333 | ACTION | 14317.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 162 | 1147500 | ACTION | 14318.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14323.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14324.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14328.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14332.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14336.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14340.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14345.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14352.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14356.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14359.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14363.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14387.1464 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 14455.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 14457.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14459.1464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 232.3537 | 1645838.3956 | ACTION | 14459.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 14460.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 14462.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14463.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14465.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14467.1464 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14468.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14479.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14483.1464 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14483.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14487.1464 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14488.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 14489.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14491.1464 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 14494.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14495.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14507.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14510.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14513.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14514.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14517.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14541.6464 | MooredSubInstallation
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 14543.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 14548.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14613.6464 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 70.3537 | 498338.3956 | ACTION | 14613.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 149 | 1055416.6667 | ACTION | 14614.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14619.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14621.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14633.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14637.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14641.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14645.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14649.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14661.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14665.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14668.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14672.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14681.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14696.1464 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 14751.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 14753.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 14756.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 14758.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14759.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14764.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14768.1464 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 219.3537 | 1553755.0622 | ACTION | 14768.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14774.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14776.1464 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14779.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14784.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 14785.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14788.1464 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 14790.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14792.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14796.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14800.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14804.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14816.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14819.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14823.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14826.6464 | MooredSubInstallation
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 14839.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 53 | 375416.6667 | ACTION | 14843.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14849.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14850.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 43 | 0 | ACTION | 14893.6464 | MooredSubInstallation
| Towing Group 2 | Delay | 61 | 432083.3333 | ACTION | 14904.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 0.91307 | 6467.5893 | ACTION | 14905.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14965.6464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 126.3537 | 895005.0622 | ACTION | 14965.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14971.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14973.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14985.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 15012.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15016.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15017.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15020.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15024.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15028.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15040.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15044.1464 | MooredSubInstallation
| Towing Group 1 | Delay | 121 | 857083.3333 | ACTION | 15092.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 319 | 2259583.3333 | ACTION | 15093.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 54 | 0 | ACTION | 15098.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15101.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15105.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15129.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15185.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15201.1464 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 295.3537 | 2092088.3956 | ACTION | 15201.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 16 | 0 | ACTION | 15201.1464 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 15207.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15209.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15221.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15225.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15229.1464 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 15229.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 15230.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 15231.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 15232.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15233.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15237.1464 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 15237.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 15238.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15249.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15252.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15256.1464 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 15257.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 15258.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15259.6464 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 15263.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 15264.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15283.6464 | MooredSubInstallation
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 15317.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 15318.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 15344.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 15346.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 15352.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15355.6464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 37.8537 | 268130.0622 | ACTION | 15355.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 15361.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15363.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15369.1464 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 15372.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15375.6464 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 15378.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15379.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15383.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15387.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15391.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15403.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15407.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15410.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15414.1464 | MooredSubInstallation
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 15432.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15438.1464 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 15498.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15510.1464 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 191.8537 | 1358963.3956 | ACTION | 15510.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15518.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15530.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15534.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15537.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15538.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15542.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15546.1464 | MooredSubInstallation
| Towing Group 3 | Delay | 47 | 332916.6667 | ACTION | 15557.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15558.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15561.6464 | MooredSubInstallation
| Towing Group 1 | Delay | 64 | 453333.3333 | ACTION | 15562.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 15563.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 15564.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15565.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15568.6464 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 15570.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 49583.3333 | ACTION | 15577.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15592.6464 | MooredSubInstallation
| Towing Group 1 | Delay | 47 | 332916.6667 | ACTION | 15624.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 92083.3333 | ACTION | 15637.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 15643.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15664.6464 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 232.3537 | 1645838.3956 | ACTION | 15664.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 15670.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15672.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15684.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15688.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15692.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15696.6464 | MooredSubInstallation
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 15697.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15700.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15705.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15712.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15716.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15719.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15723.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15747.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15819.1464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 121.3537 | 859588.3956 | ACTION | 15819.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 15825.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15827.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15839.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15843.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15847.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15851.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15873.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 44 | 0 | ACTION | 15895.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15899.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15911.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15914.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15918.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15921.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15945.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 54 | 0 | ACTION | 15999.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16041.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16071.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 30.5 | 0 | ACTION | 16071.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16079.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16091.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16095.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16099.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16103.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16107.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16119.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16123.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16126.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16130.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16154.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16226.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16234.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16239.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16246.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16250.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 16258.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16262.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16266.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16270.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16282.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16285.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16289.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16292.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16316.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 69 | 0 | ACTION | 16385.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16407.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16457.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 50 | 0 | ACTION | 16457.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16465.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16477.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16481.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16485.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16489.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16493.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16505.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 16508.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16512.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16515.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16519.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16543.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16615.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16623.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16625.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16635.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16639.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16643.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16647.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16651.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16663.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16666.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16670.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16673.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16697.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 42 | 0 | ACTION | 16739.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16793.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16811.6464 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 18 | 0 | ACTION | 16811.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16819.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16831.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16835.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16839.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16843.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16847.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16859.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 23 | 0 | ACTION | 16882.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16886.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 20 | 0 | ACTION | 16906.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16909.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16913.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16937.1464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16979.6464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 52 | 0 | ACTION | 16989.1464 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17061.1464 | MooredSubInstallation
0.5 | Array Cable Installation Vessel | Mobilize | 72 | 337500 | ACTION | 18392.8489 | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 56250 | ACTION | 18398.8489 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 108 | 1012500 | ACTION | 18506.8489 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 45 | 421875 | ACTION | 18551.8489 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Delay | 3593 | 25450416.6667 | ACTION | 19263.6464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 3701 | 26215416.6667 | ACTION | 19264.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 3439 | 24359583.3333 | ACTION | 19264.1464 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 756 | 7087500 | ACTION | 19307.8489 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 3 | 28125 | ACTION | 19310.8489 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 2 | 18750 | ACTION | 19312.8489 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 17.6333 | 165312.2283 | ACTION | 19330.4822 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19332.4822 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19333.4822 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19338.9822 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 31 | 290625 | ACTION | 19369.9822 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19375.4822 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19376.4822 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 16.1123 | 151053.2152 | ACTION | 19392.5945 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19393.5945 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 19400.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 19401.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 19401.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 34 | 240833.3333 | ACTION | 19435.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 34 | 240833.3333 | ACTION | 19435.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 35 | 247916.6667 | ACTION | 19435.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 19437.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 19437.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 19437.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 19443.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 19443.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 19443.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 56 | 525000 | ACTION | 19449.5945 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19455.0945 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19460.5945 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19462.5945 | ArrayCableInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 19463.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 19463.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19463.5945 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 19463.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19469.0945 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 19469.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 19469.3797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 19469.8797 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19474.5945 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19475.5945 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 16.1123 | 151053.2152 | ACTION | 19491.7069 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19492.7069 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19498.2069 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19503.7069 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19505.7069 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19506.7069 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19512.2069 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 19523.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 19523.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay: No Assembly Storage Available | 2462.1463 | 0 | ACTION | 19523.2928 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 2543.6463 | 0 | ACTION | 19523.2928 | MooredSubInstallation
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 19523.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 19529.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 19529.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 19529.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 19531.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 19543.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 19554.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19558.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19562.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19566.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19570.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 19584.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 19596.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19599.7928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19603.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19606.7928 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 19630.7928 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 122 | 1143750 | ACTION | 19634.2069 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19639.7069 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19640.7069 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 19645.731 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19646.731 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19652.231 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19657.731 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19659.731 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19660.731 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 19691.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 19702.7928 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 11.5 | 0 | ACTION | 19702.7928 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 19710.7928 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 19722.7928 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 19 | 0 | ACTION | 19741.7928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19745.7928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19749.7928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19753.7928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19757.7928 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 98 | 918750 | ACTION | 19758.731 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19764.231 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19769.731 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 19769.7928 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19770.731 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19773.2928 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 19775.7551 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19776.7551 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19776.7928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19780.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 19804.2928 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 59 | 553125 | ACTION | 19835.7551 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19841.2551 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19846.7551 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19848.7551 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19849.7551 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19855.2551 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19860.7551 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19861.7551 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 19866.7792 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19867.7792 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 19876.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 19884.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 19896.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19900.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19904.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19908.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19912.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 19924.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19927.7928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19931.2928 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19934.7928 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 69 | 646875 | ACTION | 19936.7792 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19942.2792 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19947.7792 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19949.7792 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19950.7792 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19956.2792 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 19958.7928 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19961.7792 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19962.7792 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 19967.8033 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19968.8033 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19974.3033 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19979.8033 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19981.8033 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19982.8033 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 20030.7928 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 118 | 1106250 | ACTION | 20100.8033 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20106.3033 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20111.8033 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20112.8033 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20117.8274 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20118.8274 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20124.3274 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20129.8274 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20131.8274 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20132.8274 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20138.3274 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 100 | 937500 | ACTION | 20238.3274 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20243.8274 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20244.8274 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20249.8516 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20250.8516 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20256.3516 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 44 | 412500 | ACTION | 20300.3516 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20305.8516 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20307.8516 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20308.8516 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20314.3516 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20319.8516 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20320.8516 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20325.8757 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20326.8757 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20332.3757 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20337.8757 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20339.8757 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20340.8757 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20346.3757 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Delay | 853 | 6042083.3333 | ACTION | 20382.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 853 | 6042083.3333 | ACTION | 20382.2928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 853 | 6042083.3333 | ACTION | 20382.7928 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 47 | 440625 | ACTION | 20393.3757 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20398.8757 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20399.8757 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20404.8998 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20405.8998 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20411.3998 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20416.8998 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20418.8998 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20419.8998 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20425.3998 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20430.8998 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20431.8998 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20436.9239 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20437.9239 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20443.4239 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 61 | 571875 | ACTION | 20504.4239 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20509.9239 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20511.9239 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20512.9239 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20518.4239 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 20519.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 20519.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 20520.0261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 20521.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 20521.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 20522.0261 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20523.9239 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20524.9239 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 20527.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 20527.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 20528.0261 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20529.948 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20530.948 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20536.448 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20541.948 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20543.948 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20544.948 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 20547.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 20547.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 20548.0261 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20550.448 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 20553.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 20553.5261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 20554.0261 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20555.948 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20556.948 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20561.9721 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20562.9721 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20568.4721 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20573.9721 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20575.9721 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20576.9721 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 2 | 18750 | ACTION | 20578.9721 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20584.4721 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20589.9721 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20590.9721 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20595.9962 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20596.9962 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20602.4962 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 20607.4391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 20607.4391 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay: No Assembly Storage Available | 576.6463 | 0 | ACTION | 20607.4391 | MooredSubInstallation
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 20607.9391 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20607.9962 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20609.9962 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20610.9962 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 20613.4391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 20613.4391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 20613.9391 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 20615.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20616.4962 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20621.9962 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20622.9962 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 20627.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20628.0203 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20629.0203 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20631.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20634.5203 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20635.4391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20639.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20640.0203 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20642.0203 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20643.0203 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20643.4391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 20655.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 14 | 131250 | ACTION | 20657.0203 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20658.9391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20662.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20662.5203 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20665.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20668.0203 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20669.0203 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20674.0445 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20675.0445 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 20689.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 43 | 403125 | ACTION | 20718.0445 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20723.5445 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20729.0445 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20731.0445 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20732.0445 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20737.5445 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20743.0445 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20744.0445 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20749.0686 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20750.0686 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 20750.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 20750.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 20751.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 20752.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 20752.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 20753.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20755.5686 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 20758.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 20758.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 20759.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20761.0686 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 20761.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20763.0686 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20764.0686 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20769.5686 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 20769.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20775.0686 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20776.0686 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 20778.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 20778.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 20779.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20781.0927 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 20781.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20782.0927 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 20784.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 20784.6724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 20785.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20785.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20787.5927 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20789.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20793.0927 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20793.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20795.0927 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20796.0927 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20797.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20801.5927 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20807.0927 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20808.0927 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 20809.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20813.1168 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20813.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20814.1168 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20816.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20819.6168 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20820.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20825.1168 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20827.1168 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20828.1168 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20833.6168 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 20838.5855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 20838.5855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 20839.0855 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20839.1168 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20840.1168 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 20844.4391 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 20844.5855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 20844.5855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 20845.0855 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20845.1409 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20846.1409 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20851.6409 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20857.1409 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20859.1409 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20860.1409 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20865.6409 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20871.1409 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20872.1409 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20877.165 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20878.165 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20883.665 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20889.165 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20891.165 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20892.165 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20897.665 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20903.165 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20904.165 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20909.1891 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20910.1891 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20915.6891 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 20916.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20921.1891 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20923.1891 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20924.1891 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 20924.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20929.6891 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20935.1891 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20936.1891 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 20936.4391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20940.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20941.2132 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20942.2132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20944.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20947.7132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20948.4391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20952.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20953.2132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20955.2132 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20956.2132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20961.7132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 20964.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20967.2132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20967.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20968.2132 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 18750 | ACTION | 20970.2132 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20971.4391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20974.9391 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 20981.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 20981.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 20982.3187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 20983.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 20983.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 20984.3187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 20989.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 20989.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 20990.3187 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 20998.9391 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 21009.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 21009.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 21010.3187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 21015.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 21015.8187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 21016.3187 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 65 | 609375 | ACTION | 21035.2132 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 3.0241 | 28351.0518 | ACTION | 21038.2374 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21039.2374 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21044.7374 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21050.2374 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21052.2374 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21053.2374 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21058.7374 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21064.2374 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21065.2374 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 21069.7318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 21069.7318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 21070.2318 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21070.2615 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 21070.9391 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 0.70731 | 5010.1245 | ACTION | 21070.9391 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21071.2615 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 21075.7318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 21075.7318 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21076.7615 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 21076.9391 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 21078.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21082.2615 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21084.2615 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21085.2615 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21090.7615 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 21090.9391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21094.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21096.2615 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21097.2615 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21098.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21102.2856 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21102.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21103.2856 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 21106.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 14 | 131250 | ACTION | 21117.2856 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 21118.9391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21122.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21122.7856 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21125.9391 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21128.2856 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 21129.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21130.2856 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21131.2856 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21136.7856 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21142.2856 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21143.2856 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21148.3097 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21149.3097 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 21153.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21154.8097 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 21212.9651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 21212.9651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 21214.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 21214.9651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 21214.9651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 21216.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 21220.9651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 21220.9651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 21222.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 21225.4391 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 76 | 712500 | ACTION | 21230.8097 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21236.3097 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21238.3097 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21239.3097 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 21240.9651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 21240.9651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 21242.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21244.8097 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 21246.9651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 21246.9651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 21248.1724 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21250.3097 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21251.3097 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21256.3338 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21257.3338 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21262.8338 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21268.3338 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21270.3338 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21271.3338 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21276.8338 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21282.3338 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21283.3338 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21288.3579 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21289.3579 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 21300.8782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 21300.8782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 21302.0855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 21306.8782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 21444.1114 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 155 | 1453125 | ACTION | 21444.3579 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 21446.1114 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21449.8579 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 21452.1114 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21455.3579 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21457.3579 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21458.3579 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21463.8579 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21469.3579 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21470.3579 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 21472.1114 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21475.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21476.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 21478.1114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 9 | 63750 | ACTION | 21487.1114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 55 | 389583.3333 | ACTION | 21542.1114 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 91 | 853125 | ACTION | 21567.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21572.882 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21578.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21580.382 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21581.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21586.882 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 44.9131 | 318134.256 | ACTION | 21587.0245 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21592.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21593.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21598.4061 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21599.4061 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21604.9061 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21610.4061 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21612.4061 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21613.4061 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21618.9061 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21624.4061 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21625.4061 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21630.4302 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21631.4302 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21636.9302 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21642.4302 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21644.4302 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21645.4302 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21650.9302 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21656.4302 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21657.4302 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21662.4544 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21663.4544 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21668.9544 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21674.4544 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21676.4544 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21677.4544 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21682.9544 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21688.4544 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21689.4544 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21694.4785 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21695.4785 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21700.9785 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21706.4785 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21708.4785 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21709.4785 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21714.9785 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21720.4785 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21721.4785 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21726.5026 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21727.5026 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21733.0026 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21738.5026 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21740.5026 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21741.5026 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21747.0026 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21752.5026 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21753.5026 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21758.5267 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21759.5267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21765.0267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21770.5267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21772.5267 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21773.5267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21779.0267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21784.5267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21785.5267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21790.5508 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21791.5508 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21797.0508 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 81 | 759375 | ACTION | 21878.0508 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21883.5508 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21885.5508 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21886.5508 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21892.0508 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21897.5508 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21898.5508 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21903.5749 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21904.5749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21910.0749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21915.5749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21917.5749 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21918.5749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21924.0749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21929.5749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21930.5749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21935.599 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21936.599 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21942.099 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21947.599 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21949.599 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21950.599 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21956.099 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 132 | 1237500 | ACTION | 22088.099 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22093.599 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22094.599 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22099.6231 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22100.6231 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22106.1231 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22111.6231 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22113.6231 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22114.6231 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22120.1231 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22125.6231 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22126.6231 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22131.6473 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22132.6473 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22138.1473 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22143.6473 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22145.6473 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22146.6473 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22152.1473 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22157.6473 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22158.6473 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22163.6714 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22164.6714 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22170.1714 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22175.6714 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22177.6714 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22178.6714 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22184.1714 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22189.6714 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22190.6714 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22195.6955 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22196.6955 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22202.1955 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22207.6955 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22209.6955 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22210.6955 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22216.1955 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22221.6955 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22222.6955 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22227.7196 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22228.7196 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22234.2196 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22239.7196 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22241.7196 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22242.7196 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22248.2196 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22253.7196 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22254.7196 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22259.7437 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22260.7437 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22266.2437 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22271.7437 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22273.7437 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22274.7437 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22280.2437 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22285.7437 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22286.7437 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22291.7678 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22292.7678 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22298.2678 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22303.7678 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22305.7678 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22306.7678 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22312.2678 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22317.7678 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22318.7678 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22323.7919 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22324.7919 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22330.2919 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22335.7919 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22337.7919 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22338.7919 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22344.2919 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22349.7919 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22350.7919 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22355.816 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22356.816 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22362.316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22367.816 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22369.816 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22370.816 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22376.316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 43 | 403125 | ACTION | 22419.316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22424.816 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22425.816 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22430.8402 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22431.8402 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22437.3402 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22442.8402 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22444.8402 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22445.8402 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22451.3402 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22456.8402 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22457.8402 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22462.8643 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22463.8643 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22469.3643 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 150 | 1406250 | ACTION | 22619.3643 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22624.8643 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22626.8643 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22627.8643 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22633.3643 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22638.8643 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22639.8643 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22644.8884 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22645.8884 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22651.3884 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22656.8884 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22658.8884 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22659.8884 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22665.3884 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22670.8884 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22671.8884 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22676.9125 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22677.9125 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22683.4125 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22688.9125 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22690.9125 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22691.9125 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22697.4125 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22702.9125 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22703.9125 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22708.9366 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22709.9366 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22715.4366 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22720.9366 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22722.9366 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22723.9366 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22729.4366 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22734.9366 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22735.9366 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22740.9607 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22741.9607 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22747.4607 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22752.9607 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22754.9607 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22755.9607 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22761.4607 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22766.9607 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22767.9607 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22772.9848 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22773.9848 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22779.4848 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22784.9848 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22786.9848 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22787.9848 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22793.4848 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22798.9848 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22799.9848 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22805.0089 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22806.0089 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22811.5089 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22817.0089 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22819.0089 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22820.0089 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22825.5089 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22831.0089 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22832.0089 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22837.0331 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22838.0331 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22843.5331 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22849.0331 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22851.0331 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22852.0331 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22857.5331 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22863.0331 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22864.0331 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22869.0572 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22870.0572 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22875.5572 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 61 | 571875 | ACTION | 22936.5572 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22942.0572 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22944.0572 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22945.0572 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22950.5572 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22956.0572 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22957.0572 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22962.0813 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22963.0813 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22968.5813 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22974.0813 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22976.0813 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22977.0813 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22982.5813 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22988.0813 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22989.0813 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22994.1054 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22995.1054 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23000.6054 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23006.1054 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23008.1054 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23009.1054 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23014.6054 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23020.1054 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23021.1054 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 23026.1295 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23027.1295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23032.6295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23038.1295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23040.1295 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23041.1295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23046.6295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23052.1295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23053.1295 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 12.133 | 113746.4839 | ACTION | 23065.2625 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23066.2625 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 53 | 496875 | ACTION | 23119.2625 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23124.7625 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23130.2625 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23132.2625 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23133.2625 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23138.7625 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23144.2625 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23145.2625 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 12.133 | 113746.4839 | ACTION | 23157.3954 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23158.3954 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23163.8954 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23169.3954 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23171.3954 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23172.3954 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23177.8954 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23183.3954 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23184.3954 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8.3958 | 78710.3425 | ACTION | 23192.7912 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23193.7912 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23199.2912 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23204.7912 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23206.7912 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23207.7912 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23213.2912 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23218.7912 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23219.7912 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8.3958 | 78710.3425 | ACTION | 23228.187 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23229.187 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23234.687 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 97 | 909375 | ACTION | 23331.687 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23337.187 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23339.187 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23340.187 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23345.687 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23351.187 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23352.187 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.5199 | 51748.6401 | ACTION | 23357.7068 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23358.7068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23364.2068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23369.7068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23371.7068 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23372.7068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23378.2068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23383.7068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23384.7068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.5199 | 51748.6401 | ACTION | 23390.2267 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23391.2267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23396.7267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23402.2267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 3 | 28125 | ACTION | 23405.2267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 153 | 1434375 | ACTION | 23558.2267 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 62.6333 | 587187.2283 | ACTION | 23620.86 | ArrayCableInstallation | ArrayCableInstallation | FALSE