## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | include_onshore_construction | max_waveheight | max_windspeed | transit_speed | num_vessels | num_ahts_vessels
0.5 | Export Cable Installation Vessel | Mobilize | 72 | 450000 | ACTION | 0 | ExportCableInstallation
1 | Mooring System Installation Vessel | Mobilize | 168 | 700000 | ACTION | 0 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Load Cable | 6 | 75000 | ACTION | 6 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 1 | 4166.6667 | ACTION | 11 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 47 | 195833.3333 | ACTION | 58 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 16 | 66666.6667 | ACTION | 74 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 28 | 116666.6667 | ACTION | 102 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 20 | 83333.3333 | ACTION | 122 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 135 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 38.4783 | 160326.25 | ACTION | 173.4783 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 175.4783 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 179.4783 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 195.6383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 199.7983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 201.7983 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 205.7983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 212.7983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 228.9583 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 233.1183 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 235.1183 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 239.1183 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 150 | 625000 | ACTION | 389.1183 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 405.2783 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 409.4383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 411.4383 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 415.4383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 34 | 141666.6667 | ACTION | 449.4383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 465.5983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 469.7583 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 471.7583 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 475.7583 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 53 | 220833.3333 | ACTION | 528.7583 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 544.9183 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 549.0783 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 551.0783 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 555.0783 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 571.2383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 20 | 83333.3333 | ACTION | 591.2383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 595.3983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 24 | 100000 | ACTION | 619.3983 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 70 | 291666.6667 | ACTION | 689.3983 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 17 | 70833.3333 | ACTION | 706.3983 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 727.3983 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 34.4783 | 143659.5833 | ACTION | 761.8766 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 766.8766 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 771.8766 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 1 | 4166.6667 | ACTION | 772.8766 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 73 | 304166.6667 | ACTION | 845.8766 | MooringSystemInstallation
| Substation Assembly Line 1 | Substation Substructure Assembly | 336 | 0 | ACTION | 862.3679 | FloatingSubstationInstallation
| Substation Assembly Line 1 | Attach Topside | 24 | 0 | ACTION | 886.3679 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay: Waiting on Substation Assembly | 360 | 1500000 | ACTION | 886.3679 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 898 | 11225000 | ACTION | 904 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Tow Plow | 0.4 | 5000 | ACTION | 904.4 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Pull Winch | 0.4 | 5000 | ACTION | 904.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Prepare Cable | 1 | 12500 | ACTION | 905.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 911.3 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 916.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Lower Cable | 1 | 12500 | ACTION | 917.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Transit | 74.4783 | 310326.25 | ACTION | 920.3549 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 922.3549 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 5 | 62500 | ACTION | 922.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 926.3549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 87 | 362500 | ACTION | 1013.3549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1029.5149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1033.6749 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1035.6749 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1039.6749 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 128 | 1600000 | ACTION | 1050.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1055.8349 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1059.9949 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1061.9949 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 14 | 175000 | ACTION | 1064.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1065.9949 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1082.1549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 10 | 41666.6667 | ACTION | 1092.1549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1096.3149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1098.3149 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1102.3149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1118.4749 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 54 | 675000 | ACTION | 1118.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1122.6349 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1124.6349 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 8 | 100000 | ACTION | 1126.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1128.6349 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1144.7949 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1148.9549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1150.9549 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1154.9549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 274 | 1141666.6667 | ACTION | 1160.3679 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 6 | 25000 | ACTION | 1160.9549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1177.1149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1181.2749 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 60 | 750000 | ACTION | 1186.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 47 | 587500 | ACTION | 1233.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 1256.7532 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1261.7532 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1266.7532 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Tow Substation to Site | 125.7972 | 524154.8611 | ACTION | 1286.165 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1288.165 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1294.165 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1298.165 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 33 | 137500 | ACTION | 1299.7532 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 30 | 125000 | ACTION | 1328.165 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 29 | 120833.3333 | ACTION | 1328.7532 | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 1343.325 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1347.485 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1369.485 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 42.4783 | 176992.9167 | ACTION | 1371.2315 | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 2 | 8333.3333 | ACTION | 1371.485 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1373.2315 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1377.2315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1393.3915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1397.5515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1399.5515 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1403.5515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 39 | 162500 | ACTION | 1410.485 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1419.7115 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Check Mooring Lines | 10 | 41666.6667 | ACTION | 1420.485 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1423.8715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1424.485 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1425.8715 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1429.8715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 62 | 258333.3333 | ACTION | 1486.485 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 58 | 241666.6667 | ACTION | 1487.8715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 1501.645 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1504.0315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1505.805 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 1507.805 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1508.1915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 2 | 8333.3333 | ACTION | 1509.805 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1510.1915 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1514.1915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 14 | 58333.3333 | ACTION | 1528.1915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1544.3515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1548.5115 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1550.5115 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 44 | 183333.3333 | ACTION | 1553.805 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1554.5115 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 16 | 66666.6667 | ACTION | 1569.805 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1570.6715 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1574.8315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1576.8315 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1580.8315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1596.9915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1601.1515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 9 | 37500 | ACTION | 1610.1515 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 1612.1515 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 51 | 212500 | ACTION | 1620.805 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 4 | 16666.6667 | ACTION | 1624.805 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 398 | 4975000 | ACTION | 1631.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1636.805 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1640.805 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 15.16 | 63166.6667 | ACTION | 1655.965 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1660.125 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 40 | 500000 | ACTION | 1671.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 66.4783 | 276992.9167 | ACTION | 1678.6298 | MooringSystemInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1682.125 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 1 | 4166.6667 | ACTION | 1683.125 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1683.6298 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1688.6298 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 18 | 75000 | ACTION | 1706.6298 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 42 | 175000 | ACTION | 1748.6298 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 67 | 279166.6667 | ACTION | 1750.125 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 7 | 29166.6667 | ACTION | 1757.125 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 15 | 62500 | ACTION | 1763.6298 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 1770.6298 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 33 | 137500 | ACTION | 1790.125 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 4 | 16666.6667 | ACTION | 1794.125 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 133 | 1662500 | ACTION | 1804.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 42.4783 | 176992.9167 | ACTION | 1813.1081 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1815.1081 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1819.1081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1835.2681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1839.4281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1841.4281 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1845.4281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1861.5881 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1865.7481 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1867.7481 | MooringSystemInstallation
| Floating Substation Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 1869.6033 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1871.7481 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1887.9081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1892.0681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1894.0681 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1898.0681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1914.2281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1918.3881 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1920.3881 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1924.3881 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 121.0382 | 1512977.8329 | ACTION | 1925.8382 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Position Onsite | 2 | 25000 | ACTION | 1927.8382 | ExportCableInstallation
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 1933.3382 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 1938.8382 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1940.5481 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1944.7081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Transit | 7 | 87500 | ACTION | 1945.8382 | ExportCableInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1946.7081 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1950.7081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 1966.8681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 1971.0281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 36 | 450000 | ACTION | 1981.8382 | ExportCableInstallation
| Export Cable Installation Vessel | Transit | 16 | 200000 | ACTION | 1997.8382 | ExportCableInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 2046.5064 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2051.5064 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2056.5064 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 65 | 812500 | ACTION | 2062.8382 | ExportCableInstallation
| Export Cable Installation Vessel | Transit | 42.6333 | 532916.3043 | ACTION | 2105.4715 | ExportCableInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 2131.9847 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2133.9847 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2137.9847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2154.1447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2158.3047 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2160.3047 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2164.3047 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2180.4647 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2184.6247 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2186.6247 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2190.6247 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2206.7847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2210.9447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2212.9447 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2216.9447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2233.1047 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2237.2647 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2239.2647 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2243.2647 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2259.4247 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2263.5847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2265.5847 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2269.5847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2285.7447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2289.9047 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 2365.383 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2370.383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2375.383 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 2450.8613 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2452.8613 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2456.8613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2473.0213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2477.1813 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2479.1813 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2483.1813 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2499.3413 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2503.5013 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2505.5013 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2509.5013 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2525.6613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2529.8213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2531.8213 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2535.8213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2551.9813 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2556.1413 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2558.1413 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2562.1413 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2578.3013 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2582.4613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2584.4613 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2588.4613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2604.6213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2608.7813 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 2684.2596 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2689.2596 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2694.2596 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 2769.7379 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2771.7379 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2775.7379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2791.8979 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2796.0579 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2798.0579 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2802.0579 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2818.2179 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2822.3779 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2824.3779 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2828.3779 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2844.5379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2848.6979 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2850.6979 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2854.6979 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2870.8579 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2875.0179 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2877.0179 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2881.0179 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2897.1779 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2901.3379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2903.3379 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2907.3379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 2923.4979 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 2927.6579 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 3003.1362 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3008.1362 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3013.1362 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 3088.6145 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3090.6145 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3094.6145 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3110.7745 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3114.9345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3116.9345 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3120.9345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3137.0945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3141.2545 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3143.2545 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3147.2545 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3163.4145 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3167.5745 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3169.5745 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3173.5745 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3189.7345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3193.8945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3195.8945 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3199.8945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3216.0545 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3220.2145 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3222.2145 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3226.2145 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3242.3745 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3246.5345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 3322.0128 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3327.0128 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3332.0128 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 3407.4911 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3409.4911 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3413.4911 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3429.6511 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3433.8111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3435.8111 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3439.8111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3455.9711 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3460.1311 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3462.1311 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3466.1311 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3482.2911 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3486.4511 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3488.4511 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3492.4511 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3508.6111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3512.7711 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3514.7711 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3518.7711 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3534.9311 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3539.0911 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3541.0911 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3545.0911 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3561.2511 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3565.4111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 27 | 112500 | ACTION | 3592.4111 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 17 | 70833.3333 | ACTION | 3609.4111 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 48.4783 | 201992.9167 | ACTION | 3657.8894 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3662.8894 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3667.8894 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 3743.3677 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3745.3677 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3749.3677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3765.5277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3769.6877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3771.6877 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3775.6877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3791.8477 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3796.0077 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3798.0077 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3802.0077 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3818.1677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3822.3277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3824.3277 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3828.3277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3844.4877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3848.6477 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3850.6477 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3854.6477 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3870.8077 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3874.9677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3876.9677 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3880.9677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 3897.1277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 3901.2877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 3976.766 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3981.766 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3986.766 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 73 | 304166.6667 | ACTION | 4059.766 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 6 | 25000 | ACTION | 4065.766 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2.4783 | 10326.25 | ACTION | 4068.2443 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4070.2443 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4074.2443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4090.4043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4094.5643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4096.5643 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4100.5643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4116.7243 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4120.8843 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4122.8843 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4126.8843 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4143.0443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4147.2043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4149.2043 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4153.2043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4169.3643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4173.5243 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4175.5243 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4179.5243 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4195.6843 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4199.8443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4201.8443 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4205.8443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4222.0043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4226.1643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 13 | 54166.6667 | ACTION | 4239.1643 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 4260.1643 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 39 | 162500 | ACTION | 4299.1643 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 10 | 41666.6667 | ACTION | 4309.1643 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 9 | 37500 | ACTION | 4318.1643 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 4329.1643 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 14.4783 | 60326.25 | ACTION | 4343.6426 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4348.6426 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4353.6426 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 27 | 112500 | ACTION | 4380.6426 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 4401.6426 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 48.4783 | 201992.9167 | ACTION | 4450.1209 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4452.1209 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4456.1209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4472.2809 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4476.4409 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4478.4409 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4482.4409 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4498.6009 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4502.7609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4504.7609 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4508.7609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4524.9209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4529.0809 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4531.0809 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4535.0809 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4551.2409 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4555.4009 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4557.4009 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4561.4009 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4577.5609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4581.7209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4583.7209 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4587.7209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4603.8809 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4608.0409 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 4683.5192 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4688.5192 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4693.5192 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 19 | 79166.6667 | ACTION | 4712.5192 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 1 | 4166.6667 | ACTION | 4713.5192 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 14 | 58333.3333 | ACTION | 4727.5192 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 22 | 91666.6667 | ACTION | 4749.5192 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 1 | 4166.6667 | ACTION | 4750.5192 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 4752.5192 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 29 | 120833.3333 | ACTION | 4781.5192 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 10 | 41666.6667 | ACTION | 4791.5192 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 12.4783 | 51992.9167 | ACTION | 4803.9975 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4805.9975 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4809.9975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4826.1575 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4830.3175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4832.3175 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4836.3175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4852.4775 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4856.6375 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4858.6375 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4862.6375 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4878.7975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4882.9575 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4884.9575 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4888.9575 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4905.1175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4909.2775 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4911.2775 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4915.2775 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4931.4375 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4935.5975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4937.5975 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4941.5975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 4957.7575 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 4961.9175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 5037.3958 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5042.3958 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5047.3958 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 5122.8741 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5124.8741 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5128.8741 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5145.0341 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5149.1941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5151.1941 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5155.1941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5171.3541 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5175.5141 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5177.5141 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5181.5141 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5197.6741 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5201.8341 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5203.8341 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5207.8341 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5223.9941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5228.1541 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5230.1541 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5234.1541 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5250.3141 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5254.4741 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5256.4741 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5260.4741 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5276.6341 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5280.7941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5 | 20833.3333 | ACTION | 5285.7941 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 5289.7941 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 17 | 70833.3333 | ACTION | 5306.7941 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 34 | 141666.6667 | ACTION | 5340.7941 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 53.4783 | 222826.25 | ACTION | 5394.2724 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5399.2724 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5404.2724 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 5479.7507 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5481.7507 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5485.7507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5501.9107 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5506.0707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5508.0707 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5512.0707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5528.2307 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5532.3907 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5534.3907 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5538.3907 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5554.5507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5558.7107 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5560.7107 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5564.7107 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5580.8707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5585.0307 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5587.0307 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5591.0307 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5607.1907 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5611.3507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5613.3507 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5617.3507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5633.5107 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5637.6707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 5713.149 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5718.149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5723.149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 40 | 166666.6667 | ACTION | 5763.149 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 10 | 41666.6667 | ACTION | 5773.149 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5790.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 5790.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 24 | 100000 | ACTION | 5797.149 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5798.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5810.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 66 | 275000 | ACTION | 5863.149 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 53 | 0 | ACTION | 5863.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5867.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5871.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 11.4783 | 47826.25 | ACTION | 5874.6273 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5875.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5876.6273 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5879.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5880.6273 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5891.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5895.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5896.7873 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5898.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5900.9473 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5902.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5902.9473 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5906.9473 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5923.1073 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5926.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5927.2673 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5929.2673 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5933.2673 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5949.4273 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5953.5873 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5955.5873 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5958.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5959.5873 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 5975.7473 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 5979.9073 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5981.9073 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5985.9073 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5998.4464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 375.5 | 2659791.6667 | ACTION | 5998.4464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6002.0673 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6004.4464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6006.2273 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6006.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6008.2273 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6012.2273 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6018.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6022.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6026.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6028.3873 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6030.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6032.5473 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6034.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6046.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6049.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6053.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6056.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6080.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 6108.0256 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6113.0256 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6118.0256 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6126.9464 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 6141.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 6143.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6149.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6152.9464 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 530 | 3754166.6667 | ACTION | 6152.9464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6158.9464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6160.9464 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 6169.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6172.9464 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 6175.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6176.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6180.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6184.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6188.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 6193.5039 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6195.5039 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6199.5039 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6200.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6204.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6207.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6211.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6215.6639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6219.8239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6221.8239 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6225.8239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 6229.5928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6235.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6241.9839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6246.1439 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6248.1439 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6252.1439 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6268.3039 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6272.4639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6274.4639 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6278.4639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6294.6239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6294.9464 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 6296.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 6298.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6298.7839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6300.7839 | MooringSystemInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6304.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6304.7839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6307.4464 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 684.5 | 4848541.6667 | ACTION | 6307.4464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6313.4464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6315.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6320.9439 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 6324.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6325.1039 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6327.1039 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6327.4464 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 6330.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6331.1039 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6331.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6335.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6339.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6343.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6347.2639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6351.4239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6355.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6358.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6362.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6365.9464 | MooredSubInstallation
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 6384.0928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6389.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 72 | 300000 | ACTION | 6423.4239 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 28 | 116666.6667 | ACTION | 6451.4239 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 3.4783 | 14492.9167 | ACTION | 6454.9022 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6459.9022 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6461.9464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 232.3537 | 1645838.3956 | ACTION | 6461.9464 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6462.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 1 | 0 | ACTION | 6462.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6464.9022 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6467.9464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6470.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6482.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6486.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 36 | 150000 | ACTION | 6500.9022 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 10 | 41666.6667 | ACTION | 6510.9022 | MooringSystemInstallation
| Towing Group 3 | Delay | 198 | 1402500 | ACTION | 6511.4464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 44 | 311666.6667 | ACTION | 6511.9464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 25 | 0 | ACTION | 6511.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6515.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6519.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6523.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6535.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6539.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6542.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6546.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 39.4783 | 164492.9167 | ACTION | 6550.3805 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6552.3805 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6556.3805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6570.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6572.5405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6576.7005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6578.7005 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6582.7005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6598.8605 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6603.0205 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6605.0205 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6609.0205 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6625.1805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6629.3405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6630.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6631.3405 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6635.3405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6642.4464 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 258.3537 | 1830005.0622 | ACTION | 6642.4464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6648.4464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 6648.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 6649.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6650.4464 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 6650.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 6651.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6651.5005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6655.6605 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6656.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6657.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6657.6605 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6661.6605 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6662.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6666.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6670.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6674.4464 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 6676.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 6677.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6677.8205 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6678.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6681.9805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 6682.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 6683.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6683.9805 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6687.9805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6690.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6693.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6697.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6700.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6704.1405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6708.3005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6724.9464 | MooredSubInstallation
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 6736.5928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 6737.0928 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 6783.7788 | MooringSystemInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 6785.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 6787.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6788.7788 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6793.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6793.7788 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6796.9464 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 60.3537 | 427505.0622 | ACTION | 6796.9464 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6798.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 2 | 0 | ACTION | 6798.9464 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6802.9464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6806.9464 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 6813.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6818.9464 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 6819.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6822.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6826.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6830.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6834.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6846.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6850.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6853.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6857.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 6869.2571 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6871.2571 | MooringSystemInstallation
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 6873.5928 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6875.2571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6881.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6891.4171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6895.5771 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6897.5771 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6901.5771 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 63 | 262500 | ACTION | 6964.5771 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6966.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 6980.7371 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 6984.8971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6986.8971 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6990.8971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7007.0571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7011.2171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7013.2171 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7017.2171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7033.3771 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7037.5371 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7039.5371 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7043.5371 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7059.6971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7063.8571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7065.8571 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7069.8571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 229 | 0 | ACTION | 7110.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 49 | 204166.6667 | ACTION | 7118.8571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7134.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7135.0171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7139.1771 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 23 | 95833.3333 | ACTION | 7162.1771 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 7170.1771 | MooringSystemInstallation
| Towing Group 3 | Delay | 376 | 2663333.3333 | ACTION | 7178.9464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7182.4464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 445.3537 | 3154588.3956 | ACTION | 7182.4464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7188.4464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7190.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7202.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7206.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7210.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7214.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7218.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 52.4783 | 218659.5833 | ACTION | 7222.6554 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7227.6554 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7230.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7232.6554 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7233.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7237.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7240.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7264.9464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7302.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 7308.1337 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7310.1337 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7314.1337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 7316.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 7318.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 7324.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 7325.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 7327.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7330.2937 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 7333.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7334.4537 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7336.4537 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7336.9464 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 463.3537 | 3282088.3956 | ACTION | 7336.9464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7340.4537 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7342.9464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 7344.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7344.9464 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 7350.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 7353.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7356.6137 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7356.9464 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 7359.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7360.7737 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7360.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7362.7737 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7364.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7366.7737 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7368.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7372.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7382.9337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7384.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7387.0937 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7388.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7389.0937 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7391.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7393.0937 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7395.4464 | MooredSubInstallation
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 7404.0928 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7409.2537 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7413.4137 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 7413.5928 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7415.4137 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7419.4137 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7419.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7435.5737 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7439.7337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7441.7337 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7445.7337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7470.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7491.4464 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 87.3537 | 618755.0622 | ACTION | 7491.4464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7499.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7511.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 7516.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7520.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7524.4464 | MooredSubInstallation
| Towing Group 3 | Delay | 37 | 262083.3333 | ACTION | 7528.4464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7528.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 83 | 345833.3333 | ACTION | 7528.7337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7532.4464 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7534.4464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7544.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7544.8937 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7547.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7549.0537 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7551.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7554.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7578.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 7624.532 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7629.532 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7634.532 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 1 | 4166.6667 | ACTION | 7635.532 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7638.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 64 | 266666.6667 | ACTION | 7699.532 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 11 | 45833.3333 | ACTION | 7710.532 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 142 | 0 | ACTION | 7720.9464 | MooredSubInstallation
| Towing Group 3 | Delay | 209 | 1480416.6667 | ACTION | 7743.4464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 33 | 137500 | ACTION | 7743.532 | MooringSystemInstallation
| Towing Group 2 | Delay | 401 | 2840416.6667 | ACTION | 7743.9464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7792.9464 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 379.3537 | 2687088.3956 | ACTION | 7792.9464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7798.9464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7800.9464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7806.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 63.4783 | 264492.9167 | ACTION | 7807.0103 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7809.0103 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7812.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7813.0103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7816.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7820.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7824.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7828.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7829.1703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7833.3303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7835.3303 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7839.3303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7840.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7844.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7847.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7851.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7855.4903 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7859.6503 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7861.6503 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7865.6503 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7875.4464 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 7880.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 7881.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7881.8103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 5 | 20833.3333 | ACTION | 7886.8103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7890.9703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7892.9703 | MooringSystemInstallation
| Towing Group 2 | Delay | 13 | 92083.3333 | ACTION | 7894.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 14 | 99166.6667 | ACTION | 7894.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 7896.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 7896.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7896.9703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7947.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 54 | 225000 | ACTION | 7950.9703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 59 | 417916.6667 | ACTION | 7955.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7955.4464 | MooredSubInstallation
| Towing Group 3 | Delay | 59 | 417916.6667 | ACTION | 7955.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 7961.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 7961.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7967.1303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7967.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7971.2903 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7971.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7973.2903 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7974.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7975.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7977.2903 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7979.4464 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 7981.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 7981.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7983.4464 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 7987.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 7987.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 7993.4503 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7995.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 7997.6103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7998.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7999.6103 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8002.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8003.6103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8005.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8019.7703 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8023.9303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8029.9464 | MooredSubInstallation
| Towing Group 2 | Transit | 46 | 325833.3333 | ACTION | 8033.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 46 | 325833.3333 | ACTION | 8033.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 8033.9303 | MooringSystemInstallation
| Towing Group 2 | Delay | 30 | 212500 | ACTION | 8063.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 30 | 212500 | ACTION | 8063.6797 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 30 | 125000 | ACTION | 8063.9303 | MooringSystemInstallation
| Towing Group 2 | Transit | 7.9131 | 56050.9226 | ACTION | 8071.0928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 7.9131 | 56050.9226 | ACTION | 8071.5928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 8077.0928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8101.9464 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 30.3537 | 215005.0622 | ACTION | 8101.9464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 8107.9464 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8109.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 48 | 200000 | ACTION | 8111.9303 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8121.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8125.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8129.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8133.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8137.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 28 | 116666.6667 | ACTION | 8139.9303 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8142.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8149.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8153.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 17.4783 | 72826.25 | ACTION | 8157.4086 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 8161.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8162.4086 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8164.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8167.4086 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8168.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 17 | 70833.3333 | ACTION | 8184.4086 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 6 | 25000 | ACTION | 8190.4086 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8192.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 9 | 37500 | ACTION | 8199.4086 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 66 | 0 | ACTION | 8258.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 66 | 275000 | ACTION | 8265.4086 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8310.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 49.4783 | 206159.5833 | ACTION | 8314.8869 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8316.8869 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8320.8869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8330.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8337.0469 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8338.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8341.2069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8343.2069 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8350.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8354.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8358.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8362.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8366.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8378.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8381.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8385.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 45 | 187500 | ACTION | 8388.2069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8388.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8392.2069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8412.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 8424.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 71 | 295833.3333 | ACTION | 8463.2069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8478.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8479.3669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8483.5269 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8496.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 14 | 58333.3333 | ACTION | 8497.5269 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8499.5269 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8503.5269 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8504.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8516.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8519.6869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8520.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8523.8469 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8524.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8525.8469 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8528.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8529.8469 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8532.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8544.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8546.0069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8550.1669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 8550.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8552.1669 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8554.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8556.1669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 17 | 70833.3333 | ACTION | 8573.1669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 20 | 0 | ACTION | 8574.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8577.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8581.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8589.3269 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8593.4869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8595.4869 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8599.4869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8605.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 8615.6469 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 8619.8069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 2 | 8333.3333 | ACTION | 8621.8069 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 33 | 0 | ACTION | 8638.4464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8646.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8710.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 96 | 400000 | ACTION | 8717.8069 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8718.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8730.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8734.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8738.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8742.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8746.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 36 | 150000 | ACTION | 8753.8069 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 8758.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8770.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8773.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8777.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8780.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 43 | 179166.6667 | ACTION | 8796.8069 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8804.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 9 | 37500 | ACTION | 8805.8069 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8814.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 155 | 0 | ACTION | 8959.9464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8982.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 188 | 783333.3333 | ACTION | 8993.8069 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 15 | 62500 | ACTION | 9008.8069 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9031.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9039.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 35 | 145833.3333 | ACTION | 9043.8069 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 3 | 12500 | ACTION | 9046.8069 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9051.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 30 | 0 | ACTION | 9081.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9085.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9089.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9093.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9097.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 59 | 245833.3333 | ACTION | 9105.8069 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9109.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9113.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 10.4783 | 43659.5833 | ACTION | 9116.2852 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9116.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9120.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9121.2852 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9126.2852 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 15 | 62500 | ACTION | 9141.2852 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9144.4464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9150.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 31 | 129166.6667 | ACTION | 9172.2852 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 17 | 70833.3333 | ACTION | 9189.2852 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 78 | 0 | ACTION | 9222.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 40 | 166666.6667 | ACTION | 9229.2852 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 43.4783 | 181159.5833 | ACTION | 9272.7635 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9274.7635 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9278.7635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9294.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9294.9235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9299.0835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9302.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9314.4464 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9318.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 9321.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9325.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 9337.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 42 | 175000 | ACTION | 9341.0835 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9341.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9343.0835 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9345.4464 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9347.0835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9349.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 9363.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9375.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9378.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9382.4464 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9385.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 44 | 0 | ACTION | 9429.9464 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9453.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 108 | 450000 | ACTION | 9455.0835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9471.2435 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9475.4035 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9477.4035 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9481.4035 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9486.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9497.5635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 96 | 0 | ACTION | 9549.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 64 | 266666.6667 | ACTION | 9561.5635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9565.7235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9567.7235 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9571.7235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9587.8835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9592.0435 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 9600.0435 | MooringSystemInstallation
| Towing Group 2 | Delay | 1523 | 10787916.6667 | ACTION | 9600.0928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 1802 | 12764166.6667 | ACTION | 9600.9464 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 1493 | 10575416.6667 | ACTION | 9600.9464 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9602.0435 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9606.0435 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9621.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9622.2035 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9626.3635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9628.3635 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9632.3635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9648.5235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9652.6835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9654.9464 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 9728.1618 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9733.1618 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 9737.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9738.1618 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 9738.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 9738.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 9739.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 9740.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 9740.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9745.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9746.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9746.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 9765.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 9766.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 9766.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 9771.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 9772.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 9772.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 13 | 92083.3333 | ACTION | 9785.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 13 | 92083.3333 | ACTION | 9785.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 14 | 99166.6667 | ACTION | 9785.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 4 | 28333.3333 | ACTION | 9789.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 4 | 28333.3333 | ACTION | 9789.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 4 | 28333.3333 | ACTION | 9789.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 9813.6401 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9815.6401 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9819.6401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 35 | 247916.6667 | ACTION | 9824.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 35 | 247916.6667 | ACTION | 9824.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 35 | 247916.6667 | ACTION | 9824.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 1 | 7083.3333 | ACTION | 9825.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 1 | 7083.3333 | ACTION | 9825.1797 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 1 | 7083.3333 | ACTION | 9825.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 4.9131 | 34800.9226 | ACTION | 9830.2391 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay: No Assembly Storage Available | 208.2927 | 0 | ACTION | 9830.2391 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 175.2927 | 0 | ACTION | 9830.2391 | MooredSubInstallation
| Towing Group 1 | Transit | 5.9131 | 41884.256 | ACTION | 9831.0928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 5.9131 | 41884.256 | ACTION | 9831.0928 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9835.8001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9836.2391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9837.0928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9837.0928 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9838.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9839.9601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9841.9601 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9845.9601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9850.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9854.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9858.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9862.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9866.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9878.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9881.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9885.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9888.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9912.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 82 | 341666.6667 | ACTION | 9927.9601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9944.1201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9948.2801 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9950.2801 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9954.2801 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 9970.4401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 9974.6001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9976.6001 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9980.6001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9984.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9992.7391 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9998.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10004.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10008.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 32 | 133333.3333 | ACTION | 10012.6001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10012.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10016.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10020.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10028.7601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10032.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10032.9201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10034.9201 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10036.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10038.9201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10039.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10043.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10055.0801 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10059.2401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10061.2401 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10067.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 30 | 0 | ACTION | 10097.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 50 | 208333.3333 | ACTION | 10111.2401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10115.2401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10131.4001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10135.5601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 5 | 20833.3333 | ACTION | 10140.5601 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10166.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10169.2391 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 3 | 0 | ACTION | 10169.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10177.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 46 | 191666.6667 | ACTION | 10186.5601 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10189.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10193.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10197.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10201.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10205.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10217.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10220.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10224.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10227.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 61 | 254166.6667 | ACTION | 10247.5601 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10251.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 10258.5601 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 9.4783 | 39492.9167 | ACTION | 10268.0384 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10273.0384 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10278.0384 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 8 | 33333.3333 | ACTION | 10286.0384 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 61 | 0 | ACTION | 10312.7391 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10337.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 54 | 225000 | ACTION | 10340.0384 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 25 | 104166.6667 | ACTION | 10365.0384 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10384.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 64 | 266666.6667 | ACTION | 10429.0384 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 42.4783 | 176992.9167 | ACTION | 10471.5167 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10473.5167 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10477.5167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10493.6767 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10497.8367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10499.8367 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10503.8367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10519.9967 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10524.1567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10526.1567 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 3 | 12500 | ACTION | 10529.1567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10533.1567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 42 | 175000 | ACTION | 10575.1567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10591.3167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10595.4767 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10597.4767 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10601.4767 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 64 | 266666.6667 | ACTION | 10665.4767 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10681.6367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10685.7967 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10687.7967 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10691.7967 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10707.9567 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10712.1167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10714.1167 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10718.1167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 10734.2767 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 10738.4367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 3 | 12500 | ACTION | 10741.4367 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 24 | 100000 | ACTION | 10765.4367 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 28 | 116666.6667 | ACTION | 10793.4367 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 38 | 158333.3333 | ACTION | 10831.4367 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 44.4783 | 185326.25 | ACTION | 10875.915 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10880.915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 47 | 195833.3333 | ACTION | 10927.915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10932.915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 11008.3933 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11010.3933 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11014.3933 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11030.5533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11034.7133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11036.7133 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11040.7133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 11061.7133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11077.8733 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11082.0333 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11084.0333 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11088.0333 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11104.1933 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11108.3533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11110.3533 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11114.3533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11130.5133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11134.6733 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11136.6733 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11140.6733 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11156.8333 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11160.9933 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11162.9933 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11166.9933 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11183.1533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 1427 | 10107916.6667 | ACTION | 11264.0928 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 1427 | 10107916.6667 | ACTION | 11264.0928 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Delay | 81 | 337500 | ACTION | 11264.1533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 1428 | 10115000 | ACTION | 11264.2391 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11268.3133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 11343.7916 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11348.7916 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11353.7916 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 11401.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 11401.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 11401.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 11403.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 11403.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 11403.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11409.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11409.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11409.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 28333.3333 | ACTION | 11413.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 28333.3333 | ACTION | 11413.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 28333.3333 | ACTION | 11413.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 66 | 275000 | ACTION | 11419.7916 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 41 | 170833.3333 | ACTION | 11460.7916 | MooringSystemInstallation
| Towing Group 1 | Delay | 54 | 382500 | ACTION | 11467.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 54 | 382500 | ACTION | 11467.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 54 | 382500 | ACTION | 11467.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 9.4783 | 39492.9167 | ACTION | 11470.2699 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11472.2699 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11476.2699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 113333.3333 | ACTION | 11483.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 113333.3333 | ACTION | 11483.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 113333.3333 | ACTION | 11483.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 11489.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 11489.3261 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 11489.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11492.4299 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11496.5899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11498.5899 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11502.5899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11518.7499 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11522.9099 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11524.9099 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11528.9099 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 11543.2391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 11543.2391 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay: No Assembly Storage Available | 1158.5 | 0 | ACTION | 11543.2391 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 1206 | 0 | ACTION | 11543.2391 | MooredSubInstallation
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 11543.3855 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11545.0699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11549.2299 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11549.2391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11549.2391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11549.3855 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11551.2299 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11551.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11555.2299 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11563.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11567.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11571.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11571.3899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11575.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11575.5499 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11577.5499 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11579.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11581.5499 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11591.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11594.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11597.7099 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11598.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11601.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11601.8699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11603.8699 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11607.8699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11624.0299 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11625.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11628.1899 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 11686.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 11686.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 11686.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11697.7391 | MooredSubInstallation
| Towing Group 1 | Delay | 14 | 99166.6667 | ACTION | 11700.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 14 | 99166.6667 | ACTION | 11700.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 14 | 99166.6667 | ACTION | 11700.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 11702.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 11702.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 11702.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 11703.6682 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11705.7391 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11708.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11708.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11708.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11708.6682 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 11710.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 11710.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 11710.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11711.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11713.6682 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11717.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 11728.7391 | MooredSubInstallation
| Towing Group 1 | Delay | 21 | 148750 | ACTION | 11731.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 21 | 148750 | ACTION | 11731.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 21 | 148750 | ACTION | 11731.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11732.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11736.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11740.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11744.7391 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 127500 | ACTION | 11749.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 127500 | ACTION | 11749.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 127500 | ACTION | 11749.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 11755.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 11755.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 11755.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11756.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 11758.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11762.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11765.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11769.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 11789.1465 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11791.1465 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11793.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11795.1465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 11809.3855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 11809.3855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 11809.5318 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11811.3065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11815.3855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11815.3855 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11815.4665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11815.5318 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11817.4665 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11821.4665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 22 | 91666.6667 | ACTION | 11843.4665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11859.6265 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11863.7865 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11865.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11865.7865 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11869.7865 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11873.2391 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11879.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11885.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 44 | 0 | ACTION | 11929.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 62 | 258333.3333 | ACTION | 11931.7865 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11933.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11937.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11941.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11945.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11947.9465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11952.1065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11954.1065 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11957.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11958.1065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 11974.2665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 11978.4265 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11980.4265 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11984.4265 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12000.5865 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 35 | 145833.3333 | ACTION | 12035.5865 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12039.7465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12041.7465 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 88 | 0 | ACTION | 12045.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12045.7465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12047.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12048.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12052.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12055.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12061.9065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12066.0665 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12079.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 12141.5448 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12146.5448 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12151.5448 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12151.7391 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 104.5 | 0 | ACTION | 12151.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12159.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12171.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 21 | 87500 | ACTION | 12172.5448 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 3 | 12500 | ACTION | 12175.5448 | MooringSystemInstallation
| Towing Group 1 | Delay | 366 | 2592500 | ACTION | 12181.3855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 366 | 2592500 | ACTION | 12181.3855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 366 | 2592500 | ACTION | 12181.5318 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 10 | 0 | ACTION | 12181.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12185.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12189.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12193.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12197.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12209.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12213.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12216.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12220.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 54.4783 | 226992.9167 | ACTION | 12230.0231 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12232.0231 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12236.0231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12244.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12252.1831 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12256.3431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12258.3431 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12262.3431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12278.5031 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12282.6631 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12284.6631 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12288.6631 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12304.8231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12308.9831 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12310.9831 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12314.9831 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12316.2391 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 12318.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 12318.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 12318.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12319.7391 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 12320.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 12320.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 12320.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12324.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12331.1431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12335.3031 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12336.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12337.3031 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12340.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12341.3031 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12344.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12348.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12352.2391 | MooredSubInstallation
| Towing Group 1 | Delay | 35 | 247916.6667 | ACTION | 12355.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 35 | 247916.6667 | ACTION | 12355.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 35 | 247916.6667 | ACTION | 12355.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12357.4631 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12361.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12361.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12361.6231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12361.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12363.6231 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12364.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12367.6231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 12381.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 12381.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 12381.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12383.7831 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 12387.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 12387.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 12387.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12387.9431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 2 | 14166.6667 | ACTION | 12389.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 2 | 14166.6667 | ACTION | 12389.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 2 | 14166.6667 | ACTION | 12389.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 4 | 28333.3333 | ACTION | 12393.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 4 | 28333.3333 | ACTION | 12393.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 4 | 28333.3333 | ACTION | 12393.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 3 | 21250 | ACTION | 12396.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 3 | 21250 | ACTION | 12396.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 3 | 21250 | ACTION | 12396.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 1 | 7083.3333 | ACTION | 12397.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 1 | 7083.3333 | ACTION | 12397.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 1 | 7083.3333 | ACTION | 12397.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 2 | 14166.6667 | ACTION | 12399.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 2 | 14166.6667 | ACTION | 12399.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 2 | 14166.6667 | ACTION | 12399.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 1 | 7083.3333 | ACTION | 12400.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 1 | 7083.3333 | ACTION | 12400.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 1 | 7083.3333 | ACTION | 12400.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 1 | 7083.3333 | ACTION | 12401.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 1 | 7083.3333 | ACTION | 12401.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 1 | 7083.3333 | ACTION | 12401.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 3 | 21250 | ACTION | 12404.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 3 | 21250 | ACTION | 12404.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 3 | 21250 | ACTION | 12404.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 53 | 0 | ACTION | 12417.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12420.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12424.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 12429.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12432.7391 | MooredSubInstallation
| Towing Group 1 | Transit | 45.9131 | 325217.5893 | ACTION | 12450.5318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 45.9131 | 325217.5893 | ACTION | 12450.5318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 45.9131 | 325217.5893 | ACTION | 12450.6782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12456.5318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12456.5318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12456.6782 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12456.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 12463.4214 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12468.4214 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12473.4214 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12487.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12528.7391 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 41 | 0 | ACTION | 12528.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 58 | 241666.6667 | ACTION | 12531.4214 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12536.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 12544.4214 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12548.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12552.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12556.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12560.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 17.4783 | 72826.25 | ACTION | 12561.8997 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12563.8997 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12564.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12567.8997 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12576.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12580.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12583.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12584.0597 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12587.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12588.2197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12590.2197 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12594.2197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12610.3797 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12611.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12614.5397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12616.5397 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12620.5397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12636.6997 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12640.8597 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12642.8597 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12646.8597 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12663.0197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12667.1797 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12669.1797 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12673.1797 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12683.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12689.3397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12691.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12693.4997 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12695.4997 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12696.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12699.4997 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12703.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12707.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12711.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12715.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12715.6597 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12719.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12719.8197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12731.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12734.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12738.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12741.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12765.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 12795.298 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12800.298 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12805.298 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 16 | 66666.6667 | ACTION | 12821.298 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 96 | 0 | ACTION | 12861.7391 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12864.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 56 | 233333.3333 | ACTION | 12877.298 | MooringSystemInstallation
| Towing Group 1 | Delay | 421 | 2982083.3333 | ACTION | 12877.5318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 421 | 2982083.3333 | ACTION | 12877.5318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 421 | 2982083.3333 | ACTION | 12877.6782 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12933.7391 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 69 | 0 | ACTION | 12933.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 59.4783 | 247826.25 | ACTION | 12936.7763 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12938.7763 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12941.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12942.7763 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12953.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12957.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12958.9363 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12961.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12963.0963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12965.0963 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12965.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12969.0963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12969.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12981.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12985.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 12985.2563 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12988.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 12989.4163 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12991.4163 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12992.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12995.4163 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13011.5763 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 13014.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 13014.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 13014.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13015.7363 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13016.2391 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 13016.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 13016.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 13016.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13017.7363 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13021.7363 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13022.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13022.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13022.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13037.8963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13042.0563 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13042.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13042.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13042.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13044.0563 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13048.0563 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 13048.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 13048.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 13048.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13064.2163 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13068.3763 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13070.3763 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13074.3763 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13088.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13090.5363 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13094.6963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13096.2391 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13101.7391 | MooredSubInstallation
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 13102.6782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 13102.6782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 13102.8245 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13108.2391 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13108.6782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13108.6782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13108.8245 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13112.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13116.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13120.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13124.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13136.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 13170.1746 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 13175.1746 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 13180.1746 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 61 | 0 | ACTION | 13197.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13200.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13204.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 13209.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13212.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13236.7391 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 13245.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 13245.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 13246.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 13247.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 13247.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 13248.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13253.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13253.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13254.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 13255.6529 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13257.6529 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13261.6529 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13269.7391 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13273.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13273.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13274.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13277.8129 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 13279.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 13279.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 13280.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13281.9729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13283.9729 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13287.9729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13304.1329 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13308.2929 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13308.7391 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 39 | 0 | ACTION | 13308.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13310.2929 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13314.2929 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13316.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13328.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13330.4529 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13332.7391 | MooredSubInstallation
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 13333.8245 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 13333.8245 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 13333.9708 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13334.6129 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13336.6129 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13336.7391 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13339.8245 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13339.8245 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13339.9708 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13340.6129 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13340.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13344.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13356.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13356.7729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13360.9329 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13362.9329 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13366.9329 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 90 | 375000 | ACTION | 13456.9329 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 121 | 857083.3333 | ACTION | 13460.9708 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 122 | 864166.6667 | ACTION | 13461.8245 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 122 | 864166.6667 | ACTION | 13461.8245 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13473.0929 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13476.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13477.2529 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13479.2529 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13483.2529 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13499.4129 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13503.5729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 165 | 0 | ACTION | 13521.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13525.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13528.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 13579.0512 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 55 | 0 | ACTION | 13583.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 13584.0512 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13587.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 13589.0512 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 13598.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 13599.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 13599.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 13600.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 13601.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 13601.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13606.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13607.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13607.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13611.2391 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 85000 | ACTION | 13619.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 85000 | ACTION | 13619.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 92083.3333 | ACTION | 13619.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 35 | 247916.6667 | ACTION | 13654.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 35 | 247916.6667 | ACTION | 13654.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 35 | 247916.6667 | ACTION | 13654.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 13655.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 13655.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 13655.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 1 | 7083.3333 | ACTION | 13656.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 1 | 7083.3333 | ACTION | 13656.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 1 | 7083.3333 | ACTION | 13656.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 21250 | ACTION | 13659.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 21250 | ACTION | 13659.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 21250 | ACTION | 13659.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 13664.5295 | MooringSystemInstallation
| Towing Group 1 | Delay | 6 | 42500 | ACTION | 13665.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 6 | 42500 | ACTION | 13665.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 6 | 42500 | ACTION | 13665.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 13666.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 13666.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 13666.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13666.5295 | MooringSystemInstallation
| Towing Group 1 | Delay | 4 | 28333.3333 | ACTION | 13670.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 4 | 28333.3333 | ACTION | 13670.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 4 | 28333.3333 | ACTION | 13670.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13670.5295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 13672.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 21250 | ACTION | 13673.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 21250 | ACTION | 13673.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 1 | 7083.3333 | ACTION | 13673.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 4 | 28333.3333 | ACTION | 13677.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 4 | 28333.3333 | ACTION | 13677.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 4 | 28333.3333 | ACTION | 13677.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 5 | 35416.6667 | ACTION | 13682.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 13683.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 13683.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13683.2391 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 206.5 | 0 | ACTION | 13683.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13686.6895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13690.8495 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13691.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13692.8495 | MooringSystemInstallation
| Towing Group 1 | Transit | 12 | 85000 | ACTION | 13695.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 12 | 85000 | ACTION | 13695.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 13 | 92083.3333 | ACTION | 13695.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13696.8495 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 6 | 42500 | ACTION | 13701.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 6 | 42500 | ACTION | 13701.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 6 | 42500 | ACTION | 13701.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13703.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13707.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13711.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13713.0095 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13715.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13717.1695 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13719.1695 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13719.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13723.1695 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13731.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13739.3295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 40.9131 | 289800.9226 | ACTION | 13742.1172 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 41.9131 | 296884.256 | ACTION | 13742.9708 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 41.9131 | 296884.256 | ACTION | 13742.9708 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13743.4895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13745.4895 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13748.1172 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13749.4895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 31 | 0 | ACTION | 13762.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13765.6495 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13765.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13769.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13769.8095 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13771.8095 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13772.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13775.8095 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13791.9695 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13796.1295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13796.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13798.1295 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13802.1295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 13818.2895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 13822.4495 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13851.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13868.7391 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 125.7683 | 890858.6445 | ACTION | 13868.7391 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 17.5 | 0 | ACTION | 13868.7391 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13874.7391 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13876.7391 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 13885.3505 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 13887.3505 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13888.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13892.7391 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13893.3505 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13896.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 13897.9278 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13900.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 13902.9278 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13904.7391 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13913.3505 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13916.7391 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 13919.3505 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13920.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13923.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13927.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13951.2391 | MooredSubInstallation
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 13973.2635 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 75.4783 | 314492.9167 | ACTION | 13978.4061 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 13980.4061 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 13984.4061 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 14000.5661 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 14004.7261 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 14006.7261 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 14010.7261 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 14011.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 14013.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14019.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14023.2391 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 280.2683 | 1985233.6445 | ACTION | 14023.2391 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 14026.8861 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14029.2391 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 14031.0461 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14031.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 14033.0461 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14036.7391 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 14037.0461 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14039.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14043.2391 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 14045.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14047.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14051.2391 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 16.16 | 67333.3333 | ACTION | 14053.2061 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14055.2391 | MooredSubInstallation
| Towing Group 1 | Transit | 11 | 77916.6667 | ACTION | 14056.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 4.16 | 17333.3333 | ACTION | 14057.3661 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 2 | 14166.6667 | ACTION | 14058.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 1 | 7083.3333 | ACTION | 14059.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 1 | 7083.3333 | ACTION | 14060.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 14061.2391 | MooredSubInstallation
| Towing Group 1 | Transit | 4 | 28333.3333 | ACTION | 14064.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14065.2391 | MooredSubInstallation
| Towing Group 1 | Delay | 21 | 148750 | ACTION | 14085.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 57 | 403750 | ACTION | 14086.2391 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 21 | 0 | ACTION | 14086.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14098.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14101.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14105.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14108.7391 | MooredSubInstallation
| Towing Group 1 | Transit | 37.9131 | 268550.9226 | ACTION | 14123.8855 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14132.7391 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14204.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14204.7391 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 231.4756 | 1639618.7689 | ACTION | 14204.7391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14210.7391 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14212.7391 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 14223.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14224.7391 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 14225.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14228.7391 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14231.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14232.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14236.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14240.7391 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14251.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14252.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14256.2391 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 14257.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14259.7391 | MooredSubInstallation
| Towing Group 3 | Transit | 10 | 70833.3333 | ACTION | 14267.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 94 | 665833.3333 | ACTION | 14361.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 151 | 1069583.3333 | ACTION | 14361.7391 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14372.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 122 | 0 | ACTION | 14381.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14385.2391 | MooredSubInstallation
| Towing Group 3 | Transit | 43.9131 | 311050.9226 | ACTION | 14405.3855 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14409.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14481.2391 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 357.3537 | 2531255.0622 | ACTION | 14481.2391 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 108.5 | 0 | ACTION | 14481.2391 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14487.2391 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14489.2391 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 14498.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 14500.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14501.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 64 | 0 | ACTION | 14565.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14569.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 70 | 0 | ACTION | 14639.2391 | MooredSubInstallation
| Towing Group 1 | Delay | 153 | 1083750 | ACTION | 14640.2391 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14643.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14647.2391 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14649.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14651.2391 | MooredSubInstallation
| Towing Group 2 | Delay | 154 | 1090833.3333 | ACTION | 14654.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14660.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14663.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14666.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14670.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14673.7391 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14680.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 14686.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14697.7391 | MooredSubInstallation
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 14740.8855 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14769.7391 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 364.3537 | 2580838.3956 | ACTION | 14769.7391 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 120.5 | 0 | ACTION | 14769.7391 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14775.7391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 14777.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14777.7391 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 14779.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14785.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14789.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14793.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14797.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14801.7391 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14805.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14805.7391 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 14811.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14817.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14821.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14824.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14828.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14852.2391 | MooredSubInstallation
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 14865.3855 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14924.2391 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 183.3537 | 1298755.0622 | ACTION | 14924.2391 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14932.2391 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14937.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14944.2391 | MooredSubInstallation
| Towing Group 2 | Delay | 25 | 177083.3333 | ACTION | 14949.2391 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 14949.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14953.2391 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14955.2391 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14957.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14961.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 14965.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14969.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 14996.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15008.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15011.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15015.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15018.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15042.7391 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15105.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15114.7391 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 249.3537 | 1766255.0622 | ACTION | 15114.7391 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 9 | 0 | ACTION | 15114.7391 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 15120.7391 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15122.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15134.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15138.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15142.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15146.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 15149.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15153.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15165.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 15166.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15170.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15173.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15177.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15201.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15273.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15281.2391 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15282.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15293.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15297.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15301.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15305.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15309.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15321.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15324.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15328.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15331.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15355.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15427.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15435.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15447.7391 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15450.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15451.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15455.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15459.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15463.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15475.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 30 | 0 | ACTION | 15505.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15509.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15512.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15516.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15540.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15612.2391 | MooredSubInstallation
| Towing Group 2 | Delay | 658 | 4660833.3333 | ACTION | 15613.2391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 838 | 5935833.3333 | ACTION | 15613.7391 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 493 | 3492083.3333 | ACTION | 15613.7391 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15618.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15620.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15632.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15636.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15640.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15644.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15648.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15660.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15663.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15667.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15670.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15694.7391 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 15750.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 15750.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 15750.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 15752.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 15752.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 15752.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 10 | 70833.3333 | ACTION | 15762.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 10 | 70833.3333 | ACTION | 15762.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 11 | 77916.6667 | ACTION | 15763.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15766.7391 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 15768.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 15768.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 15769.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15774.7391 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 92083.3333 | ACTION | 15781.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 92083.3333 | ACTION | 15781.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 92083.3333 | ACTION | 15782.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15786.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15786.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 15800.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15804.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15808.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15812.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15816.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 24 | 0 | ACTION | 15840.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15852.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15856.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15859.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15863.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15887.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 15901.2391 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15954.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15973.2391 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 18.5 | 0 | ACTION | 15973.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15981.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15993.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15997.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16001.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16005.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16009.2391 | MooredSubInstallation
| Towing Group 3 | Delay | 235 | 1664583.3333 | ACTION | 16016.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 235 | 1664583.3333 | ACTION | 16016.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 235 | 1664583.3333 | ACTION | 16017.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16021.2391 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 49583.3333 | ACTION | 16023.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 49583.3333 | ACTION | 16023.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 49583.3333 | ACTION | 16024.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16024.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16028.2391 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 16029.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 16029.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 16030.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16031.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16055.7391 | MooredSubInstallation
| Towing Group 3 | Transit | 51 | 361250 | ACTION | 16080.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 51 | 361250 | ACTION | 16080.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 51 | 361250 | ACTION | 16081.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 19 | 134583.3333 | ACTION | 16099.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 19 | 134583.3333 | ACTION | 16099.9724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 19 | 134583.3333 | ACTION | 16100.4724 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 2.9131 | 20634.256 | ACTION | 16102.8855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 2.9131 | 20634.256 | ACTION | 16102.8855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 2.9131 | 20634.256 | ACTION | 16103.3855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 16108.8855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 16108.8855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 16109.3855 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16141.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 106 | 0 | ACTION | 16161.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16233.7391 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 92.5 | 0 | ACTION | 16233.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16241.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16253.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16257.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16261.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16265.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16269.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 16282.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16294.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16298.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16301.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16305.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16329.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16401.2391 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16401.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16409.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16421.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16425.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16429.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16433.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16437.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16449.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 23 | 0 | ACTION | 16472.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16475.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16479.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16482.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16506.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 9 | 0 | ACTION | 16515.7391 | MooredSubInstallation
| Towing Group 2 | Delay | 434 | 3074166.6667 | ACTION | 16543.3855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 435 | 3081250 | ACTION | 16543.8855 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 435 | 3081250 | ACTION | 16543.8855 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16569.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16587.7391 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 18 | 0 | ACTION | 16587.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16595.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16607.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16611.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16615.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16619.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16623.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16635.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 16643.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16647.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16650.7391 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16654.2391 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16678.2391 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 16680.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 16681.1187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 16681.1187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 16682.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 16683.1187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 16683.1187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 16688.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 16689.1187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 16689.1187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 56666.6667 | ACTION | 16697.1187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 56666.6667 | ACTION | 16697.1187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 63750 | ACTION | 16697.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 15 | 106250 | ACTION | 16712.1187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 15 | 106250 | ACTION | 16712.1187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 15 | 106250 | ACTION | 16712.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 77916.6667 | ACTION | 16723.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 85000 | ACTION | 16724.1187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 85000 | ACTION | 16724.1187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 16729.6187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 16730.1187 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 16730.1187 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16750.2391 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16755.7391 | MooredSubInstallation
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 16783.5318 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay: No Assembly Storage Available | 33.2927 | 0 | ACTION | 16783.5318 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 27.7927 | 0 | ACTION | 16783.5318 | MooredSubInstallation
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 16784.0318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 16784.0318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 16789.5318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 16790.0318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 16790.0318 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16791.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16803.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 16804.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16808.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16812.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16816.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16820.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16832.5318 | MooredSubInstallation
| Towing Group 3 | Delay | 59 | 417916.6667 | ACTION | 16849.0318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 59 | 417916.6667 | ACTION | 16849.0318 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 60 | 425000 | ACTION | 16849.5318 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 21 | 0 | ACTION | 16853.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16857.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16860.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16864.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16888.0318 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16951.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16960.0318 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 8.5 | 0 | ACTION | 16960.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16968.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16980.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16984.0318 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 16986.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 16986.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 16986.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16988.0318 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 16988.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 16988.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 16988.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16992.0318 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 16994.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 16994.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 16994.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16996.0318 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 56666.6667 | ACTION | 17002.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 56666.6667 | ACTION | 17002.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 56666.6667 | ACTION | 17002.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17008.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 17013.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17016.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17020.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17023.5318 | MooredSubInstallation
| Towing Group 3 | Delay | 42 | 297500 | ACTION | 17044.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 42 | 297500 | ACTION | 17044.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 42 | 297500 | ACTION | 17044.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17047.5318 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 63750 | ACTION | 17053.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 63750 | ACTION | 17053.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 63750 | ACTION | 17053.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 22 | 0 | ACTION | 17069.5318 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 17128.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17141.5318 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 13.5 | 0 | ACTION | 17141.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17149.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17161.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17165.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17169.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17173.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17177.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17189.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17193.0318 | MooredSubInstallation
| Towing Group 3 | Delay | 143 | 1012916.6667 | ACTION | 17196.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 143 | 1012916.6667 | ACTION | 17196.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17196.5318 | MooredSubInstallation
| Towing Group 2 | Delay | 143 | 1012916.6667 | ACTION | 17196.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 21250 | ACTION | 17199.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 21250 | ACTION | 17199.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 21250 | ACTION | 17199.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17200.0318 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 17205.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 17205.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 17205.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17224.0318 | MooredSubInstallation
| Towing Group 3 | Transit | 36 | 255000 | ACTION | 17241.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 36 | 255000 | ACTION | 17241.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 36 | 255000 | ACTION | 17241.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 50 | 354166.6667 | ACTION | 17291.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 50 | 354166.6667 | ACTION | 17291.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 50 | 354166.6667 | ACTION | 17291.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 1 | 7083.3333 | ACTION | 17292.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 1 | 7083.3333 | ACTION | 17292.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 1 | 7083.3333 | ACTION | 17292.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 3 | 21250 | ACTION | 17295.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 3 | 21250 | ACTION | 17295.2651 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 3 | 21250 | ACTION | 17295.7651 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 17309.5318 | MooredSubInstallation
| Towing Group 3 | Transit | 16.9131 | 119800.9226 | ACTION | 17312.1782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 16.9131 | 119800.9226 | ACTION | 17312.1782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 16.9131 | 119800.9226 | ACTION | 17312.6782 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 102 | 0 | ACTION | 17326.0318 | MooredSubInstallation
| Towing Group 3 | Delay | 18 | 127500 | ACTION | 17330.1782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 18 | 127500 | ACTION | 17330.1782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 18 | 127500 | ACTION | 17330.6782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 17336.1782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 17336.1782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 17336.6782 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17398.0318 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 88.5 | 0 | ACTION | 17398.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17406.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17418.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17422.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17426.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17430.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17434.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17446.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17449.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17453.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17456.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17480.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17552.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17560.5318 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 17566.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17572.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17576.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17580.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 37 | 0 | ACTION | 17617.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17621.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17625.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17637.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 9 | 0 | ACTION | 17646.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17650.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17653.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17657.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17681.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 17697.0318 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 17734.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17769.0318 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 35 | 0 | ACTION | 17769.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17777.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17789.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17793.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17797.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17801.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17805.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17817.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17820.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17824.0318 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17827.5318 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17851.5318 | MooredSubInstallation
| Towing Group 3 | Delay | 530 | 3754166.6667 | ACTION | 17866.1782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 530 | 3754166.6667 | ACTION | 17866.1782 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 530 | 3754166.6667 | ACTION | 17866.6782 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17923.5318 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 17937.0318 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 18003.4114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 18003.4114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 18003.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 18005.4114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 18005.4114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 18005.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 18011.4114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 18011.4114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 18011.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 18031.4114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 18031.4114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 18031.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 1 | 7083.3333 | ACTION | 18032.4114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 1 | 7083.3333 | ACTION | 18032.4114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 1 | 7083.3333 | ACTION | 18032.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 16 | 113333.3333 | ACTION | 18048.4114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 16 | 113333.3333 | ACTION | 18048.4114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 16 | 113333.3333 | ACTION | 18048.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 5 | 35416.6667 | ACTION | 18053.4114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 5 | 35416.6667 | ACTION | 18053.4114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 5 | 35416.6667 | ACTION | 18053.9114 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 18107.3245 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 18107.3245 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay: No Assembly Storage Available | 183.7927 | 0 | ACTION | 18107.3245 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 170.2927 | 0 | ACTION | 18107.3245 | MooredSubInstallation
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 18107.8245 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 18115.3245 | MooredSubInstallation
| Towing Group 3 | Delay | 9 | 63750 | ACTION | 18116.3245 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 9 | 63750 | ACTION | 18116.3245 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 9 | 63750 | ACTION | 18116.8245 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 18122.3245 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 18122.3245 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 18122.8245 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 18127.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18131.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18135.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18139.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18143.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 18155.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18158.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18162.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18165.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 18189.8245 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 18259.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 18259.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 18260.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 18261.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 18261.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 18261.8245 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 18262.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 18267.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 18267.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 18268.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 18269.8245 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 18275.3245 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 77916.6667 | ACTION | 18279.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 85000 | ACTION | 18279.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 85000 | ACTION | 18279.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 18281.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18285.8245 | MooredSubInstallation
0.5 | Array Cable Installation Vessel | Mobilize | 72 | 337500 | ACTION | 18322.4684 | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 56250 | ACTION | 18328.4684 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 43 | 0 | ACTION | 18328.8245 | MooredSubInstallation
| Towing Group 2 | Delay | 50 | 354166.6667 | ACTION | 18329.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 50 | 354166.6667 | ACTION | 18329.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 50 | 354166.6667 | ACTION | 18329.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18332.8245 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 42500 | ACTION | 18335.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 42500 | ACTION | 18335.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 42500 | ACTION | 18335.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18336.8245 | MooredSubInstallation
| Towing Group 2 | Delay | 4 | 28333.3333 | ACTION | 18339.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 4 | 28333.3333 | ACTION | 18339.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 4 | 28333.3333 | ACTION | 18339.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18340.8245 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 18341.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 18341.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 21250 | ACTION | 18342.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 19 | 178125 | ACTION | 18347.4684 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 18347.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 18347.5578 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 18348.0578 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 18352.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18356.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18359.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 18361.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18365.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 18389.3245 | MooredSubInstallation
| Array Cable Installation Vessel | Transit | 48 | 450000 | ACTION | 18395.4684 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 18401.4708 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 18401.4708 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 18401.9708 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 18407.4708 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 18407.4708 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 18407.9708 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 18443.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 18461.3245 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 18 | 0 | ACTION | 18461.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 18469.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 18481.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 26 | 0 | ACTION | 18507.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18511.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18515.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18519.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18523.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 18535.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18538.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18542.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18545.8245 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 167 | 1565625 | ACTION | 18562.4684 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 18569.8245 | MooredSubInstallation
| Array Cable Installation Vessel | Transit | 17.6333 | 165312.2283 | ACTION | 18580.1017 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18582.1017 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18583.1017 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18588.6017 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18594.1017 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18595.1017 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 16.1123 | 151053.2152 | ACTION | 18611.2141 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18612.2141 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18617.7141 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18623.2141 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18625.2141 | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 18629.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 18641.8245 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 12.5 | 0 | ACTION | 18641.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 18649.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 18661.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 20 | 0 | ACTION | 18681.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18685.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18689.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18693.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18697.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 18709.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18713.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18716.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18720.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 18744.3245 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 18809.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 18816.3245 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 6.5 | 0 | ACTION | 18816.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 18824.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 18836.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18840.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18844.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18848.3245 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 227 | 2128125 | ACTION | 18852.2141 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18852.3245 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18853.2141 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18858.7141 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18864.2141 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 18864.3245 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18865.2141 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18867.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18871.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18874.8245 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 16.1123 | 151053.2152 | ACTION | 18881.3264 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18882.3264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18887.8264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18893.3264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18895.3264 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18896.3264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 18898.8245 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18901.8264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 18970.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 18978.8245 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 18984.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 18990.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18994.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18998.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19002.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19006.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 19018.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 30 | 0 | ACTION | 19048.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19052.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19055.8245 | MooredSubInstallation
| Towing Group 2 | Delay | 692 | 4901666.6667 | ACTION | 19099.9708 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 693 | 4908750 | ACTION | 19100.4708 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 693 | 4908750 | ACTION | 19100.4708 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 55 | 0 | ACTION | 19110.8245 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19114.3245 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 19138.3245 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 243 | 2278125 | ACTION | 19144.8264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19150.3264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19151.3264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 19152.3245 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 19156.3505 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19157.3505 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19162.8505 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19168.3505 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19170.3505 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19171.3505 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19176.8505 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19182.3505 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19183.3505 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 19188.3746 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19189.3746 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19194.8746 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19200.3746 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19202.3746 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19203.3746 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19208.8746 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 19210.3245 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19214.3746 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19215.3746 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 19220.3987 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19221.3987 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19226.8987 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19232.3987 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19234.3987 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19235.3987 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 19237.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 19237.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 19237.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 19239.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 19239.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 19239.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19240.8987 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Delay | 46 | 325833.3333 | ACTION | 19285.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 46 | 325833.3333 | ACTION | 19285.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 46 | 325833.3333 | ACTION | 19285.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 19291.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 19291.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 19291.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 19292.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 19292.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 19292.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 61 | 432083.3333 | ACTION | 19353.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 61 | 432083.3333 | ACTION | 19353.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 61 | 432083.3333 | ACTION | 19353.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 122 | 1143750 | ACTION | 19362.8987 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19368.3987 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19369.3987 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 19 | 134583.3333 | ACTION | 19372.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 19 | 134583.3333 | ACTION | 19372.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 19 | 134583.3333 | ACTION | 19372.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 19374.4229 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19375.4229 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 19378.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 19378.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 19378.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19380.9229 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 14 | 131250 | ACTION | 19394.9229 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19400.4229 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19402.4229 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19403.4229 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 37 | 262083.3333 | ACTION | 19415.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 37 | 262083.3333 | ACTION | 19415.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 37 | 262083.3333 | ACTION | 19415.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 11 | 77916.6667 | ACTION | 19426.2041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 11 | 77916.6667 | ACTION | 19426.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 11 | 77916.6667 | ACTION | 19426.7041 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 16.9131 | 119800.9226 | ACTION | 19443.1172 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay: No Assembly Storage Available | 232.7927 | 0 | ACTION | 19443.1172 | MooredSubInstallation
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 290.7927 | 0 | ACTION | 19443.1172 | MooredSubInstallation
| Towing Group 3 | Transit | 16.9131 | 119800.9226 | ACTION | 19443.6172 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 16.9131 | 119800.9226 | ACTION | 19443.6172 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 19449.1172 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 19449.6172 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 19449.6172 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 19451.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 19463.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19467.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19471.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19475.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19479.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 19491.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19494.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19498.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19501.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 19525.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 130 | 1218750 | ACTION | 19533.4229 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19538.9229 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19544.4229 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19545.4229 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 19550.447 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19551.447 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19556.947 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19562.447 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19564.447 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19565.447 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 19586.3505 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 19586.8505 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 19586.8505 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 19588.3505 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 23 | 215625 | ACTION | 19588.447 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 19588.8505 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 19588.8505 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19593.947 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 19594.3505 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 19594.8505 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 19594.8505 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 19597.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19599.447 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19600.447 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 37500 | ACTION | 19604.447 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 19605.6172 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 113333.3333 | ACTION | 19610.3505 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 113333.3333 | ACTION | 19610.8505 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 113333.3333 | ACTION | 19610.8505 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 19611.1172 | MooredSubInstallation
| Towing Group 2 | Delay | 3 | 21250 | ACTION | 19613.3505 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 3 | 21250 | ACTION | 19613.8505 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 3 | 21250 | ACTION | 19613.8505 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 28333.3333 | ACTION | 19617.3505 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 19617.6172 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 28333.3333 | ACTION | 19617.8505 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 28333.3333 | ACTION | 19617.8505 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19621.6172 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 19623.3505 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 19623.8505 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 19623.8505 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19625.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 23 | 215625 | ACTION | 19627.447 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.0241 | 9601.0518 | ACTION | 19628.4711 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19629.4711 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19629.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19633.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 19645.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19649.1172 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 20 | 187500 | ACTION | 19649.4711 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19652.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19654.9711 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19656.1172 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19660.4711 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19662.4711 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19663.4711 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19668.9711 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19674.4711 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19675.4711 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 19677.2635 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 19677.7635 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 19677.7635 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 19680.1172 | MooredSubInstallation
| Towing Group 2 | Delay | 41 | 290416.6667 | ACTION | 19718.2635 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 41 | 290416.6667 | ACTION | 19718.7635 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 41 | 290416.6667 | ACTION | 19718.7635 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 19724.2635 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 19724.7635 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 19724.7635 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 19752.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 19760.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 19772.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19776.1172 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 19779.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19780.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19784.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 19788.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 19800.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19803.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19807.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 19810.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 19834.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 182 | 1706250 | ACTION | 19857.4711 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 19862.4952 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19863.4952 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19868.9952 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19874.4952 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19876.4952 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19877.4952 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19882.9952 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 92 | 0 | ACTION | 19926.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 60 | 562500 | ACTION | 19942.9952 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19948.4952 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19949.4952 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 1 | 9375 | ACTION | 19950.4952 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 19998.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 20006.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 20018.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20022.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20026.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20030.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 82 | 768750 | ACTION | 20032.4952 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20034.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4.0241 | 37726.0518 | ACTION | 20036.5193 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20037.5193 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20043.0193 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 20046.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20048.5193 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20050.1172 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20050.5193 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20051.5193 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20053.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20057.0193 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20057.1172 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20062.5193 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20063.5193 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20068.5434 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20069.5434 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20075.0434 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20080.5434 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 20081.1172 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20082.5434 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20083.5434 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20089.0434 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20094.5434 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20095.5434 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20100.5675 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20101.5675 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20107.0675 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20112.5675 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20114.5675 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20115.5675 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20121.0675 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 97 | 0 | ACTION | 20178.1172 | MooredSubInstallation
| Towing Group 2 | Delay | 516 | 3655000 | ACTION | 20240.2635 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 516 | 3655000 | ACTION | 20240.7635 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 516 | 3655000 | ACTION | 20240.7635 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 20250.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 20258.1172 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 141 | 1321875 | ACTION | 20262.0675 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20267.5675 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20268.5675 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 20270.1172 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 37500 | ACTION | 20272.5675 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20274.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20278.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20282.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20286.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 20298.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20301.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20305.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20308.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 20332.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 83 | 778125 | ACTION | 20355.5675 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.0241 | 9601.0518 | ACTION | 20356.5916 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20357.5916 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20363.0916 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20368.5916 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20370.5916 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20371.5916 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20377.0916 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 20377.4968 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 20377.9968 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 20377.9968 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 20379.4968 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 20379.9968 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 20379.9968 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20382.5916 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20383.5916 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 20385.4968 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 20385.9968 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 20385.9968 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20388.6158 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20389.6158 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20395.1158 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20400.6158 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20402.6158 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20403.6158 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 20404.6172 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 20405.4968 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 20405.9968 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 20405.9968 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20409.1158 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 20411.4968 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 20411.9968 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 20411.9968 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 20412.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20414.6158 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20415.6158 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20420.6399 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20421.6399 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 20424.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20427.1399 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20428.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20432.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20436.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20440.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 24 | 225000 | ACTION | 20451.1399 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 20452.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20456.1172 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20456.6399 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20458.6399 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20459.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20459.6399 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 20465.4099 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 20465.6172 | MooredSubInstallation
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 20465.9099 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 20465.9099 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20469.1172 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 20471.4099 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 20471.9099 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 20471.9099 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 20493.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 20565.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 20573.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 20585.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20589.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20593.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20597.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20601.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 20613.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 20619.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20622.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20626.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20629.6172 | MooredSubInstallation
| Towing Group 2 | Delay | 159 | 1126250 | ACTION | 20630.4099 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 159 | 1126250 | ACTION | 20630.9099 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 159 | 1126250 | ACTION | 20630.9099 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 188 | 1762500 | ACTION | 20647.6399 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20653.1399 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 20653.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20658.6399 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20659.6399 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20664.664 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20665.664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20671.164 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20676.664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20678.664 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20679.664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20685.164 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20690.664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20691.664 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20696.6881 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20697.6881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20703.1881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20708.6881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20710.6881 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20711.6881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20717.1881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20722.6881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20723.6881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 20725.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20728.7122 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20729.7122 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 20733.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20735.2122 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20740.7122 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20742.7122 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20743.7122 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 20745.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20749.2122 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20749.6172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20753.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20754.7122 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20755.7122 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20757.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20760.7363 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 20761.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20761.7363 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20767.2363 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 20767.6432 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 20768.1432 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 20768.1432 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 20769.6432 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 20770.1432 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 20770.1432 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20772.7363 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 20773.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20774.7363 | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 20775.6432 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20775.7363 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 20776.1432 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 20776.1432 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20777.1172 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20780.6172 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20781.2363 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 20784.1172 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20786.7363 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20787.7363 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20792.7604 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20793.7604 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 20795.6432 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 20796.1432 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 20796.1432 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20799.2604 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 20801.6432 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 20802.1432 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 20802.1432 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20804.7604 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20806.7604 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20807.7604 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 20808.1172 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20813.2604 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 26 | 243750 | ACTION | 20839.2604 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20844.7604 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20845.7604 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20850.7845 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20851.7845 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 53.9131 | 381884.256 | ACTION | 20855.5562 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 20856.0562 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 20856.0562 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20857.2845 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 20861.5562 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 20862.0562 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 20862.0562 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 20880.1172 | MooredSubInstallation
| Towing Group 3 | Delay | 65 | 460416.6667 | ACTION | 20927.0562 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 65 | 460416.6667 | ACTION | 20927.0562 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 66 | 467500 | ACTION | 20927.5562 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 92 | 862500 | ACTION | 20949.2845 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20954.7845 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20956.7845 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20957.7845 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20963.2845 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20968.7845 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20969.7845 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 20974.8087 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20975.8087 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 16 | 150000 | ACTION | 20991.8087 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20997.3087 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21002.8087 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21004.8087 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21005.8087 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21011.3087 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21016.8087 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21017.8087 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21022.8328 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21023.8328 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21029.3328 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21034.8328 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21036.8328 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21037.8328 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21043.3328 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21048.8328 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21049.8328 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21054.8569 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21055.8569 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21061.3569 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 21064.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 21064.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 21064.7895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 21066.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 21066.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 21066.7895 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21066.8569 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21068.8569 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21069.8569 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 21072.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 21072.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 21072.7895 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21075.3569 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21080.8569 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21081.8569 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21086.881 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21087.881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 113333.3333 | ACTION | 21088.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 113333.3333 | ACTION | 21088.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 113333.3333 | ACTION | 21088.7895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 1 | 7083.3333 | ACTION | 21089.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 1 | 7083.3333 | ACTION | 21089.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 1 | 7083.3333 | ACTION | 21089.7895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 28333.3333 | ACTION | 21093.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 28333.3333 | ACTION | 21093.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21093.381 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 28333.3333 | ACTION | 21093.7895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 21099.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 21099.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 21099.7895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 3 | 21250 | ACTION | 21102.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 3 | 21250 | ACTION | 21102.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 3 | 21250 | ACTION | 21102.7895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 11 | 77916.6667 | ACTION | 21113.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 11 | 77916.6667 | ACTION | 21113.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 11 | 77916.6667 | ACTION | 21113.7895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 20 | 141666.6667 | ACTION | 21133.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 20 | 141666.6667 | ACTION | 21133.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 20 | 141666.6667 | ACTION | 21133.7895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 4 | 28333.3333 | ACTION | 21137.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 4 | 28333.3333 | ACTION | 21137.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 4 | 28333.3333 | ACTION | 21137.7895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 3 | 21250 | ACTION | 21140.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 3 | 21250 | ACTION | 21140.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 3 | 21250 | ACTION | 21140.7895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 1 | 7083.3333 | ACTION | 21141.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 1 | 7083.3333 | ACTION | 21141.2895 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 1 | 7083.3333 | ACTION | 21141.7895 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 68 | 637500 | ACTION | 21161.381 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21166.881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21168.881 | ArrayCableInstallation
| Towing Group 3 | Transit | 27.9131 | 197717.5893 | ACTION | 21169.2026 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 27.9131 | 197717.5893 | ACTION | 21169.2026 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 27.9131 | 197717.5893 | ACTION | 21169.7026 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21169.881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 21175.2026 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 21175.2026 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21175.381 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21180.881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21181.881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21186.9051 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21187.9051 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21193.4051 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21198.9051 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21200.9051 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21201.9051 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21207.4051 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21212.9051 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21213.9051 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21218.9292 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21219.9292 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21225.4292 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21230.9292 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21232.9292 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21233.9292 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21239.4292 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21244.9292 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21245.9292 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 37500 | ACTION | 21249.9292 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Towing Group 3 | Delay | 97 | 687083.3333 | ACTION | 21272.2026 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 97 | 687083.3333 | ACTION | 21272.2026 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 25 | 234375 | ACTION | 21274.9292 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.0241 | 9601.0518 | ACTION | 21275.9533 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21276.9533 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21282.4533 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21287.9533 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21289.9533 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21290.9533 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21296.4533 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21301.9533 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21302.9533 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21307.9774 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21308.9774 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21314.4774 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21319.9774 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21321.9774 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21322.9774 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21328.4774 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21333.9774 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21334.9774 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21340.0016 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21341.0016 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21346.5016 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21352.0016 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21354.0016 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21355.0016 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21360.5016 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21366.0016 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21367.0016 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21372.0257 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21373.0257 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 5 | 46875 | ACTION | 21378.0257 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21383.5257 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21389.0257 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21391.0257 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21392.0257 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21397.5257 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21403.0257 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21404.0257 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21409.0498 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Towing Group 3 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 21409.4358 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 137.2333 | 972069.0152 | ACTION | 21409.4358 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21410.0498 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 21411.4358 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 21411.4358 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21415.5498 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 21417.4358 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 21417.4358 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21421.0498 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21423.0498 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21424.0498 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21429.5498 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21435.0498 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21436.0498 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 21437.4358 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 21437.4358 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21441.0739 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21442.0739 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 21443.4358 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 21443.4358 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21447.5739 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21453.0739 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21455.0739 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21456.0739 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 16 | 150000 | ACTION | 21472.0739 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21477.5739 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 53.9131 | 381884.256 | ACTION | 21497.3489 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 53.9131 | 381884.256 | ACTION | 21497.3489 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 24 | 225000 | ACTION | 21501.5739 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21507.0739 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21508.0739 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21513.098 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21514.098 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21519.598 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21525.098 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21527.098 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21528.098 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21533.598 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21539.098 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21540.098 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21545.1221 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21546.1221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21551.6221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21557.1221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21559.1221 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21560.1221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21565.6221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21571.1221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21572.1221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21577.1462 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21578.1462 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 1 | 9375 | ACTION | 21579.1462 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21584.6462 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21590.1462 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21592.1462 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21593.1462 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21598.6462 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21604.1462 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21605.1462 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21610.1703 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21611.1703 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21616.6703 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21622.1703 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21624.1703 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21625.1703 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21630.6703 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 126 | 1181250 | ACTION | 21756.6703 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21762.1703 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21763.1703 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21768.1944 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21769.1944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21774.6944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21780.1944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21782.1944 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21783.1944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21788.6944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21794.1944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21795.1944 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21800.2186 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21801.2186 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21806.7186 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21812.2186 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21814.2186 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21815.2186 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21820.7186 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21826.2186 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21827.2186 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21832.2427 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21833.2427 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21838.7427 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21844.2427 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21846.2427 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21847.2427 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21852.7427 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21858.2427 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21859.2427 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 18750 | ACTION | 21861.2427 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 29 | 271875 | ACTION | 21890.2427 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 3.0241 | 28351.0518 | ACTION | 21893.2668 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21894.2668 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21899.7668 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21905.2668 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21907.2668 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21908.2668 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21913.7668 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21919.2668 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21920.2668 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21925.2909 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21926.2909 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21931.7909 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21937.2909 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21939.2909 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21940.2909 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21945.7909 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21951.2909 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21952.2909 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21957.315 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21958.315 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21963.815 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21969.315 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21971.315 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21972.315 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21977.815 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21983.315 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21984.315 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 21989.3391 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21990.3391 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21995.8391 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22001.3391 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22003.3391 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22004.3391 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22009.8391 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22015.3391 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22016.3391 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22021.3632 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22022.3632 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22027.8632 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22033.3632 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22035.3632 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22036.3632 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22041.8632 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22047.3632 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22048.3632 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22053.3873 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22054.3873 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22059.8873 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22065.3873 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22067.3873 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22068.3873 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22073.8873 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22079.3873 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22080.3873 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22085.4115 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22086.4115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22091.9115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22097.4115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22099.4115 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22100.4115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22105.9115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22111.4115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22112.4115 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22117.4356 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22118.4356 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22123.9356 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 82 | 768750 | ACTION | 22205.9356 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22211.4356 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22213.4356 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22214.4356 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22219.9356 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22225.4356 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22226.4356 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22231.4597 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22232.4597 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22237.9597 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22243.4597 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22245.4597 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22246.4597 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22251.9597 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22257.4597 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22258.4597 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22263.4838 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22264.4838 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 73 | 684375 | ACTION | 22337.4838 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22342.9838 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22348.4838 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22350.4838 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22351.4838 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22356.9838 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22362.4838 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22363.4838 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22368.5079 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22369.5079 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22375.0079 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22380.5079 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22382.5079 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22383.5079 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22389.0079 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22394.5079 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22395.5079 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22400.532 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22401.532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22407.032 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22412.532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22414.532 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22415.532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 64 | 600000 | ACTION | 22479.532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22485.032 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22490.532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22491.532 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22496.5561 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22497.5561 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22503.0561 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22508.5561 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22510.5561 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22511.5561 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22517.0561 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22522.5561 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22523.5561 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22528.5802 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22529.5802 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22535.0802 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22540.5802 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22542.5802 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22543.5802 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22549.0802 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22554.5802 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22555.5802 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22560.6044 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22561.6044 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22567.1044 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22572.6044 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22574.6044 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22575.6044 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22581.1044 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22586.6044 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22587.6044 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22592.6285 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22593.6285 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22599.1285 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22604.6285 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22606.6285 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22607.6285 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22613.1285 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22618.6285 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22619.6285 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22624.6526 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22625.6526 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22631.1526 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22636.6526 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22638.6526 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22639.6526 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22645.1526 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22650.6526 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22651.6526 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22656.6767 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22657.6767 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22663.1767 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22668.6767 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22670.6767 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22671.6767 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22677.1767 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22682.6767 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22683.6767 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22688.7008 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22689.7008 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22695.2008 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22700.7008 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22702.7008 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22703.7008 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22709.2008 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22714.7008 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22715.7008 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22720.7249 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22721.7249 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 29 | 271875 | ACTION | 22750.7249 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22756.2249 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22761.7249 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22763.7249 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22764.7249 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22770.2249 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22775.7249 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22776.7249 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.0241 | 47101.0518 | ACTION | 22781.749 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22782.749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22788.249 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22793.749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22795.749 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22796.749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22802.249 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22807.749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22808.749 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 12.133 | 113746.4839 | ACTION | 22820.882 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22821.882 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22827.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22832.882 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22834.882 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22835.882 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22841.382 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22846.882 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22847.882 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 12.133 | 113746.4839 | ACTION | 22860.0149 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22861.0149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22866.5149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22872.0149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22874.0149 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22875.0149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22880.5149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22886.0149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22887.0149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8.3958 | 78710.3425 | ACTION | 22895.4107 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22896.4107 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22901.9107 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22907.4107 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22909.4107 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22910.4107 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22915.9107 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22921.4107 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22922.4107 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8.3958 | 78710.3425 | ACTION | 22930.8065 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22931.8065 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22937.3065 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22942.8065 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22944.8065 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22945.8065 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22951.3065 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22956.8065 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22957.8065 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.5199 | 51748.6401 | ACTION | 22963.3263 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22964.3263 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22969.8263 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22975.3263 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22977.3263 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22978.3263 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 56 | 525000 | ACTION | 23034.3263 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23039.8263 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23045.3263 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23046.3263 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.5199 | 51748.6401 | ACTION | 23051.8462 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23052.8462 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23058.3462 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23063.8462 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 65.6333 | 615312.2283 | ACTION | 23129.4795 | ArrayCableInstallation | ArrayCableInstallation | FALSE