## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | include_onshore_construction | max_waveheight | max_windspeed | transit_speed | num_vessels | num_ahts_vessels
0.5 | Export Cable Installation Vessel | Mobilize | 72 | 450000 | ACTION | 0 | ExportCableInstallation
1 | Mooring System Installation Vessel | Mobilize | 168 | 700000 | ACTION | 0 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 4 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Load Cable | 6 | 75000 | ACTION | 6 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 45 | 187500 | ACTION | 54 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 59 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 64 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 59 | 737500 | ACTION | 65 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Tow Plow | 0.4 | 5000 | ACTION | 65.4 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Pull Winch | 0.4 | 5000 | ACTION | 65.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Prepare Cable | 1 | 12500 | ACTION | 66.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 69 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 72.3 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 77.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Lower Cable | 1 | 12500 | ACTION | 78.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 83.8402 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 85.8402 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 89.8402 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 104.8487 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 107.8572 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 109.8572 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 113.8572 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 128.8657 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 131.8742 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 133.8742 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 137.8742 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 152.8827 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 155.8912 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 157.8912 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 83 | 1037500 | ACTION | 161.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 161.8912 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 92 | 383333.3333 | ACTION | 253.8912 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 268.8997 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 271.9082 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 273.9082 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 277.9082 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 292.9167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 295.9252 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 297.9252 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 301.9252 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 143 | 1787500 | ACTION | 304.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 316.9337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 319.9422 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 321.9422 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 325.9422 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 340.9507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 343.9592 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 345.9592 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 349.9592 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 51 | 637500 | ACTION | 355.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 364.9677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 367.9762 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 369.9762 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 373.9762 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 26 | 325000 | ACTION | 381.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 388.9847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 391.9932 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 393.9932 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 14 | 175000 | ACTION | 395.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 397.9932 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 176 | 733333.3333 | ACTION | 573.9932 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 589.0017 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 194 | 2425000 | ACTION | 589.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 592.0102 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 594.0102 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 7 | 87500 | ACTION | 596.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 598.0102 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 41 | 170833.3333 | ACTION | 639.0102 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 654.0187 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 657.0272 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 659.0272 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 663.0272 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 678.0357 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 681.0442 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 695.8844 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 700.8844 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 705.8844 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 710.8844 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 715.8844 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 124 | 1550000 | ACTION | 720.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 730.7246 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 732.7246 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 736.7246 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 751.7331 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 754.7416 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 756.7416 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 760.7416 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 51 | 637500 | ACTION | 771.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 775.7501 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 778.7586 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 780.7586 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 784.7586 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 88 | 366666.6667 | ACTION | 872.7586 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 887.7671 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 890.7756 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 892.7756 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 896.7756 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 911.7841 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 914.7926 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 916.7926 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 920.7926 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 69 | 287500 | ACTION | 989.7926 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1004.8011 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1007.8096 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1009.8096 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1013.8096 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1028.8181 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1031.8266 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1033.8266 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1037.8266 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1052.8351 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1055.8436 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1057.8436 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 289 | 3612500 | ACTION | 1060.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1061.8436 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1076.8521 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 19 | 237500 | ACTION | 1079.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1079.8606 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1081.8606 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1085.8606 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 80 | 333333.3333 | ACTION | 1165.8606 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substation Assembly Line 1 | Substation Substructure Assembly | 336 | 0 | ACTION | 1167.5628 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1180.8691 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 1188.8691 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substation Assembly Line 1 | Attach Topside | 24 | 0 | ACTION | 1191.5628 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay: Waiting on Substation Assembly | 360 | 1500000 | ACTION | 1191.5628 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1191.8776 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1193.8776 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1197.8776 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 46 | 191666.6667 | ACTION | 1237.5628 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 40 | 166666.6667 | ACTION | 1237.8776 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1252.8861 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1255.8946 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1257.8946 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1261.8946 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Tow Substation to Site | 24.7337 | 103056.9444 | ACTION | 1262.2965 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1264.2965 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 1266.2965 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1272.2965 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1276.2965 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1276.9031 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1279.9116 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 201 | 2512500 | ACTION | 1280.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 1 | 12500 | ACTION | 1281.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1281.9116 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 4 | 50000 | ACTION | 1285.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1285.9116 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 14.0085 | 58368.75 | ACTION | 1290.305 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1293.3135 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1300.9201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1303.9286 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 19 | 237500 | ACTION | 1304.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1315.3135 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 1318.7688 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1323.7688 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1327.3135 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1328.7688 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1331.3135 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1333.7688 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1338.7688 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 14.0085 | 58368.75 | ACTION | 1345.322 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1348.3305 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 1353.609 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1355.609 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1359.609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 12 | 50000 | ACTION | 1360.3305 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 35 | 145833.3333 | ACTION | 1394.609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1409.6175 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 50 | 208333.3333 | ACTION | 1410.3305 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1412.626 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1414.626 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1418.626 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 10 | 41666.6667 | ACTION | 1420.3305 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 124 | 1550000 | ACTION | 1428.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 1 | 12500 | ACTION | 1429.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1432.3305 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 3 | 37500 | ACTION | 1432.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1433.6345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1436.3305 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1436.643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1438.643 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1442.643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 12 | 150000 | ACTION | 1444.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 14.0085 | 58368.75 | ACTION | 1450.339 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1453.3475 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1457.6515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1460.66 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1462.66 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1466.66 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 29 | 362500 | ACTION | 1473.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1475.3475 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1481.6685 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1484.677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 11 | 137500 | ACTION | 1484.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1486.677 | MooringSystemInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1487.3475 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1490.677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 1502.1877 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1505.6855 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1508.694 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1510.694 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 46 | 191666.6667 | ACTION | 1556.694 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1560.694 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1575.7025 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 15 | 62500 | ACTION | 1590.7025 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1593.711 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1595.711 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1599.711 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1614.7195 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1617.728 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1619.728 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1623.728 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 145 | 1812500 | ACTION | 1629.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 5 | 62500 | ACTION | 1634.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1638.7365 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1641.745 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1643.745 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1647.745 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 5 | 20833.3333 | ACTION | 1652.745 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 31 | 387500 | ACTION | 1665.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1667.7535 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1670.762 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1672.762 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1676.762 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1691.7705 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1694.779 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1696.779 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1700.779 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1715.7875 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1718.796 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1720.796 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1724.796 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1739.8045 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1742.813 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 82 | 1025000 | ACTION | 1747.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Delay | 7 | 87500 | ACTION | 1754.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 1757.6532 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 7 | 87500 | ACTION | 1761.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1762.6532 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1767.6532 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1772.6532 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1777.6532 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 19 | 237500 | ACTION | 1780.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 1792.4934 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1794.4934 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1798.4934 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1813.5019 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1816.5104 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1818.5104 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 40 | 500000 | ACTION | 1820.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1822.5104 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1837.5189 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1840.5274 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1842.5274 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1846.5274 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1861.5359 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1864.5444 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1866.5444 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1870.5444 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 55 | 687500 | ACTION | 1875.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1885.5529 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1888.5614 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 13 | 162500 | ACTION | 1888.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1890.5614 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1894.5614 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 1907.5614 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1922.5699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1925.5784 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1927.5784 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1931.5784 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 1946.5869 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 1949.5954 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1951.5954 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1955.5954 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 30 | 125000 | ACTION | 1985.5954 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2000.6039 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2003.6124 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2005.6124 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2009.6124 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2024.6209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2027.6294 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2029.6294 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 2036.6294 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2040.6294 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2055.6379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2058.6464 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2060.6464 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 67 | 279166.6667 | ACTION | 2127.6464 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2131.6464 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2146.6549 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2149.6634 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2151.6634 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2155.6634 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 281 | 3512500 | ACTION | 2169.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2170.6719 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2173.6804 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2175.6804 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2179.6804 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 13 | 162500 | ACTION | 2182.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Delay | 54 | 225000 | ACTION | 2233.6804 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 61 | 762500 | ACTION | 2243.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2248.6889 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2251.6974 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 19 | 237500 | ACTION | 2262.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 2266.5376 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2271.5376 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 77 | 320833.3333 | ACTION | 2348.5376 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2353.5376 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2358.5376 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2363.5376 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 7 | 29166.6667 | ACTION | 2370.5376 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 2381.5376 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 5 | 20833.3333 | ACTION | 2386.5376 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 27 | 112500 | ACTION | 2413.5376 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 2.8402 | 11834.1667 | ACTION | 2416.3778 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2418.3778 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2422.3778 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 2443.3778 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2458.3863 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2461.3948 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2463.3948 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2467.3948 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2482.4033 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2485.4118 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2487.4118 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2491.4118 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2506.4203 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2509.4288 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2511.4288 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2515.4288 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 261 | 3262500 | ACTION | 2523.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2530.4373 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2533.4458 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2535.4458 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2539.4458 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 17 | 212500 | ACTION | 2540.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2554.4543 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2557.4628 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2559.4628 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2563.4628 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 37 | 462500 | ACTION | 2577.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2578.4713 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2581.4798 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2583.4798 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2587.4798 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 20 | 250000 | ACTION | 2597.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2602.4883 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2605.4968 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2607.4968 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 6 | 25000 | ACTION | 2613.4968 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2617.4968 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2632.5053 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2635.5138 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2637.5138 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2641.5138 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 58 | 725000 | ACTION | 2655.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2656.5223 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2659.5308 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2661.5308 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2665.5308 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 19 | 237500 | ACTION | 2674.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2680.5393 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2683.5478 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2685.5478 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2689.5478 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2704.5563 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2707.5648 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2709.5648 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2713.5648 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 23 | 95833.3333 | ACTION | 2736.5648 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2751.5733 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2754.5818 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 88 | 1100000 | ACTION | 2762.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 2769.422 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2774.422 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 13 | 162500 | ACTION | 2775.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2779.422 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2784.422 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2789.422 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 2804.2622 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2806.2622 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2810.2622 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2825.2707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2828.2792 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2830.2792 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2834.2792 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 68 | 850000 | ACTION | 2843.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2849.2877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2852.2962 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2854.2962 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2858.2962 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2873.3047 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2876.3132 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2878.3132 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 37 | 462500 | ACTION | 2880.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2882.3132 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2897.3217 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 18 | 225000 | ACTION | 2898.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2900.3302 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2902.3302 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2906.3302 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2921.3387 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2924.3472 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2926.3472 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2930.3472 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2945.3557 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2948.3642 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2950.3642 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 54 | 675000 | ACTION | 2952.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2954.3642 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 3 | 37500 | ACTION | 2955.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 10 | 125000 | ACTION | 2965.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2969.3727 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2972.3812 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2974.3812 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2978.3812 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 2993.3897 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 2996.3982 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2998.3982 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3002.3982 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3017.4067 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 39 | 162500 | ACTION | 3056.4067 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3059.4152 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3061.4152 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3065.4152 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3080.4237 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3083.4322 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3085.4322 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3089.4322 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3104.4407 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 141 | 1762500 | ACTION | 3106.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3107.4492 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3109.4492 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3113.4492 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 21 | 262500 | ACTION | 3127.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3128.4577 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3131.4662 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 8 | 100000 | ACTION | 3135.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 4 | 50000 | ACTION | 3139.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 3146.3064 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3151.3064 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3156.3064 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3161.3064 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3166.3064 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 9 | 37500 | ACTION | 3175.3064 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3183.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 3183.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 12 | 50000 | ACTION | 3187.3064 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3191.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 5.8402 | 24334.1667 | ACTION | 3193.1466 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3195.1466 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3199.1466 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3203.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3207.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3211.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3214.1551 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3215.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 3216.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3217.1636 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3219.1636 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3220.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3223.1636 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 85 | 1062500 | ACTION | 3224.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 3232.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3236.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3238.1721 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3239.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3241.1806 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3243.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3243.1806 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3247.1806 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 30 | 375000 | ACTION | 3254.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3262.1891 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3265.1976 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3267.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3267.1976 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3271.1976 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3286.2061 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3289.2146 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3291.2146 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3295.2146 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 43 | 537500 | ACTION | 3297.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 2.5467 | 31833.15 | ACTION | 3300.3467 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Position Onsite | 2 | 25000 | ACTION | 3302.3467 | ExportCableInstallation
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 3307.8467 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3310.2231 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3313.2316 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 3313.3467 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3315.2316 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3319.2316 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Transit | 12.9045 | 161306.5217 | ACTION | 3326.2512 | ExportCableInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3334.2401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3337.2486 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 3339.1574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 323.5 | 2291458.3333 | ACTION | 3339.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3339.2486 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3343.2486 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3351.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 12.5 | 0 | ACTION | 3351.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3358.2571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3359.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3361.2656 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3363.2656 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3367.2656 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3371.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3382.2741 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3385.2826 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3387.2826 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3391.2826 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 54 | 382500 | ACTION | 3393.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 22 | 0 | ACTION | 3393.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3397.6574 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 3399.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3401.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3405.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3406.2911 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3409.2996 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3409.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3411.2996 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3415.2996 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 69 | 287500 | ACTION | 3484.2996 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 89 | 630416.6667 | ACTION | 3488.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 79 | 0 | ACTION | 3488.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3499.3081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 3500.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3502.3166 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3504.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3504.3166 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3507.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3508.3166 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3511.1574 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 3515.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 3517.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3519.6574 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 3523.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3523.3251 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3526.3336 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3528.3336 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3532.3336 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3535.1574 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 3543.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3547.3421 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 3549.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3550.3506 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 3559.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 3565.1908 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3570.1908 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3575.1908 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3580.1908 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3585.1908 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 3600.031 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3602.031 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3606.031 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 3607.1574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 591.5 | 4189791.6667 | ACTION | 3607.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 3613.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3615.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3621.0395 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3624.048 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3626.048 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3627.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3630.048 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3631.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3635.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3639.1574 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 3640.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 3642.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3643.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3645.0565 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3648.065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 3648.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3650.065 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3654.065 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 3655.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3658.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3662.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3665.6574 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 3668.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3669.0735 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3672.082 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3674.082 | MooringSystemInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 3674.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3678.082 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 3684.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3687.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3689.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3693.0905 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3696.099 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3698.099 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3702.099 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3717.1075 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3720.116 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3722.116 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3726.116 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3741.1245 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3744.133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3746.133 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3750.133 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 3761.6574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 746 | 5284166.6667 | ACTION | 3761.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3765.1415 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 3767.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3768.15 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3769.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3770.15 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3774.15 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3781.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3785.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3789.1585 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3789.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3792.167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3793.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3794.167 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3798.167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 36 | 255000 | ACTION | 3803.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 10 | 0 | ACTION | 3803.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3807.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3813.1755 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3816.184 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3818.184 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 3819.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3822.184 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3823.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3826.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3830.1574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 3830.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 3832.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3837.1925 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 3838.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3840.201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3842.201 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3846.201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 3854.1574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 3855.6574 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 3858.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3861.2095 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3864.218 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 3864.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3866.218 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3870.218 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 3875.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3885.2265 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3888.235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 3903.0752 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3908.0752 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3913.0752 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3918.0752 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3923.0752 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 3926.1574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 366.4177 | 2595458.5335 | ACTION | 3926.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 3932.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 3934.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 3937.9154 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3939.9154 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3943.9154 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 3946.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3950.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3954.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3958.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3958.9239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 3959.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 3961.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3961.9324 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 3962.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3963.9324 | MooringSystemInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 3967.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3967.9324 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 3974.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 3982.9409 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 10 | 0 | ACTION | 3984.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 3985.9494 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 3987.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3987.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3987.9494 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3991.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3991.9494 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 3993.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 3994.6574 | MooredSubInstallation
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 4003.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4006.9579 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4009.9664 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4011.9664 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4015.9664 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4018.6574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4023.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4030.9749 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4033.9834 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4035.9834 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4039.9834 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 24 | 100000 | ACTION | 4063.9834 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4078.9919 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4082.0004 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4084.0004 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4088.0004 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 79 | 329166.6667 | ACTION | 4167.0004 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 155 | 0 | ACTION | 4173.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4182.0089 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4185.0174 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4187.0174 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4191.0174 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4191.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4206.0259 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4209.0344 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4211.0344 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4215.0344 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4230.0429 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4233.0514 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4235.0514 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4239.0514 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4245.6574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 560.9177 | 3973166.8669 | ACTION | 4245.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 4251.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4253.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4254.0599 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4257.0684 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4259.0684 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4263.0684 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4265.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4278.0769 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4281.0854 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4283.0854 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4287.0854 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4302.0939 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4305.1024 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4307.1024 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4311.1024 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4326.1109 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 77 | 545416.6667 | ACTION | 4328.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 63 | 0 | ACTION | 4328.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4329.1194 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4332.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4336.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4340.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 4343.9596 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4344.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4348.9596 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4353.9596 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 4355.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4356.6574 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 4357.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4358.9596 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4359.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4363.9596 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 4378.7998 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4380.7998 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4384.7998 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4399.8083 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4402.8168 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 17 | 70833.3333 | ACTION | 4419.8168 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4421.8168 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4425.8168 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 75 | 531250 | ACTION | 4432.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 4438.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 82 | 0 | ACTION | 4438.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4440.8253 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4442.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4443.8338 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4445.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4445.8338 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4449.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4449.8338 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 4458.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 4464.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4464.8423 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4467.8508 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4469.8508 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4473.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4473.8508 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 4475.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4488.8593 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4491.8678 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4493.8678 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4497.8678 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4512.8763 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4515.8848 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4517.8848 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4521.8848 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4527.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4536.8933 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4539.9018 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4541.9018 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 4545.1574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 669.9177 | 4745250.2002 | ACTION | 4545.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4545.9018 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 4553.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4560.9103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4563.9188 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 4565.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4565.9188 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4569.9188 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4584.9273 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4587.9358 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4589.9358 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4593.9358 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 17 | 70833.3333 | ACTION | 4610.9358 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4625.9443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4628.9528 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4630.9528 | MooringSystemInstallation
| Towing Group 3 | Delay | 89 | 630416.6667 | ACTION | 4634.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 69 | 0 | ACTION | 4634.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4634.9528 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4638.1574 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 4640.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4642.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4646.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4649.9613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 4650.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4652.9698 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4654.9698 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4658.9698 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4673.9783 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4676.9868 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 27 | 0 | ACTION | 4677.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4678.9868 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4682.9868 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 4689.1574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4695.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4697.9953 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4701.0038 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 4715.844 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4720.844 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4725.844 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 6 | 25000 | ACTION | 4731.844 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4736.844 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4741.844 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 4756.6842 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4758.6842 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4762.6842 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 125 | 885416.6667 | ACTION | 4765.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 86 | 0 | ACTION | 4775.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4777.6927 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4778.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4780.7012 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4782.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4782.7012 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 4785.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4786.7012 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 4792.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 4794.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 4800.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4801.7097 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4804.7182 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4806.7182 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 4809.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4810.7182 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 4820.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4825.7267 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 4826.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4828.7352 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4830.7352 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4834.7352 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 4836.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4849.7437 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4852.7522 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4854.7522 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4858.7522 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 4863.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 74 | 308333.3333 | ACTION | 4932.7522 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4947.7607 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4950.7692 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4952.7692 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4956.7692 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4971.7777 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4974.7862 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4976.7862 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4980.7862 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 4995.7947 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 4998.8032 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5000.8032 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5004.8032 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5019.8117 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5022.8202 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5024.8202 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5028.8202 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5031.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 45 | 187500 | ACTION | 5073.8202 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5088.8287 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5091.8372 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5093.8372 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5097.8372 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 18 | 75000 | ACTION | 5115.8372 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 308 | 0 | ACTION | 5117.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5130.8457 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5133.8542 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5135.8542 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5139.8542 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5154.8627 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5157.8712 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5159.8712 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5163.8712 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5178.8797 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5181.8882 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5189.6574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 1185.9177 | 8400250.2002 | ACTION | 5189.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 5195.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 5196.7284 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5197.6574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5199.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5201.7284 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5206.7284 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5209.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5211.7284 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5213.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5216.7284 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5217.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5221.6574 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 5222.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 5224.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5225.6574 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 5230.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 5231.5686 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5233.5686 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5237.5686 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5237.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5241.1574 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 5250.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5252.5771 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5255.5856 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 5256.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5257.5856 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5261.5856 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 5267.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5276.5941 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5279.6026 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 40 | 0 | ACTION | 5281.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5281.6026 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5284.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5285.6026 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5288.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5300.6111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5303.6196 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5305.6196 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5309.6196 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5312.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5324.6281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5327.6366 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5329.6366 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5333.6366 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5348.6451 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5351.6536 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5353.6536 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5357.6536 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5367.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5372.6621 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5375.6706 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5377.6706 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5381.6706 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5384.1574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 908.9177 | 6438166.8669 | ACTION | 5384.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 16.5 | 0 | ACTION | 5384.1574 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 5390.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5392.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5396.6791 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5399.6876 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5401.6876 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5404.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5405.6876 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5420.6961 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5423.7046 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5425.7046 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 24 | 0 | ACTION | 5428.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5429.7046 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5432.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5436.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5440.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5444.7131 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5447.7216 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5449.7216 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5453.7216 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 24 | 100000 | ACTION | 5477.7216 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5492.7301 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 5500.7301 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5503.7386 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5505.7386 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5509.7386 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5552.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 66 | 275000 | ACTION | 5575.7386 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 199 | 1409583.3333 | ACTION | 5589.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 149 | 0 | ACTION | 5589.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5590.7471 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5593.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5593.7556 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5595.7556 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5599.7556 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5605.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5608.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5612.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5614.7641 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5615.6574 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 5616.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5617.7726 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 5618.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 5624.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 5632.6128 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5637.6128 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5639.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5642.6128 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 5644.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5647.6128 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 5650.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 2 | 14166.6667 | ACTION | 5652.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5652.6128 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 5667.453 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5669.453 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5673.453 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 18 | 75000 | ACTION | 5691.453 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 59 | 0 | ACTION | 5698.6574 | MooredSubInstallation
| Towing Group 2 | Delay | 53 | 375416.6667 | ACTION | 5705.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5706.4615 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5709.47 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5711.47 | MooringSystemInstallation
| Towing Group 2 | Transit | 8.6001 | 60917.6786 | ACTION | 5713.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5715.47 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5730.4785 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5733.487 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5735.487 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5739.487 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5754.4955 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5757.504 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5759.504 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5763.504 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5770.6574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 933.9177 | 6615250.2002 | ACTION | 5770.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 218.5 | 0 | ACTION | 5770.6574 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 5776.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5778.5125 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5778.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5781.521 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5783.521 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5787.521 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5790.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5794.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5798.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5802.5295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5802.6574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 5803.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5805.538 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 5805.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5806.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5807.538 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5811.538 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 5811.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 49583.3333 | ACTION | 5818.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 5818.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5826.5465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5829.555 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 10 | 41666.6667 | ACTION | 5839.555 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5841.555 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5845.555 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 36 | 255000 | ACTION | 5854.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5860.5635 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 43 | 0 | ACTION | 5861.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5863.572 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5865.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5865.572 | MooringSystemInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 92083.3333 | ACTION | 5867.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5868.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5869.572 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 5872.1574 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 5873.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 5884.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5884.5805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5887.589 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5889.589 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5893.589 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 5896.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5908.5975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5911.606 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5913.606 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5917.606 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5932.6145 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5935.623 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5937.623 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 5938.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5941.623 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5956.6315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5959.64 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5961.64 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5965.64 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 5968.1574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 700.9177 | 4964833.5335 | ACTION | 5968.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 29.5 | 0 | ACTION | 5968.1574 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 5974.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 5976.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 5980.6485 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 5983.657 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 5988.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5992.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 5996.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 5998.4972 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6000.1574 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 6001.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 6003.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6003.4972 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6004.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6008.4972 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6009.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6013.4972 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6016.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6018.4972 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6019.6574 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 6029.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 6033.3374 | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 6035.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6035.3374 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 17 | 0 | ACTION | 6036.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6039.3374 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6040.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6043.6574 | MooredSubInstallation
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 6045.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6054.3459 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6057.3544 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6059.3544 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6063.3544 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 12 | 50000 | ACTION | 6075.3544 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6090.3629 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 6097.3629 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6100.3714 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6102.3714 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6106.3714 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6121.3799 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6124.3884 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6126.3884 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6130.3884 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6136.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6145.3969 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 102 | 0 | ACTION | 6145.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6148.4054 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6150.4054 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6154.4054 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6169.4139 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6169.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6172.4224 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6174.4224 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6178.4224 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6193.4309 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6196.4394 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6198.4394 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6202.4394 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6217.4479 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6220.4564 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6222.4564 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6226.4564 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6241.4649 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6241.6574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 527.9177 | 3739416.8669 | ACTION | 6241.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 105.5 | 0 | ACTION | 6241.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6244.4734 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6246.4734 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6247.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6249.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6250.4734 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6261.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6265.4819 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6265.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6268.4904 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6269.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6270.4904 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6273.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6277.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6289.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 6291.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6295.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6298.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 31 | 129166.6667 | ACTION | 6301.4904 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 54 | 382500 | ACTION | 6301.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6302.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6305.4904 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6320.4989 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6323.5074 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6325.5074 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6326.1574 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 6328.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6329.5074 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 6330.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6336.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6344.5159 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6347.5244 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 77916.6667 | ACTION | 6347.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6349.5244 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6353.5244 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 17 | 120416.6667 | ACTION | 6364.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6368.5329 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6371.5414 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 63750 | ACTION | 6373.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 6379.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 5 | 35416.6667 | ACTION | 6384.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 6386.3816 | MooringSystemInstallation
| Towing Group 2 | Delay | 2 | 14166.6667 | ACTION | 6386.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6391.3816 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 5.6001 | 39667.6786 | ACTION | 6392.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6396.3816 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6398.1574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 513.9177 | 3640250.2002 | ACTION | 6398.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6401.3816 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6404.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6406.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6406.3816 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6409.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6418.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 6421.2218 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 6423.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6423.2218 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6427.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6427.2218 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6431.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6435.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6439.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6442.2303 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6445.2388 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6447.2388 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6451.2388 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 58 | 410833.3333 | ACTION | 6462.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 23 | 0 | ACTION | 6462.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6466.2473 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6469.2558 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6471.2558 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6474.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6475.2558 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6477.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6481.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6484.6574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 6489.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6490.2643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 6491.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6493.2728 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6495.2728 | MooringSystemInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6497.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6499.2728 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6508.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6514.2813 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 6517.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6517.2898 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6519.2898 | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 6523.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6523.2898 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 6533.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6538.2983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6541.3068 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6543.3068 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6547.3068 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6562.3153 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6565.3238 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6567.3238 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6571.3238 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6577.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6580.6574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 534.9177 | 3789000.2002 | ACTION | 6580.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 3 | 0 | ACTION | 6580.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6586.3323 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6586.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6588.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6589.3408 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6591.3408 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6595.3408 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6600.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6610.3493 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6613.3578 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 13 | 0 | ACTION | 6613.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6615.3578 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6617.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6619.3578 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6621.6574 | MooredSubInstallation
| Towing Group 1 | Delay | 41 | 290416.6667 | ACTION | 6627.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 6627.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6631.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6634.3663 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6635.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6637.3748 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6639.3748 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6643.3748 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6647.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6651.1574 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 6654.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6654.6574 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 6656.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6658.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6658.3833 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6661.3918 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6662.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6663.3918 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6667.3918 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6682.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6682.4003 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 6682.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6685.4088 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6687.4088 | MooringSystemInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 6688.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6691.4088 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 6699.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6706.4173 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6709.4258 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 6724.266 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6729.266 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 66 | 0 | ACTION | 6748.1574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6748.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 34 | 141666.6667 | ACTION | 6763.266 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6768.266 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6773.266 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6778.266 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 6793.1062 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6795.1062 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6799.1062 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6814.1147 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6817.1232 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6819.1232 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6820.1574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 427.9177 | 3031083.5335 | ACTION | 6820.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 71.5 | 0 | ACTION | 6820.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6823.1232 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 6826.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6828.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6838.1317 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6840.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6841.1402 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6843.1402 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6844.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6847.1402 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6848.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6852.1574 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 6853.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 6855.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6856.1574 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 6861.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6862.1487 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6865.1572 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6867.1572 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6868.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6871.1572 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 99166.6667 | ACTION | 6875.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6886.1657 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6889.1742 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6891.1742 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6895.1742 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 22 | 155833.3333 | ACTION | 6897.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 6898.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 1 | 7083.3333 | ACTION | 6899.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 33 | 0 | ACTION | 6901.1574 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 35416.6667 | ACTION | 6904.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6904.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6908.1574 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 6910.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6910.1827 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6911.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6913.1912 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6915.1912 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6919.1912 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 6920.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6934.1997 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6935.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6937.2082 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6939.2082 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6943.2082 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6958.2167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6961.2252 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6963.2252 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6967.2252 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 6982.2337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 6985.2422 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6987.2422 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6988.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6991.2422 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 111 | 0 | ACTION | 7046.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 126 | 525000 | ACTION | 7117.2422 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7118.6574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 584.9177 | 4143166.8669 | ACTION | 7118.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 130.5 | 0 | ACTION | 7118.6574 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7124.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7126.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 7132.2507 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 7135.2592 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7137.2592 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7138.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7141.2592 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 7156.2677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 7159.2762 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7161.2762 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7165.2762 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 48 | 340000 | ACTION | 7172.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 34 | 0 | ACTION | 7172.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7176.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 7180.2847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7180.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 7183.2932 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7184.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7185.2932 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7188.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7189.2932 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 7199.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7200.6574 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 7201.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7204.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 7204.3017 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 7207.3102 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 7207.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7207.6574 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 7209.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7211.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 8 | 33333.3333 | ACTION | 7215.3102 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 14 | 58333.3333 | ACTION | 7229.3102 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7235.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 6.8402 | 28500.8333 | ACTION | 7236.1504 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7241.1504 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 36 | 255000 | ACTION | 7245.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7246.1504 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7251.1504 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 127500 | ACTION | 7263.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Transit | 14.8402 | 61834.1667 | ACTION | 7265.9906 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7267.9906 | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 7269.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 2 | 14166.6667 | ACTION | 7271.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7271.9906 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 5 | 35416.6667 | ACTION | 7276.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 1 | 7083.3333 | ACTION | 7277.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 2 | 14166.6667 | ACTION | 7279.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7286.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 7286.9991 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 7.6001 | 53834.3452 | ACTION | 7287.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 7290.0076 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7292.0076 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7296.0076 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7307.1574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 607.9177 | 4306083.5335 | ACTION | 7307.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 20.5 | 0 | ACTION | 7307.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 7311.0161 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7313.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 7314.0246 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7315.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7316.0246 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7320.0246 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7327.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7331.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 7335.0331 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7335.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 7338.0416 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7339.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7340.0416 | MooringSystemInstallation
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 7340.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 7342.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7343.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7344.0416 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 7348.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7355.1574 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 56666.6667 | ACTION | 7356.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7358.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 7359.0501 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7362.1574 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 7363.0501 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7365.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 7366.0586 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7368.0586 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7372.0586 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 25 | 177083.3333 | ACTION | 7381.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 7387.0671 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7389.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 7390.0756 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7392.0756 | MooringSystemInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 85000 | ACTION | 7393.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7396.0756 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 7399.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 7409.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 7411.0841 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 7414.0926 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7416.0926 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7420.0926 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 7435.1011 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 7438.1096 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7440.1096 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7444.1096 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 7459.1181 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7461.6574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 540.9177 | 3831500.2002 | ACTION | 7461.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 7462.1266 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7464.1266 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7467.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7468.1266 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7469.6574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7475.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7481.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 19 | 0 | ACTION | 7500.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7504.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7508.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7512.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 7520.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 53 | 220833.3333 | ACTION | 7521.1266 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Delay | 54 | 382500 | ACTION | 7521.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7524.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 15.0085 | 62535.4167 | ACTION | 7536.1351 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7536.6574 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 3.0085 | 12535.4167 | ACTION | 7539.1436 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7540.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7543.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7547.1574 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 7548.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 7550.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 7556.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7571.1574 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 7576.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 1 | 7083.3333 | ACTION | 7577.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7643.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 81 | 0 | ACTION | 7652.1574 | MooredSubInstallation
| Towing Group 2 | Delay | 108 | 765000 | ACTION | 7685.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 5 | 35416.6667 | ACTION | 7690.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 7701.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7724.1574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 436.9177 | 3094833.5335 | ACTION | 7724.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 81 | 0 | ACTION | 7724.1574 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 7730.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7732.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7744.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7748.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 20 | 0 | ACTION | 7768.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7772.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7776.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 54 | 0 | ACTION | 7830.1574 | MooredSubInstallation
| Towing Group 3 | Delay | 104 | 736666.6667 | ACTION | 7834.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7834.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7846.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7849.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7853.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7856.6574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 7861.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 7863.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 7869.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7880.6574 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 7889.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 3 | 21250 | ACTION | 7892.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7892.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 33 | 0 | ACTION | 7913.6574 | MooredSubInstallation
| Towing Group 3 | Delay | 62 | 439166.6667 | ACTION | 7954.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 3 | 21250 | ACTION | 7957.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 7967.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7985.6574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 575.9177 | 4079416.8669 | ACTION | 7985.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 93.5 | 0 | ACTION | 7985.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7993.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8005.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8009.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8013.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8017.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8021.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8033.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8037.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8040.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8044.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8068.1574 | MooredSubInstallation
| Towing Group 1 | Delay | 111 | 786250 | ACTION | 8096.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 8102.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 12 | 85000 | ACTION | 8114.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8140.1574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 438.9177 | 3109000.2002 | ACTION | 8140.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 8141.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 8143.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 8146.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8148.1574 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 8149.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8153.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8160.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8164.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8168.1574 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 8169.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8172.1574 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 8173.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 8175.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 8175.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8176.1574 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 8181.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 8186.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8188.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8191.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8195.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8198.6574 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 8201.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 8207.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 8217.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8222.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8294.6574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 326.9177 | 2315666.8669 | ACTION | 8294.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 8300.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8302.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8314.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8318.6574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8321.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8322.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8326.6574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 8327.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 8329.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8330.6574 | MooredSubInstallation
| Towing Group 3 | Delay | 5 | 35416.6667 | ACTION | 8334.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 8340.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8342.6574 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 28333.3333 | ACTION | 8344.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8346.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8349.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 8354.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8358.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8382.1574 | MooredSubInstallation
| Towing Group 3 | Delay | 49 | 347083.3333 | ACTION | 8393.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 113333.3333 | ACTION | 8409.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 8415.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 8426.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8454.1574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 267.9177 | 1897750.2002 | ACTION | 8454.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 8460.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8462.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8474.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8478.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8482.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8486.1574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8489.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8490.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8502.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8505.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8509.1574 | MooredSubInstallation
| Towing Group 1 | Delay | 51 | 361250 | ACTION | 8511.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8512.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8536.6574 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 8538.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 8540.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 8546.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 8566.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 8572.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 8582.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8608.6574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 390.9177 | 2769000.2002 | ACTION | 8608.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 7 | 49583.3333 | ACTION | 8615.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8616.6574 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 8621.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8628.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8632.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8636.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8640.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8644.6574 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 8648.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 8650.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 8656.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8656.6574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8657.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8660.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8663.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8667.1574 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 8676.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 8682.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8691.1574 | MooredSubInstallation
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 8693.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8763.1574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 336.9177 | 2386500.2002 | ACTION | 8763.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 8769.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8771.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8783.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8787.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8791.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8795.1574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 8796.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 8798.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8799.1574 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 8804.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8811.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8814.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8818.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8821.6574 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 8824.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 1 | 7083.3333 | ACTION | 8825.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8825.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8845.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 22 | 0 | ACTION | 8867.6574 | MooredSubInstallation
| Towing Group 3 | Delay | 79 | 559583.3333 | ACTION | 8904.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 5 | 35416.6667 | ACTION | 8909.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 8919.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8939.6574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 356.9177 | 2528166.8669 | ACTION | 8939.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 8945.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8947.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8959.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8963.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 8968.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8972.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8976.6574 | MooredSubInstallation
| Towing Group 1 | Delay | 33 | 233750 | ACTION | 8978.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8980.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8992.6574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8993.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 8994.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8998.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9001.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9005.1574 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 9005.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 9020.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9044.1574 | MooredSubInstallation
| Towing Group 1 | Delay | 53 | 375416.6667 | ACTION | 9058.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 9060.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9066.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 9086.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 9092.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 6 | 42500 | ACTION | 9098.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9161.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 126 | 0 | ACTION | 9170.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9242.1574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 548.9177 | 3888166.8669 | ACTION | 9242.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 80.5 | 0 | ACTION | 9242.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9250.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9262.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9266.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9270.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9274.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9278.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9290.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9293.6574 | MooredSubInstallation
| Towing Group 2 | Delay | 52 | 368333.3333 | ACTION | 9294.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 196 | 1388333.3333 | ACTION | 9294.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9297.1574 | MooredSubInstallation
| Towing Group 1 | Transit | 4.6001 | 32584.3452 | ACTION | 9299.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9300.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 39 | 0 | ACTION | 9336.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9339.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 9346.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9370.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 25 | 0 | ACTION | 9395.6574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9410.1574 | MooredSubInstallation
| Towing Group 2 | Delay | 117 | 828750 | ACTION | 9417.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 9444.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 9446.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9452.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 7 | 49583.3333 | ACTION | 9459.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9467.6574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 547.9177 | 3881083.5335 | ACTION | 9467.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 57.5 | 0 | ACTION | 9467.6574 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9473.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 106250 | ACTION | 9474.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9475.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9487.6574 | MooredSubInstallation
| Towing Group 3 | Delay | 18 | 127500 | ACTION | 9491.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9491.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9495.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9499.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9503.6574 | MooredSubInstallation
| Towing Group 2 | Delay | 35 | 247916.6667 | ACTION | 9509.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 35416.6667 | ACTION | 9514.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9515.6574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 9518.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9519.1574 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 9520.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 9520.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9522.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9526.1574 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9526.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 9530.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 9546.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9550.1574 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 9552.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 9563.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9622.1574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 322.9177 | 2287333.5335 | ACTION | 9622.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9628.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9630.1574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9635.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9642.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9646.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9650.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9654.1574 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 9655.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 9657.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9658.1574 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9663.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9670.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 9674.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9677.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9681.1574 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 9683.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9684.6574 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 9689.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 9699.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9708.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9780.6574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 249.9177 | 1770250.2002 | ACTION | 9780.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9786.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9788.6574 | MooredSubInstallation
| Towing Group 2 | Delay | 11 | 77916.6667 | ACTION | 9797.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9800.6574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9803.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9804.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9808.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9812.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9816.6574 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 9824.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 9826.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9828.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9832.1574 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 9832.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 49583.3333 | ACTION | 9839.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 9844.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9847.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9851.1574 | MooredSubInstallation
| Towing Group 2 | Delay | 12 | 85000 | ACTION | 9851.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 12 | 85000 | ACTION | 9863.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 8 | 56666.6667 | ACTION | 9871.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 9872.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9875.1574 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 9878.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 9889.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9947.1574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 383.9177 | 2719416.8669 | ACTION | 9947.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9955.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9967.1574 | MooredSubInstallation
| Towing Group 3 | Delay | 21 | 148750 | ACTION | 9968.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9971.1574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9971.6574 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 9974.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9975.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9979.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9983.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9995.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9998.6574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 10001.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10002.1574 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 10003.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10005.6574 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 10009.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 77916.6667 | ACTION | 10020.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10029.6574 | MooredSubInstallation
| Towing Group 3 | Delay | 26 | 184166.6667 | ACTION | 10046.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 63750 | ACTION | 10055.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 10061.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 10071.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10101.6574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 401.9177 | 2846916.8669 | ACTION | 10101.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10109.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10121.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10125.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10129.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 10130.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10134.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10138.6574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10139.6574 | MooredSubInstallation
| Towing Group 1 | Delay | 45 | 318750 | ACTION | 10146.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10150.6574 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 10152.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10154.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10157.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10161.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 19 | 0 | ACTION | 10180.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10204.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 18 | 0 | ACTION | 10222.1574 | MooredSubInstallation
| Towing Group 1 | Delay | 99 | 701250 | ACTION | 10251.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 10278.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 10280.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 10286.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10294.1574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 404.9177 | 2868166.8669 | ACTION | 10294.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 10300.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10302.1574 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 10306.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10307.6574 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 10312.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10314.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10318.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10322.1574 | MooredSubInstallation
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 10323.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10326.1574 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 10327.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 10329.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10330.1574 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 10335.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 42500 | ACTION | 10341.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 34 | 0 | ACTION | 10364.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10376.1574 | MooredSubInstallation
| Towing Group 2 | Delay | 37 | 262083.3333 | ACTION | 10378.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10379.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10383.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10386.6574 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 99166.6667 | ACTION | 10392.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 10398.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 10408.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10410.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 62 | 0 | ACTION | 10472.6574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10475.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10544.6574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 472.9177 | 3349833.5335 | ACTION | 10544.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 69 | 0 | ACTION | 10544.6574 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 10550.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10552.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10564.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10568.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10572.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10576.6574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 10577.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 10579.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10580.6574 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 10585.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10592.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10596.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10599.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10603.1574 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 10605.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 10611.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 10622.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10627.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10699.1574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 375.9177 | 2662750.2002 | ACTION | 10699.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10707.1574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10712.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10719.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 10725.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10729.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10733.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10737.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10741.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 10746.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10758.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10761.6574 | MooredSubInstallation
| Towing Group 1 | Delay | 64 | 453333.3333 | ACTION | 10763.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10765.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10768.6574 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 10769.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10792.6574 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 10796.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 10798.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 10804.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 127500 | ACTION | 10822.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 7 | 49583.3333 | ACTION | 10829.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 10831.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 4 | 28333.3333 | ACTION | 10835.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 59 | 0 | ACTION | 10851.6574 | MooredSubInstallation
| Towing Group 1 | Delay | 26 | 184166.6667 | ACTION | 10861.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 2 | 14166.6667 | ACTION | 10863.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 3 | 21250 | ACTION | 10866.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 1 | 7083.3333 | ACTION | 10867.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 11 | 77916.6667 | ACTION | 10878.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10880.6574 | MooredSubInstallation
| Towing Group 1 | Transit | 9.6001 | 68001.0119 | ACTION | 10887.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10923.6574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 514.9177 | 3647333.5335 | ACTION | 10923.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 43 | 0 | ACTION | 10923.6574 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 10929.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10931.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10943.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10947.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10951.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 10954.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10958.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10962.6574 | MooredSubInstallation
| Towing Group 2 | Delay | 45 | 318750 | ACTION | 10974.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 10974.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10986.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10990.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10993.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10997.1574 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 11001.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 11003.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11009.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11021.1574 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 11029.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 4 | 28333.3333 | ACTION | 11033.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 11 | 77916.6667 | ACTION | 11044.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 2 | 14166.6667 | ACTION | 11046.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 11057.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11091.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 157 | 0 | ACTION | 11178.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11250.1574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 627.9177 | 4447750.2002 | ACTION | 11250.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 158.5 | 0 | ACTION | 11250.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11258.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11270.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 11274.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11278.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11282.1574 | MooredSubInstallation
| Towing Group 3 | Delay | 33 | 233750 | ACTION | 11283.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11286.1574 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11289.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11290.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11302.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11305.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11309.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11312.6574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 11316.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 8 | 56666.6667 | ACTION | 11324.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 11326.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11332.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11336.6574 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 11352.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 11358.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 11368.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11408.6574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 520.9177 | 3689833.5335 | ACTION | 11408.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11414.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11416.6574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11418.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11428.6574 | MooredSubInstallation
| Towing Group 1 | Delay | 47 | 332916.6667 | ACTION | 11461.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 33 | 0 | ACTION | 11461.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11465.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11469.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11473.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11477.6574 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 11488.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11489.6574 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 11490.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11493.1574 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11496.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11496.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11500.1574 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 11516.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 11522.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11524.1574 | MooredSubInstallation
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 11533.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11586.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11596.1574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 538.9177 | 3817333.5335 | ACTION | 11596.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 10 | 0 | ACTION | 11596.1574 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11602.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11604.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11616.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11620.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11624.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11628.1574 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 11629.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 11631.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11632.1574 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11637.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 11639.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 8 | 56666.6667 | ACTION | 11647.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 28333.3333 | ACTION | 11651.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 1 | 7083.3333 | ACTION | 11652.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 11654.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 1 | 7083.3333 | ACTION | 11655.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 11657.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 43 | 0 | ACTION | 11675.1574 | MooredSubInstallation
| Towing Group 2 | Delay | 20 | 141666.6667 | ACTION | 11677.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 10 | 70833.3333 | ACTION | 11687.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11687.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 11690.1574 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 11693.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11693.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11697.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11700.6574 | MooredSubInstallation
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 11703.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11724.6574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11764.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11796.6574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 427.9177 | 3031083.5335 | ACTION | 11796.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 32.5 | 0 | ACTION | 11796.6574 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 11802.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11804.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11816.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11820.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11824.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11828.6574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 11829.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 11831.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11832.6574 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 11837.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11844.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11848.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11851.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11855.1574 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 11857.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 11863.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 11874.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11879.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 52 | 0 | ACTION | 11931.1574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11964.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12003.1574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 469.9177 | 3328583.5335 | ACTION | 12003.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 38.5 | 0 | ACTION | 12003.1574 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12009.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12011.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12023.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12027.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12031.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12035.1574 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 12036.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 12038.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12039.1574 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12044.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12051.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12054.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12058.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12061.6574 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 12064.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 12070.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 12080.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12085.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12157.6574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 453.9177 | 3215250.2002 | ACTION | 12157.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12163.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12165.6574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12171.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12177.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12181.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12185.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12189.6574 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 12190.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 12192.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12193.6574 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12198.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12205.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12209.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12212.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12216.1574 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 12218.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 12224.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 12235.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12240.1574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12339.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 116 | 0 | ACTION | 12356.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12428.1574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 553.9177 | 3923583.5335 | ACTION | 12428.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 89 | 0 | ACTION | 12428.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12436.1574 | MooredSubInstallation
| Towing Group 3 | Delay | 13 | 92083.3333 | ACTION | 12441.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12447.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12448.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12452.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12456.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12460.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12464.1574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 12474.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 12476.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12476.1574 | MooredSubInstallation
| Towing Group 3 | Delay | 4 | 28333.3333 | ACTION | 12480.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12486.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 10 | 0 | ACTION | 12486.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12489.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12493.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12496.6574 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 12506.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 12512.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12520.6574 | MooredSubInstallation
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 12522.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12592.6574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 511.9177 | 3626083.5335 | ACTION | 12592.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12596.1574 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12598.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12600.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12612.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12616.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12620.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12624.6574 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 12625.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 12627.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12628.6574 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12633.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12640.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12644.1574 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 120416.6667 | ACTION | 12650.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 5 | 35416.6667 | ACTION | 12655.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 12657.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 1 | 7083.3333 | ACTION | 12658.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 12659.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 12665.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 28 | 0 | ACTION | 12672.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12675.6574 | MooredSubInstallation
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 12676.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12679.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12703.1574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12764.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 70 | 0 | ACTION | 12773.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12845.1574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 609.9177 | 4320250.2002 | ACTION | 12845.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 81 | 0 | ACTION | 12845.1574 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 12851.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12853.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12865.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12869.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12873.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12877.1574 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 12878.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 12880.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12881.1574 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 12886.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12893.1574 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 99166.6667 | ACTION | 12900.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 2 | 14166.6667 | ACTION | 12902.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 14166.6667 | ACTION | 12904.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 53 | 375416.6667 | ACTION | 12957.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 28333.3333 | ACTION | 12961.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 71 | 0 | ACTION | 12964.1574 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 12967.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12967.6574 | MooredSubInstallation
| Towing Group 2 | Transit | 9 | 63750 | ACTION | 12976.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13013.1574 | MooredSubInstallation
| Towing Group 2 | Delay | 65 | 460416.6667 | ACTION | 13041.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 1.6001 | 11334.3452 | ACTION | 13042.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 98 | 0 | ACTION | 13065.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13069.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13072.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13096.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 82 | 0 | ACTION | 13178.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13250.6574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 727.9177 | 5156083.5335 | ACTION | 13250.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 237.5 | 0 | ACTION | 13250.6574 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13256.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13258.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13270.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13274.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13278.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13282.6574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 13283.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 13285.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13286.6574 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13291.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13298.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13302.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13305.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13309.1574 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13311.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 13317.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 13328.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13333.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 46 | 0 | ACTION | 13379.1574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13418.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13451.1574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 774.9177 | 5489000.2002 | ACTION | 13451.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 32.5 | 0 | ACTION | 13451.1574 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13457.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13459.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13471.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13475.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13479.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 13487.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13491.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13495.1574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13619.1574 | MooredSubInstallation
| Towing Group 1 | Delay | 166 | 1175833.3333 | ACTION | 13623.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 128 | 0 | ACTION | 13623.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13635.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 13641.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13644.6574 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 13650.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 13652.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 4 | 28333.3333 | ACTION | 13656.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13662.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13682.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 40 | 0 | ACTION | 13684.6574 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 13688.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13688.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 1 | 0 | ACTION | 13689.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13692.6574 | MooredSubInstallation
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 13698.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13716.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13788.6574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 745.9177 | 5283583.5335 | ACTION | 13788.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 169.5 | 0 | ACTION | 13788.6574 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13794.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13796.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13808.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13812.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13816.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13820.6574 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 13821.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 13823.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13824.6574 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13829.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13836.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13840.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13843.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13847.1574 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 13849.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 13855.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 13866.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13871.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13943.1574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 614.9177 | 4355666.8669 | ACTION | 13943.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 13949.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13951.1574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13956.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13963.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13967.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13971.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13975.1574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 13976.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 13978.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13979.1574 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 13984.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13991.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13994.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13998.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14001.6574 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14004.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 14010.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 14020.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14025.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14097.6574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 398.9177 | 2825666.8669 | ACTION | 14097.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14103.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14105.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14117.6574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14124.6574 | MooredSubInstallation
| Towing Group 1 | Delay | 47 | 332916.6667 | ACTION | 14150.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 33 | 0 | ACTION | 14150.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14154.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14158.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14162.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14166.6574 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 14177.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14178.6574 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 14179.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14182.1574 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14185.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14185.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14189.1574 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14205.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 14211.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14213.1574 | MooredSubInstallation
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 14222.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 64 | 0 | ACTION | 14277.1574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14292.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14349.1574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 482.9177 | 3420666.8669 | ACTION | 14349.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 56.5 | 0 | ACTION | 14349.1574 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14355.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14357.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14369.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14373.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14377.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14381.1574 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 14382.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 14384.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14385.1574 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14390.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14397.1574 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 106250 | ACTION | 14405.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 72 | 510000 | ACTION | 14477.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 35416.6667 | ACTION | 14482.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 14488.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 1 | 7083.3333 | ACTION | 14489.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 17 | 120416.6667 | ACTION | 14506.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 111 | 0 | ACTION | 14508.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14511.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14515.1574 | MooredSubInstallation
| Towing Group 2 | Transit | 9.6001 | 68001.0119 | ACTION | 14515.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14517.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14518.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14542.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 151 | 0 | ACTION | 14693.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14765.6574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 744.9177 | 5276500.2002 | ACTION | 14765.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 248.5 | 0 | ACTION | 14765.6574 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14771.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14773.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14785.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14789.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14793.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14797.6574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 14798.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 14800.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14801.6574 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14806.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14813.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14817.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14820.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14824.1574 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14826.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 14832.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 14843.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14848.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14920.1574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 697.9177 | 4943583.5335 | ACTION | 14920.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 14926.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14928.1574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14933.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14940.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14944.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14948.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14952.1574 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 14953.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 14955.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14956.1574 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 14961.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14968.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14971.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14975.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14978.6574 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 14981.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 14987.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 10 | 70833.3333 | ACTION | 14997.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15002.6574 | MooredSubInstallation
| Towing Group 1 | Delay | 18 | 127500 | ACTION | 15015.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 0.60014 | 4251.0119 | ACTION | 15015.7398 | MooredSubInstallation | [5 empty] | 2 | 1
0.5 | Array Cable Installation Vessel | Mobilize | 72 | 337500 | ACTION | 15055.3233 | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 56250 | ACTION | 15061.3233 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 10 | 93750 | ACTION | 15071.3233 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 2 | 18750 | ACTION | 15073.3233 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15074.6574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 558.9177 | 3959000.2002 | ACTION | 15074.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Transit | 2.9045 | 27229.8913 | ACTION | 15076.2278 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15078.2278 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15079.2278 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Delay | 6 | 42500 | ACTION | 15080.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15082.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15084.7278 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 15086.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15090.2278 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15091.2278 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15094.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15098.6574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15101.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15102.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15106.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 16.2466 | 152311.9249 | ACTION | 15107.4744 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15108.4744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15110.6574 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 15113.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15113.9744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 15115.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15119.4744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15121.4744 | ArrayCableInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 15121.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15122.4744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15122.6574 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 113333.3333 | ACTION | 15137.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 62 | 439166.6667 | ACTION | 15199.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 80 | 0 | ACTION | 15202.6574 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 28333.3333 | ACTION | 15203.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15206.1574 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 15209.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15209.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 90 | 843750 | ACTION | 15212.4744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15213.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15217.9744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 15220.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15223.4744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15224.4744 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15237.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 16.2466 | 152311.9249 | ACTION | 15240.721 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15241.721 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15247.221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15252.721 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15254.721 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15255.721 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15261.221 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15266.721 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15267.721 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15269.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 15272.8794 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15273.8794 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15279.3794 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15284.8794 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15286.8794 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15287.8794 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15293.3794 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15298.8794 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15299.8794 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 15305.0378 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15306.0378 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15309.1574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 465.9177 | 3300250.2002 | ACTION | 15309.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 39.5 | 0 | ACTION | 15309.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15311.5378 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 15315.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15317.0378 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15317.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15319.0378 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15320.0378 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15325.5378 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15329.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15331.0378 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15332.0378 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15333.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15337.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 15337.1962 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15338.1962 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15341.1574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 15342.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15343.6962 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 15344.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15345.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15349.1962 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 15350.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15351.1962 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15352.1962 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15357.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15357.6962 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15360.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15363.1962 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15364.1962 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 15364.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15368.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 15369.3545 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 15370.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15370.3545 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15371.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15375.8545 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 15376.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15381.3545 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15383.3545 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15384.3545 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 15386.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15389.8545 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15395.3545 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15395.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15396.3545 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 15401.5129 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15402.5129 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15408.0129 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15413.5129 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15415.5129 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15416.5129 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15422.0129 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15427.5129 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15428.5129 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 15433.6713 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15434.6713 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15467.6574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 451.9177 | 3201083.5335 | ACTION | 15467.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 15473.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15475.6574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15477.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15487.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15491.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15495.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15499.6574 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 15500.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 15502.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15503.6574 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 15508.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15515.6574 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 92083.3333 | ACTION | 15521.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 3 | 21250 | ACTION | 15524.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 15525.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 37 | 262083.3333 | ACTION | 15562.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 42500 | ACTION | 15568.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 134 | 1256250 | ACTION | 15568.6713 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 5 | 35416.6667 | ACTION | 15573.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15574.1713 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Delay | 1 | 7083.3333 | ACTION | 15574.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 1 | 7083.3333 | ACTION | 15575.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15579.6713 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Delay | 5 | 35416.6667 | ACTION | 15580.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15581.6713 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15582.6713 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 69 | 0 | ACTION | 15584.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15588.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15588.1713 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 15591.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15593.6713 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15594.6713 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 3 | 28125 | ACTION | 15597.6713 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Delay | 45 | 0 | ACTION | 15633.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15636.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 41 | 384375 | ACTION | 15638.6713 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15640.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 2.1584 | 20234.7614 | ACTION | 15640.8297 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15641.8297 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15645.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15647.3297 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15652.8297 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15654.8297 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15655.8297 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15661.3297 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15664.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15666.8297 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15667.8297 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 15672.988 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15673.988 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15679.488 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15684.988 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15686.988 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15687.988 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15693.488 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15698.988 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15699.988 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 15705.1464 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15706.1464 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15711.6464 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15736.1574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 515.9177 | 3654416.8669 | ACTION | 15736.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 91 | 0 | ACTION | 15736.1574 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 15742.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15744.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15756.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15760.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15764.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15768.1574 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 15769.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 15771.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15772.1574 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 15777.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15784.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 15786.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15789.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15793.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15796.6574 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 15797.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 90 | 843750 | ACTION | 15801.6464 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 15803.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15807.1464 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15809.1464 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15810.1464 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 15813.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15815.6464 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15820.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15821.1464 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 15822.1464 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 15827.3048 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15828.3048 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 15833.8048 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 15839.3048 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 15841.3048 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 15842.3048 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15892.6574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 505.9177 | 3583583.5335 | ACTION | 15892.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 15898.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15900.6574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15904.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15912.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15916.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15920.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15924.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15928.6574 | MooredSubInstallation
| Towing Group 3 | Delay | 33 | 233750 | ACTION | 15931.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15940.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15944.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15947.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15951.1574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 15958.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 15960.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 5 | 35416.6667 | ACTION | 15965.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 15971.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15975.1574 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 35416.6667 | ACTION | 15976.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 58 | 410833.3333 | ACTION | 16034.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 202 | 1893750 | ACTION | 16044.3048 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16047.1574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 455.9177 | 3229416.8669 | ACTION | 16047.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 106250 | ACTION | 16049.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16049.8048 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 16053.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16055.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16055.3048 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 16055.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16056.3048 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 16061.4632 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16062.4632 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 16066.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16067.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16067.9632 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16071.1574 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16072.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16073.4632 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16075.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16075.4632 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16076.4632 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16079.1574 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 16080.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16081.9632 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 16082.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16083.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16087.4632 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 16088.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16088.4632 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 16093.6215 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16094.6215 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16095.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16098.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16100.1215 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16102.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16105.6574 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 16108.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 16114.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 15 | 140625 | ACTION | 16115.1215 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16120.6215 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16122.6215 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16123.6215 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 16124.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16129.1215 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16129.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16134.6215 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16135.6215 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 16140.7799 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16141.7799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16147.2799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16152.7799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16201.6574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 387.9177 | 2747750.2002 | ACTION | 16201.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16209.6574 | MooredSubInstallation
| Towing Group 2 | Delay | 13 | 92083.3333 | ACTION | 16214.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 16220.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16221.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 9 | 0 | ACTION | 16230.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16234.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16238.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 87 | 815625 | ACTION | 16239.7799 | ArrayCableInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16240.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16241.7799 | ArrayCableInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16242.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16242.7799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16246.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16248.2799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 16249.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16253.7799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16254.7799 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 16259.9383 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16260.9383 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16261.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16265.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16266.4383 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Delay | 82 | 580833.3333 | ACTION | 16302.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 40 | 0 | ACTION | 16305.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 40 | 375000 | ACTION | 16306.4383 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16308.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16311.9383 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16312.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16313.9383 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16314.9383 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16320.4383 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16325.9383 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16326.9383 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 16329.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 16331.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 16332.0967 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16333.0967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16336.1574 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 16337.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16338.5967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16344.0967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16346.0967 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16347.0967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16352.5967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 16357.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16358.0967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16359.0967 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 16363.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 16364.255 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16365.255 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16370.755 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 16374.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16376.255 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16378.255 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16379.255 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16384.755 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16390.255 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16391.255 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 37500 | ACTION | 16395.255 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16408.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16408.1574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 341.9177 | 2421916.8669 | ACTION | 16408.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16416.1574 | MooredSubInstallation
| Towing Group 3 | Delay | 20 | 141666.6667 | ACTION | 16428.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16428.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16432.1574 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 16434.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16436.1574 | MooredSubInstallation
| Towing Group 3 | Delay | 8 | 56666.6667 | ACTION | 16442.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 16442.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16446.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16450.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 61 | 571875 | ACTION | 16456.255 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.1584 | 10859.7614 | ACTION | 16457.4134 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16458.4134 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16462.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16463.9134 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16465.6574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 16469.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16469.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16469.4134 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 16471.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16471.4134 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16472.4134 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16472.6574 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 16477.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16477.9134 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16483.4134 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16484.4134 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 16489.5718 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16490.5718 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16496.0718 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16496.6574 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 16497.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16501.5718 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 16503.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16503.5718 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16504.5718 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16510.0718 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 16513.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16515.5718 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16516.5718 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 16521.7301 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16522.7301 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16528.2301 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16533.7301 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16535.7301 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16536.7301 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16568.6574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 443.9177 | 3144416.8669 | ACTION | 16568.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16576.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16576.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16588.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16592.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 8 | 0 | ACTION | 16600.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16604.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16608.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16612.6574 | MooredSubInstallation
| Towing Group 1 | Delay | 48 | 340000 | ACTION | 16616.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 16622.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16624.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16628.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16631.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16635.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 106 | 993750 | ACTION | 16642.7301 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16648.2301 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 16649.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 16651.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16653.7301 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16654.7301 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 16657.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16659.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 16659.8885 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16660.8885 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16666.3885 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 19 | 134583.3333 | ACTION | 16676.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 33 | 0 | ACTION | 16692.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16764.1574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 389.9177 | 2761916.8669 | ACTION | 16764.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 16770.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16772.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16784.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16788.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16792.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16796.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16800.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16812.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16815.6574 | MooredSubInstallation
| Towing Group 2 | Delay | 47 | 332916.6667 | ACTION | 16817.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16819.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16822.6574 | MooredSubInstallation
| Towing Group 1 | Delay | 147 | 1041250 | ACTION | 16823.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 16824.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 16830.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 165 | 1546875 | ACTION | 16831.3885 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16836.8885 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16838.8885 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16839.8885 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 16841.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 16844.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16845.3885 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 16846.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16846.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16850.8885 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16851.8885 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 16852.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 16857.0469 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16858.0469 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16863.5469 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 16872.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 16878.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 20 | 187500 | ACTION | 16883.5469 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 16888.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16889.0469 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 16891.0469 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 16892.0469 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 16897.5469 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 16903.0469 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 16904.0469 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16918.6574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 404.9177 | 2868166.8669 | ACTION | 16918.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 16924.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16926.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16938.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16942.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16946.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16950.6574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 16951.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16954.6574 | MooredSubInstallation
| Towing Group 3 | Delay | 7 | 49583.3333 | ACTION | 16958.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 16960.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16966.6574 | MooredSubInstallation
| Towing Group 3 | Delay | 9 | 63750 | ACTION | 16969.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 16975.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 16976.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Delay | 23 | 0 | ACTION | 16989.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16993.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16996.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17000.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17024.1574 | MooredSubInstallation
| Towing Group 3 | Delay | 50 | 354166.6667 | ACTION | 17026.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 113333.3333 | ACTION | 17042.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17096.1574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 254.9177 | 1805666.8669 | ACTION | 17096.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17104.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17116.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17120.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17124.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17128.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17132.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 22 | 0 | ACTION | 17154.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17166.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17169.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17173.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 33 | 0 | ACTION | 17206.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17209.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17233.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 17249.6574 | MooredSubInstallation
| Towing Group 1 | Delay | 187 | 1324583.3333 | ACTION | 17283.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 17289.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 247 | 1749583.3333 | ACTION | 17289.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 21250 | ACTION | 17292.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 391 | 3665625 | ACTION | 17295.0469 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 17298.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5 | 46875 | ACTION | 17300.0469 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Towing Group 3 | Transit | 8 | 56666.6667 | ACTION | 17306.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17321.6574 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 432.9177 | 3066500.2002 | ACTION | 17321.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17329.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17341.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 2 | 0 | ACTION | 17343.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17347.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17351.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17355.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 17361.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17365.6574 | MooredSubInstallation
| Towing Group 1 | Delay | 83 | 587916.6667 | ACTION | 17372.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Delay | 66 | 467500 | ACTION | 17372.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 51 | 361250 | ACTION | 17372.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Transit | 2.6001 | 18417.6786 | ACTION | 17375.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17377.6574 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 42500 | ACTION | 17378.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17381.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17384.6574 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 88 | 825000 | ACTION | 17388.0469 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17388.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Lay/Bury Cable | 0.15837 | 1484.7614 | ACTION | 17388.2053 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 17389.2053 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 17394.7053 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 17399.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 17400.2053 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 17401.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 17402.2053 | ArrayCableInstallation
| Towing Group 2 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 17405.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 17407.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Position Substructure | 2 | 14166.6667 | ACTION | 17407.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7083.3333 | ACTION | 17408.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17412.1574 | MooredSubInstallation
| Towing Group 1 | Delay | 39 | 276250 | ACTION | 17447.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Delay | 40 | 283333.3333 | ACTION | 17447.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 42500 | ACTION | 17453.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 19 | 134583.3333 | ACTION | 17466.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 17472.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 17473.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 42500 | ACTION | 17479.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 17482.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17484.1574 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 108.9177 | 771500.2002 | ACTION | 17484.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 42500 | ACTION | 17490.1574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 2 | Transit | 10.6001 | 75084.3452 | ACTION | 17490.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17492.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17504.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17508.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17512.1574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17516.1574 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 17517.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17520.1574 | MooredSubInstallation
| Towing Group 3 | Delay | 8 | 56666.6667 | ACTION | 17525.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 3 | Position Substructure | 2 | 14166.6667 | ACTION | 17527.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17532.1574 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 42500 | ACTION | 17533.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17535.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17539.1574 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 137 | 1284375 | ACTION | 17539.2053 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 17540.2053 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17542.6574 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 17553.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 13 | 121875 | ACTION | 17553.2053 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 17558.7053 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 42500 | ACTION | 17559.1396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 17564.2053 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 17565.2053 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17566.6574 | MooredSubInstallation
| Towing Group 3 | Transit | 10.6001 | 75084.3452 | ACTION | 17569.7398 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 17570.3636 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 17571.3636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 167 | 0 | ACTION | 17733.6574 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17805.6574 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 322.9177 | 2287333.5335 | ACTION | 17805.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 8 | 56666.6667 | ACTION | 17813.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 42500 | ACTION | 17819.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 38 | 269166.6667 | ACTION | 17857.6574 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Tow Substructure | 26.9822 | 191123.7879 | ACTION | 17884.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Delay | 136 | 963333.3333 | ACTION | 18020.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Position Substructure | 2 | 14166.6667 | ACTION | 18022.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 42500 | ACTION | 18028.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 460 | 4312500 | ACTION | 18031.3636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18036.8636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18042.3636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18044.3636 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18045.3636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 141666.6667 | ACTION | 18048.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18050.8636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Check Mooring Lines | 6 | 42500 | ACTION | 18054.6396 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18056.3636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18057.3636 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 1 | Transit | 10.6001 | 75084.3452 | ACTION | 18065.2398 | MooredSubInstallation | [5 empty] | 2 | 1
| Array Cable Installation Vessel | Delay | 79 | 740625 | ACTION | 18136.3636 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 18141.522 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18142.522 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18148.022 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18153.522 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18155.522 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18156.522 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18162.022 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18167.522 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18168.522 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 18173.6804 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18174.6804 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18180.1804 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18185.6804 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18187.6804 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18188.6804 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18194.1804 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18199.6804 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18200.6804 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 18205.8388 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18206.8388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18212.3388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18217.8388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18219.8388 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18220.8388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18226.3388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18231.8388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18232.8388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 37500 | ACTION | 18236.8388 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 28 | 262500 | ACTION | 18264.8388 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1.1584 | 10859.7614 | ACTION | 18265.9971 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18266.9971 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 441 | 4134375 | ACTION | 18707.9971 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18713.4971 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18718.9971 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18720.9971 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18721.9971 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 71 | 665625 | ACTION | 18792.9971 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18798.4971 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18803.9971 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18804.9971 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 18750 | ACTION | 18806.9971 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 64 | 600000 | ACTION | 18870.9971 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 3.1584 | 29609.7614 | ACTION | 18874.1555 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18875.1555 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18880.6555 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18886.1555 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18888.1555 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18889.1555 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18894.6555 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18900.1555 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18901.1555 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 18906.3139 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18907.3139 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18912.8139 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18918.3139 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 55 | 515625 | ACTION | 18973.3139 | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18975.3139 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18976.3139 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 49 | 459375 | ACTION | 19025.3139 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19030.8139 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19036.3139 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19037.3139 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 19042.4723 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19043.4723 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19048.9723 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19054.4723 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19056.4723 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19057.4723 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19062.9723 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19068.4723 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19069.4723 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 18750 | ACTION | 19071.4723 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 13 | 121875 | ACTION | 19084.4723 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 3.1584 | 29609.7614 | ACTION | 19087.6306 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19088.6306 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19094.1306 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19099.6306 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19101.6306 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19102.6306 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19108.1306 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19113.6306 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19114.6306 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 19119.789 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19120.789 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19126.289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19131.789 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19133.789 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19134.789 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19140.289 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19145.789 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19146.789 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5 | 46875 | ACTION | 19151.789 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 153 | 1434375 | ACTION | 19304.789 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 0.15837 | 1484.7614 | ACTION | 19304.9474 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19305.9474 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19311.4474 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19316.9474 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19318.9474 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19319.9474 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 31 | 290625 | ACTION | 19350.9474 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19356.4474 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19361.9474 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19362.9474 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 19368.1058 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19369.1058 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19374.6058 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 268 | 2512500 | ACTION | 19642.6058 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19648.1058 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19650.1058 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19651.1058 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19656.6058 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19662.1058 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19663.1058 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 19668.2641 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19669.2641 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19674.7641 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19680.2641 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19682.2641 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19683.2641 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19688.7641 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19694.2641 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19695.2641 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 1 | 9375 | ACTION | 19696.2641 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 3 | 28125 | ACTION | 19699.2641 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 18750 | ACTION | 19701.2641 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 28 | 262500 | ACTION | 19729.2641 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 2.1584 | 20234.7614 | ACTION | 19731.4225 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19732.4225 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19737.9225 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19743.4225 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19745.4225 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19746.4225 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19751.9225 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19757.4225 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19758.4225 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 19763.5809 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19764.5809 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19770.0809 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 140 | 1312500 | ACTION | 19910.0809 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19915.5809 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19917.5809 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19918.5809 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19924.0809 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 267 | 2503125 | ACTION | 20191.0809 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20196.5809 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20197.5809 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 20202.7393 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20203.7393 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20209.2393 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20214.7393 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20216.7393 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20217.7393 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20223.2393 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 184 | 1725000 | ACTION | 20407.2393 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20412.7393 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20413.7393 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 20418.8976 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20419.8976 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20425.3976 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20430.8976 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20432.8976 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20433.8976 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20439.3976 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 173 | 1621875 | ACTION | 20612.3976 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20617.8976 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20618.8976 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 20624.056 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20625.056 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20630.556 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20636.056 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20638.056 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20639.056 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20644.556 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20650.056 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20651.056 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 20656.2144 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20657.2144 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20662.7144 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20668.2144 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20670.2144 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20671.2144 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20676.7144 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20682.2144 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20683.2144 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 20688.3728 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20689.3728 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20694.8728 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20700.3728 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20702.3728 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20703.3728 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20708.8728 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20714.3728 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20715.3728 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 20720.5311 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20721.5311 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20727.0311 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20732.5311 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20734.5311 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20735.5311 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20741.0311 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20746.5311 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20747.5311 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 20752.6895 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20753.6895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 276 | 2587500 | ACTION | 21029.6895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21035.1895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21040.6895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21042.6895 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21043.6895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21049.1895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21054.6895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21055.6895 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 21060.8479 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21061.8479 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21067.3479 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21072.8479 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21074.8479 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21075.8479 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21081.3479 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21086.8479 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21087.8479 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 21093.0063 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21094.0063 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21099.5063 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21105.0063 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21107.0063 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21108.0063 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21113.5063 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 129 | 1209375 | ACTION | 21242.5063 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21248.0063 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21249.0063 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 21254.1646 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21255.1646 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21260.6646 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21266.1646 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21268.1646 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21269.1646 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21274.6646 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21280.1646 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21281.1646 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 21286.323 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21287.323 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21292.823 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21298.323 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21300.323 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21301.323 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21306.823 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21312.323 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21313.323 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 21318.4814 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21319.4814 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21324.9814 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 72 | 675000 | ACTION | 21396.9814 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21402.4814 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21404.4814 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21405.4814 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21410.9814 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21416.4814 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21417.4814 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 21422.6398 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21423.6398 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21429.1398 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21434.6398 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21436.6398 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21437.6398 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21443.1398 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21448.6398 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21449.6398 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4 | 37500 | ACTION | 21453.6398 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 163 | 1528125 | ACTION | 21616.6398 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 1 | 9375 | ACTION | 21617.6398 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 21 | 196875 | ACTION | 21638.6398 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 0.15837 | 1484.7614 | ACTION | 21638.7981 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21639.7981 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 65 | 609375 | ACTION | 21704.7981 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21710.2981 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21715.7981 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21717.7981 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21718.7981 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21724.2981 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21729.7981 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21730.7981 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 21735.9565 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21736.9565 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21742.4565 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21747.9565 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21749.9565 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21750.9565 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21756.4565 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21761.9565 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21762.9565 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 21768.1149 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21769.1149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21774.6149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21780.1149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21782.1149 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21783.1149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21788.6149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21794.1149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21795.1149 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 21800.2733 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21801.2733 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21806.7733 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21812.2733 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21814.2733 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21815.2733 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21820.7733 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21826.2733 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21827.2733 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 21832.4316 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21833.4316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21838.9316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21844.4316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21846.4316 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21847.4316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21852.9316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21858.4316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21859.4316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 21864.59 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21865.59 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21871.09 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21876.59 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21878.59 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21879.59 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21885.09 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21890.59 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21891.59 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 21896.7484 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21897.7484 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21903.2484 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21908.7484 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21910.7484 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21911.7484 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21917.2484 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21922.7484 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21923.7484 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 21928.9068 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21929.9068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21935.4068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21940.9068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21942.9068 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21943.9068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21949.4068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21954.9068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21955.9068 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.1584 | 48359.7614 | ACTION | 21961.0651 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21962.0651 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21967.5651 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21973.0651 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21975.0651 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21976.0651 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21981.5651 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21987.0651 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21988.0651 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 12.2672 | 115005.1936 | ACTION | 22000.3324 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22001.3324 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22006.8324 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22012.3324 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22014.3324 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22015.3324 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22020.8324 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22026.3324 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22027.3324 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 12.2672 | 115005.1936 | ACTION | 22039.5996 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22040.5996 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22046.0996 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22051.5996 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22053.5996 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22054.5996 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22060.0996 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22065.5996 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22066.5996 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8.53 | 79969.0522 | ACTION | 22075.1296 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22076.1296 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22081.6296 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22087.1296 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22089.1296 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22090.1296 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22095.6296 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22101.1296 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22102.1296 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8.53 | 79969.0522 | ACTION | 22110.6596 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22111.6596 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22117.1596 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22122.6596 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22124.6596 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22125.6596 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22131.1596 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22136.6596 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22137.6596 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.6541 | 53007.3497 | ACTION | 22143.3138 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22144.3138 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22149.8138 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22155.3138 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22157.3138 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22158.3138 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22163.8138 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22169.3138 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22170.3138 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.6541 | 53007.3497 | ACTION | 22175.9679 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22176.9679 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22182.4679 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22187.9679 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 12.9045 | 120979.8913 | ACTION | 22200.8724 | ArrayCableInstallation | ArrayCableInstallation | FALSE