## Sheet1
cost_multiplier | agent | action | duration | cost | level | time | phase | phase_name | include_onshore_construction | max_waveheight | max_windspeed | transit_speed | num_vessels | num_ahts_vessels
0.5 | Export Cable Installation Vessel | Mobilize | 72 | 450000 | ACTION | 0 | ExportCableInstallation
1 | Mooring System Installation Vessel | Mobilize | 168 | 700000 | ACTION | 0 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 2 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Load Cable | 6 | 75000 | ACTION | 6 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 13 | 162500 | ACTION | 19 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Tow Plow | 0.4 | 5000 | ACTION | 19.4 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Pull Winch | 0.4 | 5000 | ACTION | 19.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Prepare Cable | 1 | 12500 | ACTION | 20.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 26.3 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 31.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Lower Cable | 1 | 12500 | ACTION | 32.8 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 28 | 350000 | ACTION | 60.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 77.7327 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 79.7327 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 75 | 312500 | ACTION | 154.7327 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 158.7327 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 175.7977 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 180.8627 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 182.8627 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 186.8627 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 203.9277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 208.9927 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 210.9927 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 214.9927 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 235.9927 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 253.0577 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 258.1227 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 260.1227 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 264.1227 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 51 | 212500 | ACTION | 315.1227 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 332.1877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 337.2527 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 277 | 3462500 | ACTION | 337.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 339.2527 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 343.2527 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 11 | 137500 | ACTION | 348.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 360.3177 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 10 | 41666.6667 | ACTION | 370.3177 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 375.3827 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 377.3827 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 381.3827 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 385.3827 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 402.4477 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 407.5127 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 68 | 850000 | ACTION | 416.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 56 | 700000 | ACTION | 472.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 473.2454 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 478.2454 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 483.2454 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 18 | 225000 | ACTION | 490.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 548.9781 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 550.9781 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 554.9781 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 81 | 1012500 | ACTION | 571.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 572.0431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 577.1081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 579.1081 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 583.1081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substation Assembly Line 1 | Substation Substructure Assembly | 0 | 0 | ACTION | 623.9684 | FloatingSubstationInstallation
| Substation Assembly Line 1 | Attach Topside | 24 | 0 | ACTION | 647.9684 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Delay: Waiting on Substation Assembly | 24 | 100000 | ACTION | 647.9684 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Delay | 85 | 354166.6667 | ACTION | 668.1081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 685.1731 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 690.2381 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 692.2381 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 696.2381 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 713.3031 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 718.3681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 720.3681 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 18 | 75000 | ACTION | 738.3681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 742.3681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 759.4331 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 31 | 129166.6667 | ACTION | 790.4331 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 795.4981 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 797.4981 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 62 | 258333.3333 | ACTION | 859.4981 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 863.4981 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 880.5631 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 885.6281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 887.6281 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 891.6281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 908.6931 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 913.7581 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 28 | 116666.6667 | ACTION | 941.7581 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 20 | 83333.3333 | ACTION | 961.7581 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 37.7327 | 157219.5833 | ACTION | 999.4908 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 9 | 37500 | ACTION | 1008.4908 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1013.4908 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1018.4908 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 30 | 125000 | ACTION | 1048.4908 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 34 | 141666.6667 | ACTION | 1082.4908 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 24 | 100000 | ACTION | 1106.4908 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 1127.4908 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 480 | 2000000 | ACTION | 1127.9684 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 11.7327 | 48886.25 | ACTION | 1139.2235 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1141.2235 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1145.2235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 587 | 7337500 | ACTION | 1158.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1162.2885 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1167.3535 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1169.3535 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1173.3535 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1190.4185 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1195.4835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1197.4835 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1201.4835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 56 | 700000 | ACTION | 1214.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1218.5485 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1223.6135 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1225.6135 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1229.6135 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Tow Substation to Site | 109.5545 | 456477.0833 | ACTION | 1237.5229 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1239.5229 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1246.6785 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1251.7435 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1253.7435 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1257.7435 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 87 | 362500 | ACTION | 1344.7435 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Delay | 112 | 466666.6667 | ACTION | 1351.5229 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Ballast to Operational Draft | 6 | 25000 | ACTION | 1357.5229 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1361.5229 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1361.8085 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 148 | 1850000 | ACTION | 1362.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1366.8735 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1368.8735 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1372.8735 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 16.065 | 66937.5 | ACTION | 1377.5879 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1382.6529 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1389.9385 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 28 | 350000 | ACTION | 1390.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1395.0035 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 14 | 58333.3333 | ACTION | 1396.6529 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 10 | 41666.6667 | ACTION | 1405.0035 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 5 | 20833.3333 | ACTION | 1410.0035 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 33 | 137500 | ACTION | 1429.6529 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Connect Mooring Lines | 8 | 33333.3333 | ACTION | 1437.6529 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1449.6529 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1453.6529 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 55 | 229166.6667 | ACTION | 1465.0035 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 27 | 112500 | ACTION | 1492.0035 | MooringSystemInstallation
| Floating Substation Installation Vessel | Delay | 39 | 162500 | ACTION | 1492.6529 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 0.7327 | 3052.9167 | ACTION | 1492.7362 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1497.7362 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1502.7362 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 16.065 | 66937.5 | ACTION | 1508.7179 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1513.7829 | FloatingSubstationInstallation
| Export Cable Installation Vessel | Delay | 126 | 1575000 | ACTION | 1516.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 18 | 225000 | ACTION | 1534.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1535.7829 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1547.7829 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1551.7829 | FloatingSubstationInstallation
| Floating Substation Installation Vessel | Install Suction Pile Anchor | 16.065 | 66937.5 | ACTION | 1567.8479 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 1568.4689 | MooringSystemInstallation
| Export Cable Installation Vessel | Delay | 35 | 437500 | ACTION | 1569.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1570.4689 | MooringSystemInstallation
| Floating Substation Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1572.9129 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1574.4689 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1591.5339 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Connect Mooring Lines | 22 | 91666.6667 | ACTION | 1594.9129 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1596.5989 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1598.5989 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1602.5989 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Check Mooring Lines | 12 | 50000 | ACTION | 1606.9129 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1619.6639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1624.7289 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1626.7289 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 59 | 737500 | ACTION | 1628.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1630.7289 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1647.7939 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 24 | 300000 | ACTION | 1652.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1652.8589 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1654.8589 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1658.8589 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Floating Substation Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 1672.6456 | FloatingSubstationInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1675.9239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1680.9889 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1682.9889 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1686.9889 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 42 | 525000 | ACTION | 1694.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Delay | 44 | 183333.3333 | ACTION | 1730.9889 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 52 | 650000 | ACTION | 1746.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1748.0539 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 5 | 62500 | ACTION | 1751.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1753.1189 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1755.1189 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1759.1189 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 1776.1839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 61 | 254166.6667 | ACTION | 1837.1839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 1842.2489 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 156 | 1950000 | ACTION | 1907.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 1907.9816 | MooringSystemInstallation
| Export Cable Installation Vessel | Lay/Bury Cable | 4 | 50000 | ACTION | 1911.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1912.9816 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 1917.9816 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 55 | 229166.6667 | ACTION | 1972.9816 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 1974.9816 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 10.7327 | 44719.5833 | ACTION | 1985.7143 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 1987.7143 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 1991.7143 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2008.7793 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2013.8443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2015.8443 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2019.8443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2036.9093 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2041.9743 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2043.9743 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2047.9743 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2065.0393 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2070.1043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2072.1043 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2076.1043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 20 | 83333.3333 | ACTION | 2096.1043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 201 | 2512500 | ACTION | 2112.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2113.1693 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2118.2343 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2120.2343 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2124.2343 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 15 | 187500 | ACTION | 2127.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2141.2993 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2146.3643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2148.3643 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2152.3643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 15 | 62500 | ACTION | 2167.3643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 52 | 650000 | ACTION | 2179.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2184.4293 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2189.4943 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 2255.227 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2260.227 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2265.227 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Lay/Bury Cable | 89 | 1112500 | ACTION | 2268.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Delay | 2 | 25000 | ACTION | 2270.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 6 | 75000 | ACTION | 2276.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Delay | 42 | 525000 | ACTION | 2318.8 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Lay/Bury Cable | 7.9147 | 98933.2719 | ACTION | 2326.7147 | ExportCableInstallation | ExportCableInstallation | FALSE | 2 | 25 | 11.5
| Export Cable Installation Vessel | Position Onsite | 2 | 25000 | ACTION | 2328.7147 | ExportCableInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 2330.9597 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2332.9597 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2336.9597 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2354.0247 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 19 | 79166.6667 | ACTION | 2373.0247 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2378.0897 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2380.0897 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2384.0897 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 61 | 762500 | ACTION | 2389.7147 | ExportCableInstallation | ExportCableInstallation | FALSE
| Export Cable Installation Vessel | Pull In Cable | 5.5 | 68750 | ACTION | 2395.2147 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2401.1547 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2406.2197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2408.2197 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2412.2197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2429.2847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Export Cable Installation Vessel | Delay | 38 | 475000 | ACTION | 2433.2147 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2434.3497 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2436.3497 | MooringSystemInstallation
| Export Cable Installation Vessel | Terminate Cable | 5.5 | 68750 | ACTION | 2438.7147 | ExportCableInstallation | ExportCableInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2440.3497 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2457.4147 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2462.4797 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2464.4797 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2468.4797 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2485.5447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2490.6097 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2492.6097 | MooringSystemInstallation
| Export Cable Installation Vessel | Transit | 57.1589 | 714485.8696 | ACTION | 2495.8735 | ExportCableInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2496.6097 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2513.6747 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 43 | 179166.6667 | ACTION | 2556.6747 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2561.7397 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 59 | 245833.3333 | ACTION | 2620.7397 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 36 | 150000 | ACTION | 2656.7397 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 6.7327 | 28052.9167 | ACTION | 2663.4724 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2668.4724 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 2673.4724 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 2739.2051 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2741.2051 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2745.2051 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2762.2701 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2767.3351 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2769.3351 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2773.3351 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2790.4001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2795.4651 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2797.4651 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2801.4651 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2818.5301 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2823.5951 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2825.5951 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2829.5951 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2846.6601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2851.7251 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2853.7251 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2857.7251 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2874.7901 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2879.8551 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 2881.8551 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 42 | 175000 | ACTION | 2923.8551 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 2927.8551 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 2944.9201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 2949.9851 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 50 | 208333.3333 | ACTION | 2999.9851 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 7 | 29166.6667 | ACTION | 3006.9851 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 15.7327 | 65552.9167 | ACTION | 3022.7178 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3027.7178 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3032.7178 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 42 | 175000 | ACTION | 3074.7178 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 8 | 33333.3333 | ACTION | 3082.7178 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 15 | 62500 | ACTION | 3097.7178 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 16 | 66666.6667 | ACTION | 3113.7178 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 8.7327 | 36386.25 | ACTION | 3122.4505 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3124.4505 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 2 | 8333.3333 | ACTION | 3126.4505 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3130.4505 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3147.5155 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3152.5805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3154.5805 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3158.5805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 49 | 204166.6667 | ACTION | 3207.5805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3224.6455 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3229.7105 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3231.7105 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3235.7105 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3252.7755 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3257.8405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3259.8405 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3263.8405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3280.9055 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3285.9705 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3287.9705 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3291.9705 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3309.0355 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3314.1005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3316.1005 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3320.1005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3337.1655 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3342.2305 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 49 | 204166.6667 | ACTION | 3391.2305 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 71 | 295833.3333 | ACTION | 3462.2305 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 16.7327 | 69719.5833 | ACTION | 3478.9632 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3483.9632 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3488.9632 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 3554.6959 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3556.6959 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3560.6959 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3577.7609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3582.8259 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3584.8259 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3588.8259 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3605.8909 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3610.9559 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3612.9559 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3616.9559 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3634.0209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3639.0859 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3641.0859 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3645.0859 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3662.1509 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3667.2159 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3669.2159 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3673.2159 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3690.2809 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3695.3459 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3697.3459 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3701.3459 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3718.4109 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3723.4759 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 15 | 62500 | ACTION | 3738.4759 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 3759.4759 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 25 | 104166.6667 | ACTION | 3784.4759 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 47 | 195833.3333 | ACTION | 3831.4759 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 25.7327 | 107219.5833 | ACTION | 3857.2086 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3862.2086 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 3867.2086 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 17 | 70833.3333 | ACTION | 3884.2086 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 20 | 83333.3333 | ACTION | 3904.2086 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 48.7327 | 203052.9167 | ACTION | 3952.9413 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3954.9413 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3958.9413 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 3976.0063 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 3981.0713 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 3983.0713 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 3987.0713 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4004.1363 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4009.2013 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4011.2013 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4015.2013 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4032.2663 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4037.3313 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4039.3313 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 1 | 4166.6667 | ACTION | 4040.3313 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4044.3313 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4061.3963 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4066.4613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4068.4613 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4072.4613 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4089.5263 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4094.5913 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4096.5913 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4100.5913 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4117.6563 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4122.7213 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 4188.454 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4193.454 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4198.454 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 38 | 158333.3333 | ACTION | 4236.454 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 5 | 20833.3333 | ACTION | 4241.454 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 9 | 37500 | ACTION | 4250.454 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 3 | 12500 | ACTION | 4253.454 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 18.7327 | 78052.9167 | ACTION | 4272.1867 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4274.1867 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4278.1867 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4295.2517 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4300.3167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4302.3167 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4306.3167 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4323.3817 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4328.4467 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4330.4467 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4334.4467 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4351.5117 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4356.5767 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4358.5767 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4362.5767 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4379.6417 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4384.7067 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4386.7067 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4390.7067 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4407.7717 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4412.8367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4414.8367 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4418.8367 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4435.9017 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4440.9667 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 4506.6994 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4511.6994 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4516.6994 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 4582.4321 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4584.4321 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4588.4321 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4605.4971 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4610.5621 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4612.5621 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4616.5621 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4633.6271 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4638.6921 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4640.6921 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4644.6921 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4661.7571 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4666.8221 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4668.8221 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4672.8221 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4689.8871 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4694.9521 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4696.9521 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4700.9521 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4718.0171 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4723.0821 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4725.0821 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4729.0821 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4746.1471 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4751.2121 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 4816.9448 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4821.9448 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 4826.9448 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 4892.6775 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4894.6775 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4898.6775 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4915.7425 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4920.8075 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4922.8075 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4926.8075 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4943.8725 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4948.9375 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4950.9375 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4954.9375 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 4972.0025 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 4977.0675 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 4979.0675 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 4983.0675 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5000.1325 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5005.1975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5007.1975 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5011.1975 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5028.2625 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5033.3275 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5035.3275 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5039.3275 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5056.3925 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5061.4575 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 5127.1902 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5132.1902 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5137.1902 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 5202.9229 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5204.9229 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5208.9229 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5225.9879 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5231.0529 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5233.0529 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5237.0529 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5254.1179 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5259.1829 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5261.1829 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5265.1829 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5282.2479 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5287.3129 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5289.3129 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5293.3129 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5310.3779 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5315.4429 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5317.4429 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5321.4429 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5338.5079 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5343.5729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5345.5729 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5349.5729 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5366.6379 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5371.7029 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 5437.4356 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5442.4356 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5447.4356 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 5513.1683 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5515.1683 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5519.1683 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5536.2333 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5541.2983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5543.2983 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5547.2983 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5564.3633 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5569.4283 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5571.4283 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5575.4283 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5592.4933 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5597.5583 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5599.5583 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5603.5583 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5620.6233 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5625.6883 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5627.6883 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5631.6883 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5648.7533 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5653.8183 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5655.8183 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5659.8183 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5676.8833 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5681.9483 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 5747.681 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5752.681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 5757.681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 5823.4137 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5825.4137 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5829.4137 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 41 | 170833.3333 | ACTION | 5870.4137 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5887.4787 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5892.5437 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5894.5437 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5898.5437 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5915.6087 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5920.6737 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5922.6737 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5926.6737 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5943.7387 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5948.8037 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5950.8037 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5954.8037 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5971.8687 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 5976.9337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 5978.9337 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 5982.9337 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 5999.9987 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6005.0637 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6007.0637 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6011.0637 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6028.1287 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6033.1937 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 6098.9264 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6103.9264 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6108.9264 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 6174.6591 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6176.6591 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6180.6591 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6197.7241 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6202.7891 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6204.7891 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6208.7891 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6225.8541 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6230.9191 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6232.9191 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6236.9191 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6253.9841 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6259.0491 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6261.0491 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6265.0491 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6282.1141 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6287.1791 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6289.1791 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6293.1791 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6310.2441 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6315.3091 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6317.3091 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6321.3091 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6338.3741 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6343.4391 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 6409.1718 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6414.1718 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6419.1718 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6446.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 168 | 0 | ACTION | 6446.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6454.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6466.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6470.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6474.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6478.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6482.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 6484.9045 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6486.9045 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6490.9045 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6494.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6497.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6501.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6504.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6507.9695 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6513.0345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6515.0345 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6519.0345 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6528.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6536.0995 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6541.1645 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6543.1645 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6547.1645 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6564.2295 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6569.2945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6571.2945 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6575.2945 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6592.3595 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6597.4245 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6599.4245 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6600.6105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 322.5 | 2553125 | ACTION | 6600.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6603.4245 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6606.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6614.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 6614.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6620.4895 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6622.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6625.5545 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6627.5545 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6631.5545 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6634.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6638.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6642.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6646.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6648.6195 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6650.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6653.6845 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6662.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6665.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6669.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6672.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 20 | 83333.3333 | ACTION | 6673.6845 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 21 | 87500 | ACTION | 6694.6845 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6696.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 45.7327 | 190552.9167 | ACTION | 6740.4172 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6745.4172 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 6750.4172 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Transit | 14 | 58333.3333 | ACTION | 6764.4172 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6768.6105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 490.5 | 3883125 | ACTION | 6768.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6782.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 6782.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6790.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6802.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 22 | 0 | ACTION | 6824.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6828.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6832.1105 | MooredSubInstallation
| Towing Group 1 | Delay | 228 | 1805000 | ACTION | 6834.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 66 | 522500 | ACTION | 6834.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 71 | 295833.3333 | ACTION | 6835.4172 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6836.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6840.1105 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6840.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 6852.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6855.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6859.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 9 | 0 | ACTION | 6868.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 6871.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 51.7327 | 215552.9167 | ACTION | 6887.1499 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6889.1499 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6893.1499 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 6895.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6910.2149 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6915.2799 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6917.2799 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6921.2799 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6938.3449 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6943.4099 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6945.4099 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6949.4099 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 6950.1105 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 6954.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 6956.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 6960.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6962.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 6962.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6966.4749 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 6967.6105 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 689.5 | 5458541.6667 | ACTION | 6967.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 6968.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6971.5399 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 6973.5399 | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 6973.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 6975.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 6977.5399 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6982.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 6987.6105 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 6988.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 6988.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6991.6105 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 6994.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 6994.6049 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6995.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 6999.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 6999.6699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7001.6699 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7003.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7005.6699 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7015.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7019.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7022.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7022.7349 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7026.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7027.7999 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7029.7999 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7033.7999 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 46.9519 | 371702.7679 | ACTION | 7035.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 46.9519 | 371702.7679 | ACTION | 7041.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7050.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7050.8649 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7055.9299 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7118.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 7121.6626 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7122.1105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 87.0341 | 689019.7321 | ACTION | 7122.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7126.6626 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7128.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7130.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7131.6626 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7142.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7146.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7150.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7154.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7158.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7170.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7173.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7177.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7180.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 51 | 212500 | ACTION | 7182.6626 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 9 | 37500 | ACTION | 7191.6626 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7204.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 14.7327 | 61386.25 | ACTION | 7206.3953 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7208.3953 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7212.3953 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7229.4603 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7234.5253 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7236.5253 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7240.5253 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7257.5903 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7262.6553 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7264.6553 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7268.6553 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7276.6105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 235.5341 | 1864644.7321 | ACTION | 7276.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7282.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7285.7203 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7286.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 9.5 | 0 | ACTION | 7286.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7290.7853 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7292.7853 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7294.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7296.7853 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7306.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7310.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7313.8503 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7314.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7318.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7318.9153 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7320.9153 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7322.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7324.9153 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7334.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7337.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7341.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7341.9803 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7344.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7347.0453 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7349.0453 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7353.0453 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7368.6105 | MooredSubInstallation
| Towing Group 3 | Delay | 406 | 3214166.6667 | ACTION | 7379.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 97 | 767916.6667 | ACTION | 7379.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 27 | 112500 | ACTION | 7380.0453 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 252 | 1995000 | ACTION | 7380.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7397.1103 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7402.1753 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7440.6105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7454.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 7454.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7462.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 7467.908 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7472.908 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7474.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7477.908 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7478.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7482.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7486.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7490.1105 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 7499.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 7499.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 7499.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 7501.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 7501.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 7501.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7502.1105 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7507.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7507.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7507.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 71250 | ACTION | 7516.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 71250 | ACTION | 7516.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 71250 | ACTION | 7516.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 46 | 191666.6667 | ACTION | 7523.908 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 48 | 0 | ACTION | 7550.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7553.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 33 | 137500 | ACTION | 7556.908 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7557.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7560.6105 | MooredSubInstallation
| Towing Group 3 | Delay | 45 | 356250 | ACTION | 7561.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 45 | 356250 | ACTION | 7561.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 45 | 356250 | ACTION | 7561.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 87083.3333 | ACTION | 7572.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 87083.3333 | ACTION | 7572.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 11 | 87083.3333 | ACTION | 7572.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 19.7327 | 82219.5833 | ACTION | 7576.6407 | MooringSystemInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 7578.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 7578.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 7578.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7578.6407 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7582.6407 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7584.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7599.7057 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7604.7707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7606.7707 | MooringSystemInstallation
| Towing Group 3 | Transit | 29 | 229583.3333 | ACTION | 7607.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 29 | 229583.3333 | ACTION | 7607.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 29 | 229583.3333 | ACTION | 7607.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 3 | 23750 | ACTION | 7610.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 3 | 23750 | ACTION | 7610.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 3 | 23750 | ACTION | 7610.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7610.7707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 2 | 15833.3333 | ACTION | 7612.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 2 | 15833.3333 | ACTION | 7612.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 2 | 15833.3333 | ACTION | 7612.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 9 | 71250 | ACTION | 7621.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 9 | 71250 | ACTION | 7621.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 9 | 71250 | ACTION | 7621.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7622.1105 | MooredSubInstallation
| Towing Group 3 | Transit | 6 | 47500 | ACTION | 7627.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 6 | 47500 | ACTION | 7627.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 6 | 47500 | ACTION | 7627.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 9 | 71250 | ACTION | 7636.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 9 | 71250 | ACTION | 7636.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 9 | 71250 | ACTION | 7636.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 26 | 108333.3333 | ACTION | 7636.7707 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 9.9519 | 78786.1012 | ACTION | 7646.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 9.9519 | 78786.1012 | ACTION | 7646.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 9.9519 | 78786.1012 | ACTION | 7646.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7652.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7653.8357 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7656.6105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 10.5341 | 83394.7321 | ACTION | 7656.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7658.9007 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7660.9007 | MooringSystemInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7662.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7664.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7664.9007 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7676.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7680.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7681.9657 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7684.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7687.0307 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7688.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7689.0307 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7692.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7693.0307 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7704.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7708.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7710.0957 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7711.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7715.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7715.1607 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7717.1607 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7721.1607 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7738.2257 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7739.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7743.2907 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7745.2907 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7749.2907 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7766.3557 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7771.4207 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 7771.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 7773.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7779.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 7782.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 7784.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7790.1105 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7790.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 8 | 63333.3333 | ACTION | 7798.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 19 | 150416.6667 | ACTION | 7798.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 5 | 39583.3333 | ACTION | 7803.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 5 | 39583.3333 | ACTION | 7803.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 1 | 7916.6667 | ACTION | 7804.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 7810.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7811.1105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 164.5341 | 1302561.3988 | ACTION | 7811.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 71250 | ACTION | 7812.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7817.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7819.1105 | MooredSubInstallation
| Towing Group 3 | Transit | 9 | 71250 | ACTION | 7819.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 49 | 204166.6667 | ACTION | 7820.4207 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7831.1105 | MooredSubInstallation
| Towing Group 3 | Delay | 13 | 102916.6667 | ACTION | 7832.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 16 | 126666.6667 | ACTION | 7833.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 13 | 54166.6667 | ACTION | 7833.4207 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7835.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7839.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7843.1105 | MooredSubInstallation
| Towing Group 2 | Delay | 31 | 245416.6667 | ACTION | 7843.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 7846.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7847.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 16.7327 | 69719.5833 | ACTION | 7850.1534 | MooringSystemInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 7852.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7855.1534 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 7859.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 7860.1534 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7862.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7866.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 7869.6105 | MooredSubInstallation
| Towing Group 3 | Transit | 37.9519 | 300452.7679 | ACTION | 7870.5423 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 7893.6105 | MooredSubInstallation
| Towing Group 2 | Transit | 46.9519 | 371702.7679 | ACTION | 7899.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 7925.8861 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7927.8861 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7931.8861 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7948.9511 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 7952.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7954.0161 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 7954.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7956.0161 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 7958.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7960.0161 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 7960.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 7965.6105 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 95.0681 | 752622.7976 | ACTION | 7965.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 7971.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 7973.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 7977.0811 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 7980.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 7982.1461 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 7984.1461 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 7985.6105 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 7986.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 7988.1461 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7989.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7993.6105 | MooredSubInstallation
| Towing Group 1 | Transit | 7 | 55416.6667 | ACTION | 7993.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 7997.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8001.6105 | MooredSubInstallation
| Towing Group 1 | Delay | 10 | 79166.6667 | ACTION | 8003.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 16 | 66666.6667 | ACTION | 8004.1461 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8013.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8017.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8020.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8021.2111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 19 | 150416.6667 | ACTION | 8022.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8024.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8048.1105 | MooredSubInstallation
| Towing Group 3 | Delay | 79 | 625416.6667 | ACTION | 8050.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 28 | 221666.6667 | ACTION | 8050.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 30 | 125000 | ACTION | 8051.2111 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8056.2761 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8058.2761 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8062.2761 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 20.9519 | 165869.4345 | ACTION | 8071.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8079.3411 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8084.4061 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8086.4061 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8090.4061 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8107.4711 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8112.5361 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8114.5361 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8118.5361 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8120.1105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 221.0341 | 1749853.0655 | ACTION | 8120.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8126.1105 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8126.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 6 | 0 | ACTION | 8126.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8134.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8135.6011 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8140.6661 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8146.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8150.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8154.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8158.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8162.1105 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 8170.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 8172.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8174.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8177.6105 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8178.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8181.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8184.6105 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 8198.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 8204.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 8206.3988 | MooringSystemInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8208.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8211.3988 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8216.3988 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 24 | 190000 | ACTION | 8228.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 1 | 7916.6667 | ACTION | 8229.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 22.9519 | 181702.7679 | ACTION | 8252.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8280.6105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 209.0341 | 1654853.0655 | ACTION | 8280.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 8282.1315 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8284.1315 | MooringSystemInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8286.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8288.1315 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8294.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay: No Substructures in Wet Storage | 13.5 | 0 | ACTION | 8294.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8302.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8305.1965 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8310.2615 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8312.2615 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8314.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8316.2615 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8318.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8322.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8326.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8330.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8333.3265 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8338.3915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8340.3915 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8342.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8344.3915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 8356.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8359.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8363.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8366.6105 | MooredSubInstallation
| Towing Group 1 | Delay | 97 | 767916.6667 | ACTION | 8383.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 258 | 2042500 | ACTION | 8384.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 40 | 166666.6667 | ACTION | 8384.3915 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8390.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8401.4565 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8406.5215 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8408.5215 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8412.5215 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8429.5865 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8434.6515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8436.6515 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8440.6515 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8457.7165 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8462.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8462.6105 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 210.5341 | 1666728.0655 | ACTION | 8462.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8462.7815 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8464.7815 | MooringSystemInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8468.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8468.7815 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8470.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8482.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8485.8465 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8486.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8490.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8490.9115 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8494.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8498.6105 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 8503.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 8503.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 8505.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 8505.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8510.6105 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8511.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 8511.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8514.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 8519.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8522.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8526.1105 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 8531.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 8531.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 8537.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 8537.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8550.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 8556.6442 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8561.6442 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8566.6442 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 37 | 292916.6667 | ACTION | 8574.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 37 | 292916.6667 | ACTION | 8574.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 9 | 37500 | ACTION | 8575.6442 | MooringSystemInstallation
| Towing Group 1 | Delay | 15 | 118750 | ACTION | 8589.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 15 | 118750 | ACTION | 8589.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 15 | 62500 | ACTION | 8590.6442 | MooringSystemInstallation
| Towing Group 1 | Transit | 9.9519 | 78786.1012 | ACTION | 8599.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 9.9519 | 78786.1012 | ACTION | 8599.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 20 | 83333.3333 | ACTION | 8610.6442 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8630.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 87 | 0 | ACTION | 8637.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 68 | 283333.3333 | ACTION | 8678.6442 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8709.1105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 110.0341 | 871103.0655 | ACTION | 8709.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8715.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 36.7327 | 153052.9167 | ACTION | 8715.3769 | MooringSystemInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8717.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8717.3769 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8721.3769 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8729.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8733.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8737.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8738.4419 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8741.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8743.5069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8745.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8745.5069 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8749.5069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8757.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8760.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 17 | 70833.3333 | ACTION | 8766.5069 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8783.5719 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8788.6369 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8790.6369 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8794.6369 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 35 | 0 | ACTION | 8795.6105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8798.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8799.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 8804.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8807.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8811.7019 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8816.7669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8818.7669 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8822.7669 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 8831.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8839.8319 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 12 | 50000 | ACTION | 8851.8319 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8856.8969 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8858.8969 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8862.8969 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8879.9619 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8885.0269 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 8887.0269 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 8891.0269 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 8903.6105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 304.0341 | 2406936.3988 | ACTION | 8903.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 8908.0919 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 8909.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 8911.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 8913.1569 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 8923.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 13 | 54166.6667 | ACTION | 8926.1569 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8927.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 5 | 20833.3333 | ACTION | 8931.1569 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8931.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8935.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 8939.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 8951.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8955.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8958.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 8962.1105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 8966.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 8977.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 52.7327 | 219719.5833 | ACTION | 8983.8896 | MooringSystemInstallation
| Towing Group 3 | Delay | 516 | 4085000 | ACTION | 8984.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 75 | 593750 | ACTION | 8984.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 270 | 2137500 | ACTION | 8985.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8988.8896 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 8993.8896 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9001.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 9059.6223 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9061.6223 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9065.6223 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9073.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9081.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9082.6873 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9087.7523 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9089.7523 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9093.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9093.7523 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9097.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9101.1105 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 9104.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 9104.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 9104.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9105.1105 | MooredSubInstallation
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 9106.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 9106.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 9106.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9109.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9110.8173 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9112.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9112.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9112.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9115.8823 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9117.8823 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9121.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9121.8823 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9124.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9128.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9131.6105 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9132.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9132.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9132.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9134.1105 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 9138.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 9138.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 9138.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9138.9473 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9144.0123 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9146.0123 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9150.0123 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9155.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9167.0773 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9172.1423 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9174.1423 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9178.1423 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 46.9519 | 371702.7679 | ACTION | 9185.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 46.9519 | 371702.7679 | ACTION | 9185.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 46.9519 | 371702.7679 | ACTION | 9185.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9191.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9195.2073 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9200.2723 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9202.2723 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9206.2723 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9223.3373 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9227.6105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 42.5341 | 336728.0655 | ACTION | 9227.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9228.4023 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9233.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9235.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9247.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9251.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9255.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9259.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9263.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9275.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9279.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9282.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9286.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 9294.135 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9299.135 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9302.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9304.135 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9310.1105 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 9310.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 9312.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9318.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9338.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 9344.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 9353.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 9355.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9361.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 9369.8677 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9371.8677 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9375.8677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 126666.6667 | ACTION | 9377.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9382.1105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 196.5341 | 1555894.7321 | ACTION | 9382.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9388.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9390.1105 | MooredSubInstallation
| Towing Group 3 | Transit | 46 | 364166.6667 | ACTION | 9390.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9402.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9406.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9410.1105 | MooredSubInstallation
| Towing Group 3 | Delay | 22 | 174166.6667 | ACTION | 9412.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 25 | 197916.6667 | ACTION | 9413.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 0.95193 | 7536.1012 | ACTION | 9413.5423 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 38 | 158333.3333 | ACTION | 9413.8677 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9414.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9418.1105 | MooredSubInstallation
| Towing Group 2 | Delay | 42 | 332500 | ACTION | 9419.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 31666.6667 | ACTION | 9423.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 9429.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9430.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9430.9327 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9433.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9435.9977 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9437.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9437.9977 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9440.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9441.9977 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9459.0627 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9464.1277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9464.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9466.1277 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9470.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9470.1277 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 46.9519 | 371702.7679 | ACTION | 9476.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9487.1927 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9492.2577 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9494.2577 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9498.2577 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9515.3227 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9520.3877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9522.3877 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9526.3877 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 9532.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 9534.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9536.6105 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 123.0681 | 974289.4643 | ACTION | 9536.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9540.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9542.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9543.4527 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9544.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9548.5177 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9550.5177 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9554.5177 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9556.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9560.6105 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 9560.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9564.6105 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 9566.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9568.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9571.5827 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9572.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9576.6477 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9584.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9588.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9591.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9595.1105 | MooredSubInstallation
| Towing Group 1 | Transit | 46.9519 | 371702.7679 | ACTION | 9613.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9619.1105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9638.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 9642.3804 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9647.3804 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 9652.3804 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 9662.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 9664.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 9670.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 9 | 71250 | ACTION | 9679.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 30 | 125000 | ACTION | 9682.3804 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9691.1105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 215.0341 | 1702353.0655 | ACTION | 9691.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9699.1105 | MooredSubInstallation
| Towing Group 2 | Delay | 19 | 150416.6667 | ACTION | 9710.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 28 | 116666.6667 | ACTION | 9710.3804 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9711.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9715.1105 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9716.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9719.1105 | MooredSubInstallation
| Towing Group 3 | Delay | 40 | 316666.6667 | ACTION | 9719.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9723.1105 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 39583.3333 | ACTION | 9724.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9727.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9739.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 30 | 125000 | ACTION | 9740.3804 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 19 | 0 | ACTION | 9758.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9761.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9765.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 25 | 104166.6667 | ACTION | 9765.3804 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9768.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 5.7327 | 23886.25 | ACTION | 9771.1131 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9773.1131 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9777.1131 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 53 | 419583.3333 | ACTION | 9777.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 47500 | ACTION | 9783.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 9789.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9792.6105 | MooredSubInstallation
| Towing Group 3 | Transit | 5 | 39583.3333 | ACTION | 9794.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9794.1781 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9806.1105 | MooredSubInstallation
| Towing Group 3 | Delay | 27 | 213750 | ACTION | 9821.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 28 | 116666.6667 | ACTION | 9822.1781 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9827.2431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9829.2431 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9833.2431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 24 | 190000 | ACTION | 9845.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 9864.6105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 251.0341 | 1987353.0655 | ACTION | 9864.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 9872.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 9884.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 9896.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9900.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9904.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9908.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 9912.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 9924.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9928.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9931.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 9935.1105 | MooredSubInstallation
| Towing Group 3 | Delay | 90 | 712500 | ACTION | 9935.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 71 | 562083.3333 | ACTION | 9935.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 220 | 1741666.6667 | ACTION | 9936.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 103 | 429166.6667 | ACTION | 9936.2431 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 9941.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 17.9519 | 142119.4345 | ACTION | 9953.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9953.3081 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9958.3731 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 9959.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9960.3731 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9964.3731 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 9974.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 9981.4381 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 9986.5031 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 9988.5031 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 9992.5031 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10009.5681 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10014.6331 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10016.6331 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10020.6331 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10031.1105 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 78.0341 | 617769.7321 | ACTION | 10031.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 10037.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10037.6981 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10039.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10042.7631 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10044.7631 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10048.7631 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10051.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10055.1105 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 10055.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 10057.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10059.1105 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 10061.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10063.1105 | MooredSubInstallation
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 10063.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 10063.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10065.8281 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10067.1105 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 10069.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10070.8931 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10079.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10082.6105 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 10083.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10086.1105 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 10089.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10089.6105 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 10089.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 10095.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10113.6105 | MooredSubInstallation
| Towing Group 2 | Transit | 46.9519 | 371702.7679 | ACTION | 10136.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 10136.6258 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10141.6258 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 46.9519 | 371702.7679 | ACTION | 10142.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10142.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10146.6258 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 10156.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 10158.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 10164.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 10184.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10185.6105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 49.0341 | 388186.3988 | ACTION | 10185.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 10190.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 10191.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10193.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10205.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10209.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 10212.3585 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10213.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10214.3585 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10217.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10218.3585 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10221.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10233.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10235.4235 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10237.1105 | MooredSubInstallation
| Towing Group 3 | Transit | 46.9519 | 371702.7679 | ACTION | 10237.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10240.4885 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10240.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10242.4885 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10244.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10246.4885 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10263.5535 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10268.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 40 | 166666.6667 | ACTION | 10303.5535 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10308.6185 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10310.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10310.6185 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10314.6185 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10331.6835 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10336.7485 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10338.7485 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10340.1105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 198.0341 | 1567769.7321 | ACTION | 10340.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10342.7485 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 10346.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10348.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10359.8135 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10360.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10364.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10364.8785 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10366.8785 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10368.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10370.8785 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10372.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10376.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10387.9435 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10388.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10393.0085 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10395.0085 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 36 | 0 | ACTION | 10424.1105 | MooredSubInstallation
| Towing Group 2 | Delay | 233 | 1844583.3333 | ACTION | 10424.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 30 | 125000 | ACTION | 10425.0085 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 79 | 625416.6667 | ACTION | 10425.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10427.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10429.0085 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10431.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10434.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10446.0735 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10451.1385 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10458.6105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10478.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 10516.8712 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10521.8712 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10526.8712 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10530.6105 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 293.0341 | 2319853.0655 | ACTION | 10530.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 10536.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10538.6105 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 10544.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 10544.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 10546.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 10546.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10550.6105 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 10552.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 10552.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10554.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10558.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10562.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10566.6105 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 10572.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 10572.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 10578.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10578.6105 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 10578.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10582.1105 | MooredSubInstallation
| Towing Group 2 | Transit | 12 | 95000 | ACTION | 10590.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 12 | 95000 | ACTION | 10590.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 65 | 270833.3333 | ACTION | 10591.8712 | MooringSystemInstallation
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 10594.1105 | MooredSubInstallation
| Towing Group 2 | Delay | 4 | 31666.6667 | ACTION | 10594.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 4 | 31666.6667 | ACTION | 10594.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 10595.8712 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 0.7327 | 3052.9167 | ACTION | 10596.6039 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10597.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10598.6039 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10601.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10602.6039 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10619.6689 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 27 | 213750 | ACTION | 10621.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 27 | 213750 | ACTION | 10621.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 1 | 7916.6667 | ACTION | 10622.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 1 | 7916.6667 | ACTION | 10622.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 4 | 16666.6667 | ACTION | 10623.6689 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10625.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10628.7339 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Transit | 7.9519 | 62952.7679 | ACTION | 10630.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 7.9519 | 62952.7679 | ACTION | 10630.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10630.7339 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10634.7339 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10646.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10651.7989 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10656.8639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10658.8639 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10662.8639 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10679.9289 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10684.9939 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10686.9939 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10690.9939 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 10697.1105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 67.0341 | 530686.3988 | ACTION | 10697.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 10703.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 10705.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10708.0589 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10713.1239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10715.1239 | MooringSystemInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 10717.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10719.1239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 10721.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10725.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 16 | 0 | ACTION | 10741.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10745.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 12 | 0 | ACTION | 10757.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10761.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 45 | 187500 | ACTION | 10764.1239 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 10765.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 10777.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10781.1889 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10786.2539 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 10788.2539 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 10792.2539 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10814.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 39 | 162500 | ACTION | 10831.2539 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 61 | 0 | ACTION | 10838.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10841.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10845.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 10848.3189 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 10848.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 10853.3839 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 10872.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 25 | 104166.6667 | ACTION | 10878.3839 | MooringSystemInstallation
| Mooring System Installation Vessel | Delay | 40 | 166666.6667 | ACTION | 10918.3839 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 36 | 150000 | ACTION | 10954.3839 | MooringSystemInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 10982.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Delay | 30 | 125000 | ACTION | 10984.3839 | MooringSystemInstallation
| Mooring System Installation Vessel | Transit | 4.7327 | 19719.5833 | ACTION | 10989.1166 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 10994.1166 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 132 | 0 | ACTION | 11004.6105 | MooredSubInstallation
| Towing Group 3 | Delay | 496 | 3926666.6667 | ACTION | 11032.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 330 | 2612500 | ACTION | 11033.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 39 | 162500 | ACTION | 11033.1166 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11038.1166 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11076.6105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 446.0341 | 3531103.0655 | ACTION | 11076.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11082.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11084.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11096.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11100.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 11103.8493 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11104.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11105.8493 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11108.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11109.8493 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11112.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11124.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 11126.9143 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11128.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11131.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 11131.9793 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11133.9793 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11135.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11137.9793 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11150.1105 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 11152.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 11152.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 11154.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 11154.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 11155.0443 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11159.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 11160.1093 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11160.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11160.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11162.1093 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11166.1093 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11180.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11180.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 11183.1743 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 11 | 45833.3333 | ACTION | 11194.1743 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 11199.2393 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11201.2393 | MooringSystemInstallation
| Towing Group 3 | Delay | 24 | 190000 | ACTION | 11204.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 24 | 190000 | ACTION | 11204.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11205.2393 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 11210.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 11210.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 11222.3043 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 11227.3693 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11229.3693 | MooringSystemInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11231.1105 | MooredSubInstallation
| Towing Group 3 | Transit | 21 | 166250 | ACTION | 11231.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 21 | 166250 | ACTION | 11231.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11233.3693 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11239.1105 | MooredSubInstallation
| Towing Group 3 | Delay | 10 | 79166.6667 | ACTION | 11241.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 10 | 79166.6667 | ACTION | 11241.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 8 | 63333.3333 | ACTION | 11249.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 8 | 63333.3333 | ACTION | 11249.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 11250.4343 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11251.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 56 | 0 | ACTION | 11307.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11311.1105 | MooredSubInstallation
| Towing Group 3 | Delay | 62 | 490833.3333 | ACTION | 11311.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 62 | 490833.3333 | ACTION | 11311.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Delay | 62 | 258333.3333 | ACTION | 11312.4343 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11315.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 11317.4993 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11318.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11319.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11319.4993 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11323.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11323.4993 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Transit | 15 | 118750 | ACTION | 11326.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 15 | 118750 | ACTION | 11326.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 3 | 23750 | ACTION | 11329.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 3 | 23750 | ACTION | 11329.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 11330.1105 | MooredSubInstallation
| Towing Group 3 | Transit | 2.9519 | 23369.4345 | ACTION | 11332.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 2.9519 | 23369.4345 | ACTION | 11332.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11338.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 11340.5643 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11342.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 11345.6293 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 278 | 2200833.3333 | ACTION | 11360.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 23 | 182083.3333 | ACTION | 11361.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 25 | 0 | ACTION | 11367.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11370.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11374.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 11381.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11384.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11408.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 11411.362 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11416.362 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11421.362 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 11480.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 11480.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11480.6105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 148.0341 | 1171936.3988 | ACTION | 11480.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 11482.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 11482.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11486.1105 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11486.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 11487.0947 | MooringSystemInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11488.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11488.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11488.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11489.0947 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11493.0947 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11500.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11504.6105 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11508.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11508.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11508.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 11510.1597 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11512.6105 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 11514.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 11514.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 11515.2247 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11516.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11517.2247 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11521.2247 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11528.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 3 | 0 | ACTION | 11531.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11535.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 11538.2897 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 11543.3547 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11545.3547 | MooringSystemInstallation
| Towing Group 1 | Transit | 32 | 253333.3333 | ACTION | 11546.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 32 | 253333.3333 | ACTION | 11546.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11549.3547 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Delay | 4 | 31666.6667 | ACTION | 11550.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 4 | 31666.6667 | ACTION | 11550.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 64 | 506666.6667 | ACTION | 11550.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 14.9519 | 118369.4345 | ACTION | 11565.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 14.9519 | 118369.4345 | ACTION | 11565.5423 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 11566.4197 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 11571.4847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11573.4847 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11577.4847 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 46 | 0 | ACTION | 11581.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11584.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11588.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 11594.5497 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 11599.6147 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11601.6147 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11605.6147 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11612.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 11622.6797 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 11627.7447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11629.7447 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11633.7447 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 11650.8097 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11654.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 11655.8747 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 11670.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 11672.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 11678.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 11684.1105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 119.0341 | 942353.0655 | ACTION | 11684.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 11690.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 11692.1105 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 11698.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 11704.1105 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 11704.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11708.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11712.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11716.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 11720.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 11721.6074 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11726.6074 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 11731.6074 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 11732.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11735.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11739.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 11742.6105 | MooredSubInstallation
| Towing Group 2 | Transit | 46.9519 | 371702.7679 | ACTION | 11751.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 11766.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 11797.3401 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11799.3401 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11803.3401 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 11820.4051 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11822.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 11825.4701 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11827.4701 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11831.4701 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Delay | 59 | 245833.3333 | ACTION | 11890.4701 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 11907.5351 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 11912.6001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11914.6001 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11918.6001 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 11935.6651 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 11940.7301 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11942.7301 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11946.7301 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 11963.7951 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 11968.8601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11970.8601 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 11974.8601 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 11990.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 11991.9251 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 11996.9901 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 11998.9901 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12002.9901 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 12020.0551 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 12025.1201 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Delay | 260 | 0 | ACTION | 12026.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 12090.8528 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12095.8528 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12098.6105 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 533.0681 | 4220122.7976 | ACTION | 12098.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12100.8528 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12104.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12106.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12118.6105 | MooredSubInstallation
| Towing Group 3 | Delay | 20 | 158333.3333 | ACTION | 12124.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 12124.6105 | MooredSubInstallation
| Towing Group 1 | Delay | 435 | 3443750 | ACTION | 12125.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12128.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12132.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12136.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12140.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12152.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12156.1105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12158.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12159.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12163.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 12166.5855 | MooringSystemInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12168.5855 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12172.5855 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12187.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 12189.6505 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 12194.7155 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12196.7155 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12200.7155 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 12217.7805 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 12222.8455 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12224.8455 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12228.8455 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 12244.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 12244.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 12245.9105 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Delay | 5 | 39583.3333 | ACTION | 12249.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 5 | 39583.3333 | ACTION | 12249.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 12250.9755 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 12251.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 12251.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12252.9755 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12256.9755 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12257.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12257.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12259.1105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 508.0341 | 4021936.3988 | ACTION | 12259.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12265.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12267.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 12274.0405 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 12277.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 12277.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 12279.1055 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12279.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12281.1055 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12283.1105 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 12283.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 12283.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12285.1055 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12287.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12291.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12295.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 12302.1705 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12307.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 12307.2355 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12309.2355 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12310.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12313.2355 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12314.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12317.6105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12326.1105 | MooredSubInstallation
| Towing Group 3 | Transit | 46.9519 | 371702.7679 | ACTION | 12330.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 12330.3005 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 1 | Transit | 46.9519 | 371702.7679 | ACTION | 12330.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 12335.3655 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12341.6105 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 12384.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 12386.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12392.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 12401.0982 | MooringSystemInstallation
| Mooring System Installation Vessel | Load Mooring System | 5 | 20833.3333 | ACTION | 12406.0982 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 12412.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12413.6105 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 83.5341 | 661311.3988 | ACTION | 12413.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 12418.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12419.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12421.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12433.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12437.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12441.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12445.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12449.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12461.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12465.1105 | MooredSubInstallation
| Towing Group 2 | Transit | 46.9519 | 371702.7679 | ACTION | 12465.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12468.6105 | MooredSubInstallation
| Mooring System Installation Vessel | Transit | 65.7327 | 273886.25 | ACTION | 12471.8309 | MooringSystemInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12472.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12473.8309 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12477.8309 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12494.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 12494.8959 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12496.1105 | MooredSubInstallation
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 12499.9609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12501.9609 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12505.9609 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 12523.0259 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 12528.0909 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Position Onsite | 2 | 8333.3333 | ACTION | 12530.0909 | MooringSystemInstallation
| Mooring System Installation Vessel | Perform Mooring Site Survey | 4 | 16666.6667 | ACTION | 12534.0909 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 12539.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 12541.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12547.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Mooring System Installation Vessel | Install Drag Embedment Anchor | 17.065 | 71104.1667 | ACTION | 12551.1559 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Mooring System Installation Vessel | Install Mooring Line | 5.065 | 21104.1667 | ACTION | 12556.2209 | MooringSystemInstallation | MooringSystemInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 12567.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12568.1105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 237.5341 | 1880478.0655 | ACTION | 12568.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 12573.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12574.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12576.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12588.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12592.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12596.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12600.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12604.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12616.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12619.6105 | MooredSubInstallation
| Towing Group 3 | Transit | 46.9519 | 371702.7679 | ACTION | 12620.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12623.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12626.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12650.6105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12662.1105 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 12693.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 12695.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 12701.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 12721.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12722.6105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 257.0341 | 2034853.0655 | ACTION | 12722.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 12727.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12728.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12730.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12742.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12746.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12750.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12754.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12758.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12770.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12774.1105 | MooredSubInstallation
| Towing Group 1 | Transit | 46.9519 | 371702.7679 | ACTION | 12774.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12777.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12781.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 12805.1105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12830.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 66 | 0 | ACTION | 12871.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 12943.1105 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 323.0341 | 2557353.0655 | ACTION | 12943.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 12949.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 12951.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 12963.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12967.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12971.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12975.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 12979.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 12991.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12994.6105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 12998.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 12998.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13001.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13025.6105 | MooredSubInstallation
| Towing Group 2 | Delay | 310 | 2454166.6667 | ACTION | 13038.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 90 | 712500 | ACTION | 13039.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13097.6105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 323.0341 | 2557353.0655 | ACTION | 13097.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13103.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13105.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13117.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13121.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13125.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13129.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13133.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13145.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13149.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13152.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13156.1105 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 13158.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 13158.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 13160.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 13160.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13166.1105 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13166.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13166.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13180.1105 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13186.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13186.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 13192.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 13192.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 13223.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 13225.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13231.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 46.9519 | 371702.7679 | ACTION | 13239.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 46.9519 | 371702.7679 | ACTION | 13239.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13251.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13252.1105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 13.0341 | 103186.3988 | ACTION | 13252.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 13257.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13258.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13260.1105 | MooredSubInstallation
| Towing Group 1 | Transit | 13 | 102916.6667 | ACTION | 13270.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13272.1105 | MooredSubInstallation
| Towing Group 1 | Delay | 6 | 47500 | ACTION | 13276.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 5 | 0 | ACTION | 13277.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13281.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13285.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13289.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13293.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13305.1105 | MooredSubInstallation
| Towing Group 1 | Transit | 33.9519 | 268786.1012 | ACTION | 13310.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13334.1105 | MooredSubInstallation
| Towing Group 2 | Delay | 174 | 1377500 | ACTION | 13432.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 142 | 0 | ACTION | 13447.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13450.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13454.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13457.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13481.6105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13502.1105 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 13551.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13553.6105 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 314.0341 | 2486103.0655 | ACTION | 13553.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 13553.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13559.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13559.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13561.6105 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 31666.6667 | ACTION | 13563.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 5 | 39583.3333 | ACTION | 13568.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13573.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13577.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13581.6105 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 126666.6667 | ACTION | 13584.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13585.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13589.6105 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 13590.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13601.6105 | MooredSubInstallation
| Towing Group 2 | Transit | 15 | 118750 | ACTION | 13605.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 11 | 87083.3333 | ACTION | 13616.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 8 | 63333.3333 | ACTION | 13624.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 105 | 831250 | ACTION | 13664.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 40 | 316666.6667 | ACTION | 13664.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13670.1105 | MooredSubInstallation
| Towing Group 2 | Transit | 23.9519 | 189619.4345 | ACTION | 13688.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 115 | 0 | ACTION | 13716.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13720.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 13735.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13738.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13742.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13766.1105 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 13784.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 13786.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13792.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13812.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 13818.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 13838.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13838.1105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 528.0341 | 4180269.7321 | ACTION | 13838.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13844.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 13846.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 13858.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13862.1105 | MooredSubInstallation
| Towing Group 3 | Transit | 46.9519 | 371702.7679 | ACTION | 13865.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13866.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13870.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 13874.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 13886.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13889.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13893.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 13896.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 13920.6105 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 13963.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 13965.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 13971.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 13991.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 13992.6105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 304.0341 | 2406936.3988 | ACTION | 13992.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 13997.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 13998.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14000.6105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14006.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14012.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14016.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14020.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14024.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14028.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14040.6105 | MooredSubInstallation
| Towing Group 1 | Transit | 46.9519 | 371702.7679 | ACTION | 14044.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 14054.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14058.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14061.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 14072.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14076.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14100.1105 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 14118.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 14120.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14126.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14146.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 14152.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7 | 55416.6667 | ACTION | 14159.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 10 | 79166.6667 | ACTION | 14169.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 2 | 15833.3333 | ACTION | 14171.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14172.1105 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 307.0341 | 2430686.3988 | ACTION | 14172.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14174.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14180.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14192.1105 | MooredSubInstallation
| Towing Group 2 | Delay | 21 | 166250 | ACTION | 14192.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 1 | 7916.6667 | ACTION | 14193.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 2 | 15833.3333 | ACTION | 14195.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 24 | 190000 | ACTION | 14196.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 14196.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14200.1105 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14202.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 7 | 55416.6667 | ACTION | 14202.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 11 | 87083.3333 | ACTION | 14213.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 14 | 0 | ACTION | 14214.1105 | MooredSubInstallation
| Towing Group 3 | Delay | 12 | 95000 | ACTION | 14214.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14218.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14222.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14226.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14238.1105 | MooredSubInstallation
| Towing Group 2 | Transit | 29.9519 | 237119.4345 | ACTION | 14243.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 14249.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14252.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14256.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 7 | 0 | ACTION | 14263.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14266.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14290.6105 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 14333.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 14335.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14341.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14342.1105 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14361.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14362.6105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 318.0341 | 2517769.7321 | ACTION | 14362.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 20.5 | 0 | ACTION | 14362.6105 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 14367.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14368.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14370.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14382.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14386.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14390.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14394.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14398.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14410.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14414.1105 | MooredSubInstallation
| Towing Group 3 | Transit | 46.9519 | 371702.7679 | ACTION | 14414.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14417.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14421.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14445.1105 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 14488.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 14490.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14496.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14516.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14517.1105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 274.0341 | 2169436.3988 | ACTION | 14517.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 14522.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14523.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14525.1105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14530.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14537.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14541.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14545.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14549.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14553.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14565.1105 | MooredSubInstallation
| Towing Group 1 | Transit | 46 | 364166.6667 | ACTION | 14568.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 8 | 63333.3333 | ACTION | 14576.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 0.95193 | 7536.1012 | ACTION | 14577.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 42 | 0 | ACTION | 14607.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14610.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 35 | 0 | ACTION | 14645.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14649.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14652.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14676.6105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14698.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14748.6105 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 334.0341 | 2644436.3988 | ACTION | 14748.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 50 | 0 | ACTION | 14748.6105 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14754.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14756.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14768.6105 | MooredSubInstallation
| Towing Group 3 | Delay | 37 | 292916.6667 | ACTION | 14791.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 23 | 0 | ACTION | 14791.6105 | MooredSubInstallation
| Towing Group 2 | Delay | 269 | 2129583.3333 | ACTION | 14792.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14795.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14799.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14803.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14807.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14819.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14823.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14826.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 14830.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 14854.1105 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 14911.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 14911.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 14916.6105 | MooredSubInstallation
| Towing Group 3 | Delay | 7 | 55416.6667 | ACTION | 14918.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 7 | 55416.6667 | ACTION | 14918.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 14920.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 14920.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 14926.1105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 349.0341 | 2763186.3988 | ACTION | 14926.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 9.5 | 0 | ACTION | 14926.1105 | MooredSubInstallation
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14926.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 14926.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 14932.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 14934.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 14946.1105 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14946.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 14946.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14950.1105 | MooredSubInstallation
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 14952.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 14952.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14954.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14958.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 14962.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 14974.1105 | MooredSubInstallation
| Towing Group 3 | Transit | 42 | 332500 | ACTION | 14994.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 42 | 332500 | ACTION | 14994.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 17 | 134583.3333 | ACTION | 15011.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 17 | 134583.3333 | ACTION | 15011.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 2 | 15833.3333 | ACTION | 15013.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 2 | 15833.3333 | ACTION | 15013.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 4 | 31666.6667 | ACTION | 15017.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 4 | 31666.6667 | ACTION | 15017.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 86 | 680833.3333 | ACTION | 15018.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 2.9519 | 23369.4345 | ACTION | 15020.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 2.9519 | 23369.4345 | ACTION | 15020.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 56 | 0 | ACTION | 15030.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15033.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15037.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15040.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15064.6105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15094.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15136.6105 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 116.5341 | 922561.3988 | ACTION | 15136.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 42.5 | 0 | ACTION | 15136.6105 | MooredSubInstallation
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 15137.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 15139.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15142.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15144.6105 | MooredSubInstallation
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15145.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15156.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15160.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15164.6105 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 15165.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15168.6105 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 15171.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15172.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15184.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 18 | 0 | ACTION | 15202.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15206.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15209.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15213.1105 | MooredSubInstallation
| Towing Group 1 | Transit | 46.9519 | 371702.7679 | ACTION | 15218.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15237.1105 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 15262.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 15264.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15270.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 15290.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 15296.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 8 | 63333.3333 | ACTION | 15304.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15304.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15309.1105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 288.5341 | 2284228.0655 | ACTION | 15309.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 4.5 | 0 | ACTION | 15309.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15317.1105 | MooredSubInstallation
| Towing Group 3 | Delay | 16 | 126666.6667 | ACTION | 15320.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 1 | 7916.6667 | ACTION | 15321.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 7 | 55416.6667 | ACTION | 15328.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15329.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15333.1105 | MooredSubInstallation
| Towing Group 3 | Transit | 5 | 39583.3333 | ACTION | 15333.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 15339.1105 | MooredSubInstallation
| Towing Group 3 | Delay | 6 | 47500 | ACTION | 15339.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 31 | 245416.6667 | ACTION | 15340.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15343.1105 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15346.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15347.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15351.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15363.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15366.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15370.1105 | MooredSubInstallation
| Towing Group 3 | Transit | 32.9519 | 260869.4345 | ACTION | 15372.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15373.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15397.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 15412.6105 | MooredSubInstallation
| Towing Group 2 | Delay | 77 | 609583.3333 | ACTION | 15423.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15477.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15484.6105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 266.0341 | 2106103.0655 | ACTION | 15484.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 7.5 | 0 | ACTION | 15484.6105 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15490.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15492.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15504.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15508.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15512.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15516.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15520.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15532.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15536.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15539.6105 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 15542.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15543.1105 | MooredSubInstallation
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 15544.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15550.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15567.1105 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 15570.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 15576.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 15610.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 15612.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 15618.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 46.9519 | 371702.7679 | ACTION | 15623.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 102916.6667 | ACTION | 15631.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 85 | 0 | ACTION | 15652.1105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15652.6105 | MooredSubInstallation
| Towing Group 1 | Delay | 73 | 577916.6667 | ACTION | 15704.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 55416.6667 | ACTION | 15711.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 15717.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15724.1105 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 352.0341 | 2786936.3988 | ACTION | 15724.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 71.5 | 0 | ACTION | 15724.1105 | MooredSubInstallation
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15730.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15732.1105 | MooredSubInstallation
| Towing Group 1 | Transit | 24 | 190000 | ACTION | 15741.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15744.1105 | MooredSubInstallation
| Towing Group 1 | Delay | 6 | 47500 | ACTION | 15747.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 4 | 0 | ACTION | 15748.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15752.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15756.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15760.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15764.1105 | MooredSubInstallation
| Towing Group 1 | Transit | 22.9519 | 181702.7679 | ACTION | 15770.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15776.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15779.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15783.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15786.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 15810.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 15882.6105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 259.0341 | 2050686.3988 | ACTION | 15882.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 15888.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 15890.6105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 15892.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 15902.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 15 | 0 | ACTION | 15917.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15921.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15925.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15929.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 15933.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 15945.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 15949.1105 | MooredSubInstallation
| Towing Group 2 | Delay | 127 | 1005416.6667 | ACTION | 16015.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 286 | 2264166.6667 | ACTION | 16016.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 67 | 0 | ACTION | 16016.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16019.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16023.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16047.1105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16060.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16119.1105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 349.0341 | 2763186.3988 | ACTION | 16119.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 59 | 0 | ACTION | 16119.1105 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 16125.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16127.1105 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 16135.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 16135.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 16137.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 16137.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16139.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16143.1105 | MooredSubInstallation
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 16143.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 16143.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16147.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16151.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16155.1105 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 16163.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 16163.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16167.1105 | MooredSubInstallation
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 16169.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 16169.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16170.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16174.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16177.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16201.6105 | MooredSubInstallation
| Towing Group 2 | Transit | 46.9519 | 371702.7679 | ACTION | 16216.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 46.9519 | 371702.7679 | ACTION | 16216.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16273.6105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 57.5341 | 455478.0655 | ACTION | 16273.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16281.6105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16287.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16293.6105 | MooredSubInstallation
| Towing Group 2 | Delay | 23 | 182083.3333 | ACTION | 16296.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16297.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16301.6105 | MooredSubInstallation
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 16302.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16305.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16309.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16321.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 10 | 0 | ACTION | 16331.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16335.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16338.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16342.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16366.1105 | MooredSubInstallation
| Towing Group 2 | Delay | 71 | 562083.3333 | ACTION | 16373.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 249 | 1971250 | ACTION | 16374.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16438.1105 | MooredSubInstallation
| Towing Group 3 | Delay: No Completed Turbine Assemblies | 221.5341 | 1753811.3988 | ACTION | 16438.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 16444.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16446.1105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16455.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16458.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16462.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16466.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16470.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16474.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16486.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16489.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16493.1105 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 16493.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 16493.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay | 25 | 0 | ACTION | 16518.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16521.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16545.6105 | MooredSubInstallation
| Towing Group 2 | Delay | 108 | 855000 | ACTION | 16601.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 108 | 855000 | ACTION | 16601.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 16603.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 16603.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 16609.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 16609.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 15833.3333 | ACTION | 16611.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 2 | 15833.3333 | ACTION | 16611.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16617.6105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16623.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16625.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16637.6105 | MooredSubInstallation
| Towing Group 2 | Delay | 30 | 237500 | ACTION | 16641.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16641.6105 | MooredSubInstallation
| Towing Group 1 | Delay | 30 | 237500 | ACTION | 16641.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16645.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16649.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16653.6105 | MooredSubInstallation
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 142500 | ACTION | 16659.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 18 | 142500 | ACTION | 16659.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 16665.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16665.6105 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 16665.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16669.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16672.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16676.1105 | MooredSubInstallation
| Towing Group 2 | Transit | 32 | 253333.3333 | ACTION | 16697.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 32 | 253333.3333 | ACTION | 16697.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16700.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 45 | 0 | ACTION | 16745.1105 | MooredSubInstallation
| Towing Group 2 | Delay | 82 | 649166.6667 | ACTION | 16779.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 82 | 649166.6667 | ACTION | 16779.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 1 | 7916.6667 | ACTION | 16780.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 1 | 7916.6667 | ACTION | 16780.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 4 | 31666.6667 | ACTION | 16784.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 4 | 31666.6667 | ACTION | 16784.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 341 | 2699583.3333 | ACTION | 16785.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16791.1105 | MooredSubInstallation
| Towing Group 2 | Transit | 13.9519 | 110452.7679 | ACTION | 16798.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 13.9519 | 110452.7679 | ACTION | 16798.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 16804.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16817.1105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 18.5341 | 146728.0655 | ACTION | 16817.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Delay: No Substructure Storage Available | 26 | 0 | ACTION | 16817.1105 | MooredSubInstallation
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 16823.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16825.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16837.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16841.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16845.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16849.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16853.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 16865.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16868.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16872.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 16875.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 16899.6105 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 16904.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 16906.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 16912.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 16923.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 16925.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 16931.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 16932.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 16938.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 16942.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 16944.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 16950.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 16951.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 16957.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 118750 | ACTION | 16965.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 9 | 71250 | ACTION | 16966.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 28 | 221666.6667 | ACTION | 16966.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 2 | 15833.3333 | ACTION | 16968.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 2 | 15833.3333 | ACTION | 16968.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 1 | 7916.6667 | ACTION | 16969.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 1 | 7916.6667 | ACTION | 16969.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 16971.6105 | MooredSubInstallation
| Towing Group 2 | Delay | 5 | 39583.3333 | ACTION | 16974.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 5 | 39583.3333 | ACTION | 16974.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 13 | 102916.6667 | ACTION | 16978.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 16979.6105 | MooredSubInstallation
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 39583.3333 | ACTION | 16983.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 16985.1105 | MooredSubInstallation
| Towing Group 1 | Check Mooring Lines | 2 | 15833.3333 | ACTION | 16985.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 16991.6105 | MooredSubInstallation
| Towing Group 3 | Transit | 17.9519 | 142119.4345 | ACTION | 16992.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 20 | 158333.3333 | ACTION | 16994.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16995.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 16999.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17003.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17007.6105 | MooredSubInstallation
| Towing Group 3 | Delay | 17 | 134583.3333 | ACTION | 17009.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 15 | 118750 | ACTION | 17009.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 17015.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17019.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17023.1105 | MooredSubInstallation
| Towing Group 2 | Transit | 16.9519 | 134202.7679 | ACTION | 17026.5423 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17026.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17030.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17054.1105 | MooredSubInstallation
| Towing Group 1 | Delay | 78 | 617500 | ACTION | 17063.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 4 | 31666.6667 | ACTION | 17067.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 15 | 118750 | ACTION | 17082.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 2 | 15833.3333 | ACTION | 17084.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 31.9519 | 252952.7679 | ACTION | 17116.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17126.1105 | MooredSubInstallation
| Towing Group 2 | Delay: No Completed Turbine Assemblies | 99.5681 | 788247.7976 | ACTION | 17126.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 17132.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17134.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17146.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17150.1105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 17153.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17154.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17158.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17162.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17174.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17177.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17181.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17184.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17208.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17280.6105 | MooredSubInstallation
| Towing Group 1 | Delay: No Completed Turbine Assemblies | 164.0341 | 1298603.0655 | ACTION | 17280.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 17286.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17288.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17300.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17304.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17308.6105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 17321.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 28 | 0 | ACTION | 17336.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17340.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17344.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17356.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17360.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17363.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17367.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17391.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17463.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17471.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17483.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17487.1105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 17489.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17491.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17495.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17499.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17511.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17514.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17518.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17521.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17545.6105 | MooredSubInstallation
| Towing Group 3 | Delay | 583 | 4615416.6667 | ACTION | 17598.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 312 | 2470000 | ACTION | 17598.6105 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 467 | 3697083.3333 | ACTION | 17599.1105 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17617.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17625.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17637.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17641.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17645.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17649.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17653.6105 | MooredSubInstallation
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 17657.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17665.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17669.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17672.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17676.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17700.1105 | MooredSubInstallation
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 17718.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 17718.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 17718.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 17720.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 17720.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 17720.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 17726.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 17726.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 17726.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 17729.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 3 | 23750 | ACTION | 17729.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 31666.6667 | ACTION | 17730.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17772.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17780.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17792.1105 | MooredSubInstallation
| Towing Group 1 | Delay | 63 | 498750 | ACTION | 17792.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 63 | 498750 | ACTION | 17792.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 63 | 498750 | ACTION | 17793.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17796.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17800.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17804.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17808.1105 | MooredSubInstallation
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 126666.6667 | ACTION | 17809.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 134583.3333 | ACTION | 17809.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 17 | 134583.3333 | ACTION | 17809.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 17815.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 17815.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 17815.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17820.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17823.6105 | MooredSubInstallation
| Towing Group 1 | Transit | 9 | 71250 | ACTION | 17824.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 9 | 71250 | ACTION | 17824.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 10 | 79166.6667 | ACTION | 17825.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Substructure Assembly Line 1 | Substructure Assembly | 168 | 0 | ACTION | 17825.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17827.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17830.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 17854.6105 | MooredSubInstallation
| Towing Group 1 | Delay | 57 | 451250 | ACTION | 17881.1245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 57 | 451250 | ACTION | 17881.6245 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 57 | 451250 | ACTION | 17882.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 36.9519 | 292536.1012 | ACTION | 17919.0423 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 37.9519 | 300452.7679 | ACTION | 17919.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 37.9519 | 300452.7679 | ACTION | 17919.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 17925.0423 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 17925.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 17925.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 17926.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 17934.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 17946.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17950.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17954.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17958.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 17962.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 10 | 0 | ACTION | 17972.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 17984.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 17995.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 17999.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18002.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18006.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 11 | 0 | ACTION | 18017.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 18041.1105 | MooredSubInstallation
0.5 | Array Cable Installation Vessel | Mobilize | 72 | 337500 | ACTION | 18092.0014 | ArrayCableInstallation
| Array Cable Installation Vessel | Load Cable | 6 | 56250 | ACTION | 18098.0014 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 18113.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 18121.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 18133.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18137.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18141.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18145.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18149.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 18161.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18164.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18168.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18171.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 18195.6105 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 106 | 993750 | ACTION | 18204.0014 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 27 | 253125 | ACTION | 18231.0014 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 18267.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 18275.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 18287.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18291.6105 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 63 | 590625 | ACTION | 18294.0014 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18295.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18299.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18303.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 18315.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18319.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18322.6105 | MooredSubInstallation
| Array Cable Installation Vessel | Transit | 30.1589 | 282739.4022 | ACTION | 18324.1603 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18326.1105 | MooredSubInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18326.1603 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18327.1603 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 18350.1105 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 38 | 356250 | ACTION | 18365.1603 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18370.6603 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18376.1603 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18377.1603 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 18750 | ACTION | 18379.1603 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 18422.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 18430.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 18442.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18446.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18450.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18454.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18458.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 18470.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18473.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18477.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18480.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 18504.6105 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 154 | 1443750 | ACTION | 18533.1603 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 14.0261 | 131494.4853 | ACTION | 18547.1864 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18548.1864 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18553.6864 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18559.1864 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18561.1864 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18562.1864 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 18576.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Move Substructure | 8 | 0 | ACTION | 18584.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Prepare for Turbine Assembly | 12 | 0 | ACTION | 18596.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18600.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18604.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18608.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Tower Section | 4 | 0 | ACTION | 18612.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Nacelle | 12 | 0 | ACTION | 18624.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Delay | 6 | 0 | ACTION | 18630.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18634.1105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18637.6105 | MooredSubInstallation
| Turbine Assembly Line 1 | Lift and Attach Blade | 3.5 | 0 | ACTION | 18641.1105 | MooredSubInstallation
| Towing Group 2 | Delay | 733 | 5802916.6667 | ACTION | 18658.5764 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 734 | 5810833.3333 | ACTION | 18659.0423 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 734 | 5810833.3333 | ACTION | 18659.0764 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Mechanical Completion | 24 | 0 | ACTION | 18665.1105 | MooredSubInstallation
| Array Cable Installation Vessel | Delay | 140 | 1312500 | ACTION | 18702.1864 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18707.6864 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18713.1864 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 18714.1864 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 16.0261 | 150244.4853 | ACTION | 18730.2124 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18731.2124 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Turbine Assembly Line 1 | Electrical Completion | 72 | 0 | ACTION | 18737.1105 | MooredSubInstallation
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 18778.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 18778.5563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 18778.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 18780.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 18780.5563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 18780.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 18786.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 18786.5563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 18786.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 102916.6667 | ACTION | 18799.5563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 13 | 102916.6667 | ACTION | 18799.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 14 | 110833.3333 | ACTION | 18800.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 19 | 150416.6667 | ACTION | 18818.5563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 19 | 150416.6667 | ACTION | 18818.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 19 | 150416.6667 | ACTION | 18819.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 6 | 47500 | ACTION | 18825.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 55416.6667 | ACTION | 18825.5563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 7 | 55416.6667 | ACTION | 18825.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 18831.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 18831.5563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 18831.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 104 | 975000 | ACTION | 18835.2124 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18840.7124 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 28 | 221666.6667 | ACTION | 18859.5563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 28 | 221666.6667 | ACTION | 18859.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 29 | 229583.3333 | ACTION | 18860.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 15 | 118750 | ACTION | 18874.5563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 15 | 118750 | ACTION | 18874.5904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 15 | 118750 | ACTION | 18875.0904 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 17.9519 | 142119.4345 | ACTION | 18893.0423 | MooredSubInstallation | [5 empty] | 3 | 1
| Turbine Assembly Line 1 | Delay: No Assembly Storage Available | 155.9319 | 0 | ACTION | 18893.0423 | MooredSubInstallation
| Towing Group 3 | Transit | 18.9519 | 150036.1012 | ACTION | 18893.5082 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 18.9519 | 150036.1012 | ACTION | 18893.5423 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 54 | 506250 | ACTION | 18894.7124 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 18899.0423 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 18899.5082 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 18899.5423 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 18900.2124 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 18902.2124 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 18903.2124 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 77 | 721875 | ACTION | 18980.2124 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 18985.7124 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 423 | 3965625 | ACTION | 19408.7124 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19414.2124 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19415.2124 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 19420.1503 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19421.1503 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19426.6503 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19432.1503 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19434.1503 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19435.1503 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19440.6503 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19446.1503 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19447.1503 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 19452.0881 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19453.0881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19458.5881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 142 | 1331250 | ACTION | 19600.5881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19606.0881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 19608.0881 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19609.0881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 19614.5881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 19620.0881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 19621.0881 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 19626.026 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 19627.026 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Delay | 1102 | 8724166.6667 | ACTION | 20001.5082 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 1102 | 8724166.6667 | ACTION | 20001.5423 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 1103 | 8732083.3333 | ACTION | 20002.0423 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 423 | 3965625 | ACTION | 20050.026 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20055.526 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20061.026 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20063.026 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20064.026 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20069.526 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20075.026 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20076.026 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 20080.9638 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20081.9638 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20087.4638 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20092.9638 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20094.9638 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20095.9638 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20101.4638 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 19 | 178125 | ACTION | 20120.4638 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 20121.0222 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 20121.0563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 20121.5563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 20123.0222 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 20123.0563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 20123.5563 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20125.9638 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20126.9638 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 20129.0222 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 20129.0563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 20129.5563 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 20131.9017 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20132.9017 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20138.4017 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20143.9017 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20145.9017 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20146.9017 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 20149.0222 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 20149.0563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 20 | 158333.3333 | ACTION | 20149.5563 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20152.4017 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 20155.0222 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 20155.0563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 20155.5563 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20157.9017 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20158.9017 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 20163.8395 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20164.8395 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20170.3395 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 31 | 245416.6667 | ACTION | 20186.5563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 32 | 253333.3333 | ACTION | 20187.0222 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 32 | 253333.3333 | ACTION | 20187.0563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 62 | 490833.3333 | ACTION | 20248.5563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 62 | 490833.3333 | ACTION | 20249.0222 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 62 | 490833.3333 | ACTION | 20249.0563 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Transit | 14.9519 | 118369.4345 | ACTION | 20263.9742 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 14.9519 | 118369.4345 | ACTION | 20264.0082 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Transit | 15.9519 | 126286.1012 | ACTION | 20264.5082 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 2 | 15833.3333 | ACTION | 20266.5082 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 3 | 23750 | ACTION | 20266.9742 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 3 | 23750 | ACTION | 20267.0082 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Ballast to Towing Draft | 6 | 47500 | ACTION | 20272.5082 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Towing Draft | 6 | 47500 | ACTION | 20272.9742 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Towing Draft | 6 | 47500 | ACTION | 20273.0082 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 154 | 1443750 | ACTION | 20324.3395 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20329.8395 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20331.8395 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20332.8395 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20338.3395 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20343.8395 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20344.8395 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 20349.7774 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20350.7774 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 140 | 1312500 | ACTION | 20490.7774 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20496.2774 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 100 | 937500 | ACTION | 20596.2774 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20601.7774 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20603.7774 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20604.7774 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20610.2774 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 12 | 112500 | ACTION | 20622.2774 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20627.7774 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20628.7774 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 20633.7152 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20634.7152 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20640.2152 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20645.7152 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20647.7152 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20648.7152 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20654.2152 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20659.7152 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20660.7152 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 20665.6531 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20666.6531 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Delay | 472 | 3736666.6667 | ACTION | 20744.5082 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 472 | 3736666.6667 | ACTION | 20744.9742 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 472 | 3736666.6667 | ACTION | 20745.0082 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 108 | 1012500 | ACTION | 20774.6531 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20780.1531 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20785.6531 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20787.6531 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20788.6531 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20794.1531 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20799.6531 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20800.6531 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 20805.5909 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20806.5909 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20812.0909 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20817.5909 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20819.5909 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20820.5909 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20826.0909 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20831.5909 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20832.5909 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 20837.5288 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20838.5288 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20844.0288 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20849.5288 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20851.5288 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20852.5288 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20858.0288 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20863.5288 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Tow Substructure | 119.514 | 946152.5 | ACTION | 20864.0222 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Tow Substructure | 119.514 | 946152.5 | ACTION | 20864.4882 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Tow Substructure | 119.514 | 946152.5 | ACTION | 20864.5222 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 20864.5288 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Position Substructure | 2 | 15833.3333 | ACTION | 20866.0222 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Position Substructure | 2 | 15833.3333 | ACTION | 20866.4882 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Position Substructure | 2 | 15833.3333 | ACTION | 20866.5222 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 20869.4666 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20870.4666 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Ballast to Operational Draft | 6 | 47500 | ACTION | 20872.0222 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Ballast to Operational Draft | 6 | 47500 | ACTION | 20872.4882 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Ballast to Operational Draft | 6 | 47500 | ACTION | 20872.5222 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20875.9666 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 20881.4666 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 20883.4666 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 20884.4666 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 118750 | ACTION | 20887.4882 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 15 | 118750 | ACTION | 20887.5222 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 16 | 126666.6667 | ACTION | 20888.0222 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Delay | 100 | 791666.6667 | ACTION | 20987.4882 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Delay | 100 | 791666.6667 | ACTION | 20987.5222 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Delay | 100 | 791666.6667 | ACTION | 20988.0222 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 2 | Connect Mooring Lines, Pre-tension and pre-stretch | 4 | 31666.6667 | ACTION | 20992.0222 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 39583.3333 | ACTION | 20992.4882 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Connect Mooring Lines, Pre-tension and pre-stretch | 5 | 39583.3333 | ACTION | 20992.5222 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Delay | 109 | 1021875 | ACTION | 20993.4666 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Check Mooring Lines | 6 | 47500 | ACTION | 20998.0222 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 3 | Check Mooring Lines | 6 | 47500 | ACTION | 20998.4882 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Check Mooring Lines | 6 | 47500 | ACTION | 20998.5222 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 20998.9666 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21004.4666 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21005.4666 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 21010.4045 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21011.4045 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21016.9045 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21022.4045 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21024.4045 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21025.4045 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21030.9045 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 8 | 75000 | ACTION | 21038.9045 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21044.4045 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 2 | Transit | 46.9519 | 371702.7679 | ACTION | 21044.9742 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21045.4045 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Towing Group 3 | Transit | 46.9519 | 371702.7679 | ACTION | 21045.4401 | MooredSubInstallation | [5 empty] | 3 | 1
| Towing Group 1 | Transit | 46.9519 | 371702.7679 | ACTION | 21045.4742 | MooredSubInstallation | [5 empty] | 3 | 1
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 21050.3423 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21051.3423 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21056.8423 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21062.3423 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21064.3423 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21065.3423 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21070.8423 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21076.3423 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21077.3423 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 21082.2802 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21083.2802 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21088.7802 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 71 | 665625 | ACTION | 21159.7802 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21165.2802 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21167.2802 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21168.2802 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21173.7802 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21179.2802 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21180.2802 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 21185.218 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21186.218 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 11 | 103125 | ACTION | 21197.218 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21202.718 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21208.218 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21210.218 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21211.218 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21216.718 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21222.218 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21223.218 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 21228.1559 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21229.1559 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21234.6559 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21240.1559 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21242.1559 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21243.1559 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21248.6559 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21254.1559 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21255.1559 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 21260.0937 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21261.0937 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 107 | 1003125 | ACTION | 21368.0937 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21373.5937 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21379.0937 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21381.0937 | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 79 | 740625 | ACTION | 21460.0937 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21461.0937 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21466.5937 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21472.0937 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21473.0937 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 21478.0316 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21479.0316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21484.5316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 205 | 1921875 | ACTION | 21689.5316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21695.0316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21697.0316 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21698.0316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21703.5316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21709.0316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21710.0316 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 21714.9694 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21715.9694 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21721.4694 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21726.9694 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21728.9694 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21729.9694 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21735.4694 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21740.9694 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21741.9694 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 1 | 9375 | ACTION | 21742.9694 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 15 | 140625 | ACTION | 21757.9694 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 3.9378 | 36917.3219 | ACTION | 21761.9072 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21762.9072 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21768.4072 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 42 | 393750 | ACTION | 21810.4072 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21815.9072 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 21817.9072 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21818.9072 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 9 | 84375 | ACTION | 21827.9072 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 21833.4072 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 21838.9072 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 21839.9072 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 21844.8451 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 21845.8451 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 194 | 1818750 | ACTION | 22039.8451 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22045.3451 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22050.8451 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22052.8451 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22053.8451 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22059.3451 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22064.8451 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22065.8451 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22070.7829 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22071.7829 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22077.2829 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22082.7829 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22084.7829 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22085.7829 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22091.2829 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22096.7829 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22097.7829 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22102.7208 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22103.7208 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22109.2208 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22114.7208 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22116.7208 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22117.7208 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22123.2208 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22128.7208 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22129.7208 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22134.6586 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22135.6586 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22141.1586 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22146.6586 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22148.6586 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22149.6586 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22155.1586 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22160.6586 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22161.6586 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22166.5965 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22167.5965 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22173.0965 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22178.5965 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22180.5965 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22181.5965 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22187.0965 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22192.5965 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22193.5965 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22198.5343 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22199.5343 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22205.0343 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22210.5343 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 7 | 65625 | ACTION | 22217.5343 | ArrayCableInstallation
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22219.5343 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22220.5343 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22226.0343 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22231.5343 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22232.5343 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22237.4722 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22238.4722 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22243.9722 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22249.4722 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22251.4722 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22252.4722 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22257.9722 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22263.4722 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22264.4722 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22269.41 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22270.41 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22275.91 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22281.41 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22283.41 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22284.41 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22289.91 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22295.41 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22296.41 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22301.3479 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 3 | 28125 | ACTION | 22304.3479 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22305.3479 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 100 | 937500 | ACTION | 22405.3479 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22410.8479 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22416.3479 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22418.3479 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22419.3479 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22424.8479 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22430.3479 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22431.3479 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22436.2857 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22437.2857 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22442.7857 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22448.2857 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22450.2857 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22451.2857 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22456.7857 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22462.2857 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22463.2857 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22468.2236 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22469.2236 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22474.7236 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22480.2236 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22482.2236 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22483.2236 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22488.7236 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22494.2236 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22495.2236 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22500.1614 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22501.1614 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22506.6614 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22512.1614 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22514.1614 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22515.1614 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22520.6614 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22526.1614 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22527.1614 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22532.0993 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22533.0993 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22538.5993 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22544.0993 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22546.0993 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22547.0993 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22552.5993 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22558.0993 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22559.0993 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22564.0371 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22565.0371 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22570.5371 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22576.0371 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22578.0371 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22579.0371 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22584.5371 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22590.0371 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22591.0371 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22595.975 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22596.975 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22602.475 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22607.975 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22609.975 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22610.975 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22616.475 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22621.975 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22622.975 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22627.9128 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22628.9128 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 8 | 75000 | ACTION | 22636.9128 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22642.4128 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22647.9128 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22649.9128 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22650.9128 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22656.4128 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22661.9128 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22662.9128 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22667.8507 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22668.8507 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22674.3507 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22679.8507 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22681.8507 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22682.8507 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22688.3507 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22693.8507 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22694.8507 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22699.7885 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22700.7885 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22706.2885 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22711.7885 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22713.7885 | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 2 | 18750 | ACTION | 22715.7885 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22716.7885 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22722.2885 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22727.7885 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22728.7885 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22733.7264 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22734.7264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22740.2264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22745.7264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22747.7264 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22748.7264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22754.2264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22759.7264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22760.7264 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22765.6642 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22766.6642 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22772.1642 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22777.6642 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22779.6642 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22780.6642 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22786.1642 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22791.6642 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22792.6642 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22797.602 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22798.602 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22804.102 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 7 | 65625 | ACTION | 22811.102 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22816.602 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22818.602 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22819.602 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22825.102 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22830.602 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22831.602 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22836.5399 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22837.5399 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22843.0399 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22848.5399 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22850.5399 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22851.5399 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22857.0399 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22862.5399 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22863.5399 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22868.4777 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22869.4777 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22874.9777 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22880.4777 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22882.4777 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22883.4777 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22888.9777 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22894.4777 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22895.4777 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22900.4156 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22901.4156 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22906.9156 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22912.4156 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22914.4156 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22915.4156 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22920.9156 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22926.4156 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22927.4156 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22932.3534 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22933.3534 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22938.8534 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22944.3534 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22946.3534 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22947.3534 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22952.8534 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22958.3534 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22959.3534 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 22964.2913 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22965.2913 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22970.7913 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22976.2913 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 22978.2913 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 22979.2913 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 22984.7913 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 22990.2913 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 22991.2913 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 18750 | ACTION | 22993.2913 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 3 | 28125 | ACTION | 22996.2913 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 2 | 18750 | ACTION | 22998.2913 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Delay | 1 | 9375 | ACTION | 22999.2913 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Lay/Bury Cable | 0.93785 | 8792.3219 | ACTION | 23000.2291 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23001.2291 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23006.7291 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23012.2291 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23014.2291 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23015.2291 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23020.7291 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23026.2291 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23027.2291 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 23032.167 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23033.167 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23038.667 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23044.167 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23046.167 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23047.167 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23052.667 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23058.167 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23059.167 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 23064.1048 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23065.1048 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23070.6048 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23076.1048 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23078.1048 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23079.1048 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23084.6048 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23090.1048 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23091.1048 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 23096.0427 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23097.0427 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23102.5427 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23108.0427 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23110.0427 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23111.0427 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23116.5427 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23122.0427 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23123.0427 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 23127.9805 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23128.9805 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23134.4805 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 39 | 365625 | ACTION | 23173.4805 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23178.9805 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23180.9805 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23181.9805 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23187.4805 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23192.9805 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23193.9805 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 23198.9184 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23199.9184 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23205.4184 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23210.9184 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23212.9184 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23213.9184 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23219.4184 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23224.9184 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23225.9184 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 23230.8562 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23231.8562 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23237.3562 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23242.8562 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23244.8562 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23245.8562 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23251.3562 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 52 | 487500 | ACTION | 23303.3562 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23308.8562 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23309.8562 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 23314.7941 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23315.7941 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23321.2941 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23326.7941 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23328.7941 | ArrayCableInstallation
| Array Cable Installation Vessel | Delay | 17 | 159375 | ACTION | 23345.7941 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23346.7941 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23352.2941 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23357.7941 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23358.7941 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 23363.7319 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23364.7319 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23370.2319 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23375.7319 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23377.7319 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23378.7319 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23384.2319 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23389.7319 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23390.7319 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 23395.6698 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23396.6698 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 8 | 75000 | ACTION | 23404.6698 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23410.1698 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23415.6698 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23417.6698 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23418.6698 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23424.1698 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23429.6698 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23430.6698 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 23435.6076 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23436.6076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23442.1076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23447.6076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23449.6076 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23450.6076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23456.1076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23461.6076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23462.6076 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 4.9378 | 46292.3219 | ACTION | 23467.5455 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23468.5455 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 83 | 778125 | ACTION | 23551.5455 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23557.0455 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23562.5455 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23564.5455 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23565.5455 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23571.0455 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23576.5455 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23577.5455 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 12.0467 | 112937.754 | ACTION | 23589.5922 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23590.5922 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23596.0922 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23601.5922 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23603.5922 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23604.5922 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23610.0922 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23615.5922 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23616.5922 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 12.0467 | 112937.754 | ACTION | 23628.6388 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23629.6388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23635.1388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23640.6388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23642.6388 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23643.6388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23649.1388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23654.6388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23655.6388 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8.3095 | 77901.6126 | ACTION | 23663.9484 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23664.9484 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23670.4484 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23675.9484 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23677.9484 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23678.9484 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23684.4484 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23689.9484 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23690.9484 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 8.3095 | 77901.6126 | ACTION | 23699.2579 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23700.2579 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23705.7579 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23711.2579 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23713.2579 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23714.2579 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23719.7579 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23725.2579 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23726.2579 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.4336 | 50939.9102 | ACTION | 23731.6914 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23732.6914 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 10 | 93750 | ACTION | 23742.6914 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23748.1914 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23753.6914 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Position Onsite | 2 | 18750 | ACTION | 23755.6914 | ArrayCableInstallation
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23756.6914 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23762.1914 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23767.6914 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lower Cable | 1 | 9375 | ACTION | 23768.6914 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Lay/Bury Cable | 5.4336 | 50939.9102 | ACTION | 23774.125 | ArrayCableInstallation | ArrayCableInstallation | FALSE | 2 | 25 | 11.5
| Array Cable Installation Vessel | Prepare Cable | 1 | 9375 | ACTION | 23775.125 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Pull In Cable | 5.5 | 51562.5 | ACTION | 23780.625 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Terminate Cable | 5.5 | 51562.5 | ACTION | 23786.125 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 51 | 478125 | ACTION | 23837.125 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Delay | 8 | 75000 | ACTION | 23845.125 | ArrayCableInstallation | ArrayCableInstallation | FALSE
| Array Cable Installation Vessel | Transit | 6.1589 | 57739.4022 | ACTION | 23851.2839 | ArrayCableInstallation | ArrayCableInstallation | FALSE